## Sheet1
Job Number | Number | Summary | Date | Type | External? | Budget Cost | Budget Hours | Line Item Amount | Cost Rate Override | Actual Cost | Gross Profit (%) | Assignee | Estimated Start Date | Estimated End Date | Actual Start Date | Actual Completion Date | Completed By | Category Code
22-0063-ER | WO0003 | FEE | 2022-07-14T15:29:55.943 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | FEE
22-0063-ER | WO00010, Complete | Roof Labor | 2022-07-14T15:31:00.000 | WO | 0 | 4800 | 59.15 | 7994.52 | 4800 |  | 39.9589 |  | 07/14/2022 | 07/21/2022 |  | 2022-12-05T08:08:04.367 | Olson, Jonathon | Roof Labor
22-0063-ER | WO00011, Complete | Materials | 2022-11-23T18:39:00.000 | WO | 0 | 2340.944 | 8 | 2926.18 | 80 |  | 20 |  | 11/23/2022 | 11/23/2022 |  | 2022-12-05T08:08:04.397 | Olson, Jonathon | Materials
22-0063-ER | WO00012 | gutter labor and material | 2022-12-01T21:44:00.000 | WO | 0 | 1599.9989 | 38.86 | 4448.21 | 1600 |  | 64.0305 |  | 07/14/2022 | 12/01/2022 |  |  |  | gutter labor and material
22-0063-ER | WO00013 | Punch | 2023-05-20T22:42:00.000 | WO | 0 | 939.6877 | 17.16 | 1808.05 | 51.9724 |  | 48.0276 |  | 05/20/2023 | 07/15/2022 |  |  |  | Punch
22-0063-ER | WO00014 | Stan Gully | 2023-06-28T17:40:00.000 | WO | 0 | 499.9997 | 11.85 | 847.18 | 500 |  | 40.9807 |  | 06/28/2023 | 07/15/2022 |  |  |  | Gutters
22-0099-ER | WO0004, Complete | Roofing Labor | 2022-08-09T12:56:56.000 | WO | 0 | 5681.7439 | 88.5 | 16500.82 | 5681.75 |  | 65.5669 |  | 08/09/2022 | 08/22/2022 |  | 2022-08-09T13:05:45.197 | Dehnke, Josh | RFG
22-0099-ER | WO0005, Complete | Siding Labor | 2022-08-09T12:56:56.000 | WO | 0 | 4499.9981 | 45.42 | 7231.48 | 4500 |  | 37.7721 |  | 08/09/2022 | 08/16/2022 |  | 2023-03-16T09:50:29.030 | Olson, Jonathon | SDG
22-0099-ER | WO0006, Complete | Gutter Labor | 2022-08-09T12:56:56.000 | WO | 0 | 562.32 | 3.33 | 562.32 | 100 |  | 0 |  | 08/09/2022 | 08/09/2022 |  | 2022-08-09T13:05:45.237 | Dehnke, Josh | SFG
22-0099-ER | WO0008, Complete | Materials | 2022-08-09T13:51:00.000 | WO | 0 | 11898.242 | 8 | 10572.55 | 11898.24 |  | -12.539 |  | 08/09/2022 | 08/09/2022 |  | 2022-08-09T13:05:45.173 | Dehnke, Josh | RFG
22-0207-ER | WO0001 | FEE | 2022-10-03T09:43:37.267 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | FEE
22-0207-ER | WO0006, Complete | Materials | 2022-10-03T09:44:00.000 | WO | 0 | 5024.4 | 8 | 5024.4 | 100 |  | 0 |  | 10/03/2022 | 10/03/2022 |  | 2022-10-03T08:50:23.930 | Olson, Jonathon | Materials
22-0207-ER | WO0007, Complete | Labor | 2022-10-03T09:45:00.000 | WO | 0 | 3360.0006 | 76.52 | 9530.7 | 3360 |  | 64.7455 |  | 10/03/2022 | 10/11/2022 |  | 2022-10-05T09:44:11.287 | Olson, Jonathon | Labor
22-0207-ER | WO0008, Complete | Supplement | 2022-12-30T15:35:00.000 | WO | 0 | 3500 | 8 | 3500 | 100 |  | 0 |  | 12/30/2022 | 12/30/2022 |  | 2022-12-30T14:35:52.147 | Dehnke, Josh | SUPP
22-0207-ER | WO0009, Complete | Punch | 2023-05-08T22:16:00.000 | WO | 0 | 500 |  | 500 | 100 |  | 0 |  |  |  |  | 2023-05-08T21:23:50.500 | Olson, Jonathon | Punch
22-0225-D | WO0001 | Concrete Demo and Repair | 2022-11-22T16:20:37.000 | WO | 0 | 22750 |  | 35000 | 65 |  | 35 | [6 empty] | CNC
22-0225-D | WO0002, Complete | Permit and Engineer | 2022-11-22T16:20:37.000 | WO | 0 | 1450.0006 |  | 3178 | 1450 |  | 54.3738 |  |  |  |  | 2022-12-09T10:25:02.257 | Hicks, Dave | FEE
22-0225-D | WO0003 | Brick pavers Labor | 2022-11-22T16:20:37.000 | WO | 0 | 1120 |  | 2800 | 40 |  | 60 | [6 empty] | MAS
22-0225-D | WO0006 | Pillar Removal | 2023-05-08T10:06:00.000 | WO | 0 | 46.4212 | 17 | 2800 | 46.42 |  | 98.3421 |  | 05/11/2023 | 05/12/2023
22-0225-D | WO0007, Complete | Support Material | 2023-05-08T10:07:00.000 | WO | 0 | 894.1016 | 8 | 5600 | 894.1 |  | 84.0339 |  | 05/08/2023 | 05/08/2023 |  | 2023-05-08T09:21:31.523 | Burrell, Bianca
22-0225-D | WO0008 | Beacon Carpentry | 2023-05-08T10:08:00.000 | WO | 0 | 899.9984 | 8 | 5600 | 900 |  | 83.9286 |  | 05/08/2023 | 05/08/2023
22-0225-D | WO0009 | Handrail & Spindles | 2023-05-08T10:41:00.000 | WO | 0 | 197.1769 | 9.3 | 4310.85 | 197.1769 |  | 95.426 |  | 05/08/2023 | 11/22/2022
22-0225-D | WO00010 | Beacon Carpentry - Removal | 2023-05-08T10:43:00.000 | WO | 0 | 0 | 8 | 0 | 0 |  | 0 |  | 05/08/2023 | 05/08/2023
22-0228-ER | WO0001, Complete | CON | 2023-02-14T12:29:13.000 | WO | 0 | 61.87 | 37 | 61.87 | 100 |  | 0 |  | 02/06/2023 | 02/10/2023 |  | 2023-05-02T17:13:55.463 | Sleem, Michael | CON
22-0228-ER | WO0002, Complete | DOR | 2023-02-14T12:29:13.413 | WO | 0 | 798.8 | 3.43 | 798.8 | 100 |  | 0 |  | 02/14/2023 | 02/14/2023 |  | 2023-05-02T17:13:55.457 | Sleem, Michael | DOR
22-0228-ER | WO0005, Complete | FNC | 2023-02-14T12:29:13.637 | WO | 0 | 308.16 | 0.35 | 308.16 | 100 |  | 0 |  | 02/14/2023 | 02/14/2023 |  | 2023-05-02T17:13:55.453 | Sleem, Michael | FNC
22-0228-ER | WO0006, Complete | INS | 2023-02-14T12:29:13.000 | WO | 0 | 252.75 | 36.02 | 252.75 | 100 |  | 0 |  | 04/03/2023 | 04/07/2023 |  | 2023-04-10T08:35:57.233 | Burrell, Bianca | INS
22-0228-ER | WO0007, Complete | LAB | 2023-02-14T12:29:13.757 | WO | 0 | 31.02 | 0 | 31.02 | 100 |  | 0 |  | 02/14/2023 | 02/14/2023 |  | 2023-05-02T17:13:55.447 | Sleem, Michael | LAB
22-0228-ER | WO0008, Complete | PNT | 2023-02-14T12:29:13.000 | WO | 0 | 1247.3706 | 11.25 | 1496.54 | 1247.37 |  | 16.6497 |  | 02/14/2023 | 02/14/2023 |  | 2023-02-14T11:46:44.027 | Burrell, Bianca | PNT
22-0228-ER | WO0009, Complete | RFG | 2023-02-14T12:29:13.000 | WO | 0 | 5103.3135 | 50.68 | 13689.77 | 5103.32 |  | 62.7217 |  | 02/14/2023 | 02/21/2023 |  | 2023-02-14T13:11:28.670 | Burrell, Bianca | RFG
22-0228-ER | WO00010, Complete | SDG | 2023-02-14T12:29:13.987 | WO | 0 | 545.22 | 2 | 545.22 | 100 |  | 0 |  | 02/14/2023 | 02/14/2023 |  | 2023-05-02T17:13:55.443 | Sleem, Michael | SDG
22-0228-ER | WO00011, Complete | SFG | 2023-02-14T12:29:14.080 | WO | 0 | 761.64 | 2.2 | 761.64 | 100 |  | 0 |  | 02/14/2023 | 02/14/2023 |  | 2023-05-02T17:13:39.873 | Sleem, Michael | SFG
22-0228-ER | WO00012, Complete | WDA | 2023-02-14T12:29:14.143 | WO | 0 | 556.48 | 1.35 | 556.48 | 100 |  | 0 |  | 02/14/2023 | 02/14/2023 |  | 2023-05-02T17:13:35.210 | Sleem, Michael | WDA
22-0228-ER | WO00013, Complete | Window Material | 2023-02-14T12:29:14.000 | WO | 0 | 17405.006 | 0 | 26692.42 | 17405 |  | 34.7942 |  | 02/14/2023 | 02/14/2023 |  | 2023-02-14T13:05:35.777 | Burrell, Bianca | WDW
22-0228-ER | WO00014, Complete | Window Labor | 2023-02-14T13:55:00.000 | WO | 0 | 17405.0088 |  | 18415.29 | 17405 |  | 5.4861 |  | 04/03/2023 | 04/10/2023 |  | 2023-04-10T08:34:42.910 | Burrell, Bianca
22-0228-ER | WO00015, Complete | Hardwood Refinishing | 2023-03-06T11:06:00.000 | WO | 0 | 2335.0008 | 0 | 3152.25 | 2335 |  | 25.9259 |  | 02/06/2023 | 02/10/2023 |  | 2023-03-06T10:09:59.720 | Burrell, Bianca
22-0282-EST
22-0286-ER | WO0001, Complete | Permit | 2022-08-29T14:33:09.000 | WO | 0 | 0 |  | 0 | 0 |  | 0 |  |  |  |  | 2022-10-21T12:37:04.007 | Dehnke, Josh | FEE
22-0286-ER | WO0003, Complete | Roofing Labor | 2022-08-29T14:33:09.000 | WO | 0 | 8300 | 77.65 | 9784.26 | 8300 |  | 15.1699 |  | 08/29/2022 | 09/16/2022 |  | 2022-11-27T19:01:04.810 | Olson, Jonathon | RFG
22-0286-ER | WO0004, Complete | Roofing Materials | 2022-08-29T14:34:00.000 | WO | 0 | 7786 | 8 | 8430.28 | 7786 |  | 7.6425 |  | 08/29/2022 | 08/29/2022 |  | 2022-10-21T12:37:03.977 | Dehnke, Josh | Roofing Materials
22-0286-ER | WO0005 | Metal Wrap | 2023-01-03T12:35:00.000 | WO | 0 | 553.2496 | 11.74 | 1103.06 | 50.1559 |  | 49.8441 |  | 01/03/2023 | 09/16/2022 |  |  |  | SFG
22-0286-ER | WO0006 | LR Roof repair | 2023-07-18T15:25:00.000 | WO | 0 | 2350.0025 | 57.95 | 10135.35 | 2350 |  | 76.8138 |  | 07/18/2023 | 09/16/2022 |  |  |  | LR Roof repair
22-0300-C | WO0001, Complete | Permit | 2022-08-29T14:33:09.000 | WO | 0 | 0 |  | 0 | 0 |  | 0 |  |  |  |  | 2022-10-21T12:37:04.007 | Dehnke, Josh | FEE
22-0300-C | WO0003, Complete | Roofing Labor | 2022-08-29T14:33:09.000 | WO | 0 | 8300 | 77.65 | 9784.26 | 8300 |  | 15.1699 |  | 08/29/2022 | 09/16/2022 |  | 2022-11-27T19:01:04.810 | Olson, Jonathon | RFG
22-0300-C | WO0004, Complete | Roofing Materials | 2022-08-29T14:34:00.000 | WO | 0 | 7786 | 8 | 8430.28 | 7786 |  | 7.6425 |  | 08/29/2022 | 08/29/2022 |  | 2022-10-21T12:37:03.977 | Dehnke, Josh | Roofing Materials
22-0300-C | WO0005 | Metal Wrap | 2023-01-03T12:35:00.000 | WO | 0 | 553.2496 | 11.74 | 1103.06 | 50.1559 |  | 49.8441 |  | 01/03/2023 | 09/16/2022 |  |  |  | SFG
22-0300-C | WO0006 | LR Roof repair | 2023-07-18T15:25:00.000 | WO | 0 | 2350.0025 | 57.95 | 10135.35 | 2350 |  | 76.8138 |  | 07/18/2023 | 09/16/2022 |  |  |  | LR Roof repair
22-0337-RET-ER
22-0340-C | WO0001 | DMO | 2023-02-17T12:30:03.023 | WO | 0 | 427.2 |  | 427.2 | 100 |  | 0 | [6 empty] | DMO
22-0340-C | WO0002 | Wood Trim | 2023-02-17T12:30:03.000 | WO | 0 | 560 | 5.99 | 806.02 | 560 |  | 30.5228 |  | 02/17/2023 | 02/17/2023 |  |  |  | DOR
22-0340-C | WO0003 | FEE | 2023-02-17T12:30:03.257 | WO | 0 | 600 |  | 600 | 100 |  | 0 | [6 empty] | FEE
22-0340-C | WO0004 | Finish Carpentry | 2023-02-17T12:30:03.000 | WO | 0 | 1257.21 | 11.92 | 1257.21 | 100 |  | 0 |  | 02/17/2023 | 02/20/2023 |  |  |  | FNC
22-0340-C | WO0005 | Framing/Sheathing | 2023-02-17T12:30:03.000 | WO | 0 | 496.77 | 4.43 | 496.77 | 100 |  | 0 |  | 02/17/2023 | 02/17/2023 |  |  |  | FRM
22-0340-C | WO0006 | Insulation | 2023-02-17T12:30:03.000 | WO | 0 | 254.76 | 0.72 | 254.76 | 100 |  | 0 |  | 02/17/2023 | 02/17/2023 |  |  |  | INS
22-0340-C | WO0007 | Siding | 2023-02-17T12:30:03.000 | WO | 0 | 3013.563 | 51.06 | 8610.18 | 35 |  | 65 |  | 02/17/2023 | 02/24/2023 |  |  |  | SDG
22-0340-C | WO0008 | Gutters and Fascia | 2023-02-17T12:30:04.000 | WO | 0 | 349.9999 | 1.66 | 569.25 | 350 |  | 38.5156 |  | 02/17/2023 | 02/17/2023 |  |  |  | SFG
22-0340-C | WO0009 | Materials | 2023-02-17T12:30:00.000 | WO | 0 | 8626.74 | 8 | 8626.74 | 100 |  | 0 |  | 02/17/2023 | 02/17/2023 |  |  |  | Materials
22-0341-C
22-0342-C
22-0361-ER
22-0374-ER | WO0005, Complete | PNT | 2022-07-20T09:34:39.000 | WO | 0 | 0 | 18.79 | 88.94 | 0 |  | 100 |  | 04/17/2023 | 04/19/2023 |  | 2023-05-22T10:30:40.477 | Trevino, Jeovani | PNT
22-0374-ER | WO0007, Complete | Gutters | 2022-07-20T09:34:40.000 | WO | 0 | 1200 | 146.1 | 1348.2 | 1200 |  | 10.9924 |  | 07/20/2022 | 08/11/2022 |  | 2023-01-16T10:06:48.443 | Trevino, Jeovani | SFG
22-0374-ER | WO0008, Complete | Labor | 2022-07-21T11:22:00.000 | WO | 0 | 6999.9954 | 198.75 | 21148.15 | 7000 |  | 66.9002 |  | 07/20/2022 | 08/19/2022 |  | 2022-10-31T07:58:04.523 | Trevino, Jeovani | Roofing Labor
22-0374-ER | WO0009, Complete | materials | 2022-07-24T19:33:00.000 | WO | 0 | 5784.7504 | 143 | 10720.72 | 5784.75 |  | 46.0414 |  | 07/24/2022 | 08/12/2022 |  | 2022-08-26T11:08:53.330 | Trevino, Jeovani | materials
22-0374-ER | WO00010, Complete | gutter materials | 2022-12-02T15:35:00.000 | WO | 0 | 100 | 8 | 1626.63 | 100 |  | 93.8523 |  | 12/02/2022 | 12/02/2022 |  | 2023-01-16T10:06:48.473 | Trevino, Jeovani
22-0374-ER | WO00011, Complete | Gutter trailer | 2023-02-16T10:23:00.000 | WO | 0 | 250.0003 | 65.81 | 642.24 | 250 |  | 61.0737 |  | 02/16/2023 | 08/19/2022 |  | 2023-02-16T10:13:02.663 | Trevino, Jeovani | gutter trailer rental
22-0374-ER | WO00012 | Jesus Repair Work | 2023-08-24T10:39:00.000 | WO | 0 | 0 | 8 | 0 | 825 |  | 0 |  | 08/24/2023 | 08/24/2023 |  |  |  | Repair
22-0394-ER | WO0001 | AWN | 2022-12-06T09:18:25.000 | WO | 0 | 0 | 2.37 | 404.58 | 0 |  | 100 |  | 12/06/2022 | 12/06/2022 |  |  |  | AWN
22-0394-ER | WO0003 | ELE | 2022-12-06T09:18:25.683 | WO | 0 |  |  |  | 0 |  | 0 | [6 empty] | ELE
22-0394-ER | WO0004 | FEE | 2022-12-06T09:18:25.717 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | FEE
22-0394-ER | WO0006, Complete | Sheathing | 2022-12-06T09:18:25.000 | WO | 0 |  |  |  | 1000 |  | 0 |  |  |  |  | 2023-06-12T10:20:32.667 | Trevino, Jeovani | FRM
22-0394-ER | WO0007 | PNT | 2022-12-06T09:18:25.000 | WO | 0 | 0 | 2.02 | 263.8 | 0 |  | 100 |  | 12/06/2022 | 12/06/2022 |  |  |  | PNT
22-0394-ER | WO00011, Complete | Materials | 2022-12-06T09:18:00.000 | WO | 0 | 4102.79 | 8 | 4595.78 | 4102.79 |  | 10.727 |  | 12/06/2022 | 12/06/2022 |  | 2023-06-12T10:20:32.837 | Trevino, Jeovani | Materials
22-0394-ER | WO00012, Complete | Roofing Labor | 2022-12-06T09:19:00.000 | WO | 0 | 4099.9951 | 88.56 | 9903.92 | 4100 |  | 58.6023 |  | 12/06/2022 | 12/13/2022 |  | 2023-06-12T10:20:32.787 | Trevino, Jeovani | Roofing Labor
22-0394-ER | WO00013 | Gutters | 2022-12-06T09:26:00.000 | WO | 0 | 0 | 24.84 | 2515.49 | 0 |  | 100 |  | 12/06/2022 | 12/07/2022 |  |  |  | Gutters
22-0394-ER | WO00014 | Siding Material | 2022-12-06T09:33:00.000 | WO | 0 | 0 | 8 | 1989.04 | 0 |  | 100 |  | 12/06/2022 | 12/06/2022 |  |  |  | Siding Material
22-0394-ER | WO00015 | Siding Labor | 2022-12-06T09:34:00.000 | WO | 0 | 0 | 17.9 | 1369.93 | 0 |  | 100 |  | 12/06/2022 | 12/09/2022 |  |  |  | Siding Labor
22-0394-ER | WO00016, Complete | Marlon labor | 2023-06-21T12:30:00.000 | WO | 0 | 320.0001 | 12.75 | 632.35 | 320 |  | 49.3951 |  | 06/21/2023 | 12/08/2022 |  | 2023-06-26T21:26:46.170 | Trevino, Jeovani | Marlon labor
22-0400-ER | WO0001, Complete | Dumpster | 2022-09-30T09:07:45.000 | WO | 0 | 558.52 |  | 558.52 | 100 |  | 0 |  |  |  |  | 2022-10-06T15:40:23.063 | Hicks, Dave | DMO
22-0400-ER | WO0002, Complete | Permits | 2022-09-30T09:07:46.000 | WO | 0 | 0 |  | 0 | 0 |  | 0 |  |  |  |  | 2022-10-17T08:55:33.247 | Dehnke, Josh | FEE
22-0400-ER | WO0003, Complete | Materials | 2022-09-30T09:07:46.000 | WO | 0 | 7661.59 |  | 7661.59 | 100 |  | 0 |  |  |  |  | 2022-10-06T15:16:02.283 | Hicks, Dave | RFG
22-0400-ER | WO0004, Complete | Gutter Materials | 2022-09-30T09:07:46.000 | WO | 0 | 257.35 |  | 257.35 | 100 |  | 0 |  |  |  |  | 2022-10-06T15:19:46.420 | Hicks, Dave | SFG
22-0400-ER | WO0005, Complete | House and Garage Labor | 2022-09-30T09:25:00.000 | WO | 0 | 7999.272 | 96.55 | 19998.18 | 40 |  | 60 |  | 09/30/2022 | 10/14/2022 |  | 2022-10-06T15:48:02.640 | Hicks, Dave
22-0400-ER | WO0006, Complete | Supplement Sheathing | 2022-12-30T12:48:00.000 | WO | 0 | 11868 | 8 | 11868 | 100 |  | 0 |  | 12/30/2022 | 12/30/2022 |  | 2022-12-30T11:49:17.083 | Dehnke, Josh | SUP
22-0400-ER | WO0007, Complete | Punch Items | 2023-03-20T17:53:00.000 | WO | 0 | 600 | 8 | 600 | 600 |  | 0 |  | 03/20/2023 | 03/20/2023 |  | 2023-05-08T21:08:01.117 | Olson, Jonathon | Punch Items
22-0410-ER | WO0006, Complete | labor | 2022-09-18T22:04:00.000 | WO | 0 | 5849.19 | 116.18 | 17194.77 | 5849.19 |  | 65.9827 |  | 09/18/2022 | 10/04/2022 |  | 2022-09-18T21:13:05.153 | Trevino, Jeovani | roofing labor
22-0410-ER | WO0007, Complete | materials | 2022-09-18T22:06:00.000 | WO | 0 | 7703.93 | 8 | 7703.93 | 100 |  | 0 |  | 09/18/2022 | 09/18/2022 |  | 2022-09-18T21:13:05.153 | Trevino, Jeovani | materials
22-0410-ER | WO0008 | roofing repair | 2023-06-08T15:38:00.000 | WO | 0 | 500.0001 | 18.12 | 1316.33 | 500 |  | 62.0156 |  | 06/08/2023 | 09/19/2022 |  |  |  | roofing repair
22-0421-ER | WO0002, Complete | FEE | 2022-09-12T12:31:33.203 | WO | 0 | 0 |  | 0 | 0 |  | 0 |  |  |  |  | 2022-09-19T08:31:37.117 | Olson, Jonathon | FEE
22-0421-ER | WO0003, Complete | roofing labor | 2022-09-12T12:31:33.000 | WO | 0 | 6222.0521 | 26.76 | 13382.34 | 6222.05 |  | 53.5055 |  | 09/15/2022 | 09/19/2022 |  | 2022-09-19T07:40:54.490 | Olson, Jonathon | RFG
22-0421-ER | WO0004, Complete | gutter labor | 2022-09-12T12:31:33.000 | WO | 0 | 2600.0015 | 23.67 | 6996.53 | 2600 |  | 62.8387 |  | 09/20/2022 | 09/22/2022 |  | 2022-09-19T08:01:18.020 | Olson, Jonathon | SFG
22-0421-ER | WO0005, Complete | Roofing and gutter materials | 2022-09-12T12:35:00.000 | WO | 0 | 8056.54 | 8 | 8056.54 | 100 |  | 0 |  | 09/12/2022 | 09/12/2022 |  | 2022-09-12T11:53:33.353 | Olson, Jonathon | MAT
22-0421-ER | WO0006, Complete | reglet flashing | 2022-10-27T20:31:00.000 | WO | 0 | 850 | 8 | 850 | 100 |  | 0 |  | 10/27/2022 | 10/27/2022 |  | 2022-12-14T17:26:46.743 | Olson, Jonathon | reglet flashing
22-0444-ER | WO0001 | DMO | 2023-08-10T14:17:10.570 | WO | 0 | 883.8 |  | 883.8 | 100 |  | 0 | [6 empty] | DMO
22-0444-ER | WO0002 | DOR | 2023-08-10T14:17:10.680 | WO | 0 | 1208.4 | 4.62 | 1208.4 | 100 |  | 0 |  | 08/10/2023 | 08/10/2023 |  |  |  | DOR
22-0444-ER | WO0003 | ELS | 2023-08-10T14:17:10.773 | WO | 0 | 12560.81 | 56.13 | 12560.81 | 100 |  | 0 |  | 08/10/2023 | 08/18/2023 |  |  |  | ELS
22-0444-ER | WO0004 | FEE | 2023-08-10T14:17:10.897 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | FEE
22-0444-ER | WO0005, Complete | RFG | 2023-08-10T14:17:10.000 | WO | 0 | 21172.6724 | 167.9 | 38186.32 | 21172.67 |  | 44.5543 |  | 08/10/2023 | 09/05/2023 |  | 2023-08-21T20:19:50.000 | Burrell, Bianca | RFG
22-0444-ER | WO0006, Complete | SFG | 2023-08-10T14:17:11.000 | WO | 0 | 7199.9974 | 55.88 | 12966.45 | 7200 |  | 44.4721 |  | 08/10/2023 | 08/18/2023 |  | 2023-08-21T20:19:50.000 | Burrell, Bianca | SFG
22-0453-ER | WO0002, Complete | DOR | 2022-09-22T22:42:07.360 | WO | 0 | 341.18 | 1.02 | 341.18 | 100 |  | 0 |  | 09/22/2022 | 09/22/2022 |  | 2023-05-25T11:41:56.247 | Olson, Jonathon | DOR
22-0453-ER | WO0008, Complete | roofing labor | 2022-09-22T22:43:00.000 | WO | 0 | 4207.9566 | 91.52 | 13525.61 | 4183 |  | 68.889 |  | 09/22/2022 | 10/04/2022 |  | 2022-10-17T07:36:48.230 | Olson, Jonathon | Roofing labor
22-0453-ER | WO00010, Complete | Materials | 2022-09-22T22:45:00.000 | WO | 0 | 6174.38 | 8 | 6174.38 | 100 |  | 0 |  | 09/22/2022 | 09/22/2022 |  | 2022-10-11T12:51:33.320 | Olson, Jonathon | Materials
22-0453-ER | WO00011, Complete | Punch | 2023-05-08T22:42:00.000 | WO | 0 | 1000 | 8 | 500 | 1000 |  | -100 |  | 05/08/2023 | 05/08/2023 |  | 2023-05-25T11:41:56.277 | Olson, Jonathon | Punch
22-0458-ER | WO0001, Complete | Cleaning | 2022-08-23T11:44:33.000 | WO | 0 | 172.64 | 1.45 | 172.64 | 0 |  | 0 |  | 08/23/2022 | 08/23/2022 |  | 2022-09-23T12:15:56.780 | Dehnke, Josh | CLN
22-0458-ER | WO0004, Complete | Fence | 2022-08-23T11:44:34.000 | WO | 0 | 1289.928 | 5.47 | 2149.88 | 60 |  | 40 |  | 10/13/2022 | 10/13/2022 |  | 2022-10-17T08:42:31.787 | Dehnke, Josh | FEN
22-0458-ER | WO0008, Complete | Paint | 2022-08-23T11:44:34.000 | WO | 0 | 373.49 | 2.23 | 373.49 | 100 |  | 0 |  | 08/23/2022 | 08/23/2022 |  | 2023-05-02T17:14:56.380 | Sleem, Michael | PNT
22-0458-ER | WO0009, Complete | Roofing Labor | 2022-08-23T11:44:34.000 | WO | 0 | 8237.565 | 160.88 | 18305.7 | 45 |  | 55 |  | 08/23/2022 | 09/30/2022 |  | 2022-09-02T12:56:55.187 | Deville , Jard | RFG
22-0458-ER | WO00010, Complete | Siding | 2022-08-23T11:44:35.000 | WO | 0 | 11000.0017 | 26.62 | 14327.9 | 11000 |  | 23.2267 |  | 04/04/2023 | 04/07/2023 |  | 2023-04-10T08:41:54.230 | Burrell, Bianca | SDG
22-0458-ER | WO00014, Complete | Roofing Materials | 2022-08-24T11:31:00.000 | WO | 0 | 5588.91 | 8 | 5588.91 | 100 |  | 0 |  | 08/24/2022 | 08/24/2022 |  | 2022-08-25T16:01:29.560 | Deville , Jard | Roofing Materials
22-0458-ER | WO00015, Complete | Siding Materials | 2022-08-24T11:32:00.000 | WO | 0 | 16871.4773 | 8 | 18492.33 | 16871.48 |  | 8.765 |  | 08/24/2022 | 08/24/2022 |  | 2022-10-17T08:43:25.327 | Dehnke, Josh | Siding Materials
22-0458-ER | WO00016, Complete | Permit | 2022-09-01T12:00:00.000 | WO | 0 | 0 | 8 | 0 | 647 |  | 0 |  | 09/01/2022 | 09/01/2022 |  | 2022-09-09T12:11:36.337 | Deville , Jard | Permit
22-0463-ER | WO0001 | DMO | 2023-05-09T13:47:11.343 | WO | 0 | 190.62 | 1.98 | 190.62 | 100 |  | 0 |  | 05/09/2023 | 05/09/2023 |  |  |  | DMO
22-0463-ER | WO0002, Complete | RFG | 2023-05-09T13:47:11.000 | WO | 0 | 6495.7828 |  | 5852.51 | 6495.78 |  | -10.9914 |  |  |  |  | 2023-06-19T10:56:54.420 | Trevino, Jeovani | RFG
22-0463-ER | WO0003 | SDG | 2023-05-09T13:47:11.650 | WO | 0 | 499.51 | 1.62 | 499.51 | 100 |  | 0 |  | 05/09/2023 | 05/09/2023 |  |  |  | SDG
22-0463-ER | WO0004 | SFG | 2023-05-09T13:47:11.000 | WO | 0 | 959.9994 | 7.93 | 1929.81 | 960 |  | 50.2542 |  | 05/09/2023 | 05/09/2023 |  |  |  | SFG
22-0463-ER | WO0005, Complete | Ramirez roofing | 2023-06-12T15:21:00.000 | WO | 0 | 6550 | 95.26 | 12827.26 | 6550 |  | 48.9369 |  | 05/09/2023 | 06/12/2023 |  | 2023-06-19T10:56:54.400 | Trevino, Jeovani | Ramirez roofing
22-0467-ER | WO0006, Complete | roofing labor | 2022-09-11T16:21:00.000 | WO | 0 | 6642.5859 | 97.13 | 11559.2 | 7500 |  | 42.5342 |  | 09/07/2022 | 10/03/2022 |  | 2022-10-24T09:11:15.583 | Trevino, Jeovani | roofing labor
22-0467-ER | WO0007, Complete | material | 2022-09-11T16:39:00.000 | WO | 0 | 3990.96 |  | 3990.96 | 100 |  | 0 |  |  |  |  | 2022-09-19T14:04:54.993 | Trevino, Jeovani | roofing and siding
22-0467-ER | WO0008, Complete | siding labor | 2022-12-02T15:38:00.000 | WO | 0 | 6300.0037 | 41.23 | 8241.03 | 6300 |  | 23.5532 |  | 05/08/2023 | 05/12/2023 |  | 2023-05-15T11:37:16.820 | Trevino, Jeovani | siding labor
22-0467-ER | WO0009, Complete | siding materials | 2022-12-02T15:41:00.000 | WO | 0 | 5233.3697 | 8 | 8235.6 | 5233.37 |  | 36.4543 |  | 12/02/2022 | 12/02/2022 |  | 2023-01-03T13:12:15.390 | Dehnke, Josh | siding materials
22-0467-ER | WO00010, Complete | gutter labor | 2022-12-29T12:26:00.000 | WO | 0 | 799.9997 | 16.8 | 1253.81 | 800 |  | 36.1945 |  | 09/29/2022 | 12/29/2022 |  | 2023-01-16T10:07:44.497 | Trevino, Jeovani | gutter labor
22-0467-ER | WO00011 | plumbing | 2023-08-02T11:22:00.000 | WO | 0 | 0 |  | 0 | 100 |  | 0 | [6 empty] | plumbing finish
22-0471-ER | WO0001, Complete | CDC | 2022-08-18T09:41:33.357 | WO | 0 | 48.16 |  | 48.16 | 100 |  | 0 |  |  |  |  | 2022-09-18T23:01:03.233 | Trevino, Jeovani | CDC
22-0471-ER | WO0002, Complete | CLN | 2022-08-18T09:41:33.543 | WO | 0 | 138.69 | 2.17 | 138.69 | 100 |  | 0 |  | 08/18/2022 | 08/18/2022 |  | 2022-09-23T11:18:01.873 | Dehnke, Josh | CLN
22-0471-ER | WO0003, Complete | CON | 2022-08-18T09:41:33.000 | WO | 0 | 200.0003 | 8.8 | 747.62 | 200 |  | 73.2484 |  | 08/18/2022 | 08/19/2022 |  | 2022-09-18T23:00:11.247 | Trevino, Jeovani | CON
22-0471-ER | WO0004, Complete | DMO | 2022-08-18T09:41:33.780 | WO | 0 | 670.22 |  | 670.22 | 100 |  | 0 |  |  |  |  | 2022-09-18T22:57:48.297 | Trevino, Jeovani | DMO
22-0471-ER | WO0006 | ELE | 2022-08-18T09:41:33.920 | WO | 0 | 92.4 | 0.57 | 92.4 | 100 |  | 0 |  | 08/18/2022 | 08/18/2022 |  |  |  | ELE
22-0471-ER | WO0007 | ELS | 2022-08-18T09:41:34.133 | WO | 0 | 819.99 | 3.43 | 819.99 | 100 |  | 0 |  | 08/18/2022 | 08/18/2022 |  |  |  | ELS
22-0471-ER | WO0008, Complete | FEE | 2022-08-18T09:41:34.410 | WO | 0 | 1620 |  | 1620 | 100 |  | 0 |  |  |  |  | 2022-09-18T23:01:16.940 | Trevino, Jeovani | FEE
22-0471-ER | WO0009, Complete | FEN | 2022-08-18T09:41:34.537 | WO | 0 | 141.37 |  | 141.37 | 100 |  | 0 |  |  |  |  | 2022-10-21T11:00:34.313 | Dehnke, Josh | FEN
22-0471-ER | WO00010, Complete | FNC | 2022-08-18T09:41:34.613 | WO | 0 | 56.16 | 0.43 | 56.16 | 100 |  | 0 |  | 08/18/2022 | 08/18/2022 |  | 2022-09-23T11:18:01.857 | Dehnke, Josh | FNC
22-0471-ER | WO00011, Complete | framing material | 2022-08-18T09:41:34.000 | WO | 0 | 1474.04 |  | 1474.04 | 100 |  | 0 |  |  |  |  | 2022-09-18T22:58:15.877 | Trevino, Jeovani | FRM
22-0471-ER | WO00012, Complete | HVC | 2022-08-18T09:41:34.787 | WO | 0 | 549.27 | 2.27 | 549.27 | 100 |  | 0 |  | 08/18/2022 | 08/18/2022 |  | 2022-09-23T11:18:01.847 | Dehnke, Josh | HVC
22-0471-ER | WO00013, Complete | INS | 2022-08-18T09:41:34.913 | WO | 0 | 47.72 |  | 47.72 | 100 |  | 0 |  |  |  |  | 2022-09-18T23:01:58.220 | Trevino, Jeovani | INS
22-0471-ER | WO00015, Complete | MSD | 2022-08-18T09:41:35.087 | WO | 0 | 240.6 | 2.67 | 240.6 | 100 |  | 0 |  | 08/18/2022 | 08/18/2022 |  | 2022-09-23T11:18:01.837 | Dehnke, Josh | MSD
22-0471-ER | WO00016, Complete | PNT | 2022-08-18T09:41:35.147 | WO | 0 | 376.96 |  | 376.96 | 100 |  | 0 |  |  |  |  | 2022-09-18T22:58:41.310 | Trevino, Jeovani | PNT
22-0471-ER | WO00021, Complete | exterior work | 2022-09-02T14:13:00.000 | WO | 0 | 13476.799 | 79.36 | 19252.57 | 70 |  | 30 |  | 08/18/2022 | 09/02/2022 |  | 2022-09-30T12:05:35.147 | Trevino, Jeovani | Jenny Construction
22-0471-ER | WO00022, Complete | interior work | 2022-09-22T15:43:00.000 | WO | 0 | 16054.353 | 192.38 | 22934.79 | 70 |  | 30 |  | 08/18/2022 | 09/22/2022 |  | 2022-09-23T11:18:01.817 | Dehnke, Josh | jenny construction
22-0471-ER | WO00023, Complete | fence | 2022-09-22T15:53:00.000 | WO | 0 | 0 | 8 | 1006.73 | 0 |  | 100 |  | 09/22/2022 | 09/22/2022 |  | 2022-10-21T11:00:34.267 | Dehnke, Josh | jenny construction
22-0471-ER | WO00024 | fence labor | 2022-12-02T15:48:00.000 | WO | 0 | 0 | 21.82 | 1242.45 | 0 |  | 100 |  | 08/18/2022 | 12/02/2022 |  |  |  | fence labor
22-0477-ER | WO0002, Complete | FEE | 2023-01-22T14:01:14.963 | WO | 0 | 0 |  | 0 | 0 |  | 0 |  |  |  |  | 2023-02-16T14:16:48.277 | Olson, Jonathon | FEE
22-0477-ER | WO0003, Complete | FRM | 2023-01-22T14:01:15.013 | WO | 0 | 0 |  | 0 | 0 |  | 0 |  |  |  |  | 2023-02-16T14:16:48.277 | Olson, Jonathon | FRM
22-0477-ER | WO0005, Complete | Window Wraps | 2023-01-22T14:01:15.000 | WO | 0 | 1125.0012 | 14.8 | 2869.33 | 1125 |  | 60.7922 |  | 01/22/2023 | 01/23/2023 |  | 2023-02-16T14:16:48.293 | Olson, Jonathon | SDG
22-0477-ER | WO0007, Complete | Roofing Materials | 2023-01-22T14:01:00.000 | WO | 0 | 3882.48 | 8 | 3882.48 | 100 |  | 0 |  | 01/22/2023 | 01/22/2023 |  | 2023-02-16T14:16:48.277 | Olson, Jonathon | Roofing Materials
22-0477-ER | WO0008, Complete | Roofing Labor | 2023-01-22T14:02:00.000 | WO | 0 | 5300 | 80.65 | 11175.75 | 5300 |  | 52.5759 |  | 01/22/2023 | 01/31/2023 |  | 2023-02-16T14:16:48.263 | Olson, Jonathon | Roofing Labor
22-0477-ER | WO0009 | Gutter Labor and Materials | 2023-01-22T14:02:00.000 | WO | 0 | 2460.0002 | 20.95 | 3162.95 | 2460 |  | 22.2245 |  | 01/22/2023 | 01/23/2023 |  |  |  | Gutter Labor and Materials
22-0479-ER | WO0003, Complete | FPL | 2022-09-09T15:52:44.390 | WO | 0 | 360.79 | 0.6 | 360.79 | 100 |  | 0 |  | 09/09/2022 | 09/09/2022 |  | 2022-09-23T11:19:18.960 | Dehnke, Josh | FPL
22-0479-ER | WO0008, Complete | SPE | 2022-09-09T15:52:44.847 | WO | 0 | 398.71 | 0.82 | 398.71 | 100 |  | 0 |  | 09/09/2022 | 09/09/2022 |  | 2022-09-23T11:19:18.930 | Dehnke, Josh | SPE
22-0479-ER | WO0009, Complete | roofing labor | 2022-09-12T09:14:00.000 | WO | 0 | 5000 | 81.79 | 11154.99 | 5000 |  | 55.177 |  | 09/09/2022 | 09/20/2022 |  | 2022-09-23T11:19:18.897 | Dehnke, Josh | roofing labor
22-0479-ER | WO00010, Complete | material | 2022-09-12T09:18:00.000 | WO | 0 | 4020.56 | 8 | 4020.56 | 100 |  | 0 |  | 09/12/2022 | 09/12/2022 |  | 2022-09-19T11:45:15.833 | Trevino, Jeovani | Roofing and siding material
22-0479-ER | WO00011, Complete | DMO | 2022-12-20T22:40:52.820 | WO | 0 | 696.39 | 1.98 | 696.39 | 100 |  | 0 |  | 12/20/2022 | 12/20/2022 |  | 2023-03-27T12:00:13.730 | Trevino, Jeovani | DMO
22-0479-ER | WO00012 | FEE | 2022-12-20T22:40:52.913 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | FEE
22-0479-ER | WO00013, Complete | FPL | 2022-12-20T22:40:52.970 | WO | 0 | 360.79 | 0.6 | 360.79 | 100 |  | 0 |  | 12/20/2022 | 12/20/2022 |  | 2023-03-27T12:00:13.683 | Trevino, Jeovani | FPL
22-0479-ER | WO00014 | FRM | 2022-12-20T22:40:53.050 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | FRM
22-0479-ER | WO00016, Complete | Window wraps | 2022-12-20T22:40:53.000 | WO | 0 | 949.9998 | 24.6 | 3261.97 | 950 |  | 70.8765 |  | 12/20/2022 | 12/22/2022 |  | 2023-03-27T11:59:39.387 | Trevino, Jeovani | SDG
22-0479-ER | WO00017, Complete | SFG | 2022-12-20T22:40:53.830 | WO | 0 | 681.67 | 2.05 | 681.67 | 100 |  | 0 |  | 12/20/2022 | 12/20/2022 |  | 2023-03-27T12:00:13.747 | Trevino, Jeovani | SFG
22-0479-ER | WO00018, Complete | SPE | 2022-12-20T22:40:53.913 | WO | 0 | 398.71 | 0.82 | 398.71 | 100 |  | 0 |  | 12/20/2022 | 12/20/2022 |  | 2023-03-27T12:00:13.747 | Trevino, Jeovani | SPE
22-0507-IR | WO0005, Complete | Materials | 2022-10-21T11:09:00.000 | WO | 0 | 5559.28 | 8 | 5559.28 | 100 |  | 0 |  | 10/21/2022 | 10/21/2022 |  | 2022-10-21T12:25:19.123 | Olson, Jonathon | Materials
22-0507-IR | WO0006, Complete | Labor | 2022-10-21T11:10:00.000 | WO | 0 | 5500.0039 | 101.19 | 14467.07 | 5500 |  | 61.9826 |  | 10/20/2022 | 11/02/2022 |  | 2022-10-28T07:39:45.787 | Olson, Jonathon | Labor
22-0507-IR | WO0007 | gutter labor | 2022-10-23T23:16:00.000 | WO | 0 | 667.1 | 12.62 | 667.1 | 667.1 |  | 0 |  | 10/20/2022 | 10/23/2022 |  |  |  | gutter labor
22-0507-IR | WO0008, Complete | Dump trailer and material pickup | 2022-10-26T15:30:00.000 | WO | 0 |  |  |  | 650 |  | 0 |  |  |  |  | 2022-10-28T07:39:45.820 | Olson, Jonathon
22-0200-IR | WO0001, Complete | CAB | 2022-08-10T11:48:42.000 | WO | 0 | 215.24 | 64.92 | 215.24 | 100 |  | 0 | Deville , Jard | 09/14/2022 | 09/23/2022 |  | 2022-09-23T12:12:15.967 | Burrell, Bianca | CAB
22-0200-IR | WO0002, Complete | Tile Materials | 2022-08-10T11:48:42.000 | WO | 0 | 693.5502 | 26.63 | 5241.62 | 693.55 |  | 86.7684 |  | 08/10/2022 | 08/16/2022 |  | 2022-09-02T11:57:21.587 | Deville , Jard | FCT
22-0200-IR | WO0003, Complete | FCW | 2022-08-10T11:48:42.000 | WO | 0 | 0 | 0.48 | 103.05 | 0 |  | 100 |  | 08/10/2022 | 08/10/2022 |  | 2022-09-23T12:12:44.177 | Burrell, Bianca | FCW
22-0200-IR | WO0004, Complete | FRM | 2022-08-10T11:48:42.000 | WO | 0 | 0 | 0.95 | 195.38 | 0 |  | 100 |  | 08/10/2022 | 08/10/2022 |  | 2022-09-23T12:12:44.193 | Burrell, Bianca | FRM
22-0200-IR | WO0005, Complete | Plumbing/Tim | 2022-08-10T11:48:43.000 | WO | 0 | 349.9997 | 2.92 | 743.5 | 350 |  | 52.9254 |  | 08/10/2022 | 08/10/2022 |  | 2022-09-23T12:12:15.920 | Burrell, Bianca | PLM
22-0200-IR | WO0006, Complete | Tile labor | 2022-08-10T11:48:43.000 | WO | 0 | 1455.62 | 90.92 | 2911.24 | 50 |  | 50 |  | 09/09/2022 | 09/23/2022 |  | 2022-09-23T12:12:15.843 | Burrell, Bianca | TIL
22-0515-IR | WO0001, Complete | Contents | 2022-07-12T12:26:38.000 | WO | 0 | 37.122 | 2 | 123.74 | 30 |  | 70 |  | 07/12/2022 | 07/12/2022 |  | 2023-02-22T10:41:39.080 | Dehnke, Josh | CON
22-0515-IR | WO0002, Complete | Dumpster | 2022-07-12T12:26:38.000 | WO | 0 | 227.91 | 1.98 | 227.91 | 100 |  | 0 |  | 07/12/2022 | 07/12/2022 |  | 2023-02-22T10:41:23.697 | Dehnke, Josh | DMO
22-0515-IR | WO0003, Complete | Drywall labor and materials | 2022-07-12T12:26:38.000 | WO | 0 | 2600.0013 | 25.27 | 3566.82 | 2600 |  | 27.1059 |  | 07/12/2022 | 07/14/2022 |  | 2023-02-22T10:41:23.677 | Dehnke, Josh | DRY
22-0515-IR | WO0004 | Carpet and pad labor and materials | 2022-07-12T12:26:38.000 | WO | 0 | 1042.936 | 23.02 | 2607.34 | 40 |  | 60 |  | 03/29/2023 | 03/31/2023 |  |  |  | FCC
22-0515-IR | WO0005, Complete | PNT | 2022-07-12T12:26:38.770 | WO | 0 |  |  |  | 0 |  | 0 |  |  |  |  | 2023-02-22T10:41:23.720 | Dehnke, Josh | PNT
22-0525-IR
22-0532-RET-ER | WO0001, Complete | APP | 2022-08-30T16:13:15.630 | WO | 0 | 401.65 | 3.02 | 401.65 | 100 |  | 0 |  | 08/30/2022 | 08/30/2022 |  | 2023-03-13T10:46:59.643 | Trevino, Jeovani | APP
22-0532-RET-ER | WO0002, Complete | CAB Labor | 2022-08-30T16:13:15.000 | WO | 0 | 1000.0006 | 37.73 | 6379.63 | 1000 |  | 84.3251 |  | 03/26/2023 | 03/30/2023 |  | 2023-04-03T11:29:30.680 | Trevino, Jeovani | CAB
22-0532-RET-ER | WO0003 | CLN | 2022-08-30T16:13:15.000 | WO | 0 | 63.83 | 0.85 | 63.83 | 100 |  | 0 |  | 04/17/2023 | 04/17/2023 |  |  |  | CLN
22-0532-RET-ER | WO0004, Complete | beacon | 2022-08-30T16:13:15.000 | WO | 0 | 1000.0005 | 4.93 | 1531.88 | 1000 |  | 34.7207 |  | 08/30/2022 | 08/30/2022 |  | 2022-09-18T22:56:47.633 | Trevino, Jeovani | DRY
22-0532-RET-ER | WO0005, Complete | FCV | 2022-08-30T16:13:15.000 | WO | 0 | 629.8698 |  | 589.16 | 629.87 |  | -6.9098 |  |  |  |  | 2022-12-01T08:36:11.247 | Trevino, Jeovani | FCV
22-0532-RET-ER | WO0006, Complete | FCW | 2022-08-30T16:13:16.013 | WO | 0 | 11.23 | 0.1 | 11.23 | 100 |  | 0 |  | 08/30/2022 | 08/30/2022 |  | 2022-09-23T11:22:04.557 | Dehnke, Josh | FCW
22-0532-RET-ER | WO0007, Complete | flooring labor | 2022-08-30T16:13:16.000 | WO | 0 | 600 | 0.26 | 297.26 | 600 |  | -101.8435 |  | 08/30/2022 | 08/30/2022 |  | 2023-02-13T11:34:59.057 | Trevino, Jeovani | FNC
22-0532-RET-ER | WO0008, Complete | FRM | 2022-08-30T16:13:16.407 | WO | 0 | 6.43 | 0.07 | 6.43 | 100 |  | 0 |  | 08/30/2022 | 08/30/2022 |  | 2022-09-23T11:22:04.493 | Dehnke, Josh | FRM
22-0532-RET-ER | WO0009, Complete | INS | 2022-08-30T16:13:16.547 | WO | 0 | 15.79 | 0.05 | 15.79 | 100 |  | 0 |  | 08/30/2022 | 08/30/2022 |  | 2022-09-23T11:22:04.463 | Dehnke, Josh | INS
22-0532-RET-ER | WO00010 | PLM | 2022-08-30T16:13:16.000 | WO | 0 | 680.57 | 47.67 | 680.57 | 100 |  | 0 |  | 03/31/2023 | 04/07/2023 |  |  |  | PLM
22-0532-RET-ER | WO00011, Complete | PNT | 2022-08-30T16:13:16.893 | WO | 0 | 5.21 | 0.04 | 5.21 | 100 |  | 0 |  | 08/30/2022 | 08/30/2022 |  | 2022-09-23T11:22:04.510 | Dehnke, Josh | PNT
22-0532-RET-ER | WO00012 | TIL | 2022-08-30T16:13:17.000 | WO | 0 | 0 | 1.72 | 383.41 | 0 |  | 100 |  | 08/30/2022 | 08/30/2022 |  |  |  | TIL
22-0532-RET-ER | WO00013, Complete | WTR | 2022-08-30T16:13:17.193 | WO | 0 | 0 |  | 0 | 0 |  | 0 |  |  |  |  | 2022-09-23T11:22:04.527 | Dehnke, Josh | WTR
22-0532-RET-ER | WO00014, Complete | Flooring Labor | 2023-01-03T14:21:00.000 | WO | 0 | 565.8464 | 15.67 | 799.86 | 70.7432 |  | 29.2568 |  | 01/03/2023 | 08/31/2022 |  | 2023-01-03T13:22:26.983 | Dehnke, Josh | FCW
22-0532-RET-ER | WO00016, Complete | countertop labor | 2023-01-09T14:39:15.000 | WO | 0 | 778.9 | 6.57 | 778.9 | 100 |  | 0 |  | 01/11/2023 | 08/30/2022 |  | 2023-03-13T10:46:59.627 | Trevino, Jeovani | CAB
22-0532-RET-ER | WO00017, Complete | cabinet material | 2023-02-13T12:44:00.000 | WO | 0 | 6445.16 | 8 | 8070.8 | 6445.16 |  | 20.1422 |  | 02/13/2023 | 02/13/2023 |  | 2023-02-13T12:06:52.223 | Trevino, Jeovani | cabinet material
22-0532-RET-ER | WO00018 | countertop material | 2023-07-19T10:07:00.000 | WO | 0 | 675.73 | 8 | 675.73 | 100 |  | 0 |  | 07/19/2023 | 07/19/2023 |  |  |  | countertop material
22-0535-RET-ER | WO0001 | Carpet Stair Labor | 2023-07-22T16:18:00.000 | WO | 0 | 450 | 8 | 750 | 450 |  | 40 |  | 07/22/2023 | 07/22/2023 |  |  |  | CPT
22-0536-IR | WO0001 | DMO | 2023-05-16T11:37:23.240 | WO | 0 | 455 |  | 455 | 100 |  | 0 | [6 empty] | DMO
22-0536-IR | WO0002 | FEE | 2023-05-16T11:37:23.330 | WO | 0 | 500 |  | 500 | 100 |  | 0 | [6 empty] | FEE
22-0536-IR | WO0003 | FNC | 2023-05-16T11:37:23.407 | WO | 0 | 709.64 | 6 | 709.64 | 100 |  | 0 |  | 05/16/2023 | 05/16/2023 |  |  |  | FNC
22-0536-IR | WO0004 | SDG | 2023-05-16T11:37:23.473 | WO | 0 | 19017.91 | 70.58 | 19017.91 | 100 |  | 0 |  | 05/16/2023 | 05/25/2023 |  |  |  | SDG
22-0536-IR | WO0005 | SFG | 2023-05-16T11:37:23.563 | WO | 0 | 16411.92 | 60.21 | 16411.92 | 100 |  | 0 |  | 05/16/2023 | 05/24/2023 |  |  |  | SFG
22-0536-IR | WO0006 | WDV | 2023-05-16T11:37:23.633 | WO | 0 | 26910 |  | 26910 | 100 |  | 0 | [6 empty] | WDV
22-0543-ER | WO0002, Complete | Cabinet, trim, appliances labor | 2022-10-06T15:31:46.000 | WO | 0 | 1344.54 | 13.88 | 1792.72 | 75 |  | 25 |  | 10/06/2022 | 10/06/2022 |  | 2023-05-02T13:00:17.240 | Sleem, Michael | CAB
22-0543-ER | WO0003, Complete | Final Clean | 2022-10-06T15:31:46.000 | WO | 0 | 176.076 | 42.8 | 440.19 | 40 |  | 60 |  | 11/14/2022 | 11/18/2022 |  | 2022-11-15T04:52:49.740 | Burrell, Bianca | CLN
22-0543-ER | WO0004, Complete | Contents (Jard) | 2022-10-06T15:31:46.000 | WO | 0 | 370.308 | 9.9 | 617.18 | 60 |  | 40 |  | 10/06/2022 | 10/07/2022 |  | 2022-10-11T14:07:14.287 | Burrell, Bianca | CON
22-0543-ER | WO0005, Complete | Floor Demo | 2022-10-06T15:31:46.000 | WO | 0 | 0 | 1.98 | 340.1 | 0 |  | 100 |  | 10/06/2022 | 10/06/2022 |  | 2022-10-12T14:19:46.063 | Dehnke, Josh | DMO
22-0543-ER | WO0006, Complete | Drywall/Paint (Jard) | 2022-10-06T15:31:46.000 | WO | 0 | 2300.0014 | 43.62 | 6156.98 | 2300 |  | 62.644 |  | 10/06/2022 | 10/10/2022 |  | 2022-10-11T14:07:14.253 | Burrell, Bianca | DRY
22-0543-ER | WO0007, Complete | Floor Covering Plank - Material | 2022-10-06T15:31:46.000 | WO | 0 | 2764.692 | 8 | 4607.82 | 60 |  | 40 |  | 10/07/2022 | 10/07/2022 |  | 2022-10-11T14:08:04.620 | Burrell, Bianca | FCV
22-0543-ER | WO00013, Complete | Plumbing - Lights | 2022-10-06T15:31:47.000 | WO | 0 | 530.56 | 5.47 | 1061.12 | 50 |  | 50 |  | 10/06/2022 | 10/06/2022 |  | 2022-10-17T08:51:52.953 | Dehnke, Josh | PLM
22-0543-ER | WO00016, Complete | Floor Covering Plank - Labor (Jard) | 2022-10-07T15:27:00.000 | WO | 0 | 4146.792 | 50.39 | 6911.32 | 60 |  | 40 |  | 09/05/2022 | 10/17/2022 |  | 2022-10-07T14:31:49.773 | Burrell, Bianca
22-0543-ER | WO00017, Complete | Cabinet Materials | 2022-10-12T15:10:00.000 | WO | 0 | 5503.1011 | 8 | 11069.03 | 5503.1 |  | 50.2838 |  | 10/12/2022 | 10/12/2022 |  | 2022-10-12T14:19:46.093 | Dehnke, Josh | CAB
22-0543-ER | WO00018, Complete | Cabinet Labor | 2022-12-13T18:16:00.000 | WO | 0 | 3500.0001 | 8 | 5567.92 | 3500 |  | 37.1399 |  | 12/29/2022 | 12/29/2022 |  | 2023-04-10T09:38:05.327 | Burrell, Bianca
22-0553-ER | WO0002, Complete | FEE | 2022-12-20T13:49:59.463 | WO | 0 | 0 |  | 0 | 0 |  | 0 |  |  |  |  | 2022-12-20T13:00:28.677 | Olson, Jonathon | FEE
22-0553-ER | WO0006, Complete | Materials | 2022-12-20T13:51:00.000 | WO | 0 | 5957.87 | 8 | 5957.87 | 100 |  | 0 |  | 12/20/2022 | 12/20/2022 |  | 2022-12-20T13:00:28.693 | Olson, Jonathon | Materials
22-0553-ER | WO0007, Complete | Labor | 2022-12-20T13:52:00.000 | WO | 0 | 10093.38 | 125.22 | 20122.06 | 10093.38 |  | 49.8392 |  | 01/02/2023 | 12/30/2022 |  | 2022-12-20T13:00:28.707 | Olson, Jonathon | Labor
22-0553-ER | WO0008, Complete | Punch | 2023-01-03T12:49:00.000 | WO | 0 | 600 | 8 | 600 | 100 |  | 0 |  | 01/03/2023 | 01/03/2023 |  | 2023-05-09T09:29:42.657 | Olson, Jonathon | SFG
22-0559-IR | WO0001 | CLN | 2023-04-04T15:16:14.257 | WO | 0 | 54.48 | 0.77 | 54.48 | 100 |  | 0 |  | 04/04/2023 | 04/04/2023 |  |  |  | CLN
22-0559-IR | WO0002, Complete | DMO | 2023-04-04T15:16:14.393 | WO | 0 | 195.76 | 1.98 | 195.76 | 100 |  | 0 |  | 04/04/2023 | 04/04/2023 |  | 2023-04-15T22:28:32.783 | Olson, Jonathon | DMO
22-0559-IR | WO0003, Complete | ELS | 2023-04-04T15:16:14.000 | WO | 0 | 0 | 0.45 | 24.26 | 0 |  | 100 |  | 04/04/2023 | 04/04/2023 |  | 2023-05-05T09:30:25.617 | Olson, Jonathon | ELS
22-0559-IR | WO0004 | PNT | 2023-04-04T15:16:14.673 | WO | 0 | 442.31 | 3.72 | 442.31 | 100 |  | 0 |  | 04/04/2023 | 04/04/2023 |  |  |  | PNT
22-0559-IR | WO0005, Complete | Roofing Labor | 2023-04-04T15:16:14.000 | WO | 0 | 3200.0042 | 69.83 | 10575.38 | 3200 |  | 69.741 |  | 04/04/2023 | 04/13/2023 |  | 2023-04-07T22:32:51.893 | Olson, Jonathon | RFG
22-0559-IR | WO0006 | Downspouts | 2023-04-04T15:16:14.000 | WO | 0 | 668.03 | 1.55 | 668.03 | 100 |  | 0 |  | 04/04/2023 | 04/04/2023 |  |  |  | SFG
22-0559-IR | WO0009 | Pergola | 2023-04-04T15:16:15.000 | WO | 0 | 980.54 | 3.5 | 980.54 | 100 |  | 0 |  | 04/04/2023 | 04/04/2023 |  |  |  | XST
22-0559-IR | WO00010, Complete | Roofing Material | 2023-04-05T15:04:10.000 | WO | 0 | 3654.48 |  | 3654.48 | 100 |  | 0 |  |  |  |  | 2023-04-07T22:32:51.907 | Olson, Jonathon | Material Work Order
22-0577-IR | WO00014, Complete | CAB | 2022-10-04T09:24:26.527 | WO | 0 | 836.4 | 1.32 | 836.4 | 100 |  | 0 |  | 10/04/2022 | 10/04/2022 |  | 2022-10-21T11:03:11.490 | Dehnke, Josh | CAB
22-0577-IR | WO00015, Complete | CON | 2022-10-04T09:24:26.887 | WO | 0 | 628.81 | 10 | 628.81 | 100 |  | 0 |  | 10/04/2022 | 10/05/2022 |  | 2022-10-21T11:03:11.567 | Dehnke, Josh | CON
22-0577-IR | WO00016, Complete | DOR | 2022-10-04T09:24:27.040 | WO | 0 | 719.45 | 1.57 | 719.45 | 100 |  | 0 |  | 10/04/2022 | 10/04/2022 |  | 2022-10-21T11:03:11.583 | Dehnke, Josh | DOR
22-0577-IR | WO00017, Complete | DRY | 2022-10-04T09:24:27.197 | WO | 0 | 1484.35 | 9.27 | 1484.35 | 100 |  | 0 |  | 10/04/2022 | 10/05/2022 |  | 2022-10-17T08:00:01.477 | Trevino, Jeovani | DRY
22-0577-IR | WO00018, Complete | FCC | 2022-10-04T09:24:27.417 | WO | 0 | 853 |  | 853 | 100 |  | 0 |  |  |  |  | 2022-10-17T08:00:01.430 | Trevino, Jeovani | FCC
22-0577-IR | WO00019, Complete | FNC | 2022-10-04T09:24:27.000 | WO | 0 | 549.9998 | 4.27 | 748.52 | 550 |  | 26.5217 |  | 10/04/2022 | 10/04/2022 |  | 2022-10-21T11:03:11.603 | Dehnke, Josh | FNC
22-0577-IR | WO00020, Complete | FNH | 2022-10-04T09:24:27.827 | WO | 0 | 278.42 | 1.55 | 278.42 | 100 |  | 0 |  | 10/04/2022 | 10/04/2022 |  | 2022-10-21T11:03:11.627 | Dehnke, Josh | FNH
22-0577-IR | WO00021, Complete | HVC | 2022-10-04T09:24:27.980 | WO | 0 | 32.79 | 0.12 | 32.79 | 100 |  | 0 |  | 10/04/2022 | 10/04/2022 |  | 2022-10-21T11:03:11.657 | Dehnke, Josh | HVC
22-0577-IR | WO00022, Complete | MBL | 2022-10-04T09:24:28.120 | WO | 0 | 182.73 | 1.07 | 182.73 | 100 |  | 0 |  | 10/04/2022 | 10/04/2022 |  | 2022-10-21T11:03:11.697 | Dehnke, Josh | MBL
22-0577-IR | WO00023, Complete | MSD | 2022-10-04T09:24:28.307 | WO | 0 | 226.2 | 0.35 | 226.2 | 100 |  | 0 |  | 10/04/2022 | 10/04/2022 |  | 2022-10-21T11:03:11.727 | Dehnke, Josh | MSD
22-0577-IR | WO00024 | PLM | 2022-10-04T09:24:28.507 | WO | 0 | 729.17 | 2.87 | 729.17 | 100 |  | 0 |  | 10/04/2022 | 10/04/2022 |  |  |  | PLM
22-0577-IR | WO00025, Complete | PNL | 2022-10-04T09:24:28.633 | WO | 0 | 370.73 | 2.48 | 370.73 | 100 |  | 0 |  | 10/04/2022 | 10/04/2022 |  | 2022-10-21T11:03:11.757 | Dehnke, Josh | PNL
22-0577-IR | WO00026, Complete | PNT | 2022-10-04T09:24:28.000 | WO | 0 | 1873.452 | 24.02 | 3122.42 | 60 |  | 40 |  | 10/04/2022 | 10/06/2022 |  | 2022-10-17T08:00:20.173 | Trevino, Jeovani | PNT
22-0577-IR | WO00027, Complete | carpet labor | 2022-10-18T11:22:00.000 | WO | 0 | 1675.0009 | 17.52 | 2797.23 | 1675 |  | 40.1193 |  | 10/04/2022 | 10/18/2022 |  | 2022-10-24T08:39:51.760 | Trevino, Jeovani | george
22-0579-ER | WO0002, Complete | CO: Granite and Cabinet and FCW Extending | 2022-09-22T16:29:39.000 | WO | 0 | 7200.003 | 51.57 | 9373.82 | 7200 |  | 23.1903 |  | 09/22/2022 | 09/23/2022 |  | 2022-12-09T10:03:03.330 | Hicks, Dave | CAB
22-0579-ER | WO0007, Complete | Wood Floors | 2022-09-22T16:29:39.000 | WO | 0 | 3142.35 | 19.53 | 3142.35 | 100 |  | 0 |  | 09/22/2022 | 09/26/2022 |  | 2022-09-28T10:09:47.020 | Hicks, Dave | FCW
22-0579-ER | WO0009, Complete | Cabinets Materials | 2022-09-22T16:29:40.000 | WO | 0 | 247.296 |  | 706.56 | 35 |  | 65 |  |  |  |  | 2022-12-09T10:03:14.350 | Hicks, Dave | HVC
22-0579-ER | WO00011 | Install trash cabinet and fridge panels | 2022-09-22T16:29:40.000 | WO | 0 | 283.6 | 37.95 | 283.6 | 100 |  | 0 |  | 04/17/2023 | 04/21/2023 |  |  |  | LAB
22-0579-ER | WO00012, Complete | Staining | 2022-09-22T16:29:40.000 | WO | 0 | 0 | 4.92 | 630.93 | 0 |  | 100 |  | 09/22/2022 | 09/22/2022 |  | 2022-12-09T10:03:03.353 | Hicks, Dave | PNT
22-0585-ER | WO0001 | material- awning | 2023-07-03T13:52:19.000 | WO | 0 | 84.136 |  | 105.17 | 80 |  | 20 | [6 empty] | AWN
22-0585-ER | WO0006 | FEE | 2023-07-03T13:52:19.987 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | FEE
22-0585-ER | WO0008, Complete | material- roof | 2023-07-03T13:52:20.000 | WO | 0 | 3671.4491 |  | 4149.51 | 3671.45 |  | 11.5209 |  |  |  |  | 2023-07-31T12:32:34.197 | Schmidt, Jeremy | RFG
22-0585-ER | WO0009 | material- window wrap (aluminum) | 2023-07-03T13:52:20.000 | WO | 0 | 270.264 |  | 337.83 | 80 |  | 20 | [6 empty] | SDG
22-0585-ER | WO00011 | material- window screens (2) | 2023-07-03T13:52:20.000 | WO | 0 | 95.896 |  | 119.87 | 80 |  | 20 | [6 empty] | WDR
22-0585-ER | WO00012 | labor- window | 2023-07-03T13:52:20.000 | WO | 0 | 157.718 | 0 | 286.76 | 55 |  | 45 |  | 07/03/2023 | 07/03/2023 |  |  |  | WDW
22-0585-ER | WO00013 | labor- awning | 2023-07-03T13:17:48.000 | WO | 0 | 242 | 0.62 | 440 | 55 |  | 45 |  | 07/03/2023 | 07/03/2023 |  |  |  | Labor Work Order
22-0585-ER | WO00015 | labor- garage exterior door (insulated) | 2023-07-03T13:24:48.000 | WO | 0 | 128.472 | 9.66 | 160.59 | 80 |  | 20 |  | 07/03/2023 | 07/12/2023 |  |  |  | Labor Work Order
22-0585-ER | WO00017 | labor- window screens (2) | 2023-07-03T13:29:07.000 | WO | 0 | 20.52 | 0.3 | 25.65 | 80 |  | 20 |  | 07/03/2023 | 07/03/2023 |  |  |  | Labor Work Order
22-0585-ER | WO00019 | overhead garage door | 2023-07-03T13:32:36.000 | WO | 0 | 698.265 | 2.34 | 775.85 | 90 |  | 10 |  | 07/03/2023 | 07/03/2023 |  |  |  | Labor Work Order
22-0585-ER | WO00020 | material- service door/storm door | 2023-07-05T11:50:00.000 | WO | 0 | 352.984 |  | 441.23 | 80 |  | 20 | [6 empty] | DOR
22-0585-ER | WO00021 | labor- service door and storm door | 2023-07-05T11:30:50.000 | WO | 0 | 85.045 | 1.72 | 170.09 | 50 |  | 50 |  | 07/03/2023 | 07/03/2023 |  |  |  | Labor Work Order
22-0585-ER | WO00022 | labor- clean and paint garage door | 2023-07-05T12:32:00.000 | WO | 0 | 307.266 | 10.13 | 512.11 | 60 |  | 40 |  | 07/03/2023 | 07/05/2023
22-0585-ER | WO00023 | siding labor and material.. one piece | 2023-07-11T12:20:00.000 | WO | 0 | 39.18 | 8.26 | 58.75 | 39.18 |  | 33.3106 |  | 07/04/2023 | 07/11/2023
22-0585-ER | WO00027, Complete | roofing and gutters/downspouts | 2023-07-13T12:51:00.000 | WO | 0 | 6073.2367 | 88.21 | 14510.39 | 6073.23 |  | 58.1456 |  | 07/03/2023 | 07/27/2023 |  | 2023-07-27T09:11:13.907 | Schmidt, Jeremy
22-0585-ER | WO00028 | labor- window wraps | 2023-07-27T10:05:00.000 | WO | 0 | 952.569 | 23.36 | 2116.82 | 45 |  | 55 |  | 07/03/2023 | 07/27/2023
22-0590-ER | WO0002, Complete | ELE | 2022-09-15T11:35:50.000 | WO | 0 | 0 | 1.72 | 398.51 | 0 |  | 100 |  | 09/15/2022 | 09/15/2022 |  | 2023-04-28T12:08:47.687 | Olson, Jonathon | ELE
22-0590-ER | WO0004 | FEE | 2022-09-15T11:35:50.743 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | FEE
22-0590-ER | WO0009, Complete | siding labor | 2022-09-15T11:36:00.000 | WO | 0 | 7199.996 | 66.49 | 11130.79 | 7200 |  | 35.3146 |  | 09/15/2022 | 09/29/2022 |  | 2023-04-28T12:08:47.687 | Olson, Jonathon | siding labor
22-0590-ER | WO00010, Complete | siding materials | 2022-09-15T11:37:00.000 | WO | 0 | 6922.7055 |  | 10619.21 | 6922.71 |  | 34.8096 |  |  |  |  | 2022-10-21T12:42:50.590 | Dehnke, Josh | siding materials
22-0590-ER | WO00011, Complete | roofing materials | 2022-09-27T10:13:00.000 | WO | 0 | 4971.44 | 16 | 4971.44 | 100 |  | 0 |  | 09/15/2022 | 09/27/2022 |  | 2022-09-27T09:20:15.747 | Olson, Jonathon | roofing materials
22-0590-ER | WO00012, Complete | roofing labor | 2022-09-27T10:13:00.000 | WO | 0 | 4400 | 78.03 | 10625.14 | 4400 |  | 58.5888 |  | 09/15/2022 | 09/27/2022 |  | 2022-09-28T14:55:31.587 | Olson, Jonathon | roofing labor
22-0590-ER | WO00013, Complete | Window Wraps | 2023-02-17T12:43:00.000 | WO | 0 | 2125.24 | 41.35 | 5313.1 | 40 |  | 60 |  | 02/17/2023 | 09/26/2022 |  | 2023-05-09T09:32:34.747 | Olson, Jonathon
22-0598-WAR | WO0002, Complete | ELE | 2022-10-06T18:52:44.000 | WO | 0 | 259.6504 | 8.83 | 1668.79 | 259.65 |  | 84.4408 |  | 10/06/2022 | 10/07/2022 |  | 2022-11-12T22:59:28.233 | Olson, Jonathon | ELE
22-0598-WAR | WO0006, Complete | Roofing Labor | 2022-10-06T18:53:00.000 | WO | 0 | 3680.0029 | 50.65 | 7951.21 | 3680 |  | 53.7177 |  | 10/06/2022 | 10/12/2022 |  | 2022-10-08T07:45:10.433 | Olson, Jonathon | Roofing Labor
22-0598-WAR | WO0007, Complete | Materials | 2022-10-06T18:53:00.000 | WO | 0 | 2433.46 | 8 | 2433.46 | 100 |  | 0 |  | 10/06/2022 | 10/06/2022 |  | 2022-10-06T20:00:04.953 | Olson, Jonathon | Materials
22-0598-WAR | WO0008 | Punch | 2023-06-02T13:24:00.000 | WO | 0 | 500 | 8 | 800 | 500 |  | 37.5 |  | 06/02/2023 | 06/02/2023
22-0600-IR | WO0001 | Warranty Tile Labor | 2022-08-15T09:35:00.000 | WO | 0 | 9550 | 8 | 9550 | 100 |  | 0 |  | 08/15/2022 | 08/15/2022 |  |  |  | TIL
22-0603-ER | WO0001 | ACT | 2023-07-05T18:17:47.703 | WO | 0 | 3558.04 | 17.83 | 3558.04 | 100 |  | 0 |  | 07/05/2023 | 07/07/2023 |  |  |  | ACT
22-0603-ER | WO0002 | CAB | 2023-07-05T18:17:47.783 | WO | 0 | 445.23 | 4.05 | 445.23 | 100 |  | 0 |  | 07/05/2023 | 07/05/2023 |  |  |  | CAB
22-0603-ER | WO0003 | CLN | 2023-07-05T18:17:47.847 | WO | 0 | 298.18 | 3.85 | 298.18 | 100 |  | 0 |  | 07/05/2023 | 07/05/2023 |  |  |  | CLN
22-0603-ER | WO0004, Complete | CPS - College Hunks | 2023-07-05T18:17:47.000 | WO | 0 | 4718.997 | 72 | 8550.72 | 4719 |  | 44.8117 |  | 07/05/2023 | 07/17/2023 |  | 2023-07-17T08:48:03.840 | Burrell, Bianca | CPS
22-0603-ER | WO0005 | DMO | 2023-07-05T18:17:48.330 | WO | 0 | 396.99 | 2.27 | 396.99 | 100 |  | 0 |  | 07/05/2023 | 07/05/2023 |  |  |  | DMO
22-0603-ER | WO0006 | FCC | 2023-07-05T18:17:48.440 | WO | 0 | 1884.93 | 5.38 | 1884.93 | 100 |  | 0 |  | 07/05/2023 | 07/05/2023 |  |  |  | FCC
22-0603-ER | WO0007 | FCV | 2023-07-05T18:17:48.503 | WO | 0 | 3645.63 | 14.37 | 3645.63 | 100 |  | 0 |  | 07/05/2023 | 07/06/2023 |  |  |  | FCV
22-0603-ER | WO0008 | FEE | 2023-07-05T18:17:48.563 | WO | 0 | 6480 |  | 6480 | 100 |  | 0 | [6 empty] | FEE
22-0603-ER | WO0009 | FNC | 2023-07-05T18:17:48.627 | WO | 0 | 394.51 | 3.4 | 394.51 | 100 |  | 0 |  | 07/05/2023 | 07/05/2023 |  |  |  | FNC
22-0603-ER | WO00010 | FNH | 2023-07-05T18:17:48.767 | WO | 0 | 92.62 | 0.9 | 92.62 | 100 |  | 0 |  | 07/05/2023 | 07/05/2023 |  |  |  | FNH
22-0603-ER | WO00011 | HVC | 2023-07-05T18:17:48.830 | WO | 0 | 26.92 | 0.15 | 26.92 | 100 |  | 0 |  | 07/05/2023 | 07/05/2023 |  |  |  | HVC
22-0603-ER | WO00012 | INS | 2023-07-05T18:17:48.893 | WO | 0 | 77.85 | 0.35 | 77.85 | 100 |  | 0 |  | 07/05/2023 | 07/05/2023 |  |  |  | INS
22-0603-ER | WO00013 | LAB | 2023-07-05T18:17:48.970 | WO | 0 | 94.16 | 1.5 | 94.16 | 100 |  | 0 |  | 07/05/2023 | 07/05/2023 |  |  |  | LAB
22-0603-ER | WO00014 | LIT | 2023-07-05T18:17:49.050 | WO | 0 | 84.98 | 0.53 | 84.98 | 100 |  | 0 |  | 07/05/2023 | 07/05/2023 |  |  |  | LIT
22-0603-ER | WO00015 | MBL | 2023-07-05T18:17:49.127 | WO | 0 | 280.37 | 1.42 | 280.37 | 100 |  | 0 |  | 07/05/2023 | 07/05/2023 |  |  |  | MBL
22-0603-ER | WO00016 | MSD | 2023-07-05T18:17:49.173 | WO | 0 | 19.25 | 0.2 | 19.25 | 100 |  | 0 |  | 07/05/2023 | 07/05/2023 |  |  |  | MSD
22-0603-ER | WO00017 | PLA | 2023-07-05T18:17:49.283 | WO | 0 | 2645.72 | 15.07 | 2645.72 | 100 |  | 0 |  | 07/05/2023 | 07/06/2023 |  |  |  | PLA
22-0603-ER | WO00018 | PLM | 2023-07-05T18:17:49.407 | WO | 0 | 2326.3 | 9.07 | 2326.3 | 100 |  | 0 |  | 07/05/2023 | 07/06/2023 |  |  |  | PLM
22-0603-ER | WO00019 | PNT | 2023-07-05T18:17:49.470 | WO | 0 | 162.56 | 1.05 | 162.56 | 100 |  | 0 |  | 07/05/2023 | 07/05/2023 |  |  |  | PNT
22-0603-ER | WO00020 | TBA | 2023-07-05T18:17:49.550 | WO | 0 | 104.64 | 1.15 | 104.64 | 100 |  | 0 |  | 07/05/2023 | 07/05/2023 |  |  |  | TBA
22-0603-ER | WO00021 | TIL | 2023-07-05T18:17:49.707 | WO | 0 | 4436.64 | 20.3 | 4436.64 | 100 |  | 0 |  | 07/05/2023 | 07/07/2023 |  |  |  | TIL
22-0603-ER | WO00022 | WDT | 2023-07-05T18:17:49.957 | WO | 0 | 53.57 | 0.6 | 53.57 | 100 |  | 0 |  | 07/05/2023 | 07/05/2023 |  |  |  | WDT
22-0603-ER | WO00023 | WPR | 2023-07-05T18:17:50.097 | WO | 0 | 546.23 | 3.2 | 546.23 | 100 |  | 0 |  | 07/05/2023 | 07/05/2023 |  |  |  | WPR
22-0606-ER | WO0002 | FRM | 2023-03-08T15:24:45.000 | WO | 0 | 781.8 | 24.95 | 1954.5 | 40 |  | 60 |  | 03/08/2023 | 03/10/2023 |  |  |  | FRM
22-0606-ER | WO0003 | GLS | 2023-03-08T15:24:46.007 | WO | 0 | 41.01 |  | 41.01 | 100 |  | 0 | [6 empty] | GLS
22-0606-ER | WO0004, Complete | RFG | 2023-03-08T15:24:46.000 | WO | 0 | 4500 | 61.26 | 11512.42 | 4500 |  | 60.9118 |  | 03/08/2023 | 03/16/2023 |  | 2023-04-21T13:59:30.913 | Olson, Jonathon | RFG
22-0606-ER | WO0005 | SDG | 2023-03-08T15:24:46.000 | WO | 0 | 1800.0002 | 8.75 | 1607.71 | 1800 |  | -11.9605 |  | 03/08/2023 | 03/09/2023 |  |  |  | SDG
22-0606-ER | WO0006 | SFG | 2023-03-08T15:24:46.000 | WO | 0 | 167.676 | 1.66 | 419.19 | 40 |  | 60 |  | 03/08/2023 | 03/08/2023 |  |  |  | SFG
22-0606-ER | WO0007 | WDR | 2023-03-08T15:24:46.477 | WO | 0 | 112.8 | 0.5 | 112.8 | 100 |  | 0 |  | 03/08/2023 | 03/08/2023 |  |  |  | WDR
22-0606-ER | WO0008 | WDW | 2023-03-08T15:24:46.583 | WO | 0 | 270.95 | 0 | 270.95 | 100 |  | 0 |  | 03/08/2023 | 03/08/2023 |  |  |  | WDW
22-0606-ER | WO0009, Complete | Roofing MAterial | 2023-04-14T16:11:47.000 | WO | 0 | 5256.75 |  | 5256.75 | 100 |  | 0 |  |  |  |  | 2023-04-14T16:12:15.687 | Olson, Jonathon | Material Work Order
22-0606-ER | WO00010, Complete | Stan Gully | 2023-06-28T18:28:00.000 | WO | 0 | 300.0001 | 9.59 | 763.19 | 300 |  | 60.6913 |  | 03/08/2023 | 06/28/2023 |  | 2023-07-20T08:35:22.977 | Trevino, Jeovani | Gutters
22-0614-ER | WO0002, Complete | Content Labor | 2022-09-23T14:39:02.000 | WO | 0 | 104.62 | 2 | 104.62 | 100 |  | 0 |  | 09/23/2022 | 09/23/2022 |  | 2022-11-29T14:12:47.710 | Hicks, Dave | CON
22-0614-ER | WO0007 | OSB 1/2 | 2022-09-23T14:39:02.000 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | FRM
22-0614-ER | WO0009 | Permits | 2022-09-23T14:39:02.000 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | MPR
22-0614-ER | WO00010, Complete | Panting Labor | 2022-09-23T14:39:02.000 | WO | 0 | 571.8405 | 15.5 | 1633.83 | 35 |  | 65 |  | 09/23/2022 | 09/26/2022 |  | 2022-10-18T14:19:47.900 | Hicks, Dave | PNT
22-0614-ER | WO00012, Complete | Shed Materials | 2022-09-23T14:39:03.000 | WO | 0 | 387.21 |  | 387.21 | 100 |  | 0 |  |  |  |  | 2022-09-27T14:30:56.463 | Hicks, Dave | SDG
22-0614-ER | WO00016, Complete | Window Labor | 2022-09-23T14:39:03.000 | WO | 0 | 611.842 | 18.95 | 1748.12 | 35 |  | 65 |  | 09/23/2022 | 09/26/2022 |  | 2022-10-18T14:21:56.820 | Hicks, Dave | WDW
22-0614-ER | WO00017, Complete | House Materials | 2022-09-23T14:40:00.000 | WO | 0 | 8053.19 | 8 | 8053.19 | 100 |  | 0 |  | 09/23/2022 | 09/23/2022 |  | 2022-09-27T14:30:44.080 | Hicks, Dave | MAT
22-0614-ER | WO00018, Complete | House/Shed Labor | 2022-09-24T15:01:00.000 | WO | 0 | 5600.0062 | 59.17 | 19436.57 | 5600 |  | 71.1883 |  | 09/23/2022 | 10/03/2022 |  | 2022-10-18T14:23:56.983 | Hicks, Dave
22-0614-ER | WO00019 | Window Materials | 2022-10-13T12:25:00.000 | WO | 0 | 4107.72 | 8 | 4107.72 | 100 |  | 0 |  | 10/13/2022 | 10/13/2022
22-0614-ER | WO00020, Complete | Painting Materials | 2022-10-13T12:27:00.000 | WO | 0 | 0 | 8 | 0 | 0 |  | 0 |  | 10/13/2022 | 10/13/2022 |  | 2022-10-18T14:28:25.583 | Hicks, Dave
22-0614-ER | WO00021 | Pressure washing and Stain reimbursement | 2023-03-31T10:12:00.000 | WO | 0 | 850.0003 | 15.35 | 782.87 | 850 |  | -8.5749 |  | 09/23/2022 | 09/26/2022
22-0616-ER | WO0002 | ELE | 2022-09-21T14:23:44.000 | WO | 0 | 0 | 0 | 15.41 | 0 |  | 100 |  | 09/21/2022 | 09/21/2022 |  |  |  | ELE
22-0616-ER | WO0003 | FEE | 2022-09-21T14:23:44.530 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | FEE
22-0616-ER | WO0008, Complete | Roofing material | 2022-09-21T14:32:00.000 | WO | 0 | 5500.79 | 16 | 5500.79 | 100 |  | 0 |  | 09/21/2022 | 09/21/2022 |  | 2022-09-23T09:25:06.893 | Olson, Jonathon | Roofing material
22-0616-ER | WO0009, Complete | roofing labor | 2022-09-21T14:33:00.000 | WO | 0 | 3705.8029 | 14.35 | 12695.41 | 3705.8 |  | 70.8099 |  | 09/29/2022 | 09/30/2022 |  | 2022-09-28T14:56:14.470 | Olson, Jonathon | roofing labor
22-0616-ER | WO00010, Complete | siding labor | 2022-09-21T14:33:00.000 | WO | 0 | 2300 | 13.17 | 712.8 | 2300 |  | -222.6712 |  | 09/21/2022 | 09/22/2022 |  | 2022-12-06T12:05:42.717 | Olson, Jonathon | siding labor
22-0616-ER | WO00011, Complete | siding material | 2022-09-21T17:38:00.000 | WO | 0 | 519.81 | 8 | 519.81 | 100 |  | 0 |  | 09/21/2022 | 09/21/2022 |  | 2022-11-12T22:58:21.563 | Olson, Jonathon | siding material
22-0616-ER | WO00012, Complete | Garage Light | 2022-12-06T13:04:00.000 | WO | 0 | 200 | 10.37 | 315.45 | 200 |  | 36.5985 |  | 09/21/2022 | 12/06/2022 |  | 2023-05-25T11:43:34.087 | Olson, Jonathon | Garage Light
22-0616-ER | WO00013 | Punch | 2023-05-25T12:43:00.000 | WO | 0 | 399.9996 | 15.22 | 956.82 | 400 |  | 58.1949 |  | 05/25/2023 | 09/21/2022 |  |  |  | Punch
22-0622-ER | WO0001 | Awnings | 2022-10-21T15:44:18.000 | WO | 0 | 1499.9998 | 4.97 | 1565.77 | 1500 |  | 4.2005 |  | 10/21/2022 | 10/21/2022 |  |  |  | AWN
22-0622-ER | WO0002, Complete | Dumpster | 2022-10-21T15:44:18.000 | WO | 0 | 18.99 | 0.2 | 18.99 | 100 |  | 0 |  | 10/21/2022 | 10/21/2022 |  | 2022-10-24T08:53:01.347 | Dehnke, Josh | DMO
22-0622-ER | WO0003, Complete | Permit | 2022-10-21T15:44:18.000 | WO | 0 | 0 |  | 0 | 0 |  | 0 |  |  |  |  | 2022-10-24T08:53:01.410 | Dehnke, Josh | FEE
22-0622-ER | WO0004, Complete | Materials | 2022-10-21T15:44:18.000 | WO | 0 | 3468.13 |  | 3468.13 | 100 |  | 0 |  |  |  |  | 2022-10-21T14:50:44.897 | Hicks, Dave | FPL
22-0622-ER | WO0005, Complete | Labor house roof | 2022-10-21T15:44:18.000 | WO | 0 | 3769.4797 | 54.33 | 8572.24 | 3769.48 |  | 56.0269 |  | 10/21/2022 | 10/31/2022 |  | 2022-12-09T10:28:02.367 | Hicks, Dave | RFG
22-0622-ER | WO0006, Complete | Gutters Labor and materials | 2022-12-01T09:55:00.000 | WO | 0 | 1038.0595 | 13.97 | 1268.66 | 1038.06 |  | 18.1767 |  | 10/21/2022 | 12/01/2022 |  | 2023-01-17T15:35:25.603 | Hicks, Dave
22-0623-ER | WO0001 | DMO | 2023-05-19T12:30:13.827 | WO | 0 |  |  |  | 0 |  | 0 | [6 empty] | DMO
22-0623-ER | WO0002 | FEE | 2023-05-19T12:30:13.940 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | FEE
22-0623-ER | WO0003, Complete | Roofing Labor | 2023-05-19T12:30:14.000 | WO | 0 | 3000.0036 | 58.76 | 10563.43 | 3000 |  | 71.6001 |  | 05/19/2023 | 05/29/2023 |  | 2023-05-30T09:29:51.677 | Olson, Jonathon | RFG
22-0623-ER | WO0004 | Wraps/Guards/Garage Wrap | 2023-05-19T12:30:14.000 | WO | 0 | 5000.0003 | 62.98 | 11212.02 | 5000 |  | 55.405 |  | 05/19/2023 | 05/25/2023 |  |  |  | SDG
22-0623-ER | WO0005, Complete | Material Work Order | 2023-05-25T14:17:54.000 | WO | 0 | 4494.62 |  | 4494.62 | 100 |  | 0 |  |  |  |  | 2023-05-25T14:25:37.587 | Olson, Jonathon | Material Work Order
22-0629-C | WO0001 | DMO | 2022-11-14T17:44:28.723 | WO | 0 |  |  |  | 0 |  | 0 | [6 empty] | DMO
22-0629-C | WO0002 | FEE | 2022-11-14T17:44:28.977 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | FEE
22-0629-C | WO0003, Complete | Roofing Labor | 2022-11-14T17:44:29.000 | WO | 0 | 3599.9945 | 80.4 | 12434.57 | 3600 |  | 71.0485 |  | 11/14/2022 | 11/24/2022 |  | 2023-05-15T08:57:57.237 | Olson, Jonathon | RFG
22-0629-C | WO0004 | SDG | 2022-11-14T17:44:29.243 | WO | 0 | 175.48 | 0.85 | 175.48 | 100 |  | 0 |  | 11/14/2022 | 11/14/2022 |  |  |  | SDG
22-0629-C | WO0005, Complete | Gutter Labor | 2022-11-14T17:44:29.000 | WO | 0 | 1299.9999 | 6.88 | 1668.17 | 1300 |  | 22.0703 |  | 11/14/2022 | 11/14/2022 |  | 2023-05-15T08:57:57.267 | Olson, Jonathon | SFG
22-0629-C | WO0007, Complete | Roofing Material | 2022-11-14T17:49:00.000 | WO | 0 | 5078.68 | 44 | 5078.68 | 100 |  | 0 |  | 11/14/2022 | 11/18/2022 |  | 2022-11-15T04:49:42.647 | Burrell, Bianca
22-0636-ER
22-0640-IR | WO0001 | CLN | 2022-09-12T11:16:54.000 | WO | 0 |  |  |  | 0 |  | 0 | [6 empty] | CLN
22-0640-IR | WO0004, Complete | PNT | 2022-09-12T11:16:55.000 | WO | 0 | 650.004 | 17.65 | 1083.34 | 60 |  | 40 |  | 04/17/2023 | 04/19/2023 |  | 2023-06-26T09:25:04.470 | Trevino, Jeovani | PNT
22-0640-IR | WO0007, Complete | labor | 2022-09-12T11:17:00.000 | WO | 0 | 5250 | 88 | 13617.99 | 5250 |  | 61.4481 |  | 09/12/2022 | 09/23/2022 |  | 2022-11-28T01:25:36.847 | Trevino, Jeovani | roofing labor
22-0640-IR | WO0008, Complete | materials | 2022-09-12T11:19:00.000 | WO | 0 | 5838.85 | 8 | 5838.85 | 100 |  | 0 |  | 09/12/2022 | 09/12/2022 |  | 2022-09-18T23:08:14.430 | Trevino, Jeovani | materials
22-0640-IR | WO0009, Complete | Extra Materials | 2022-09-23T12:43:00.000 | WO | 0 | 0 | 8 | 167.49 | 0 |  | 100 |  | 09/23/2022 | 09/23/2022 |  | 2022-09-23T11:44:35.513 | Dehnke, Josh | MAT
22-0640-IR | WO00010, Complete | gutter labor | 2022-11-10T10:32:00.000 | WO | 0 | 149.9997 | 10.25 | 746.78 | 150 |  | 79.9138 |  | 09/12/2022 | 11/10/2022 |  | 2023-01-02T00:19:53.137 | Trevino, Jeovani | gutters
22-0640-IR | WO00011, Complete | roof repair | 2023-06-26T14:31:00.000 | WO | 0 | 499.9999 | 14.25 | 1364.61 | 500 |  | 63.3595 |  | 06/26/2023 | 09/22/2022 |  | 2023-06-28T12:28:35.810 | Trevino, Jeovani | roof repair
22-0653-ER | WO0001 | CAB | 2022-12-27T15:03:15.517 | WO | 0 | 276.83 | 2.22 | 276.83 | 100 |  | 0 |  | 12/27/2022 | 12/27/2022 |  |  |  | CAB
22-0653-ER | WO0002, Complete | CON | 2022-12-27T15:03:15.000 | WO | 0 | 1534.0003 | 135 | 3032.64 | 1534 |  | 49.417 |  | 03/20/2023 | 04/07/2023 |  | 2023-03-27T08:55:43.113 | Burrell, Bianca | CON
22-0653-ER | WO0003 | CPS | 2022-12-27T15:03:15.857 | WO | 0 | 106.32 |  | 106.32 | 100 |  | 0 | [6 empty] | CPS
22-0653-ER | WO0005 | DOR | 2022-12-27T15:03:16.190 | WO | 0 | 492.32 | 1.27 | 492.32 | 100 |  | 0 |  | 12/27/2022 | 12/27/2022 |  |  |  | DOR
22-0653-ER | WO0006, Complete | PNT/DRY ROB | 2022-12-27T15:03:16.000 | WO | 0 | 4400.0013 | 43.79 | 7931.36 | 4400 |  | 44.524 |  | 03/20/2023 | 03/24/2023 |  | 2023-03-27T08:52:23.447 | Burrell, Bianca | DRY
22-0653-ER | WO0007 | ELE | 2022-12-27T15:03:16.580 | WO | 0 | 229.63 | 0.37 | 229.63 | 100 |  | 0 |  | 12/27/2022 | 12/27/2022 |  |  |  | ELE
22-0653-ER | WO00010, Complete | Hardwood Refinishing - All Starr Refinishing | 2022-12-27T15:03:16.000 | WO | 0 | 5979.085 | 112.62 | 8541.55 | 70 |  | 30 |  | 03/29/2023 | 12/28/2022 |  | 2023-04-10T09:29:00.320 | Burrell, Bianca | FCW
22-0653-ER | WO00011 | FNC | 2022-12-27T15:03:16.990 | WO | 0 | 841.71 | 7.15 | 841.71 | 100 |  | 0 |  | 12/27/2022 | 12/27/2022 |  |  |  | FNC
22-0653-ER | WO00012 | FRM | 2022-12-27T15:03:17.117 | WO | 0 | 337.22 | 0.62 | 337.22 | 100 |  | 0 |  | 12/27/2022 | 12/27/2022 |  |  |  | FRM
22-0653-ER | WO00013 | LIT | 2022-12-27T15:03:17.227 | WO | 0 | 171.86 | 1.07 | 171.86 | 100 |  | 0 |  | 12/27/2022 | 12/27/2022 |  |  |  | LIT
22-0653-ER | WO00014 | MPR | 2022-12-27T15:03:17.523 | WO | 0 | 378.51 | 3.27 | 378.51 | 100 |  | 0 |  | 12/27/2022 | 12/27/2022 |  |  |  | MPR
22-0653-ER | WO00016, Complete | PLM | 2022-12-27T15:03:17.000 | WO | 0 | 739.56 | 20.92 | 739.56 | 100 |  | 0 |  | 03/20/2023 | 03/22/2023 |  | 2023-03-27T08:53:34.440 | Burrell, Bianca | PLM
22-0653-ER | WO00017 | Staining | 2022-12-27T15:03:17.000 | WO | 0 | 785.09 | 5.97 | 785.09 | 100 |  | 0 |  | 12/27/2022 | 12/28/2022 |  |  |  | PNT
22-0653-ER | WO00020, Complete | Tile Labor - Beacon | 2023-03-06T09:44:00.000 | WO | 0 | 5700.0024 | 80 | 6914.03 | 5700 |  | 17.5589 |  | 03/15/2023 | 03/27/2023 |  | 2023-03-27T08:57:56.730 | Burrell, Bianca
22-0668-ER | WO0007, Complete | Roofing Labor | 2022-10-24T12:42:00.000 | WO | 0 | 8500.0029 | 165.48 | 21701.23 | 8500 |  | 60.8317 |  | 10/24/2022 | 11/15/2022 |  | 2022-11-12T22:57:37.850 | Olson, Jonathon | Roofing Labor
22-0668-ER | WO0008, Complete | Materials | 2022-10-24T12:44:00.000 | WO | 0 | 10696.27 | 8 | 10696.27 | 100 |  | 0 |  | 10/24/2022 | 10/24/2022 |  | 2022-11-06T21:19:31.937 | Olson, Jonathon | Materials
22-0669-ER | WO0001, Complete | Dumpster | 2022-09-30T10:16:40.000 | WO | 0 | 500.0001 | 1.98 | 755.18 | 500 |  | 33.7906 |  | 09/30/2022 | 09/30/2022 |  | 2022-11-29T14:11:22.493 | Dehnke, Josh | DMO
22-0669-ER | WO0003, Complete | HVAC | 2022-09-30T10:16:41.000 | WO | 0 | 0 | 1.75 | 263.68 | 0 |  | 100 |  | 09/30/2022 | 09/30/2022 |  | 2022-11-29T14:11:22.517 | Dehnke, Josh | HVC
22-0669-ER | WO0005, Complete | House Labor | 2022-09-30T10:16:42.000 | WO | 0 | 2236.4095 | 24.13 | 3440.63 | 65 |  | 35 |  | 09/30/2022 | 10/04/2022 |  | 2022-12-07T06:50:52.857 | Hicks, Dave | RFG
22-0669-ER | WO0006, Complete | Garage Labor | 2022-09-30T10:16:42.000 | WO | 0 | 900.0005 | 16.72 | 1055.36 | 900 |  | 14.721 |  | 03/20/2023 | 03/22/2023 |  | 2023-03-23T09:09:10.157 | Olson, Jonathon | SDG
22-0669-ER | WO0008, Complete | Window screen wrap gutters Labor and Materials | 2022-09-30T10:16:42.000 | WO | 0 | 2580.16 | 28.43 | 5160.32 | 50 |  | 50 |  | 09/30/2022 | 10/03/2022 |  | 2022-12-09T10:29:08.757 | Hicks, Dave | WDR
22-0669-ER | WO0009, Complete | Materials | 2022-09-30T10:21:00.000 | WO | 0 | 1320.41 | 8 | 1320.41 | 100 |  | 0 |  | 09/30/2022 | 09/30/2022 |  | 2022-11-29T14:11:22.530 | Dehnke, Josh
22-0669-ER | WO00010, Complete | Garage Siding Materials | 2022-09-30T10:33:00.000 | WO | 0 | 806.4798 | 8 | 552.77 | 806.48 |  | -45.8979 |  | 09/30/2022 | 09/30/2022 |  | 2022-12-09T10:29:08.770 | Hicks, Dave
22-0669-ER | WO00011, Complete | Punch | 2023-05-08T22:02:00.000 | WO | 0 | 500 |  | 500 | 100 |  | 0 |  |  |  |  | 2023-05-11T22:01:01.200 | Olson, Jonathon
22-0673-ER | WO0002, Complete | FEE | 2022-09-09T10:01:30.000 | WO | 0 | 0 |  | 0 | 603.44 |  | 0 |  |  |  |  | 2022-09-23T11:45:42.757 | Dehnke, Josh | FEE
22-0673-ER | WO0003, Complete | FRM | 2022-09-09T10:01:30.370 | WO | 0 | 0 |  | 0 | 0 |  | 0 |  |  |  |  | 2022-09-23T11:45:42.740 | Dehnke, Josh | FRM
22-0673-ER | WO0004, Complete | material | 2022-09-09T10:01:30.000 | WO | 0 | 6015.4514 |  | 5138.03 | 6015.45 |  | -17.077 |  |  |  |  | 2022-09-18T21:02:39.490 | Trevino, Jeovani | RFG
22-0673-ER | WO0005, Complete | WDR | 2022-09-09T10:01:30.840 | WO | 0 | 45.44 | 0.42 | 45.44 | 100 |  | 0 |  | 09/09/2022 | 09/09/2022 |  | 2022-09-23T11:45:42.720 | Dehnke, Josh | WDR
22-0673-ER | WO0006, Complete | WDW | 2022-09-09T10:01:30.963 | WO | 0 | 231.8 | 0 | 231.8 | 100 |  | 0 |  | 09/09/2022 | 09/09/2022 |  | 2022-09-23T11:45:42.697 | Dehnke, Josh | WDW
22-0673-ER | WO0007, Complete | labor | 2022-09-14T16:16:00.000 | WO | 0 | 6499.9984 | 117.13 | 16865.24 | 6500 |  | 61.4592 |  | 09/09/2022 | 09/27/2022 |  | 2022-09-18T21:02:39.507 | Trevino, Jeovani | labor
22-0674-ER | WO0002 | FEE | 2022-11-15T09:54:30.690 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | FEE
22-0674-ER | WO0006, Complete | Materials | 2022-11-16T11:21:00.000 | WO | 0 | 2290.152 | 8 | 2862.69 | 80 |  | 20 |  | 11/16/2022 | 11/16/2022 |  | 2022-11-23T17:36:22.147 | Olson, Jonathon | Materials
22-0674-ER | WO0007, Complete | Roofing Labor | 2022-11-16T11:23:00.000 | WO | 0 | 3999.9984 | 58.92 | 8296.17 | 4000 |  | 51.785 |  | 11/15/2022 | 11/22/2022 |  | 2022-12-05T07:44:45.100 | Olson, Jonathon | Roofing Labor
22-0674-ER | WO0008 | Gutter and window wraps | 2022-11-16T11:26:00.000 | WO | 0 | 1899.9992 | 30.32 | 4162.32 | 1900 |  | 54.3524 |  | 11/15/2022 | 11/16/2022 |  |  |  | Gutter and window wraps
22-0685-IR | WO0004 | FEE | 2023-01-26T12:35:34.647 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | FEE
22-0685-IR | WO00011, Complete | Siding Labor | 2023-01-26T12:36:00.000 | WO | 0 | 3400.0023 | 67.15 | 9540.92 | 3400 |  | 64.364 |  | 01/26/2023 | 02/03/2023 |  | 2023-04-15T22:26:52.897 | Olson, Jonathon | Siding Labor
22-0685-IR | WO00012, Complete | Siding Material | 2023-01-26T12:36:00.000 | WO | 0 | 4399.9988 | 8 | 3833.73 | 4400 |  | -14.7707 |  | 01/26/2023 | 01/26/2023 |  | 2023-01-26T11:42:02.867 | Olson, Jonathon | Siding Material
22-0685-IR | WO00013 | Roofing Labor | 2023-01-26T12:36:00.000 | WO | 0 | 329.388 | 12.63 | 823.47 | 40 |  | 60 |  | 01/26/2023 | 01/26/2023 |  |  |  | Roofing Labor
22-0685-IR | WO00014 | Roofing Material | 2023-01-26T12:37:00.000 | WO | 0 | 322.53 | 8 | 322.53 | 100 |  | 0 |  | 01/26/2023 | 01/26/2023 |  |  |  | Roofing Material
22-0689-IR | WO0001, Complete | CDC | 2023-05-02T16:06:52.780 | WO | 0 | 31.58 |  | 31.58 | 100 |  | 0 |  |  |  |  | 2023-08-23T09:24:18.007 | Sleem, Michael | CDC
22-0689-IR | WO0002, Complete | CLN | 2023-05-02T16:06:52.827 | WO | 0 | 391.47 | 4.8 | 391.47 | 100 |  | 0 |  | 05/02/2023 | 05/02/2023 |  | 2023-08-23T09:24:18.043 | Sleem, Michael | CLN
22-0689-IR | WO0003, Complete | CON | 2023-05-02T16:06:52.890 | WO | 0 | 964.32 | 12 | 964.32 | 100 |  | 0 |  | 05/02/2023 | 05/03/2023 |  | 2023-08-23T09:24:18.067 | Sleem, Michael | CON
22-0689-IR | WO0004, Complete | DMO | 2023-05-02T16:06:52.950 | WO | 0 | 191.74 | 1.8 | 191.74 | 100 |  | 0 |  | 05/02/2023 | 05/02/2023 |  | 2023-08-23T09:24:18.080 | Sleem, Michael | DMO
22-0689-IR | WO0005, Complete | DOR | 2023-05-02T16:06:53.027 | WO | 0 | 43.3 | 0.37 | 43.3 | 100 |  | 0 |  | 05/02/2023 | 05/02/2023 |  | 2023-08-23T09:24:18.107 | Sleem, Michael | DOR
22-0689-IR | WO0006, Complete | DRY | 2023-05-02T16:06:53.103 | WO | 0 | 1885.57 | 13.42 | 1885.57 | 100 |  | 0 |  | 05/02/2023 | 05/03/2023 |  | 2023-08-23T09:24:18.127 | Sleem, Michael | DRY
22-0689-IR | WO0007, Complete | FCC | 2023-05-02T16:06:53.197 | WO | 0 | 3371.67 | 8.85 | 3371.67 | 100 |  | 0 |  | 05/02/2023 | 05/03/2023 |  | 2023-08-23T09:24:18.137 | Sleem, Michael | FCC
22-0689-IR | WO0008, Complete | FNC | 2023-05-02T16:06:53.310 | WO | 0 | 557.92 | 5 | 557.92 | 100 |  | 0 |  | 05/02/2023 | 05/02/2023 |  | 2023-08-23T09:24:18.157 | Sleem, Michael | FNC
22-0689-IR | WO0009, Complete | PNT | 2023-05-02T16:06:53.373 | WO | 0 | 1291.84 | 10.87 | 1291.84 | 100 |  | 0 |  | 05/02/2023 | 05/03/2023 |  | 2023-08-23T09:24:18.167 | Sleem, Michael | PNT
22-0689-IR | WO00010, Complete | Simpley quality | 2023-07-13T12:55:00.000 | WO | 0 | 0 | 8 | 0 | 100 |  | 0 |  | 07/13/2023 | 07/13/2023 |  | 2023-08-23T09:24:18.187 | Sleem, Michael | Simpley quality
22-0702-IR | WO0004, Complete | Final Cleaning | 2022-11-11T12:30:13.000 | WO | 0 | 1999.9997 | 7.22 | 2601.47 | 2000 |  | 23.1204 |  | 04/14/2023 | 04/14/2023 |  | 2023-04-24T10:24:38.113 | Dehnke, Josh | CLN
22-0702-IR | WO0005, Complete | Demo Labor | 2022-11-11T12:30:13.000 | WO | 0 | 1553.895 | 5 | 1726.55 | 90 |  | 10 |  | 11/11/2022 | 11/11/2022 |  | 2022-12-07T14:37:00.497 | Dehnke, Josh | DMO
22-0702-IR | WO0007, Complete | Drywall Labor | 2022-11-11T12:30:13.000 | WO | 0 | 10801.0315 | 193.44 | 30860.09 | 35 |  | 65 |  | 11/11/2022 | 12/12/2022 |  | 2023-01-23T11:21:10.840 | Dehnke, Josh | DRY
22-0702-IR | WO0008, Complete | Electrical Labor | 2022-11-11T12:30:13.000 | WO | 0 | 7510.864 |  | 9388.58 | 80 |  | 20 |  |  |  |  | 2022-12-16T10:12:32.377 | Dehnke, Josh | ELE
22-0702-IR | WO0009, Complete | Carpet Labor | 2022-11-11T12:30:13.000 | WO | 0 | 2007.975 | 36.45 | 4015.95 | 50 |  | 50 |  | 03/27/2023 | 03/31/2023 |  | 2023-04-11T12:08:16.950 | Dehnke, Josh | FCC
22-0702-IR | WO00012, Complete | FEE | 2022-11-11T12:30:13.980 | WO | 0 | 0 |  | 0 | 0 |  | 0 |  |  |  |  | 2023-04-24T10:24:38.143 | Dehnke, Josh | FEE
22-0702-IR | WO00015, Complete | Framing Labor | 2022-11-11T12:30:14.000 | WO | 0 | 2239.62 | 21.12 | 4479.24 | 50 |  | 50 |  | 11/11/2022 | 11/15/2022 |  | 2022-12-07T14:37:00.513 | Dehnke, Josh | FRM
22-0702-IR | WO00016, Complete | HVC Cleaning | 2022-11-11T12:30:14.000 | WO | 0 | 0 | 1.97 | 355.13 | 0 |  | 100 |  | 04/14/2023 | 04/14/2023 |  | 2023-04-24T10:24:38.160 | Dehnke, Josh | HVC
22-0702-IR | WO00017, Complete | Insulation Labor/Materilas | 2022-11-11T12:30:14.000 | WO | 0 | 7965.0013 | 59.55 | 14898.63 | 7965 |  | 46.5387 |  | 11/11/2022 | 11/21/2022 |  | 2022-12-27T11:32:15.373 | Dehnke, Josh | INS
22-0702-IR | WO00019, Complete | Light Materials | 2022-11-11T12:30:14.000 | WO | 0 | 580.17 |  | 580.17 | 100 |  | 0 |  |  |  |  | 2023-03-09T09:46:55.553 | Dehnke, Josh | LIT
22-0702-IR | WO00021, Complete | Plumbing Labor | 2022-11-11T12:30:14.000 | WO | 0 | 10133.84 | 12.78 | 12667.3 | 80 |  | 20 |  | 11/11/2022 | 11/14/2022 |  | 2022-12-16T10:12:32.393 | Dehnke, Josh | PLM
22-0702-IR | WO00024, Complete | Backsplash Labor | 2022-11-11T12:30:16.000 | WO | 0 | 1052 | 23.87 | 1052 | 100 |  | 0 |  | 03/29/2023 | 03/31/2023 |  | 2023-04-18T08:53:14.797 | Dehnke, Josh | TIL
22-0702-IR | WO00027, Complete | Cabinet Labor | 2022-11-11T12:36:00.000 | WO | 0 | 2511.2311 | 18.87 | 2843.53 | 88.3139 |  | 11.6861 |  | 11/11/2022 | 11/15/2022 |  | 2023-02-13T08:56:46.270 | Dehnke, Josh | CAB
22-0702-IR | WO00028, Complete | Drywall / Paint Materials | 2022-12-07T11:38:00.000 | WO | 0 | 8659.848 | 8 | 10824.81 | 80 |  | 20 |  | 12/07/2022 | 12/07/2022 |  | 2023-01-16T08:09:22.847 | Dehnke, Josh | DRY
22-0702-IR | WO00029, Complete | Paint Labor (Texture and Paint) | 2022-12-07T15:31:00.000 | WO | 0 | 4059.8075 | 99.77 | 11599.45 | 35 |  | 65 |  | 11/11/2022 | 12/07/2022 |  | 2023-02-06T07:21:19.760 | Dehnke, Josh | PNT
22-0702-IR | WO00030, Complete | Cabinet Materials | 2022-12-07T15:40:00.000 | WO | 0 | 21739 | 8 | 25506 | 21739 |  | 14.7691 |  | 12/07/2022 | 12/07/2022 |  | 2022-12-08T11:04:09.457 | Dehnke, Josh | CAB
22-0702-IR | WO00031 | Appliance Materials | 2022-12-07T15:46:00.000 | WO | 0 | 7962.27 | 8 | 7962.27 | 100 |  | 0 |  | 12/07/2022 | 12/07/2022 |  |  |  | APP
22-0702-IR | WO00032, Complete | Ceiling Tiles | 2022-12-07T15:49:00.000 | WO | 0 | 0 | 50.1 | 9560.87 | 0 |  | 100 |  | 11/11/2022 | 12/07/2022 |  | 2022-12-16T10:12:32.410 | Dehnke, Josh | ACT
22-0702-IR | WO00033, Complete | Trim Materials | 2022-12-07T15:54:00.000 | WO | 0 | 7031.48 | 8 | 8789.35 | 80 |  | 20 |  | 12/07/2022 | 12/07/2022 |  | 2023-03-09T09:46:30.133 | Dehnke, Josh | FNC
22-0702-IR | WO00034, Complete | Carpet Materials | 2022-12-07T16:03:00.000 | WO | 0 | 7456.2 | 8 | 9320.25 | 80 |  | 20 |  | 12/07/2022 | 12/07/2022 |  | 2022-12-16T10:12:32.423 | Dehnke, Josh | CPT
22-0702-IR | WO00035, Complete | LVP Materials | 2022-12-07T16:07:00.000 | WO | 0 | 4393.376 | 8 | 5491.72 | 80 |  | 20 |  | 12/07/2022 | 12/07/2022 |  | 2022-12-16T10:12:32.473 | Dehnke, Josh | LVP
22-0702-IR | WO00036, Complete | Door Materials | 2022-12-07T16:13:00.000 | WO | 0 | 4555.464 | 8 | 5694.33 | 80 |  | 20 |  | 12/07/2022 | 12/07/2022 |  | 2023-03-09T09:46:55.503 | Dehnke, Josh | DOR
22-0702-IR | WO00037, Complete | Backsplash Materials | 2022-12-07T16:27:00.000 | WO | 0 | 196.64 | 8 | 196.64 | 100 |  | 0 |  | 12/07/2022 | 12/07/2022 |  | 2023-03-09T09:46:55.537 | Dehnke, Josh | TIL
22-0702-IR | WO00038, Complete | Finish Carpentry 2 (Bryan) | 2023-02-07T15:38:00.000 | WO | 0 | 1950 | 18.14 | 1953.02 | 1950 |  | 0.15463 |  | 03/27/2023 | 03/31/2023 |  | 2023-04-11T12:08:16.980 | Dehnke, Josh | FNC
22-0702-IR | WO00039, Complete | LVP Labor | 2023-03-09T10:14:00.000 | WO | 0 | 2821.476 | 35 | 4702.46 | 60 |  | 40 |  | 03/06/2023 | 03/09/2023 |  | 2023-03-15T15:09:28.107 | Dehnke, Josh | LVP
22-0702-IR | WO00040, Complete | Trim Labor (Bryan) | 2023-03-09T10:17:00.000 | WO | 0 | 2484.845 | 35 | 4517.9 | 55 |  | 45 |  | 03/21/2023 | 03/24/2023 |  | 2023-04-18T08:53:34.143 | Dehnke, Josh | FNC
22-0702-IR | WO00041, Complete | Door Labor (Bryan) | 2023-03-09T10:18:00.000 | WO | 0 | 1106.677 | 22.62 | 1702.58 | 65 |  | 35 |  | 03/09/2023 | 11/14/2022 |  | 2023-04-11T12:08:16.987 | Dehnke, Josh | DOR
22-0702-IR | WO00042, Complete | Finish Carpentry 1 (Bryan) | 2023-03-09T10:25:00.000 | WO | 0 | 1379.385 | 42.82 | 2758.77 | 50 |  | 50 |  | 03/09/2023 | 11/24/2022 |  | 2023-04-18T12:53:17.637 | Dehnke, Josh | FNC
22-0702-IR | WO00043, Complete | Trim Paint Labor (Bryan) | 2023-03-16T16:24:00.000 | WO | 0 | 2400 | 56.29 | 6089.35 | 2400 |  | 60.5869 |  | 03/16/2023 | 12/05/2022 |  | 2023-04-18T08:56:39.353 | Dehnke, Josh | PNT
22-0702-IR | WO00044, Complete | Material Pick Up | 2023-04-03T16:06:00.000 | WO | 0 | 250.0004 | 13.74 | 1062.71 | 250 |  | 76.4752 |  | 03/27/2023 | 04/03/2023 |  | 2023-04-11T12:08:17.000 | Dehnke, Josh | Material Pick Up
22-0702-IR | WO00045, Complete | Finish Carpentry 3 | 2023-04-18T10:09:00.000 | WO | 0 | 2999.9971 | 53.98 | 6990.67 | 3000 |  | 57.0857 |  | 03/28/2023 | 12/05/2022 |  | 2023-04-24T10:24:38.160 | Dehnke, Josh | FNC
22-0706-ER | WO0001, Complete | Drywall Labor | 2022-09-24T15:48:29.000 | WO | 0 | 636.8085 | 9.13 | 1415.13 | 45 |  | 55 |  | 09/24/2022 | 09/24/2022 |  | 2022-10-17T09:07:40.737 | Dehnke, Josh | DRY
22-0706-ER | WO0002, Complete | Electrical Labor | 2022-09-24T15:48:29.000 | WO | 0 | 30.96 | 0.18 | 30.96 | 100 |  | 0 |  | 09/24/2022 | 09/24/2022 |  | 2023-05-15T11:43:35.697 | Dehnke, Josh | ELE
22-0706-ER | WO0003, Complete | Tile Labor | 2022-09-24T15:48:29.000 | WO | 0 | 219.445 | 2.97 | 438.89 | 50 |  | 50 |  | 09/24/2022 | 09/24/2022 |  | 2022-12-13T10:26:07.333 | Hicks, Dave | FCT
22-0706-ER | WO0004, Complete | Tile Materials | 2022-09-24T15:48:29.000 | WO | 0 | 135 | 0 | 208.26 | 135 |  | 35.1772 |  | 09/24/2022 | 09/24/2022 |  | 2022-12-09T10:23:38.393 | Hicks, Dave | FNH
22-0706-ER | WO0007, Complete | Plumbing Labor and Materials | 2022-09-24T15:48:30.000 | WO | 0 | 699.9996 | 2.4 | 996.16 | 700 |  | 29.7302 |  | 09/24/2022 | 09/24/2022 |  | 2022-10-17T09:07:40.703 | Dehnke, Josh | PLM
22-0706-ER | WO0009, Complete | Wallpaper Labor and Materials | 2022-09-24T15:48:30.000 | WO | 0 | 0 | 5.45 | 981.82 | 0 |  | 100 |  | 09/24/2022 | 09/24/2022 |  | 2023-05-15T11:43:35.710 | Dehnke, Josh | WPR
22-0706-ER | WO00010, Complete | Drywall Materials | 2022-09-24T15:49:00.000 | WO | 0 | 65.55 | 8 | 65.55 | 100 |  | 0 |  | 09/24/2022 | 09/24/2022 |  | 2022-10-17T09:07:40.667 | Dehnke, Josh
22-0707-ER | WO0002, Complete | Roofing Labor | 2022-10-17T12:26:30.000 | WO | 0 | 3199.9981 | 28.39 | 7922.67 | 3200 |  | 59.6096 |  | 10/19/2022 | 10/25/2022 |  | 2022-11-04T14:57:14.273 | Olson, Jonathon | RFG
22-0707-ER | WO0003, Complete | dump trailer | 2022-10-17T12:26:30.000 | WO | 0 | 500 |  | 13.48 | 500 |  | -3609.1988 |  |  |  |  | 2022-11-04T14:57:14.287 | Olson, Jonathon | SDG
22-0707-ER | WO0004, Complete | Roofing/Siding materials | 2022-10-17T12:27:00.000 | WO | 0 | 5241.95 | 37 | 5241.95 | 100 |  | 0 |  | 10/17/2022 | 10/25/2022 |  | 2022-10-28T15:20:35.777 | Olson, Jonathon | RFG/SDG
22-0707-ER | WO0005, Complete | labor- Window and door wraps | 2023-07-25T13:22:31.000 | WO | 0 | 600 | 9.87 | 1496.87 | 600 |  | 59.9164 |  | 10/17/2022 | 10/18/2022 |  | 2023-07-31T11:35:49.060 | Schmidt, Jeremy | Labor Work Order
22-0713-ER | WO0001 | DMO | 2023-05-23T12:12:33.457 | WO | 0 |  |  |  | 0 |  | 0 | [6 empty] | DMO
22-0713-ER | WO0002 | ELS | 2023-05-23T12:12:33.663 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | ELS
22-0713-ER | WO0003 | FEE | 2023-05-23T12:12:33.803 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | FEE
22-0713-ER | WO0004, Complete | Roof install | 2023-05-23T12:12:33.000 | WO | 0 | 4800.0005 | 78.85 | 13545.51 | 4800 |  | 64.5639 |  | 05/23/2023 | 06/02/2023 |  | 2023-05-25T14:24:11.153 | Olson, Jonathon | RFG
22-0713-ER | WO0005 | Siding Repair | 2023-05-23T12:12:34.000 | WO | 0 | 270.0001 | 2.17 | 661.41 | 270 |  | 59.1781 |  | 05/23/2023 | 05/23/2023 |  |  |  | SFG
22-0713-ER | WO0006, Complete | Roofing Materials | 2023-05-23T11:13:15.000 | WO | 0 | 5145.69 |  | 5145.69 | 100 |  | 0 |  |  |  |  | 2023-05-25T14:24:11.170 | Olson, Jonathon | Material Work Order
22-0713-ER | WO0008 | Gutters | 2023-07-31T10:20:47.000 | WO | 0 | 492.0003 | 0.38 | 2199.69 | 492 |  | 77.6332 |  | 08/01/2023 | 08/01/2023 |  |  |  | SFG
22-0717-ER | WO0003 | Garage Door Labor | 2023-06-08T09:22:18.000 | WO | 0 | 660.95 | 6.1 | 660.95 | 100 |  | 0 |  | 06/08/2023 | 06/08/2023 |  |  |  | DOR
22-0717-ER | WO0004 | FEE | 2023-06-08T09:22:19.047 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | FEE
22-0717-ER | WO0006 | Framing / Demo Labor | 2023-06-08T09:22:19.000 | WO | 0 | 2416.588 | 46.7 | 6041.47 | 40 |  | 60 |  | 06/08/2023 | 06/15/2023 |  |  |  | FRM
22-0717-ER | WO0007 | Insulation Labor | 2023-06-08T09:22:19.000 | WO | 0 | 422.38 | 8.67 | 844.76 | 50 |  | 50 |  | 06/08/2023 | 06/08/2023 |  |  |  | INS
22-0717-ER | WO00010 | Roofing Labor | 2023-06-08T09:22:19.000 | WO | 0 | 769.221 | 9.22 | 1709.38 | 45 |  | 55 |  | 06/08/2023 | 06/09/2023 |  |  |  | RFG
22-0717-ER | WO00011 | Siding Labor | 2023-06-08T09:22:19.000 | WO | 0 | 2850.5295 | 41.15 | 6334.51 | 45 |  | 55 |  | 06/08/2023 | 06/13/2023 |  |  |  | SDG
22-0717-ER | WO00017 | Garage Materials | 2023-06-08T08:30:04.000 | WO | 0 | 7884.59 |  | 7884.59 | 100 |  | 0 | [6 empty] | Material Work Order
22-0720-ER | WO0003, Complete | FEE | 2022-10-02T18:45:56.520 | WO | 0 | 0 |  | 0 | 0 |  | 0 |  |  |  |  | 2022-10-21T12:44:37.490 | Dehnke, Josh | FEE
22-0720-ER | WO00011, Complete | Roofing Material | 2022-10-17T14:06:00.000 | WO | 0 | 4235.98 | 8 | 4235.98 | 100 |  | 0 |  | 10/17/2022 | 10/17/2022 |  | 2022-10-17T13:23:05.700 | Olson, Jonathon | Roofing Material
22-0720-ER | WO00012, Complete | Roofing Labor | 2022-10-17T14:06:00.000 | WO | 0 | 3499.9991 | 78.13 | 11311.41 | 3500 |  | 69.0578 |  | 10/02/2022 | 10/17/2022 |  | 2022-10-21T12:44:37.147 | Dehnke, Josh | Roofing Labor
22-0720-ER | WO00014, Complete | Garage door material | 2022-10-17T14:16:00.000 | WO | 0 | 1470.0004 | 20.45 | 1294.98 | 1470 |  | -13.5153 |  | 10/02/2022 | 10/17/2022 |  | 2022-11-12T22:56:48.060 | Olson, Jonathon | Garage door material
22-0720-ER | WO00015, Complete | Window Material | 2022-10-17T14:16:00.000 | WO | 0 | 288.39 | 8 | 288.39 | 100 |  | 0 |  | 10/17/2022 | 10/17/2022 |  | 2022-10-21T12:44:37.193 | Dehnke, Josh | Window Material
22-0720-ER | WO00016 | Window Labor | 2022-10-17T14:16:00.000 | WO | 0 | 276.82 | 9.75 | 276.82 | 100 |  | 0 |  | 10/02/2022 | 10/17/2022 |  |  |  | Window Labor
22-0724-ER | WO0001, Complete | Haul Debris | 2022-09-30T11:08:03.000 | WO | 0 | 245.83 | 2.48 | 245.83 | 100 |  | 0 |  | 09/30/2022 | 09/30/2022 |  | 2022-10-17T09:08:47.440 | Dehnke, Josh | DMO
22-0724-ER | WO0002, Complete | Garage Door Labor and Materials | 2022-09-30T11:08:03.000 | WO | 0 | 800.95 | 1.63 | 800.95 | 100 |  | 0 |  | 09/30/2022 | 09/30/2022 |  | 2022-10-17T09:08:47.370 | Dehnke, Josh | DOR
22-0724-ER | WO0003, Complete | Permit | 2022-09-30T11:08:03.000 | WO | 0 | 0 |  | 0 | 0 |  | 0 |  |  |  |  | 2022-11-29T14:13:05.397 | Dehnke, Josh | FEE
22-0724-ER | WO0004, Complete | Materials | 2022-09-30T11:08:03.000 | WO | 0 | 4759.21 |  | 4759.21 | 100 |  | 0 |  |  |  |  | 2022-10-17T09:08:47.513 | Dehnke, Josh | FNH
22-0724-ER | WO0005, Complete | Window Materials | 2022-09-30T11:08:03.000 | WO | 0 | 436.6 |  | 436.6 | 100 |  | 0 |  |  |  |  | 2022-10-17T09:08:47.573 | Dehnke, Josh | PNT
22-0724-ER | WO0006, Complete | House and Garage Labor | 2022-09-30T11:08:04.000 | WO | 0 | 5045.6428 | 68.88 | 11166.83 | 5045.64 |  | 54.8158 |  | 09/30/2022 | 10/11/2022 |  | 2022-10-31T11:29:31.557 | Hicks, Dave | RFG
22-0724-ER | WO0007, Complete | Window Labor | 2022-09-30T11:08:04.000 | WO | 0 | 1364.9361 | 22.02 | 3035.89 | 44.96 |  | 55.04 |  | 09/30/2022 | 10/04/2022 |  | 2022-10-31T11:29:31.573 | Hicks, Dave | SDG
22-0724-ER | WO0008, Complete | door labor | 2023-03-23T14:54:00.000 | WO | 0 | 100 | 8.87 | 152.54 | 100 |  | 34.4434 |  | 03/23/2023 | 09/30/2022 |  | 2023-05-01T10:46:17.997 | Trevino, Jeovani | door labor
22-0731-ER | WO00010, Complete | RFG | 2022-10-09T22:27:53.000 | WO | 0 | 6437.11 | 56.84 | 9018.49 | 6437.11 |  | 28.6232 |  | 10/09/2022 | 10/14/2022 |  | 2022-10-21T11:06:09.477 | Dehnke, Josh | RFG
22-0731-ER | WO00011, Complete | SDG | 2022-10-09T22:27:53.000 | WO | 0 | 1000 | 7.87 | 2081.98 | 1000 |  | 51.9688 |  | 10/09/2022 | 10/09/2022 |  | 2023-01-20T10:47:38.387 | Trevino, Jeovani | SDG
22-0731-ER | WO00012, Complete | SFG | 2022-10-09T22:27:53.000 | WO | 0 | 585.168 | 3.98 | 975.28 | 60 |  | 40 |  | 10/09/2022 | 10/09/2022 |  | 2023-02-06T11:13:39.650 | Trevino, Jeovani | SFG
22-0731-ER | WO00013, Complete | WDR | 2022-10-09T22:27:53.940 | WO | 0 | 446.07 | 0.58 | 446.07 | 100 |  | 0 |  | 10/09/2022 | 10/09/2022 |  | 2023-01-03T13:30:58.530 | Dehnke, Josh | WDR
22-0731-ER | WO00014, Complete | WDV | 2022-10-09T22:27:54.000 | WO | 0 | 166.796 | 1.45 | 416.99 | 40 |  | 60 |  | 10/09/2022 | 10/09/2022 |  | 2023-02-06T11:12:22.203 | Trevino, Jeovani | WDV
22-0731-ER | WO00015, Complete | material | 2022-10-09T22:28:00.000 | WO | 0 | 3939.86 | 8 | 3939.86 | 100 |  | 0 |  | 10/09/2022 | 10/09/2022 |  | 2022-10-09T21:30:20.553 | Trevino, Jeovani | roofing material
22-0731-ER | WO00016, Complete | interior labor | 2022-11-16T11:04:00.000 | WO | 0 | 1250.0008 | 31.43 | 2287.82 | 1250 |  | 45.3628 |  | 10/09/2022 | 11/16/2022 |  | 2022-11-21T10:51:45.280 | Trevino, Jeovani | interior work
22-0731-ER | WO00017, Complete | interior materials | 2022-11-21T11:53:00.000 | WO | 0 | 0 | 11.77 | 1153.24 | 0 |  | 100 |  | 10/09/2022 | 11/21/2022 |  | 2022-11-21T10:55:35.123 | Trevino, Jeovani | interior materials
22-0731-ER | WO00018, Complete | metal roof labor | 2023-01-13T11:01:00.000 | WO | 0 | 1730.9992 | 40.67 | 3677.25 | 1731 |  | 52.9268 |  | 03/21/2023 | 03/24/2023 |  | 2023-04-03T11:31:52.393 | Trevino, Jeovani | metal roof labor
22-0731-ER | WO00019, Complete | metal roofing material | 2023-03-06T11:28:00.000 | WO | 0 | 2236.9996 | 8 | 1457.72 | 2237 |  | -53.4588 |  | 03/06/2023 | 03/06/2023 |  | 2023-03-06T10:29:59.633 | Trevino, Jeovani | metal roof material
22-0734-ER | WO0001, Complete | ELS | 2023-02-16T13:58:57.417 | WO | 0 | 9900 | 2.55 | 9900 | 100 |  | 0 |  | 02/16/2023 | 02/16/2023 |  | 2023-04-10T09:07:33.320 | Olson, Jonathon | ELS
22-0734-ER | WO0002 | FRM | 2023-02-16T13:58:57.623 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | FRM
22-0734-ER | WO0003, Complete | Roofing Labor | 2023-02-16T13:58:57.000 | WO | 0 | 5900 | 87.78 | 14030.13 | 5900 |  | 57.9476 |  | 02/16/2023 | 02/28/2023 |  | 2023-04-15T22:25:46.930 | Olson, Jonathon | RFG
22-0734-ER | WO0005 | Window Wraps | 2023-02-16T13:58:58.000 | WO | 0 | 2625 | 44.92 | 6855.77 | 2625 |  | 61.7111 |  | 02/16/2023 | 02/23/2023 |  |  |  | SFG
22-0734-ER | WO0006, Complete | Material Work Order | 2023-04-10T14:19:28.533 | WO | 0 | 5097.19 |  | 5097.19 | 100 |  | 0 |  |  |  |  | 2023-04-15T22:25:46.947 | Olson, Jonathon | Material Work Order
22-0734-ER | WO0007 | door wrap | 2023-07-17T13:40:00.000 | WO | 0 | 400.0003 | 11.8 | 520.13 | 400 |  | 23.0961 |  | 02/23/2023 | 07/17/2023 |  |  |  | door wrap
22-0741-ER | WO0001 | DMO | 2022-10-31T14:24:10.687 | WO | 0 | 142.44 | 1.5 | 142.44 | 100 |  | 0 |  | 10/31/2022 | 10/31/2022 |  |  |  | DMO
22-0741-ER | WO0002 | FEE | 2022-10-31T14:24:10.843 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | FEE
22-0741-ER | WO0003 | PNT | 2022-10-31T14:24:10.973 | WO | 0 | 287.8 | 0.7 | 287.8 | 100 |  | 0 |  | 10/31/2022 | 10/31/2022 |  |  |  | PNT
22-0741-ER | WO0004 | RFG | 2022-10-31T14:24:11.000 | WO | 0 | 3624.188 | 54.3 | 9060.47 | 40 |  | 60 |  | 10/31/2022 | 11/08/2022 |  |  |  | RFG
22-0741-ER | WO0005 | SDG | 2022-10-31T14:24:11.000 | WO | 0 | 1215.54 | 22.53 | 3038.85 | 40 |  | 60 |  | 10/31/2022 | 11/02/2022 |  |  |  | SDG
22-0741-ER | WO0006 | SFG | 2022-10-31T14:24:11.317 | WO | 0 | 472.73 | 1.92 | 472.73 | 100 |  | 0 |  | 10/31/2022 | 10/31/2022 |  |  |  | SFG
22-0741-ER | WO0007 | WDS | 2022-10-31T14:24:11.410 | WO | 0 | 416.25 | 5 | 416.25 | 100 |  | 0 |  | 10/31/2022 | 10/31/2022 |  |  |  | WDS
22-0741-ER | WO0008, Complete | roofing materials | 2022-11-21T11:45:00.000 | WO | 0 | 4613.61 | 8 | 4613.61 | 100 |  | 0 |  | 11/21/2022 | 11/21/2022 |  | 2022-11-21T10:46:02.673 | Trevino, Jeovani | material
22-0741-ER | WO0009, Complete | siding material | 2022-11-21T11:46:00.000 | WO | 0 | 707.91 | 8 | 707.91 | 100 |  | 0 |  | 11/21/2022 | 11/21/2022 |  | 2022-11-21T10:48:32.090 | Trevino, Jeovani | siding material
22-0761-ER | WO0002 | FEE | 2022-10-12T11:51:04.900 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | FEE
22-0761-ER | WO0003 | HVC | 2022-10-12T11:51:04.993 | WO | 0 | 262.7 | 1.74 | 262.7 | 100 |  | 0 |  | 10/12/2022 | 10/12/2022 |  |  |  | HVC
22-0761-ER | WO0006, Complete | Gutter/Downspout | 2022-10-12T11:51:05.000 | WO | 0 | 88.56 | 0.58 | 88.56 | 100 |  | 0 |  | 10/12/2022 | 10/12/2022 |  | 2023-05-24T11:30:22.777 | Olson, Jonathon | SFG
22-0761-ER | WO0007 | Window Screens | 2022-10-12T11:51:05.000 | WO | 0 | 164.95 | 0.43 | 164.95 | 100 |  | 0 |  | 10/12/2022 | 10/12/2022 |  |  |  | WDR
22-0761-ER | WO0008, Complete | Roofing Materials | 2023-01-17T11:31:00.000 | WO | 0 | 6714.798 | 8 | 5337.69 | 6714.8 |  | -25.7997 |  | 01/17/2023 | 01/17/2023 |  | 2023-04-17T07:59:09.033 | Olson, Jonathon | Roofing Materials
22-0761-ER | WO0009, Complete | Siding Materials | 2023-01-17T11:31:00.000 | WO | 0 | 2280.11 | 8 | 2280.11 | 100 |  | 0 |  | 01/17/2023 | 01/17/2023 |  | 2023-04-17T07:59:09.050 | Olson, Jonathon | Siding Materials
22-0761-ER | WO00010, Complete | Roofing Labor | 2023-01-17T11:32:00.000 | WO | 0 | 6199.9963 | 111.71 | 16467.41 | 6200 |  | 62.3499 |  | 01/17/2023 | 10/26/2022 |  | 2023-04-21T13:58:52.703 | Olson, Jonathon | Roofing Labor
22-0761-ER | WO00011, Complete | Siding Labor | 2023-01-17T11:32:00.000 | WO | 0 | 4999.9991 | 89.33 | 11205.66 | 5000 |  | 55.3797 |  | 01/17/2023 | 10/24/2022 |  | 2023-05-24T11:29:54.400 | Olson, Jonathon | Siding Labor
22-0761-ER | WO00012 | window wraps | 2023-07-17T09:25:00.000 | WO | 0 | 400.0003 | 8 | 745.71 | 400 |  | 46.3598 |  | 07/17/2023 | 07/17/2023 |  |  |  | window wraps
22-0765-ER | WO0001 | DMO | 2023-03-30T08:57:29.253 | WO | 0 |  |  |  | 0 |  | 0 | [6 empty] | DMO
22-0765-ER | WO0002 | FEE | 2023-03-30T08:57:29.547 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | FEE
22-0765-ER | WO0003, Complete | RFG | 2023-03-30T08:57:29.000 | WO | 0 | 3500.0056 | 92.13 | 14766.71 | 3500 |  | 76.298 |  | 03/30/2023 | 04/13/2023 |  | 2023-05-25T14:25:17.203 | Olson, Jonathon | RFG
22-0765-ER | WO0004 | SDG | 2023-03-30T08:57:30.027 | WO | 0 | 456.61 | 2 | 456.61 | 100 |  | 0 |  | 03/30/2023 | 03/30/2023 |  |  |  | SDG
22-0765-ER | WO0005 | Gutter Work | 2023-03-30T08:57:30.000 | WO | 0 | 650.0001 | 4.15 | 921.39 | 650 |  | 29.4544 |  | 03/30/2023 | 03/30/2023 |  |  |  | SFG
22-0765-ER | WO0006, Complete | Roofing Materials | 2023-03-30T07:59:32.000 | WO | 0 | 4750.84 |  | 4750.84 | 100 |  | 0 |  |  |  |  | 2023-05-24T08:28:46.810 | Olson, Jonathon | Material Work Order
22-0765-ER | WO0007, Complete | Chimney Labor | 2023-05-24T09:27:00.000 | WO | 0 | 6514.75 | 8 | 6514.75 | 100 |  | 0 |  | 05/24/2023 | 05/24/2023 |  | 2023-05-25T14:25:17.187 | Olson, Jonathon | Chimney Labor
22-0771-ER | WO0002 | ELE | 2022-11-29T13:55:14.000 | WO | 0 | 209.632 | 3.27 | 524.08 | 40 |  | 60 |  | 11/29/2022 | 11/29/2022 |  |  |  | ELE
22-0771-ER | WO0003 | FEE | 2022-11-29T13:55:14.643 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | FEE
22-0771-ER | WO0009 | Window Well | 2022-11-29T13:55:15.000 | WO | 0 | 29.9999 | 1.1 | 170.49 | 30 |  | 82.4037 |  | 11/29/2022 | 11/29/2022 |  |  |  | SPE
22-0771-ER | WO00010, Complete | Roofing Material | 2022-11-29T13:56:00.000 | WO | 0 | 3636.58 | 8 | 3636.58 | 100 |  | 0 |  | 11/29/2022 | 11/29/2022 |  | 2022-12-09T08:31:17.720 | Olson, Jonathon | Roofing Materials
22-0771-ER | WO00011, Complete | Roofing Labor | 2022-11-29T13:56:00.000 | WO | 0 | 3000.0017 | 58.88 | 9345.13 | 3000 |  | 67.8977 |  | 11/29/2022 | 12/06/2022 |  | 2022-12-09T08:31:17.687 | Olson, Jonathon | Roofing Labor
22-0771-ER | WO00012 | Siding Labor | 2023-03-20T12:39:00.000 | WO | 0 | 5299.996 | 91.79 | 13962.68 | 5300 |  | 62.0417 |  | 03/20/2023 | 12/09/2022 |  |  |  | Siding Labor
22-0771-ER | WO00013 | Siding Materials | 2023-03-20T12:39:00.000 | WO | 0 | 8745.22 | 8 | 8745.22 | 100 |  | 0 |  | 03/20/2023 | 03/20/2023 |  |  |  | Siding Materials
22-0775-ER | WO0006, Complete | Materials | 2022-10-21T13:57:00.000 | WO | 0 | 4701.56 | 8 | 4701.56 | 100 |  | 0 |  | 10/21/2022 | 10/21/2022 |  | 2022-10-23T22:09:11.603 | Olson, Jonathon | MAT
22-0775-ER | WO0007, Complete | Roofing Labor | 2022-10-23T23:07:00.000 | WO | 0 | 4000.0036 | 69.63 | 9440.45 | 4000 |  | 57.6291 |  | 10/21/2022 | 10/31/2022 |  | 2022-10-28T07:41:42.643 | Olson, Jonathon | Roofing Labor
22-0775-ER | WO0008, Complete | gutter labor | 2022-10-25T15:46:00.000 | WO | 0 | 1400 | 16.09 | 1837.19 | 1400 |  | 23.7967 |  | 10/21/2022 | 10/25/2022 |  | 2022-12-12T11:53:47.887 | Olson, Jonathon | gutter labor
22-0775-ER | WO0009 | Stan downspout install | 2023-08-17T09:37:00.000 | WO | 0 | 150 | 8.46 | 254.37 | 150 |  | 41.0308 |  | 08/17/2023 | 10/21/2022 |  |  |  | Stan down spout install
22-0784-C | WO0005, Complete | material | 2022-08-26T13:44:00.000 | WO | 0 | 4470.151 | 8 | 3102.69 | 4470.15 |  | -44.0734 |  | 08/26/2022 | 08/26/2022 |  | 2022-09-14T15:08:07.023 | Trevino, Jeovani | material
22-0784-C | WO0006, Complete | labor | 2022-08-26T13:46:00.000 | WO | 0 | 3199.9976 | 53.9 | 7859.1 | 3200 |  | 59.2829 |  | 08/26/2022 | 09/02/2022 |  | 2022-10-21T11:19:04.893 | Dehnke, Josh | labor
22-0793-ER | WO0001, Complete | Dumpster | 2023-05-04T13:26:50.000 | WO | 0 | 640.65 | 3.3 | 640.65 | 100 |  | 0 |  | 05/04/2023 | 05/04/2023 |  | 2023-08-06T18:05:10.043 | Burrell, Bianca | DMO
22-0793-ER | WO0002, Complete | Tile - Labor | 2023-05-04T13:26:50.000 | WO | 0 | 8118.48 | 76.95 | 13530.8 | 60 |  | 40 |  | 05/04/2023 | 05/15/2023 |  | 2023-08-06T18:05:10.013 | Burrell, Bianca | FCT
22-0793-ER | WO0003, Complete | PM Labor | 2023-05-04T13:26:51.000 | WO | 0 | 1801.15 | 20 | 1801.15 | 100 |  | 0 |  | 05/04/2023 | 05/17/2023 |  | 2023-08-06T18:05:10.030 | Burrell, Bianca | LAB
22-0793-ER | WO0004 | MTL | 2023-05-04T13:26:51.150 | WO | 0 | 1950 |  | 1950 | 100 |  | 0 | [6 empty] | MTL
22-0793-ER | WO0005, Complete | Finish Metals | 2023-05-04T13:26:51.000 | WO | 0 | 3103.25 | 12.75 | 3103.25 | 100 |  | 0 |  | 05/04/2023 | 05/05/2023 |  | 2023-08-06T18:05:10.043 | Burrell, Bianca | SDG
22-0793-ER | WO0006, Complete | Tile - Material | 2023-05-04T13:26:51.000 | WO | 0 | 1859.7814 |  | 3669.25 | 1859.78 |  | 49.3144 |  |  |  |  | 2023-05-04T12:29:44.130 | Burrell, Bianca | TIL
22-0802-ER | WO0002 | FEE | 2022-10-05T17:10:19.290 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | FEE
22-0802-ER | WO0006, Complete | Gutters and Wraps | 2022-10-05T17:10:20.000 | WO | 0 | 2800 | 27.48 | 3546.23 | 2800 |  | 21.0429 |  | 10/05/2022 | 10/10/2022 |  | 2023-04-15T22:26:21.440 | Olson, Jonathon | SFG
22-0802-ER | WO0007, Complete | Materials | 2022-10-05T17:26:00.000 | WO | 0 | 4828.3694 | 8 | 4742.66 | 4828.37 |  | -1.8072 |  | 10/05/2022 | 10/05/2022 |  | 2023-04-10T11:53:36.563 | Olson, Jonathon | Materials
22-0802-ER | WO0008, Complete | Roofing Labor | 2022-10-05T17:27:00.000 | WO | 0 | 4200.0057 | 80.71 | 11522.27 | 4200 |  | 63.5488 |  | 10/05/2022 | 10/17/2022 |  | 2023-04-15T22:26:21.423 | Olson, Jonathon | Roofing Labor
22-0802-ER | WO0009, Complete | Gutter Cut down and fasica | 2023-08-24T10:36:00.000 | WO | 0 | 449.9998 | 11.23 | 531.36 | 450 |  | 15.3117 |  | 08/24/2023 | 10/05/2022 |  | 2023-08-24T09:37:20.580 | Dehnke, Josh | Gutter Repair
22-0808-ER | WO0005, Complete | Permit | 2023-02-24T14:16:46.000 | WO | 0 | 0 |  | 0 | 0 |  | 0 |  |  |  |  | 2023-02-24T13:56:58.133 | Olson, Jonathon | FEE
22-0808-ER | WO0006, Complete | HVC | 2023-02-24T14:16:46.213 | WO | 0 | 234.76 | 1.75 | 234.76 | 100 |  | 0 |  | 02/24/2023 | 02/24/2023 |  | 2023-02-24T13:56:58.103 | Olson, Jonathon | HVC
22-0808-ER | WO00010, Complete | Dumpster | 2023-02-24T14:18:00.000 | WO | 0 | 0 | 8 | 356 | 0 |  | 100 |  | 02/24/2023 | 02/24/2023 |  | 2023-02-24T13:41:56.903 | Olson, Jonathon | Dumpster
22-0808-ER | WO00013, Complete | House Roofing Labor | 2023-02-24T14:19:00.000 | WO | 0 | 3008.0778 | 57.64 | 7713.02 | 3008.08 |  | 61 |  | 02/24/2023 | 03/03/2023 |  | 2023-02-24T13:56:58.073 | Olson, Jonathon | House Roofing Labor
22-0808-ER | WO00014, Complete | House Materials | 2023-02-24T14:33:00.000 | WO | 0 | 2364.8202 | 8 | 2275.13 | 2364.82 |  | -3.9422 |  | 02/24/2023 | 02/24/2023 |  | 2023-02-24T13:56:58.150 | Olson, Jonathon | House Materials
22-0808-ER | WO00015, Complete | Gutter Labor | 2023-02-24T14:34:00.000 | WO | 0 | 399.9998 | 14.67 | 1631.54 | 400 |  | 75.4833 |  | 02/24/2023 | 02/24/2023 |  | 2023-02-24T13:56:58.167 | Olson, Jonathon | Gutter Labor
22-0808-ER | WO00016, Complete | Siding Materials | 2023-02-24T14:34:00.000 | WO | 0 | 5200.7572 | 8 | 6338.63 | 5200.76 |  | 17.9514 |  | 02/24/2023 | 02/24/2023 |  | 2023-02-24T13:56:58.180 | Olson, Jonathon | Siding Materials
22-0808-ER | WO00017, Complete | Siding Labor | 2023-02-24T14:35:00.000 | WO | 0 | 3000.0011 | 50 | 5737.95 | 3000 |  | 47.7165 |  | 02/24/2023 | 03/02/2023 |  | 2023-04-15T22:33:46.360 | Olson, Jonathon | Siding Labor
22-0808-ER | WO00018 | window wraps repair | 2023-07-17T13:29:00.000 | WO | 0 | 0 | 8 | 0 | 100 |  | 0 |  | 07/17/2023 | 07/17/2023 |  |  |  | window wraps repair
22-0808-ER | WO00019 | window wraps | 2023-07-18T15:42:00.000 | WO | 0 | 0 | 8 | 0 | 100 |  | 0 |  | 07/18/2023 | 07/18/2023 |  |  |  | window wraps
22-0477-RET-ER | WO0001 | DMO | 2023-05-30T13:37:55.003 | WO | 0 | 98.33 | 1 | 98.33 | 100 |  | 0 |  | 05/30/2023 | 05/30/2023 |  |  |  | DMO
22-0477-RET-ER | WO0002 | FEE | 2023-05-30T13:37:55.160 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | FEE
22-0477-RET-ER | WO0003 | FRM | 2023-05-30T13:37:55.303 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | FRM
22-0477-RET-ER | WO0004 | RFG | 2023-05-30T13:37:55.000 | WO | 0 | 2903.4148 | 42.05 | 6598.67 | 44 |  | 56 |  | 05/30/2023 | 06/05/2023 |  |  |  | RFG
22-0477-RET-ER | WO0005 | SFG | 2023-05-30T13:37:55.000 | WO | 0 | 500 | 2.85 | 2280.68 | 500 |  | 78.0767 |  | 05/30/2023 | 05/30/2023 |  |  |  | SFG
22-0477-RET-ER | WO0006 | WDS | 2023-05-30T13:37:56.177 | WO | 0 | 897.28 | 0 | 897.28 | 100 |  | 0 |  | 05/30/2023 | 05/30/2023 |  |  |  | WDS
22-0477-RET-ER | WO0007 | Material Work Order | 2023-05-30T12:38:26.017 | WO | 0 | 2863.29 |  | 2863.29 | 100 |  | 0 | [6 empty] | Material Work Order
22-0477-RET-ER | WO0008 | DMO | 2023-06-26T12:39:56.450 | WO | 0 | 98.33 | 1 | 98.33 | 100 |  | 0 |  | 06/26/2023 | 06/26/2023 |  |  |  | DMO
22-0477-RET-ER | WO0009 | SFG | 2023-06-26T12:39:56.000 | WO | 0 | 999.9998 | 16.25 | 2477.43 | 1000 |  | 59.6356 |  | 06/26/2023 | 06/27/2023 |  |  |  | SFG
22-0821-IR
22-0822-ER | WO0001, Complete | APP | 2022-12-12T15:21:26.867 | WO | 0 | 842.67 | 4.58 | 842.67 | 100 |  | 0 |  | 12/12/2022 | 12/12/2022 |  | 2023-05-02T17:24:16.630 | Sleem, Michael | APP
22-0822-ER | WO0002, Complete | CAB | 2022-12-12T15:21:26.950 | WO | 0 | 1539.05 | 3.34 | 1539.05 | 100 |  | 0 |  | 12/12/2022 | 12/12/2022 |  | 2023-05-02T17:24:16.647 | Sleem, Michael | CAB
22-0822-ER | WO0003, Complete | CLN | 2022-12-12T15:21:27.020 | WO | 0 | 250.15 | 0.57 | 250.15 | 100 |  | 0 |  | 12/12/2022 | 12/12/2022 |  | 2023-05-02T17:24:16.680 | Sleem, Michael | CLN
22-0822-ER | WO0004, Complete | Door - Labor | 2022-12-12T15:21:27.000 | WO | 0 | 1241.68 | 10.75 | 1241.68 | 100 |  | 0 |  | 12/12/2022 | 12/13/2022 |  | 2023-05-02T17:24:16.693 | Sleem, Michael | DOR
22-0822-ER | WO0005, Complete | Drywall | 2022-12-12T15:21:27.000 | WO | 0 | 9730.71 | 23.55 | 19461.42 | 50 |  | 50 |  | 01/09/2023 | 01/12/2023 |  | 2023-01-24T09:19:42.790 | Burrell, Bianca | DRY
22-0822-ER | WO0006, Complete | ELE | 2022-12-12T15:21:27.387 | WO | 0 | 484.21 | 2.95 | 484.21 | 100 |  | 0 |  | 12/12/2022 | 12/12/2022 |  | 2023-05-02T17:24:16.710 | Sleem, Michael | ELE
22-0822-ER | WO0007, Complete | Carpet - labor | 2022-12-12T15:21:27.000 | WO | 0 | 1106.3325 | 3.22 | 1702.05 | 65 |  | 35 |  | 03/09/2023 | 03/10/2023 |  | 2023-03-13T10:50:38.257 | Burrell, Bianca | FCC
22-0822-ER | WO0008, Complete | Vinyl - Labor | 2022-12-12T15:21:27.000 | WO | 0 | 384.748 | 13.55 | 549.64 | 70 |  | 30 |  | 03/22/2023 | 03/23/2023 |  | 2023-03-27T09:19:37.330 | Burrell, Bianca | FCR
22-0822-ER | WO0009, Complete | Underlayment | 2022-12-12T15:21:27.000 | WO | 0 | 79.5001 | 9.98 | 221.15 | 79.5 |  | 64.0515 |  | 02/01/2023 | 02/02/2023 |  | 2023-01-27T11:52:49.527 | Burrell, Bianca | FCV
22-0822-ER | WO00010, Complete | Hardwood - Material | 2022-12-12T15:21:27.000 | WO | 0 | 5576.941 |  | 4748.79 | 5576.94 |  | -17.4392 |  |  |  |  | 2023-01-24T09:22:43.237 | Burrell, Bianca | FCW
22-0822-ER | WO00011, Complete | Base & Trim Material | 2022-12-12T15:21:27.000 | WO | 0 | 1406.1005 |  | 2522.09 | 1406.1 |  | 44.2486 |  |  |  |  | 2023-03-27T09:18:27.990 | Burrell, Bianca | FNC
22-0822-ER | WO00012, Complete | FNH | 2022-12-12T15:21:28.117 | WO | 0 | 726.29 | 7.82 | 726.29 | 100 |  | 0 |  | 12/12/2022 | 12/12/2022 |  | 2023-05-02T17:24:16.740 | Sleem, Michael | FNH
22-0822-ER | WO00013, Complete | FRM | 2022-12-12T15:21:28.000 | WO | 0 | 346.64 | 41.85 | 866.6 | 40 |  | 60 |  | 01/26/2023 | 02/01/2023 |  | 2023-01-27T11:52:18.510 | Burrell, Bianca | FRM
22-0822-ER | WO00014, Complete | HVC | 2022-12-12T15:21:28.370 | WO | 0 | 959.78 | 3.62 | 959.78 | 100 |  | 0 |  | 12/12/2022 | 12/12/2022 |  | 2023-05-02T17:24:16.757 | Sleem, Michael | HVC
22-0822-ER | WO00015, Complete | Insulation | 2022-12-12T15:21:28.000 | WO | 0 | 1529.096 | 27.33 | 3822.74 | 40 |  | 60 |  | 02/17/2023 | 02/23/2023 |  | 2023-01-12T18:03:07.483 | Burrell, Bianca | INS
22-0822-ER | WO00016, Complete | LIT | 2022-12-12T15:21:28.840 | WO | 0 | 108.66 | 1.62 | 108.66 | 100 |  | 0 |  | 12/12/2022 | 12/12/2022 |  | 2023-05-02T17:24:16.773 | Sleem, Michael | LIT
22-0822-ER | WO00017, Complete | MPR | 2022-12-12T15:21:28.977 | WO | 0 | 2313.844 | 131.85 | 2765.88 | 83.6567 |  | 16.3433 |  | 01/02/2023 | 12/30/2022 |  | 2023-05-02T17:24:16.787 | Sleem, Michael | MPR
22-0822-ER | WO00018, Complete | Mirrors | 2022-12-12T15:21:29.000 | WO | 0 | 431.13 | 1.55 | 431.13 | 100 |  | 0 |  | 12/12/2022 | 12/12/2022 |  | 2023-05-02T17:24:16.803 | Sleem, Michael | MSD
22-0822-ER | WO00019, Complete | PLM | 2022-12-12T15:21:29.160 | WO | 0 | 2212.87 | 8.45 | 2212.87 | 100 |  | 0 |  | 12/12/2022 | 12/13/2022 |  | 2023-05-02T17:24:16.803 | Sleem, Michael | PLM
22-0822-ER | WO00020, Complete | Paint | 2022-12-12T15:21:29.000 | WO | 0 | 4869.87 | 65.4 | 9739.74 | 50 |  | 50 |  | 01/16/2023 | 01/26/2023 |  | 2023-01-27T11:48:29.347 | Burrell, Bianca | PNT
22-0822-ER | WO00021, Complete | Scaffolding | 2022-12-12T15:21:29.000 | WO | 0 | 177.0345 | 22 | 393.41 | 45 |  | 55 |  | 01/12/2023 | 01/16/2023 |  | 2023-01-27T11:48:29.363 | Burrell, Bianca | SCF
22-0822-ER | WO00025, Complete | Doors & Trim | 2022-12-12T20:15:00.000 | WO | 0 | 4309.36 |  | 4309.36 | 100 |  | 0 |  |  |  |  | 2023-05-02T17:24:16.820 | Sleem, Michael
22-0822-ER | WO00026, Complete | Bathroom Vanity - Labor | 2022-12-12T20:25:00.000 | WO | 0 | 286.37 | 10.47 | 286.37 | 100 |  | 0 |  | 12/12/2022 | 12/12/2022 |  | 2023-05-02T17:24:16.833 | Sleem, Michael
22-0822-ER | WO00027, Complete | Vinyl - Material | 2022-12-12T20:30:00.000 | WO | 0 | 136.5001 | 8 | 387.14 | 136.5 |  | 64.7414 |  | 02/23/2023 | 02/23/2023 |  | 2023-02-22T13:11:37.490 | Burrell, Bianca
22-0822-ER | WO00028, Complete | Hardwood - Labor | 2022-12-12T20:32:00.000 | WO | 0 | 4699.9986 | 36.8 | 6389.87 | 4700 |  | 26.4461 |  | 02/02/2023 | 02/08/2023 |  | 2023-02-20T08:05:07.153 | Burrell, Bianca
22-0822-ER | WO00029, Complete | Carpet - Material | 2022-12-12T20:32:00.000 | WO | 0 | 3875.52 | 8 | 3875.52 | 100 |  | 0 |  | 02/08/2023 | 02/09/2023 |  | 2023-02-20T08:05:07.140 | Burrell, Bianca
22-0822-ER | WO00030, Complete | Hardwood - Refinishing | 2022-12-12T20:33:00.000 | WO | 0 | 3800.0027 | 55.25 | 6227.43 | 3800 |  | 38.9796 |  | 02/09/2023 | 02/17/2023 |  | 2023-02-20T08:05:07.123 | Burrell, Bianca
22-0822-ER | WO00031, Complete | Door & Trim Staining | 2023-03-14T17:27:11.000 | WO | 0 | 4010.82 | 59.46 | 4010.82 | 100 |  | 0 |  | 12/12/2022 | 12/29/2022 |  | 2023-05-02T17:23:29.983 | Sleem, Michael | Labor Work Order
22-0822-ER | WO00032, Complete | Trim Labor | 2023-03-14T17:28:07.000 | WO | 0 | 2184.8891 | 22.68 | 2559.65 | 2184.89 |  | 14.6411 |  | 03/22/2023 | 03/24/2023 |  | 2023-03-27T09:22:11.753 | Burrell, Bianca | Labor Work Order
22-0833-IR | WO0001, Complete | contents labor | 2022-11-10T09:18:52.000 | WO | 0 | 51.56 | 1 | 51.56 | 100 |  | 0 |  | 11/10/2022 | 11/10/2022 |  | 2023-01-06T08:20:30.443 | Olson, Jonathon | CON
22-0833-IR | WO0002, Complete | dumpster | 2022-11-10T09:18:52.000 | WO | 0 | 81.33 |  | 81.33 | 100 |  | 0 |  |  |  |  | 2023-01-06T08:20:30.427 | Olson, Jonathon | DMO
22-0833-IR | WO0003, Complete | Interior Labor | 2022-11-10T09:18:52.000 | WO | 0 | 1133.06 | 6.12 | 1133.06 | 100 |  | 0 |  | 11/10/2022 | 11/10/2022 |  | 2023-01-06T08:20:30.413 | Olson, Jonathon | DRY
22-0833-IR | WO0004, Complete | Electrical labor | 2022-11-10T09:18:52.000 | WO | 0 | 258.57 | 0 | 258.57 | 100 |  | 0 |  | 11/10/2022 | 11/10/2022 |  | 2023-01-06T08:20:30.397 | Olson, Jonathon | ELE
22-0833-IR | WO0005, Complete | FPL | 2022-11-10T09:18:53.000 | WO | 0 | 0 | 1.8 | 618.64 | 0 |  | 100 |  | 11/10/2022 | 11/10/2022 |  | 2023-01-06T08:20:30.380 | Olson, Jonathon | FPL
22-0833-IR | WO00013, Complete | Roofing Labor | 2022-11-12T23:41:00.000 | WO | 0 | 7899.9938 | 117.63 | 16831.13 | 7900 |  | 53.0632 |  | 11/10/2022 | 11/25/2022 |  | 2022-11-27T18:58:55.680 | Olson, Jonathon | Roofing Labor
22-0833-IR | WO00014, Complete | Roofing Material | 2022-11-12T23:42:00.000 | WO | 0 | 6896.97 | 8 | 6896.97 | 100 |  | 0 |  | 11/12/2022 | 11/12/2022 |  | 2022-11-18T20:09:49.697 | Olson, Jonathon | Roofing Material
22-0833-IR | WO00015 | window screens | 2022-11-12T23:46:00.000 | WO | 0 | 54.63 | 0.14 | 54.63 | 100 |  | 0 |  | 11/10/2022 | 11/10/2022 |  |  |  | Gutter Labor and Material
22-0833-IR | WO00016, Complete | Interior Material | 2022-12-07T14:32:00.000 | WO | 0 | 144.48 | 8 | 144.48 | 100 |  | 0 |  | 12/07/2022 | 12/07/2022 |  | 2023-01-03T11:56:29.623 | Dehnke, Josh | Interior material
22-0833-IR | WO00017 | Stan Gully | 2023-06-28T18:03:00.000 | WO | 0 | 799.9994 | 21.53 | 1347.22 | 800 |  | 40.6185 |  | 06/28/2023 | 11/12/2022 |  |  |  | Gutters
22-0834-IR | WO0009 | Insulation, Drywall and Paint | 2023-06-28T11:52:05.000 | WO | 0 | 2049.7886 | 31.22 | 5093.06 | 2049.79 |  | 59.7533 |  | 06/28/2023 | 06/29/2023 |  |  |  | DRY
22-0834-IR | WO00011 | hardwood floor | 2023-06-28T11:52:06.000 | WO | 0 | 4056.7192 | 32.27 | 4357.94 | 4056.72 |  | 6.912 |  | 06/28/2023 | 07/03/2023 |  |  |  | FCW
22-0834-IR | WO00012 | Finish Carpentry, Cabinet Install | 2023-06-28T11:52:06.000 | WO | 0 | 1950.545 | 29.64 | 3901.09 | 50 |  | 50 |  | 06/28/2023 | 07/05/2023 |  |  |  | FNC
22-0834-IR | WO00017 | Cabinet and Tops Materials | 2023-06-28T10:56:37.000 | WO | 0 | 10486.2005 | 58.2 | 15567.03 | 10486.2 |  | 32.6384 |  | 06/28/2023 | 07/06/2023 |  |  |  | Material Work Order
22-0834-IR | WO00018 | CounterTops | 2023-06-28T12:26:00.000 | WO | 0 | 2538.22 | 16.63 | 2538.22 | 100 |  | 0 |  | 06/28/2023 | 07/06/2023 |  |  |  | Ctop
22-0837-ER | WO0001, Complete | Drywall and Painting Labor | 2022-09-24T16:17:29.000 | WO | 0 | 1374.27 | 8.25 | 1374.27 | 100 |  | 0 |  | 09/24/2022 | 09/24/2022 |  | 2022-10-17T09:17:49.660 | Dehnke, Josh | DRY
22-0837-ER | WO0002, Complete | Drywall and Painting Materials | 2022-09-24T16:17:29.000 | WO | 0 | 57.25 |  | 57.25 | 100 |  | 0 |  |  |  |  | 2022-10-17T09:17:49.710 | Dehnke, Josh | PNT
22-0842-IR | WO0001 | DMO | 2023-05-04T11:40:29.610 | WO | 0 | 513.25 | 3.97 | 513.25 | 100 |  | 0 |  | 05/04/2023 | 05/04/2023 |  |  |  | DMO
22-0842-IR | WO0002 | ELE | 2023-05-04T11:40:29.703 | WO | 0 | 1201.3 | 9.6 | 1201.3 | 100 |  | 0 |  | 05/04/2023 | 05/05/2023 |  |  |  | ELE
22-0842-IR | WO0003 | EQC | 2023-05-04T11:40:29.773 | WO | 0 | 16.85 | 0.2 | 16.85 | 100 |  | 0 |  | 05/04/2023 | 05/04/2023 |  |  |  | EQC
22-0842-IR | WO0004 | FEE | 2023-05-04T11:40:29.823 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | FEE
22-0842-IR | WO0005 | FNH | 2023-05-04T11:40:29.903 | WO | 0 | 180 | 0 | 180 | 100 |  | 0 |  | 05/04/2023 | 05/04/2023 |  |  |  | FNH
22-0842-IR | WO0006 | HVC | 2023-05-04T11:40:29.983 | WO | 0 | 152.28 | 0.97 | 152.28 | 100 |  | 0 |  | 05/04/2023 | 05/04/2023 |  |  |  | HVC
22-0842-IR | WO0007 | LIT | 2023-05-04T11:40:30.143 | WO | 0 | 218.12 | 1.57 | 218.12 | 100 |  | 0 |  | 05/04/2023 | 05/04/2023 |  |  |  | LIT
22-0842-IR | WO0008 | SDG | 2023-05-04T11:40:30.237 | WO | 0 | 26643.52 | 98.88 | 26643.52 | 100 |  | 0 |  | 05/04/2023 | 05/19/2023 |  |  |  | SDG
22-0842-IR | WO0009 | SFG | 2023-05-04T11:40:30.353 | WO | 0 | 732.11 | 2.97 | 732.11 | 100 |  | 0 |  | 05/04/2023 | 05/04/2023 |  |  |  | SFG
22-0753-ER | WO0001, Complete | CON | 2022-12-15T13:40:24.000 | WO | 0 | 215.117 | 5.87 | 307.31 | 70 |  | 30 |  | 12/15/2022 | 12/15/2022 |  | 2023-02-15T14:39:51.073 | Burrell, Bianca | CON
22-0753-ER | WO0002, Complete | FCC | 2022-12-15T13:40:24.000 | WO | 0 | 593.245 | 8.97 | 1186.49 | 50 |  | 50 |  | 12/15/2022 | 12/16/2022 |  | 2023-02-15T14:39:51.083 | Burrell, Bianca | FCC
22-0753-ER | WO0003, Complete | Floor Covering Carpet - Material | 2022-12-15T13:41:00.000 | WO | 0 | 5128.7816 | 8 | 4919.94 | 5128.78 |  | -4.2448 |  | 02/12/2023 | 02/12/2023 |  | 2023-02-15T14:39:51.093 | Burrell, Bianca
22-0855-ER | WO0005, Complete | Electrical Labor / Materials | 2022-09-20T11:33:27.000 | WO | 0 | 482.64 | 1.5 | 482.64 | 100 |  | 0 |  | 09/20/2022 | 09/20/2022 |  | 2023-01-23T11:21:52.507 | Dehnke, Josh | ELE
22-0855-ER | WO0007 | Framing / window / door Labor | 2022-09-20T11:33:28.000 | WO | 0 | 3228.12 | 43 | 6456.24 | 50 |  | 50 |  | 04/03/2023 | 04/07/2023 |  |  |  | FRM
22-0855-ER | WO00012 | Siding Labor | 2022-09-20T11:33:28.000 | WO | 0 | 1961.045 | 19.98 | 3922.09 | 50 |  | 50 |  | 04/10/2023 | 04/12/2023 |  |  |  | SDG
22-0855-ER | WO00015, Complete | Demo Labor | 2023-01-04T09:49:00.000 | WO | 0 | 2553.2206 | 10.43 | 3881.95 | 2553.22 |  | 34.2284 |  | 01/04/2023 | 09/20/2022 |  | 2023-01-23T11:21:52.527 | Dehnke, Josh | DMO
22-0855-ER | WO00016, Complete | Storage Container / Contents | 2023-01-04T09:50:00.000 | WO | 0 | 0 | 20 | 1077.26 | 0 |  | 100 |  | 01/04/2023 | 09/21/2022 |  | 2023-01-23T11:21:52.537 | Dehnke, Josh | CON
22-0855-ER | WO00017 | Concrete Labor / Materials | 2023-01-04T09:50:00.000 | WO | 0 | 6496.048 | 43 | 9993.92 | 65 |  | 35 |  | 03/27/2023 | 03/31/2023 |  |  |  | CNC
22-0855-ER | WO00019 | Roofing Labor | 2023-01-04T09:52:00.000 | WO | 0 | 1048.278 | 7 | 1905.96 | 55 |  | 45 |  | 04/07/2023 | 04/07/2023 |  |  |  | RFG
22-0855-ER | WO00022, Complete | Tree Removal | 2023-01-04T10:00:00.000 | WO | 0 | 2200.0008 | 8 | 2213 | 2200 |  | 0.5874 |  | 01/04/2023 | 01/04/2023 |  | 2023-01-11T08:26:28.430 | Trevino, Jeovani | Tree
22-0855-ER | WO00023, Complete | Materials for Garage | 2023-01-11T15:34:00.000 | WO | 0 | 8809.9983 | 40 | 9084.28 | 8810 |  | 3.0193 |  | 01/04/2023 | 01/11/2023 |  | 2023-01-11T14:44:11.933 | Dehnke, Josh | MAT
22-0859-ER | WO0002, Complete | ELE | 2022-10-18T23:27:23.000 | WO | 0 | 0 | 4.83 | 882.55 | 0 |  | 100 |  | 10/18/2022 | 10/18/2022 |  | 2023-01-03T11:59:37.687 | Dehnke, Josh | ELE
22-0859-ER | WO0003, Complete | FEE | 2022-10-18T23:27:23.000 | WO | 0 | 0 |  | 0 | 636.62 |  | 0 |  |  |  |  | 2023-02-21T13:55:17.553 | Olson, Jonathon | FEE
22-0859-ER | WO0005, Complete | HVC | 2022-10-18T23:27:24.000 | WO | 0 | 0 | 1.75 | 263.68 | 0 |  | 100 |  | 10/18/2022 | 10/18/2022 |  | 2023-01-03T11:59:37.700 | Dehnke, Josh | HVC
22-0859-ER | WO0006, Complete | PNT | 2022-10-18T23:27:24.000 | WO | 0 | 0 | 3.42 | 388.86 | 0 |  | 100 |  | 10/18/2022 | 10/18/2022 |  | 2023-02-21T13:55:24.233 | Olson, Jonathon | PNT
22-0859-ER | WO00010, Complete | Roofing Materials | 2022-10-18T23:28:00.000 | WO | 0 | 6868.34 | 8 | 6868.34 | 100 |  | 0 |  | 10/18/2022 | 10/18/2022 |  | 2022-11-10T15:52:28.657 | Olson, Jonathon | Roofing Materials
22-0859-ER | WO00011, Complete | gutter and window wrap labor | 2022-10-18T23:29:00.000 | WO | 0 | 4600.0016 | 31.65 | 4369.29 | 4600 |  | -5.2803 |  | 10/18/2022 | 10/20/2022 |  | 2023-04-15T22:34:36.723 | Olson, Jonathon | Gutter and window wrap labor
22-0859-ER | WO00012, Complete | Roofing Labor | 2022-10-18T23:31:00.000 | WO | 0 | 5500 | 120.75 | 15876.71 | 5500 |  | 65.3581 |  | 10/18/2022 | 11/02/2022 |  | 2022-11-18T15:27:50.403 | Olson, Jonathon | Roofing Labor
22-0867-IR | WO0003 | Roofing Labor | 2023-04-12T22:44:13.000 | WO | 0 | 949.9999 | 6.85 | 1709.46 | 950 |  | 44.4269 |  | 04/12/2023 | 04/12/2023 |  |  |  | RFG
22-0869-ER | WO0001, Complete | Vanity Labor | 2023-01-11T11:52:50.000 | WO | 0 | 1479.52 |  | 1479.52 | 100 |  | 0 |  |  |  |  | 2023-04-24T08:20:21.773 | Burrell, Bianca | CAB
22-0869-ER | WO0002, Complete | CON | 2023-01-11T11:52:50.000 | WO | 0 | 1200.0005 | 20 | 1275.9 | 1200 |  | 5.9487 |  | 01/11/2023 | 01/13/2023 |  | 2023-03-13T11:02:53.547 | Burrell, Bianca | CON
22-0869-ER | WO0004, Complete | DRY | 2023-01-11T11:52:50.000 | WO | 0 | 1991.92 | 43.65 | 3983.84 | 50 |  | 50 |  | 02/27/2023 | 03/03/2023 |  | 2023-03-13T11:02:08.460 | Burrell, Bianca | DRY
22-0869-ER | WO0005, Complete | FCC - Labor | 2023-01-11T11:52:50.000 | WO | 0 | 2738.556 | 47.93 | 6846.39 | 40 |  | 60 |  | 03/05/2023 | 03/10/2023 |  | 2023-03-13T11:05:10.610 | Burrell, Bianca | FCC
22-0869-ER | WO0006, Complete | FCT | 2023-01-11T11:52:51.000 | WO | 0 | 1476.631 | 42.38 | 2271.74 | 65 |  | 35 |  | 02/27/2023 | 03/03/2023 |  | 2023-03-13T11:04:04.167 | Burrell, Bianca | FCT
22-0869-ER | WO0007, Complete | FNC | 2023-01-11T11:52:51.000 | WO | 0 | 442.1803 |  | 576.88 | 442.18 |  | 23.3497 |  |  |  |  | 2023-03-13T11:01:17.337 | Burrell, Bianca | FNC
22-0869-ER | WO0009, Complete | HVC | 2023-01-11T11:52:51.687 | WO | 0 | 79.46 | 0.37 | 79.46 | 100 |  | 0 |  | 01/11/2023 | 01/11/2023 |  | 2023-04-24T08:20:21.693 | Burrell, Bianca | HVC
22-0869-ER | WO00010, Complete | PLM | 2023-01-11T11:52:51.000 | WO | 0 | 418.894 | 2.35 | 598.42 | 70 |  | 30 |  | 01/11/2023 | 01/11/2023 |  | 2023-04-24T08:20:21.710 | Burrell, Bianca | PLM
22-0869-ER | WO00012, Complete | WPR | 2023-01-11T11:52:52.000 | WO | 0 | 374.84 | 50.1 | 937.1 | 40 |  | 60 |  | 02/26/2023 | 03/03/2023 |  | 2023-03-13T10:58:00.937 | Burrell, Bianca | WPR
22-0869-ER | WO00013, Complete | Bathroom Floor Tile | 2023-01-11T11:59:00.000 | WO | 0 | 337.5998 | 8 | 478.85 | 337.6 |  | 29.4978 |  | 01/11/2023 | 01/11/2023 |  | 2023-03-13T10:55:38.693 | Burrell, Bianca
22-0869-ER | WO00014, Complete | Carpet Material | 2023-01-16T23:06:00.000 | WO | 0 | 842.814 | 8 | 936.46 | 90 |  | 10 |  | 01/16/2023 | 01/16/2023 |  | 2023-03-13T10:55:45.310 | Burrell, Bianca
22-0869-ER | WO00015, Complete | Vanity Materials | 2023-01-18T11:57:00.000 | WO | 0 | 777.34 | 15.2 | 777.34 | 100 |  | 0 |  | 01/11/2023 | 01/18/2023 |  | 2023-04-24T08:20:21.727 | Burrell, Bianca | CAB
22-0869-ER | WO00016, Complete | Drywall / Paint | 2023-01-18T11:59:00.000 | WO | 0 | 265.308 | 53 | 663.27 | 40 |  | 60 |  | 03/05/2023 | 03/10/2023 |  | 2023-03-13T10:55:09.483 | Burrell, Bianca | DRY
22-0869-ER | WO00017 | Change Order | 2023-03-13T11:53:00.000 | WO | 0 | 0 | 8 | 0 | 100 |  | 0 |  | 03/13/2023 | 03/13/2023
22-0869-ER | WO00018, Complete | Carpentry Labor | 2023-03-13T11:59:00.000 | WO | 0 | 587.3 | 13.45 | 587.3 | 100 |  | 0 |  | 01/11/2023 | 03/13/2023 |  | 2023-04-24T08:20:21.757 | Burrell, Bianca
22-0872-IR | WO0002 | FEE | 2023-01-18T20:56:05.023 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | FEE
22-0872-IR | WO0004, Complete | PNT | 2023-01-18T20:56:05.263 | WO | 0 | 99.27 | 0.72 | 99.27 | 100 |  | 0 |  | 01/18/2023 | 01/18/2023 |  | 2023-05-15T09:10:31.590 | Olson, Jonathon | PNT
22-0872-IR | WO0008, Complete | Siding Materials | 2023-02-06T10:22:00.000 | WO | 0 | 13632.32 | 8 | 13632.32 | 100 |  | 0 |  | 02/06/2023 | 02/06/2023 |  | 2023-04-14T15:58:53.603 | Olson, Jonathon | Siding Materials
22-0872-IR | WO0009 | Siding Labor | 2023-02-06T10:22:00.000 | WO | 0 | 5000.006 | 98.07 | 15042.86 | 5000 |  | 66.7616 |  | 01/18/2023 | 02/06/2023 |  |  |  | Siding Labor
22-0872-IR | WO00010, Complete | Roofing Materials | 2023-02-06T10:23:00.000 | WO | 0 | 5288.25 | 8 | 5288.25 | 100 |  | 0 |  | 02/06/2023 | 02/06/2023 |  | 2023-04-14T15:50:02.273 | Olson, Jonathon | Roofing Materials
22-0872-IR | WO00011, Complete | Roofing Labor | 2023-02-06T10:23:00.000 | WO | 0 | 2999.9963 | 78.55 | 13133.57 | 3000 |  | 77.1578 |  | 01/18/2023 | 02/06/2023 |  | 2023-05-15T09:00:44.150 | Olson, Jonathon | Roofing Labor
22-0872-IR | WO00012 | Gutter and window wraps | 2023-02-06T10:26:00.000 | WO | 0 | 2199.9993 | 29.1 | 4095.75 | 2200 |  | 46.2858 |  | 01/18/2023 | 02/06/2023 |  |  |  | Gutter and window wraps
22-0881-IR | WO0002 | Cabinets | 2023-08-23T17:12:19.000 | WO | 0 | 1982.93 | 19.93 | 1982.93 | 100 |  | 0 |  | 08/25/2023 | 08/30/2023 |  |  |  | CAB
22-0881-IR | WO0003 | Contents | 2023-08-23T17:12:20.000 | WO | 0 | 612.96 | 8 | 612.96 | 100 |  | 0 |  | 08/23/2023 | 08/23/2023 |  |  |  | CON
22-0881-IR | WO0005 | Dumpster | 2023-08-23T17:12:20.000 | WO | 0 | 336.6 | 1.98 | 336.6 | 100 |  | 0 |  | 08/23/2023 | 08/23/2023 |  |  |  | DMO
22-0881-IR | WO0006 | Drywall & Paint | 2023-08-23T17:12:20.000 | WO | 0 | 1195.99 | 9.58 | 1195.99 | 100 |  | 0 |  | 08/23/2023 | 08/23/2023 |  |  |  | DRY
22-0881-IR | WO0007 | Handyman | 2023-08-23T17:12:20.000 | WO | 0 | 1746.32 | 7.12 | 1746.32 | 100 |  | 0 |  | 08/23/2023 | 08/23/2023 |  |  |  | ELE
22-0881-IR | WO0009 | Plumbing | 2023-08-23T17:12:21.000 | WO | 0 | 727.27 | 3.08 | 727.27 | 100 |  | 0 |  | 08/23/2023 | 08/23/2023 |  |  |  | PLM
22-0881-IR | WO00011 | Countertop | 2023-08-23T17:13:00.000 | WO | 0 | 3604.58 | 33.54 | 3604.58 | 100 |  | 0 |  | 08/23/2023 | 08/29/2023
22-0881-IR | WO00012 | Cabinets - Material | 2023-08-23T17:25:00.000 | WO | 0 | 11891.1248 |  | 14272.8 | 11887 |  | 16.6868
22-0883-ER | WO0001 | ACT | 2023-03-07T16:45:07.640 | WO | 0 | 1415.46 | 7.45 | 1415.46 | 100 |  | 0 |  | 03/07/2023 | 03/07/2023 |  |  |  | ACT
22-0883-ER | WO0002 | CAB | 2023-03-07T16:45:07.733 | WO | 0 | 1819.95 | 4.02 | 1819.95 | 100 |  | 0 |  | 03/07/2023 | 03/07/2023 |  |  |  | CAB
22-0883-ER | WO0003 | CLN | 2023-03-07T16:45:07.813 | WO | 0 | 480.78 | 5.95 | 480.78 | 100 |  | 0 |  | 03/07/2023 | 03/07/2023 |  |  |  | CLN
22-0883-ER | WO0004 | CON | 2023-03-07T16:45:07.907 | WO | 0 | 3285.03 | 43.1 | 3285.03 | 100 |  | 0 |  | 03/07/2023 | 03/13/2023 |  |  |  | CON
22-0883-ER | WO0005 | CPS | 2023-03-07T16:45:08.000 | WO | 0 | 211.88 |  | 211.88 | 100 |  | 0 | [6 empty] | CPS
22-0883-ER | WO0006 | DMO | 2023-03-07T16:45:08.093 | WO | 0 | 1225.99 | 13.13 | 1225.99 | 100 |  | 0 |  | 03/07/2023 | 03/08/2023 |  |  |  | DMO
22-0883-ER | WO0007 | DOR | 2023-03-07T16:45:08.190 | WO | 0 | 1752.21 | 4.15 | 1752.21 | 100 |  | 0 |  | 03/07/2023 | 03/07/2023 |  |  |  | DOR
22-0883-ER | WO0008 | DRY | 2023-03-07T16:45:08.273 | WO | 0 |  |  |  | 0 |  | 0 | [6 empty] | DRY
22-0883-ER | WO0009 | ELE | 2023-03-07T16:45:08.380 | WO | 0 | 619.1 | 3.87 | 619.1 | 100 |  | 0 |  | 03/07/2023 | 03/07/2023 |  |  |  | ELE
22-0883-ER | WO00010 | FCC | 2023-03-07T16:45:08.460 | WO | 0 | 1025.3 | 5.52 | 1025.3 | 100 |  | 0 |  | 03/07/2023 | 03/07/2023 |  |  |  | FCC
22-0883-ER | WO00011 | FCV | 2023-03-07T16:45:08.543 | WO | 0 |  |  |  | 0 |  | 0 | [6 empty] | FCV
22-0883-ER | WO00012 | Trim Staining | 2023-03-07T16:45:08.000 | WO | 0 | 1130.185 | 11.14 | 1614.55 | 70 |  | 30 |  | 03/07/2023 | 03/08/2023 |  |  |  | FEE
22-0883-ER | WO00013 | FNC | 2023-03-07T16:45:08.667 | WO | 0 | 1302.82 | 6.42 | 1302.82 | 100 |  | 0 |  | 03/07/2023 | 03/07/2023 |  |  |  | FNC
22-0883-ER | WO00014 | FNH | 2023-03-07T16:45:08.730 | WO | 0 | 243.05 | 1.92 | 243.05 | 100 |  | 0 |  | 03/07/2023 | 03/07/2023 |  |  |  | FNH
22-0883-ER | WO00015, Complete | Christian's Work | 2023-03-07T16:45:08.000 | WO | 0 | 2913.7725 | 68.93 | 6475.05 | 45 |  | 55 |  | 04/10/2023 | 04/19/2023 |  | 2023-04-24T08:41:02.650 | Burrell, Bianca | FRM
22-0883-ER | WO00016 | INS | 2023-03-07T16:45:08.933 | WO | 0 |  |  |  | 0 |  | 0 | [6 empty] | INS
22-0883-ER | WO00017 | LIT | 2023-03-07T16:45:09.033 | WO | 0 | 137.62 | 0.53 | 137.62 | 100 |  | 0 |  | 03/07/2023 | 03/07/2023 |  |  |  | LIT
22-0883-ER | WO00018 | MBL | 2023-03-07T16:45:09.093 | WO | 0 | 146.3 | 0.85 | 146.3 | 100 |  | 0 |  | 03/07/2023 | 03/07/2023 |  |  |  | MBL
22-0883-ER | WO00019 | MSD | 2023-03-07T16:45:09.157 | WO | 0 | 399.59 |  | 399.59 | 100 |  | 0 | [6 empty] | MSD
22-0883-ER | WO00020 | PLM | 2023-03-07T16:45:09.220 | WO | 0 | 2146.63 | 1.27 | 2146.63 | 100 |  | 0 |  | 03/07/2023 | 03/07/2023 |  |  |  | PLM
22-0883-ER | WO00021 | PNL | 2023-03-07T16:45:09.313 | WO | 0 | 3923.88 | 22.77 | 3923.88 | 100 |  | 0 |  | 03/07/2023 | 03/09/2023 |  |  |  | PNL
22-0883-ER | WO00022, Complete | PNT/DRY | 2023-03-07T16:45:09.000 | WO | 0 | 3199.9993 | 7.75 | 1400.21 | 3200 |  | -128.5371 |  | 03/07/2023 | 03/08/2023 |  | 2023-08-06T18:01:06.797 | Burrell, Bianca | PNT
22-0883-ER | WO00023, Complete | TIL | 2023-03-07T16:45:09.453 | WO | 0 | 477.78 | 1.45 | 477.78 | 100 |  | 0 |  | 03/07/2023 | 03/07/2023 |  | 2023-08-21T20:21:15.690 | Burrell, Bianca | TIL
22-0883-ER | WO00024 | WPR | 2023-03-07T16:45:09.517 | WO | 0 | 1648.85 | 7.85 | 1648.85 | 100 |  | 0 |  | 03/07/2023 | 03/07/2023 |  |  |  | WPR
22-0883-ER | WO00025, Complete | Tile Material | 2023-04-21T17:50:00.000 | WO | 0 | 414.4745 | 8 | 753.59 | 55 |  | 45 |  | 04/21/2023 | 04/21/2023 |  | 2023-08-06T18:01:15.110 | Burrell, Bianca
22-0883-ER | WO00026, Complete | Change Order Framing | 2023-04-24T09:37:00.000 | WO | 0 | 6750.0044 |  | 14291.41 | 6750 |  | 52.7688 |  |  |  |  | 2023-04-24T08:41:02.633 | Burrell, Bianca
22-0892-ER | WO0002, Complete | FEE | 2023-04-10T15:27:07.930 | WO | 0 | 0 |  | 0 | 0 |  | 0 |  |  |  |  | 2023-05-11T13:42:15.630 | Dehnke, Josh | FEE
22-0892-ER | WO0004, Complete | RFG | 2023-04-10T15:27:08.000 | WO | 0 | 4250 | 70.48 | 11026.49 | 4250 |  | 61.4565 |  | 04/10/2023 | 04/20/2023 |  | 2023-05-11T13:42:15.597 | Dehnke, Josh | RFG
22-0892-ER | WO0006, Complete | Material Work Order | 2023-05-04T13:50:29.000 | WO | 0 | 5701.8309 | 3.21 | 5889.22 | 5701.83 |  | 3.1819 |  | 04/19/2023 | 04/19/2023 |  | 2023-05-10T11:47:16.290 | Dehnke, Josh | Material Work Order
22-0892-ER | WO0007, Complete | Gutter Material and Labor | 2023-05-26T14:03:00.000 | WO | 0 | 1921.4039 | 21.41 | 1959.96 | 98.0328 |  | 1.9672 |  | 04/10/2023 | 05/26/2023 |  | 2023-06-05T13:15:46.360 | Dehnke, Josh | GTR
22-0906-IR | WO0001 | CON | 2023-04-03T22:23:58.160 | WO | 0 | 79.16 | 1.47 | 79.16 | 100 |  | 0 |  | 04/03/2023 | 04/03/2023 |  |  |  | CON
22-0906-IR | WO0003 | FEE | 2023-04-03T22:23:58.350 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | FEE
22-0906-IR | WO0004 | INS | 2023-04-03T22:23:58.000 | WO | 0 | 84.508 | 0.47 | 211.27 | 40 |  | 60 |  | 04/03/2023 | 04/03/2023 |  |  |  | INS
22-0906-IR | WO0005 | LAB | 2023-04-03T22:23:58.460 | WO | 0 | 1.84 | 0 | 1.84 | 100 |  | 0 |  | 04/03/2023 | 04/03/2023 |  |  |  | LAB
22-0906-IR | WO0006 | PLA | 2023-04-03T22:23:58.000 | WO | 0 | 239.144 | 3.23 | 597.86 | 40 |  | 60 |  | 04/03/2023 | 04/03/2023 |  |  |  | PLA
22-0906-IR | WO0007 | PNT | 2023-04-03T22:23:58.000 | WO | 0 | 117.416 | 2.47 | 293.54 | 40 |  | 60 |  | 04/03/2023 | 04/03/2023 |  |  |  | PNT
22-0906-IR | WO0008, Complete | Roofing Labor | 2023-04-03T22:23:58.000 | WO | 0 | 3000.0039 | 55.98 | 8880.98 | 3000 |  | 66.2199 |  | 04/03/2023 | 04/11/2023 |  | 2023-04-07T22:31:30.383 | Olson, Jonathon | RFG
22-0906-IR | WO0009 | Wraps | 2023-04-03T22:23:58.000 | WO | 0 | 2128.37 | 13.47 | 2128.37 | 100 |  | 0 |  | 04/03/2023 | 04/04/2023 |  |  |  | SDG
22-0906-IR | WO00010, Complete | Roofing Materials | 2023-04-03T21:25:21.000 | WO | 0 | 4099.9988 |  | 2837.23 | 4100 |  | -44.5071 |  |  |  |  | 2023-04-07T22:31:30.370 | Olson, Jonathon | Material Work Order
22-0906-IR | WO00011 | Interior Materials | 2023-04-03T21:28:21.000 | WO | 0 | 120.57 |  | 120.57 | 100 |  | 0 | [6 empty] | Material Work Order
22-0910-ER | WO0002 | Countertop - Material | 2022-10-21T08:42:16.000 | WO | 0 | 321.864 |  | 536.44 | 60 |  | 40 | [6 empty] | CAB
22-0910-ER | WO0003 | Carpet Cleaning | 2022-10-21T08:42:16.000 | WO | 0 | 177.798 | 3.37 | 296.33 | 60 |  | 40 |  | 10/21/2022 | 10/21/2022 |  |  |  | CLN
22-0910-ER | WO0005 | Pad Replace & Re-Stretch | 2022-10-21T08:42:16.000 | WO | 0 | 465.66 | 6 | 776.1 | 60 |  | 40 |  | 10/21/2022 | 10/21/2022 |  |  |  | FCC
22-0910-ER | WO0006 | Hard Surface - Labor | 2022-10-21T08:42:16.000 | WO | 0 | 644.888 | 8.68 | 936.34 | 68.8733 |  | 31.1267 |  | 10/21/2022 | 10/21/2022 |  |  |  | FCR
22-0910-ER | WO0008 | Base & Toe Kick | 2022-10-21T08:42:17.000 | WO | 0 | 250.77 | 1.53 | 417.95 | 60 |  | 40 |  | 10/21/2022 | 10/21/2022 |  |  |  | FNC
22-0910-ER | WO0009 | MPR | 2022-10-21T08:42:17.373 | WO | 0 | 45.92 | 0.4 | 45.92 | 100 |  | 0 |  | 10/21/2022 | 10/21/2022 |  |  |  | MPR
22-0910-ER | WO00010 | PLM | 2022-10-21T08:42:17.443 | WO | 0 | 627.33 | 1.67 | 627.33 | 100 |  | 0 |  | 10/21/2022 | 10/21/2022 |  |  |  | PLM
22-0910-ER | WO00011 | Drywall & Paint | 2022-10-21T08:42:17.000 | WO | 0 | 1209.942 | 14.45 | 2016.57 | 60 |  | 40 |  | 10/21/2022 | 10/24/2022 |  |  |  | PNT
22-0910-ER | WO00012, Complete | Hard Surface - Material | 2022-10-25T16:40:00.000 | WO | 0 | 514.82 | 8 | 514.82 | 100 |  | 0 |  | 10/25/2022 | 10/25/2022 |  | 2023-01-03T11:05:51.360 | Dehnke, Josh
22-0910-ER | WO00013 | Countertop - Labor | 2022-10-25T16:54:00.000 | WO | 0 | 252.234 | 12.19 | 420.39 | 60 |  | 40 |  | 10/21/2022 | 10/25/2022
22-0926-ER | WO0001 | DMO | 2023-04-30T22:40:58.130 | WO | 0 |  |  |  | 0 |  | 0 | [6 empty] | DMO
22-0926-ER | WO0002 | FEE | 2023-04-30T22:40:58.203 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | FEE
22-0926-ER | WO0003 | FPL | 2023-04-30T22:40:58.243 | WO | 0 |  |  |  | 0 |  | 0 | [6 empty] | FPL
22-0926-ER | WO0004, Complete | Roofing Labor | 2023-04-30T22:40:58.000 | WO | 0 | 2750.0011 | 66.28 | 11123.16 | 2750 |  | 75.2768 |  | 04/30/2023 | 05/09/2023 |  | 2023-05-09T10:03:37.677 | Olson, Jonathon | RFG
22-0926-ER | WO0005 | SDG | 2023-04-30T22:40:58.000 | WO | 0 | 110.336 | 0.42 | 275.84 | 40 |  | 60 |  | 04/30/2023 | 04/30/2023 |  |  |  | SDG
22-0926-ER | WO0006 | SFG | 2023-04-30T22:40:58.463 | WO | 0 | 478.31 | 2.1 | 478.31 | 100 |  | 0 |  | 04/30/2023 | 04/30/2023 |  |  |  | SFG
22-0926-ER | WO0007 | XST | 2023-04-30T22:40:58.000 | WO | 0 | 1173.84 | 7.27 | 2934.6 | 40 |  | 60 |  | 04/30/2023 | 04/30/2023 |  |  |  | XST
22-0926-ER | WO0008, Complete | Roofing Materials | 2023-04-30T21:41:36.000 | WO | 0 | 5709.35 |  | 5709.35 | 100 |  | 0 |  |  |  |  | 2023-04-30T21:41:59.200 | Olson, Jonathon | Material Work Order
22-0930-ER | WO0001 | DMO | 2023-07-18T14:39:57.930 | WO | 0 | 15.77 |  | 15.77 | 100 |  | 0 | [6 empty] | DMO
22-0930-ER | WO0002 | FEE | 2023-07-18T14:39:58.163 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | FEE
22-0930-ER | WO0003 | RFG | 2023-07-18T14:39:58.303 | WO | 0 | 7701.15 |  | 7701.15 | 100 |  | 0 | [6 empty] | RFG
22-0930-ER | WO0004 | WDR | 2023-07-18T14:39:58.663 | WO | 0 | 401.32 | 0.58 | 401.32 | 100 |  | 0 |  | 07/18/2023 | 07/18/2023 |  |  |  | WDR
22-0930-ER | WO0005 | LR roofing labor | 2023-07-18T14:40:00.000 | WO | 0 | 6500.006 | 158.59 | 21401.24 | 6500 |  | 69.6279 |  | 07/18/2023 | 08/09/2023 |  |  |  | LR Roofing labor
22-0936-ER | WO0001 | AWN | 2023-04-21T10:18:33.990 | WO | 0 | 683.94 | 4.35 | 683.94 | 100 |  | 0 |  | 04/21/2023 | 04/21/2023 |  |  |  | AWN
22-0936-ER | WO0002, Complete | Roofing Labor | 2023-04-21T10:18:34.000 | WO | 0 | 3399.998 | 73.95 | 11337.03 | 3400 |  | 70.0098 |  | 04/21/2023 | 05/03/2023 |  | 2023-04-27T10:27:16.893 | Olson, Jonathon | DMO
22-0936-ER | WO0003 | FEE | 2023-04-21T10:18:34.147 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | FEE
22-0936-ER | WO0004 | FRM | 2023-04-21T10:18:34.217 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | FRM
22-0936-ER | WO0006 | SFG | 2023-04-21T10:18:34.390 | WO | 0 | 1812.87 | 7.52 | 1812.87 | 100 |  | 0 |  | 04/21/2023 | 04/21/2023 |  |  |  | SFG
22-0936-ER | WO0007, Complete | Material Work Order | 2023-04-21T09:18:53.440 | WO | 0 | 3809.62 |  | 3809.62 | 100 |  | 0 |  |  |  |  | 2023-04-27T10:27:16.910 | Olson, Jonathon | Material Work Order
22-0936-ER | WO0008 | Awnings | 2023-04-21T09:20:49.000 | WO | 0 | 686.11 |  | 686.11 | 100 |  | 0 | [6 empty] | Material Work Order
22-0855-RET-ER | WO0003 | Garage Door Labor/Materials | 2023-08-18T10:34:16.000 | WO | 0 | 3139.6875 | 16.43 | 4186.25 | 75 |  | 25 |  | 08/18/2023 | 08/21/2023 |  |  |  | DOR
22-0855-RET-ER | WO0006 | Metal Labor | 2023-08-18T10:34:17.000 | WO | 0 | 6292.6325 | 167.17 | 17978.95 | 35 |  | 65 |  | 08/18/2023 | 10/05/2023 |  |  |  | MTL
22-0855-RET-ER | WO0008 | Shingle Labor | 2023-08-18T10:34:17.000 | WO | 0 | 5387.037 | 168.03 | 17956.79 | 30 |  | 70 |  | 08/18/2023 | 09/13/2023 |  |  |  | RFG
22-0855-RET-ER | WO00010 | Soffit, Fascia and Gutter labor | 2023-08-18T10:34:18.000 | WO | 0 | 1420.818 | 20.31 | 2368.03 | 60 |  | 40 |  | 08/18/2023 | 08/21/2023 |  |  |  | SFG
22-0855-RET-ER | WO00011 | Metal Roof Materials | 2023-08-18T09:44:43.000 | WO | 0 | 7493.0483 |  | 7623.3 | 7493.05 |  | 1.7086 | [6 empty] | Material Work Order
22-0855-RET-ER | WO00012 | Shingle Materials | 2023-08-18T09:45:31.000 | WO | 0 | 9593.44 |  | 9593.44 | 100 |  | 0 | [6 empty] | Material Work Order
22-0942-ER | WO0004, Complete | Gutters and Wraps | 2022-12-08T15:53:00.000 | WO | 0 | 614.9999 | 15.92 | 1547.15 | 615 |  | 60.2495 |  | 12/08/2022 | 12/08/2022 |  | 2023-04-15T22:34:52.683 | Olson, Jonathon | Gutters and Wraps
22-0950-ER | WO0001, Complete | DMO | 2023-04-10T10:27:20.000 | WO | 0 | 0 | 1.98 | 200.11 | 0 |  | 100 |  | 04/10/2023 | 04/10/2023 |  | 2023-05-22T10:11:01.443 | Trevino, Jeovani | DMO
22-0950-ER | WO0002 | FEE | 2023-04-10T10:27:21.117 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | FEE
22-0950-ER | WO0003, Complete | RFG | 2023-04-10T10:27:21.000 | WO | 0 | 4999.9989 | 75.25 | 12255.47 | 5000 |  | 59.2019 |  | 04/10/2023 | 04/20/2023 |  | 2023-05-22T10:10:54.063 | Trevino, Jeovani | RFG
22-0950-ER | WO0004 | WDP | 2023-04-10T10:27:21.000 | WO | 0 | 0 | 0.33 | 186.74 | 0 |  | 100 |  | 04/10/2023 | 04/10/2023 |  |  |  | WDP
22-0950-ER | WO0005 | WDR | 2023-04-10T10:27:21.000 | WO | 0 | 0 | 0.27 | 124.32 | 0 |  | 100 |  | 04/10/2023 | 04/10/2023 |  |  |  | WDR
22-0950-ER | WO0006 | WDW | 2023-04-10T10:27:22.000 | WO | 0 | 0 | 0 | 223.81 | 0 |  | 100 |  | 04/10/2023 | 04/10/2023 |  |  |  | WDW
22-0950-ER | WO0007, Complete | material | 2023-04-10T10:27:00.000 | WO | 0 | 5513.6093 | 8 | 5672.35 | 5513.61 |  | 2.7985 |  | 04/10/2023 | 04/10/2023 |  | 2023-04-10T09:29:27.290 | Trevino, Jeovani | material
22-0952-RET-ER | WO0001 | debris haul away | 2023-06-26T11:41:55.000 | WO | 0 | 84.9999 | 1.98 | 205.68 | 85 |  | 58.6737 |  | 06/26/2023 | 06/26/2023 |  |  |  | DMO
22-0952-RET-ER | WO0002 | FEE | 2023-06-26T11:41:56.047 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | FEE
22-0952-RET-ER | WO0003 | roof labor | 2023-06-26T11:41:56.000 | WO | 0 | 4257.1104 | 54.12 | 8868.98 | 48 |  | 52 |  | 06/26/2023 | 07/04/2023 |  |  |  | RFG
22-0952-RET-ER | WO0004 | window wrap labor | 2023-06-26T11:41:56.000 | WO | 0 | 670.3584 | 79 | 1396.58 | 48 |  | 52 |  | 06/26/2023 | 07/06/2023 |  |  |  | SDG
22-0952-RET-ER | WO0005 | fascia labor | 2023-06-26T11:41:56.000 | WO | 0 | 106.0224 | 1.42 | 220.88 | 48 |  | 52 |  | 06/26/2023 | 06/26/2023 |  |  |  | SFG
22-0952-RET-ER | WO0006 | roof materials | 2023-06-26T14:33:32.000 | WO | 0 | 2774.295 |  | 3699.06 | 75 |  | 25 | [6 empty] | Material Work Order
22-0952-RET-ER | WO0007 | window wrap material | 2023-06-26T14:37:45.000 | WO | 0 | 225.3238 |  | 285.22 | 79 |  | 21 | [6 empty] | Material Work Order
22-0952-RET-ER | WO0008 | fascia material | 2023-06-26T14:40:28.000 | WO | 0 | 77.7202 |  | 98.38 | 79 |  | 21 | [6 empty] | Material Work Order
22-0953-ER | WO0001, Complete | Dumpster | 2022-12-07T14:54:03.000 | WO | 0 |  |  |  | 0 |  | 0 |  |  |  |  | 2023-08-10T09:03:03.527 | Trevino, Jeovani | DMO
22-0953-ER | WO0002, Complete | RFG | 2022-12-07T14:54:03.000 | WO | 0 | 7500.0056 | 165.21 | 25701.41 | 7500 |  | 70.8187 |  | 12/07/2022 | 12/30/2022 |  | 2023-06-19T10:55:47.707 | Trevino, Jeovani | RFG
22-0953-ER | WO0003 | Siding labor and materials | 2022-12-07T14:54:04.000 | WO | 0 | 1100.0002 | 7.45 | 1236.86 | 1100 |  | 11.0651 |  | 12/07/2022 | 12/07/2022 |  |  |  | SDG
22-0953-ER | WO0004, Complete | Gutter Labor | 2022-12-07T14:54:04.000 | WO | 0 |  |  |  | 0 |  | 0 |  |  |  |  | 2023-08-10T09:03:03.487 | Trevino, Jeovani | SFG
22-0953-ER | WO0005 | USR | 2022-12-07T14:54:04.463 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | USR
22-0953-ER | WO0006, Complete | Materials | 2022-12-07T14:55:00.000 | WO | 0 | 11050.0023 | 8 | 9428.04 | 11050 |  | -17.2036 |  | 12/07/2022 | 12/07/2022 |  | 2023-06-19T10:55:47.687 | Trevino, Jeovani
22-0953-ER | WO0007, Complete | Gutter materials | 2022-12-07T14:59:00.000 | WO | 0 | 0 | 8 | 884.84 | 0 |  | 100 |  | 12/07/2022 | 12/07/2022 |  | 2023-08-10T09:03:03.447 | Trevino, Jeovani
22-0958-ER | WO0001, Complete | DMO | 2023-04-10T10:36:12.367 | WO | 0 | 47.48 | 0.5 | 47.48 | 100 |  | 0 |  | 04/10/2023 | 04/10/2023 |  | 2023-08-01T10:44:27.830 | Trevino, Jeovani | DMO
22-0958-ER | WO0002 | FEE | 2023-04-10T10:36:12.600 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | FEE
22-0958-ER | WO0003, Complete | RFG | 2023-04-10T10:36:12.000 | WO | 0 | 6500 | 94.97 | 15280.43 | 6500 |  | 57.4619 |  | 04/10/2023 | 04/24/2023 |  | 2023-07-05T11:28:56.833 | Trevino, Jeovani | RFG
22-0958-ER | WO0004, Complete | SDG | 2023-04-10T10:36:13.000 | WO | 0 | 0 | 0 | 251.37 | 0 |  | 100 |  | 04/10/2023 | 04/10/2023 |  | 2023-07-05T11:29:32.657 | Trevino, Jeovani | SDG
22-0958-ER | WO0005, Complete | SFG | 2023-04-10T10:36:13.000 | WO | 0 | 450.0002 | 3.69 | 895.35 | 450 |  | 49.7403 |  | 04/10/2023 | 04/10/2023 |  | 2023-07-05T11:29:32.670 | Trevino, Jeovani | SFG
22-0958-ER | WO0006, Complete | material | 2023-04-10T10:36:00.000 | WO | 0 | 5258.68 | 8 | 4639.53 | 5258.68 |  | -13.3451 |  | 04/10/2023 | 04/10/2023 |  | 2023-07-05T11:28:56.803 | Trevino, Jeovani | material
22-0958-ER | WO0007 | Fascia labor | 2023-08-01T11:45:00.000 | WO | 0 | 129.9999 | 9.5 | 216.78 | 130 |  | 40.0314 |  | 04/10/2023 | 08/01/2023 |  |  |  | fascia labor
22-0968-IR | WO0002, Complete | Roofing, Downspouts, Gutter Screen and dumpster labor | 2023-05-01T13:11:12.000 | WO | 0 | 4499.9982 | 4.05 | 9014.6 | 4500 |  | 50.081 |  | 05/01/2023 | 05/01/2023 |  | 2023-05-08T10:56:34.917 | Dehnke, Josh | RFG
22-0968-IR | WO0004, Complete | Roofing Materials | 2023-05-01T13:25:00.000 | WO | 0 | 7002.9 | 8 | 7002.9 | 100 |  | 0 |  | 05/01/2023 | 05/01/2023 |  | 2023-05-08T10:56:35.073 | Dehnke, Josh | RFG
22-0616-RET-ER
22-0971-IR | WO0001, Complete | Dumpster | 2022-12-14T10:25:14.000 | WO | 0 |  |  |  | 0 |  | 0 |  |  |  |  | 2023-01-17T07:42:13.630 | Hicks, Dave | DMO
22-0971-IR | WO0002, Complete | Gutters labor and materials | 2022-12-14T10:25:14.000 | WO | 0 | 781.2504 | 3.9 | 1052.08 | 781.25 |  | 25.7423 |  | 12/14/2022 | 12/14/2022 |  | 2023-01-17T07:42:13.657 | Hicks, Dave | SFG
22-0973-IR | WO0001 | CON | 2022-12-05T17:23:55.783 | WO | 0 | 733.83 | 11 | 733.83 | 100 |  | 0 |  | 12/05/2022 | 12/06/2022 |  |  |  | CON
22-0973-IR | WO0002 | DOR | 2022-12-05T17:23:56.267 | WO | 0 | 483.45 | 4.18 | 483.45 | 100 |  | 0 |  | 12/05/2022 | 12/05/2022 |  |  |  | DOR
22-0973-IR | WO0003, Complete | Floor Covering Wood - Labor | 2022-12-05T17:23:56.000 | WO | 0 | 3448.32 | 66.84 | 6429.13 | 53.6359 |  | 46.3641 |  | 12/05/2022 | 12/14/2022 |  | 2023-03-13T10:32:34.213 | Burrell, Bianca | FCW
22-0973-IR | WO0004 | FNC | 2022-12-05T17:23:56.533 | WO | 0 | 8.57 |  | 8.57 | 100 |  | 0 | [6 empty] | FNC
22-0973-IR | WO0005 | FNH | 2022-12-05T17:23:56.643 | WO | 0 | 232.51 | 0.8 | 232.51 | 100 |  | 0 |  | 12/05/2022 | 12/05/2022 |  |  |  | FNH
22-0973-IR | WO0006, Complete | Floor Covering Wood - material | 2022-12-05T17:24:00.000 | WO | 0 | 5975.9996 | 8 | 4733.87 | 5976 |  | -26.2392 |  | 12/05/2022 | 12/05/2022 |  | 2023-03-13T10:32:34.180 | Burrell, Bianca
22-0973-IR | WO0007 | Labor Work Order | 2023-02-22T12:07:49.283 | WO | 0 | 1208.81 | 10.47 | 1208.81 | 100 |  | 0 |  | 12/05/2022 | 12/06/2022 |  |  |  | Labor Work Order
22-0973-IR | WO0008 | Door/Trim Material | 2023-03-13T11:34:00.000 | WO | 0 | 1221.09 | 8 | 1221.09 | 100 |  | 0 |  | 03/13/2023 | 03/13/2023
22-0869-RET-ER | WO0001, Complete | Vanity D&R | 2023-04-21T15:31:49.000 | WO | 0 | 441.875 | 0 | 631.25 | 70 |  | 30 |  | 04/21/2023 | 04/21/2023 |  | 2023-07-03T09:56:25.207 | Burrell, Bianca | CAB
22-0869-RET-ER | WO0002, Complete | CON | 2023-04-21T15:31:49.000 | WO | 0 | 521.07 | 0 | 868.45 | 60 |  | 40 |  | 04/21/2023 | 04/24/2023 |  | 2023-07-03T10:03:21.113 | Burrell, Bianca | CON
22-0869-RET-ER | WO0003, Complete | DMO | 2023-04-21T15:31:49.000 | WO | 0 | 232.0435 | 0 | 356.99 | 65 |  | 35 |  | 04/21/2023 | 04/21/2023 |  | 2023-07-03T09:56:25.190 | Burrell, Bianca | DMO
22-0869-RET-ER | WO0004, Complete | Door D&R | 2023-04-21T15:31:49.000 | WO | 0 | 71.03 | 0 | 71.03 | 100 |  | 0 |  | 04/21/2023 | 04/21/2023 |  | 2023-07-03T10:00:21.937 | Burrell, Bianca | DOR
22-0869-RET-ER | WO0005, Complete | DRY/PNT-ROB | 2023-04-21T15:31:49.000 | WO | 0 | 1888.2305 | 0 | 2904.97 | 65 |  | 35 |  | 04/21/2023 | 05/07/2023 |  | 2023-06-26T14:24:13.230 | Burrell, Bianca | DRY
22-0869-RET-ER | WO0006, Complete | Tile Labor | 2023-04-21T15:31:49.000 | WO | 0 | 1039.77 | 0 | 1732.95 | 60 |  | 40 |  | 04/21/2023 | 04/23/2023 |  | 2023-06-26T14:24:19.627 | Burrell, Bianca | FCT
22-0869-RET-ER | WO0007 | Refunded items | 2023-04-21T15:31:49.000 | WO | 0 | 1087.97 | 0 | 1087.97 | 100 |  | 0 |  | 04/21/2023 | 04/22/2023 |  |  |  | FNC
22-0869-RET-ER | WO00012, Complete | Plumbing - Dan | 2023-04-21T15:31:50.000 | WO | 0 | 658.273 | 0 | 940.39 | 70 |  | 30 |  | 04/21/2023 | 04/24/2023 |  | 2023-07-03T09:56:09.447 | Burrell, Bianca | PLM
22-0869-RET-ER | WO00015, Complete | Tile Material | 2023-04-21T15:33:00.000 | WO | 0 | 0 | 8 | 0 | 100 |  | 0 |  | 04/21/2023 | 04/21/2023 |  | 2023-06-26T14:24:26.073 | Burrell, Bianca
22-0869-RET-ER | WO00016, Complete | Change Order | 2023-06-30T10:01:00.000 | WO | 0 | 5299.322 |  | 7570.46 | 70 |  | 30 |  |  |  |  | 2023-07-03T10:00:31.340 | Burrell, Bianca
22-0978-IR | WO0001 | DMO | 2023-04-24T14:02:10.393 | WO | 0 | 59 | 0.5 | 59 | 100 |  | 0 |  | 04/24/2023 | 04/24/2023 |  |  |  | DMO
22-0978-IR | WO0002 | DOR | 2023-04-24T14:02:10.593 | WO | 0 | 290.35 | 1.65 | 290.35 | 100 |  | 0 |  | 04/24/2023 | 04/24/2023 |  |  |  | DOR
22-0978-IR | WO0003 | SDG | 2023-04-24T14:02:10.750 | WO | 0 | 532.22 | 2.9 | 532.22 | 100 |  | 0 |  | 04/24/2023 | 04/24/2023 |  |  |  | SDG
22-0978-IR | WO0004 | Gutter Gaurds | 2023-04-24T14:02:10.000 | WO | 0 | 800 | 19.42 | 2725.44 | 800 |  | 70.6469 |  | 04/24/2023 | 05/15/2023 |  |  |  | SFG
22-0978-IR | WO0007 | Material Work Order | 2023-05-15T09:47:26.000 | WO | 0 | 399.9998 |  | 615.57 | 400 |  | 35.0196 | [6 empty] | Material Work Order
22-0979-ER | WO0001 | APP | 2023-05-11T14:36:14.810 | WO | 0 | 981.9 | 5.35 | 981.9 | 100 |  | 0 |  | 05/11/2023 | 05/11/2023 |  |  |  | APP
22-0979-ER | WO0002 | CAB | 2023-05-11T14:36:14.903 | WO | 0 | 3987.602 | 43.26 | 6371.85 | 62.5815 |  | 37.4185 |  | 05/11/2023 | 05/22/2023 |  |  |  | CAB
22-0979-ER | WO0003 | CLN | 2023-05-11T14:36:14.970 | WO | 0 | 282.37 | 3.5 | 282.37 | 100 |  | 0 |  | 05/11/2023 | 05/11/2023 |  |  |  | CLN
22-0979-ER | WO0004 | CNC | 2023-05-11T14:36:15.047 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | CNC
22-0979-ER | WO0005, Complete | DMO | 2023-05-11T14:36:15.127 | WO | 0 | 362.64 | 1.98 | 362.64 | 100 |  | 0 |  | 05/11/2023 | 05/11/2023 |  | 2023-08-06T17:57:52.130 | Burrell, Bianca | DMO
22-0979-ER | WO0006 | DOR | 2023-05-11T14:36:15.237 | WO | 0 | 4706.97 | 7.3 | 4706.97 | 100 |  | 0 |  | 05/11/2023 | 05/11/2023 |  |  |  | DOR
22-0979-ER | WO0007, Complete | DRY/PNT - Complete Painting | 2023-05-11T14:36:15.000 | WO | 0 | 11485.896 | 116.43 | 19143.16 | 60 |  | 40 |  | 05/11/2023 | 05/24/2023 |  | 2023-06-26T14:58:56.300 | Burrell, Bianca | DRY
22-0979-ER | WO0008, Complete | FCC | 2023-05-11T14:36:15.683 | WO | 0 | 0 |  | 0 | 0 |  | 0 |  |  |  |  | 2023-08-06T17:57:52.120 | Burrell, Bianca | FCC
22-0979-ER | WO0009, Complete | Kitchen Floor | 2023-05-11T14:36:15.000 | WO | 0 | 497.406 | 2.83 | 710.58 | 70 |  | 30 |  | 05/11/2023 | 05/11/2023 |  | 2023-08-06T17:57:52.113 | Burrell, Bianca | FCT
22-0979-ER | WO00010, Complete | Kitchen Floor - Material | 2023-05-11T14:36:15.000 | WO | 0 | 181.596 |  | 302.66 | 60 |  | 40 |  |  |  |  | 2023-08-06T17:57:52.103 | Burrell, Bianca | FCV
22-0979-ER | WO00011 | FEE | 2023-05-11T14:36:15.907 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | FEE
22-0979-ER | WO00012 | FNC | 2023-05-11T14:36:15.983 | WO | 0 | 2006.9 | 12.3 | 2006.9 | 100 |  | 0 |  | 05/11/2023 | 05/12/2023 |  |  |  | FNC
22-0979-ER | WO00013 | FNH | 2023-05-11T14:36:16.110 | WO | 0 | 489.09 | 2.68 | 489.09 | 100 |  | 0 |  | 05/11/2023 | 05/11/2023 |  |  |  | FNH
22-0979-ER | WO00014, Complete | FRM | 2023-05-11T14:36:16.203 | WO | 0 | 24.16 | 0.12 | 24.16 | 100 |  | 0 |  | 05/11/2023 | 05/11/2023 |  | 2023-08-06T17:57:52.100 | Burrell, Bianca | FRM
22-0979-ER | WO00015 | HVC | 2023-05-11T14:36:16.390 | WO | 0 | 87.7 | 0.47 | 87.7 | 100 |  | 0 |  | 05/11/2023 | 05/11/2023 |  |  |  | HVC
22-0979-ER | WO00016, Complete | INS - In House | 2023-05-11T14:36:16.000 | WO | 0 | 215.4325 | 1.1 | 253.45 | 85 |  | 15 |  | 05/11/2023 | 05/11/2023 |  | 2023-08-06T17:57:52.093 | Burrell, Bianca | INS
22-0979-ER | WO00017 | LAB | 2023-05-11T14:36:16.740 | WO | 0 | -425.47 | 1 | -425.47 | 100 |  | 0 |  | 05/11/2023 | 05/11/2023 |  |  |  | LAB
22-0979-ER | WO00018 | PLM | 2023-05-11T14:36:16.867 | WO | 0 | 1084.02 | 3.53 | 1084.02 | 100 |  | 0 |  | 05/11/2023 | 05/11/2023 |  |  |  | PLM
22-0979-ER | WO00020, Complete | Floor Tile | 2023-05-11T14:36:17.000 | WO | 0 | 1750.62 | 9.97 | 2295.42 | 76.2658 |  | 23.7342 |  | 05/11/2023 | 05/12/2023 |  | 2023-08-06T17:57:52.083 | Burrell, Bianca | TIL
22-0979-ER | WO00021 | WDT | 2023-05-11T14:36:17.760 | WO | 0 | 53.8 | 0.6 | 53.8 | 100 |  | 0 |  | 05/11/2023 | 05/11/2023 |  |  |  | WDT
22-0979-ER | WO00022, Complete | Tile Labor | 2023-06-07T13:08:00.000 | WO | 0 | 1022.802 | 11.48 | 1237.89 | 82.6246 |  | 17.3754 |  | 05/11/2023 | 06/07/2023 |  | 2023-07-17T08:51:31.157 | Burrell, Bianca
22-0979-ER | WO00023, Complete | Hard Surface Labor | 2023-06-07T13:09:00.000 | WO | 0 | 0 | 8 | 0 | 100 |  | 0 |  | 06/07/2023 | 06/07/2023 |  | 2023-08-06T17:57:52.067 | Burrell, Bianca
22-0979-ER | WO00024, Complete | Hard Surface Material | 2023-06-07T13:09:00.000 | WO | 0 | 0 | 8 | 0 | 100 |  | 0 |  | 06/07/2023 | 06/07/2023 |  | 2023-08-06T17:57:52.073 | Burrell, Bianca
22-0987-ER | WO0002 | Roofing and Dumpster Labor | 2023-05-05T12:10:52.000 | WO | 0 | 4779.9972 | 37.7 | 10772.99 | 4780 |  | 55.6298 |  | 05/05/2023 | 05/10/2023 |  |  |  | RFG
22-0987-ER | WO0003 | SDG | 2023-05-05T12:10:52.000 | WO | 0 | 4770.065 | 90.77 | 9540.13 | 50 |  | 50 |  | 05/05/2023 | 05/19/2023 |  |  |  | SDG
22-0987-ER | WO0004, Complete | Roofing Materials | 2023-05-05T11:11:19.000 | WO | 0 | 7812.7331 | 20.01 | 9005.15 | 7812.73 |  | 13.2415 |  | 05/05/2023 | 05/11/2023 |  | 2023-05-08T10:57:03.147 | Dehnke, Josh | Material Work Order
22-0987-ER | WO0005, Complete | Siding Materials | 2023-05-05T11:12:48.000 | WO | 0 | 8339.8753 |  | 13527.91 | 8339.87 |  | 38.3506 |  |  |  |  | 2023-06-19T09:44:38.620 | Dehnke, Josh | Material Work Order
22-0989-ER | WO0001, Complete | Contents Labor | 2022-11-22T15:59:34.000 | WO | 0 | 239.34 | 4.4 | 239.34 | 100 |  | 0 |  | 11/22/2022 | 11/22/2022 |  | 2023-01-24T10:22:19.210 | Hicks, Dave | CON
22-0989-ER | WO0002 | Materials | 2022-11-22T15:59:34.000 | WO | 0 | 1074.1445 |  | 1652.53 | 65 |  | 35 | [6 empty] | DMO
22-0989-ER | WO0003 | Door materials and labor | 2022-11-22T15:59:34.000 | WO | 0 | 731.63 | 11.27 | 731.63 | 100 |  | 0 |  | 04/10/2023 | 04/11/2023 |  |  |  | DOR
22-0989-ER | WO0004 | Electrician | 2022-11-22T15:59:34.000 | WO | 0 | 420.277 | 4 | 646.58 | 65 |  | 35 |  | 04/12/2023 | 04/12/2023 |  |  |  | ELE
22-0989-ER | WO0006, Complete | Carpentry Labor | 2022-11-22T15:59:35.000 | WO | 0 | 3334.76 | 41.49 | 3786.55 | 3334.76 |  | 11.9314 |  | 11/22/2022 | 11/29/2022 |  | 2023-01-24T10:19:26.447 | Hicks, Dave | FNH
22-0989-ER | WO0009 | Landscape Labor | 2022-11-22T15:59:35.000 | WO | 0 | 1256.436 | 32 | 2094.06 | 60 |  | 40 |  | 11/22/2022 | 11/25/2022 |  |  |  | LAB
22-0989-ER | WO00012 | Painting and seal Stucco | 2022-11-22T15:59:35.000 | WO | 0 | 816.72 | 17.12 | 1088.96 | 75 |  | 25 |  | 04/19/2023 | 04/21/2023 |  |  |  | PNT
22-0989-ER | WO00015 | Stucco Labor and Materials | 2022-11-22T15:59:36.000 | WO | 0 | 2468.5505 | 19.47 | 3797.77 | 65 |  | 35 |  | 04/17/2023 | 04/19/2023 |  |  |  | STU
22-0989-ER | WO00016, Complete | Engineer Report | 2023-01-03T15:21:00.000 | WO | 0 | 1400 | 8 | 1400 | 100 |  | 0 |  | 01/03/2023 | 01/03/2023 |  | 2023-01-03T14:22:17.523 | Dehnke, Josh | Fee
22-0989-ER | WO00017 | Concrete work | 2023-01-11T13:57:00.000 | WO | 0 | 4228.37 | 44 | 8456.74 | 50 |  | 50 |  | 04/03/2023 | 04/07/2023
22-0989-ER | WO00018 | Framing Labor | 2023-05-24T15:00:00.000 | WO | 0 | 2386.613 | 50.8 | 5447.12 | 43.8142 |  | 56.1858 |  | 05/24/2023 | 11/28/2022 |  |  |  | FRM
22-0991-ER | WO0001, Complete | DMO | 2023-03-27T09:37:07.000 | WO | 0 | 0 | 1.98 | 189.92 | 0 |  | 100 |  | 03/27/2023 | 03/27/2023 |  | 2023-03-30T07:49:55.227 | Olson, Jonathon | DMO
22-0991-ER | WO0002, Complete | FEE | 2023-03-27T09:37:08.000 | WO | 0 | 0 |  | 0 | 851.07 |  | 0 |  |  |  |  | 2023-03-30T07:51:15.057 | Olson, Jonathon | FEE
22-0991-ER | WO0003, Complete | Roofing Labor | 2023-03-27T09:37:08.000 | WO | 0 | 8999.9939 | 129.47 | 19844.1 | 9000 |  | 54.6465 |  | 03/27/2023 | 04/14/2023 |  | 2023-03-30T07:49:29.923 | Olson, Jonathon | RFG
22-0991-ER | WO0005, Complete | Gutters and Window Wraps | 2023-03-27T09:37:08.000 | WO | 0 | 6999.9928 | 81.18 | 15270.99 | 7000 |  | 54.1615 |  | 03/27/2023 | 03/31/2023 |  | 2023-05-30T09:45:25.623 | Olson, Jonathon | SFG
22-0991-ER | WO0006, Complete | Roofing Materials | 2023-03-27T09:05:21.000 | WO | 0 | 7167.4721 |  | 6502.76 | 7167.47 |  | -10.222 |  |  |  |  | 2023-03-30T07:49:29.940 | Olson, Jonathon | Material Work Order
22-1000-ER | WO0002 | FEE | 2023-05-11T09:21:02.553 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | FEE
22-1000-ER | WO0003, Complete | Roofing Labor | 2023-05-11T09:21:02.000 | WO | 0 | 5230 | 100.39 | 14497.24 | 5230 |  | 63.9242 |  | 05/11/2023 | 05/26/2023 |  | 2023-05-16T15:01:29.847 | Olson, Jonathon | RFG
22-1000-ER | WO0004 | Gutters | 2023-05-11T09:21:02.000 | WO | 0 | 949.9998 | 8.48 | 1552.81 | 950 |  | 38.8206 |  | 05/11/2023 | 05/12/2023 |  |  |  | SFG
22-1000-ER | WO0005 | WDS | 2023-05-11T09:21:02.833 | WO | 0 |  |  |  | 0 |  | 0 | [6 empty] | WDS
22-1000-ER | WO0006, Complete | Roofing Material | 2023-05-11T08:21:42.000 | WO | 0 | 5523.79 |  | 5523.79 | 100 |  | 0 |  |  |  |  | 2023-05-12T12:46:28.487 | Olson, Jonathon | Material Work Order
22-1001-ER | WO0003 | FEE | 2023-04-07T23:29:15.610 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | FEE
22-1001-ER | WO0004 | FRM | 2023-04-07T23:29:15.670 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | FRM
22-1001-ER | WO0005, Complete | Roofing Labor | 2023-04-07T23:29:16.000 | WO | 0 | 4900 | 61.75 | 10812.83 | 4900 |  | 54.6835 |  | 04/07/2023 | 04/17/2023 |  | 2023-04-15T22:27:23.243 | Olson, Jonathon | RFG
22-1001-ER | WO0006 | Wraps and Gutters | 2023-04-07T23:29:18.000 | WO | 0 | 949.9996 | 7.47 | 1450.7 | 950 |  | 34.5144 |  | 04/07/2023 | 04/07/2023 |  |  |  | SDG
22-1001-ER | WO0007 | SFG | 2023-04-07T23:29:20.950 | WO | 0 |  |  |  | 0 |  | 0 | [6 empty] | SFG
22-1001-ER | WO0008, Complete | Roofing Materials | 2023-04-07T22:29:40.000 | WO | 0 | 4860.2211 |  | 5362.76 | 4860.22 |  | 9.3709 |  |  |  |  | 2023-04-07T22:30:03.420 | Olson, Jonathon | Material Work Order
22-1001-ER | WO0009 | wraps | 2023-07-25T12:45:00.000 | WO | 0 | 850.0006 | 18.47 | 1696.09 | 850 |  | 49.8847 |  | 04/07/2023 | 07/25/2023 |  |  |  | wraps
22-1003-C
22-0802-RET-ER
22-1017-ER | WO0001, Complete | Siding Materials | 2022-12-16T08:18:34.000 | WO | 0 | 0 |  | 1629.56 | 0 |  | 100 |  |  |  |  | 2023-03-14T21:41:09.430 | Olson, Jonathon | SDG
22-1017-ER | WO0002, Complete | Siding Labor | 2022-12-16T08:19:00.000 | WO | 0 | 2199.9997 | 24.15 | 2198.92 | 2200 |  | -0.0491 |  | 12/16/2022 | 12/19/2022 |  | 2023-04-15T22:34:04.620 | Olson, Jonathon
22-1018-D | WO0003, Complete | Roofing Labor | 2023-04-28T15:28:38.000 | WO | 0 | 4100.0038 | 73.28 | 11550.12 | 4100 |  | 64.5025 |  | 04/28/2023 | 05/09/2023 |  | 2023-05-08T12:04:39.630 | Olson, Jonathon | RFG
22-1018-D | WO0004, Complete | Material Work Order | 2023-04-28T14:28:56.203 | WO | 0 | 4163.03 |  | 4163.03 | 100 |  | 0 |  |  |  |  | 2023-04-28T14:36:04.130 | Olson, Jonathon | Material Work Order
22-1020-EOC | WO0001, Complete | Materials | 2023-03-13T09:31:00.000 | WO | 0 | 4600 | 8 | 4600 | 100 |  | 0 |  | 03/13/2023 | 03/13/2023 |  | 2023-03-13T10:24:05.910 | Dehnke, Josh | MAT
22-1020-EOC | WO0002, Complete | Profit 1 of 2 | 2023-03-13T09:32:00.000 | WO | 0 | 0 | 8 | 2050 | 0 |  | 100 |  | 03/13/2023 | 03/13/2023 |  | 2023-05-26T13:35:01.870 | Dehnke, Josh | Profit
22-1020-EOC | WO0003, Complete | Profit 2 of 2 | 2023-03-13T09:33:00.000 | WO | 0 | 0 | 8 | 1050 | 0 |  | 100 |  | 03/13/2023 | 03/13/2023 |  | 2023-08-21T08:18:57.393 | Dehnke, Josh | Profit
22-1020-EOC | WO0004, Complete | Overhead and Admin | 2023-03-13T09:37:00.000 | WO | 0 | 0 | 8 | 2734 | 0 |  | 100 |  | 03/13/2023 | 03/13/2023 |  | 2023-08-21T08:18:57.360 | Dehnke, Josh | Overhead and Admin
22-1020-EOC | WO0005, Complete | Final Clean | 2023-03-13T11:24:00.000 | WO | 0 | 0 | 8 | 300 | 0 |  | 100 |  | 05/05/2023 | 05/05/2023 |  | 2023-08-21T08:18:57.347 | Dehnke, Josh | CLN
22-1020-EOC | WO0006, Complete | Doors Labor | 2023-03-13T11:25:00.000 | WO | 0 | 385.8 | 8 | 643 | 60 |  | 40 |  | 04/28/2023 | 04/28/2023 |  | 2023-08-21T08:18:57.297 | Dehnke, Josh | Doors and Windows
22-1020-EOC | WO0007, Complete | Finish Hardware | 2023-03-13T11:25:00.000 | WO | 0 | 178.5 | 8 | 357 | 50 |  | 50 |  | 05/03/2023 | 05/03/2023 |  | 2023-08-21T08:18:57.393 | Dehnke, Josh | FNH
22-1020-EOC | WO0008, Complete | Tile Labor | 2023-03-13T11:26:00.000 | WO | 0 | 6900.006 | 44 | 12670 | 6900 |  | 45.5406 |  | 04/24/2023 | 04/28/2023 |  | 2023-06-05T13:15:25.323 | Dehnke, Josh | TIL
22-1020-EOC | WO0009, Complete | Glass Labor | 2023-03-13T11:28:00.000 | WO | 0 | 750 | 17 | 1250 | 60 |  | 40 |  | 05/01/2023 | 05/02/2023 |  | 2023-08-21T08:18:57.423 | Dehnke, Josh | GLS
22-1020-EOC | WO00010, Complete | Countertop Labor | 2023-03-13T11:29:00.000 | WO | 0 | 3461 | 17 | 3461 | 100 |  | 0 |  | 05/04/2023 | 05/05/2023 |  | 2023-08-21T08:18:57.457 | Dehnke, Josh | CTP
22-1020-EOC | WO00011, Complete | Vanity labor | 2023-03-13T11:30:00.000 | WO | 0 | 871.2 | 44 | 1452 | 60 |  | 40 |  | 04/24/2023 | 04/28/2023 |  | 2023-08-21T08:18:57.487 | Dehnke, Josh | CAB
22-1020-EOC | WO00012, Complete | Drywall Labor | 2023-03-13T11:30:00.000 | WO | 0 | 2571 | 17 | 2571 | 100 |  | 0 |  | 04/21/2023 | 04/24/2023 |  | 2023-05-26T13:35:01.920 | Dehnke, Josh | DRY
22-1020-EOC | WO00013, Complete | Plumbing Labor | 2023-03-13T11:31:00.000 | WO | 0 | 4732 | 8 | 4732 | 100 |  | 0 |  | 04/20/2023 | 04/20/2023 |  | 2023-05-26T13:35:01.967 | Dehnke, Josh | PLM
22-1020-EOC | WO00014, Complete | Electrical Labor | 2023-03-13T11:32:00.000 | WO | 0 | 0 | 8 | 63 | 0 |  | 100 |  | 04/19/2023 | 04/19/2023 |  | 2023-05-26T13:35:01.997 | Dehnke, Josh | ELE
22-1020-EOC | WO00015, Complete | Demo Labor | 2023-03-13T11:32:00.000 | WO | 0 | 1429 | 17 | 1429 | 100 |  | 0 |  | 04/17/2023 | 04/18/2023 |  | 2023-05-05T14:54:27.167 | Dehnke, Josh | DMO
22-1020-EOC | WO00016, Complete | Site Set Up | 2023-03-13T11:33:00.000 | WO | 0 | 500 | 8 | 1000 | 50 |  | 50 |  | 04/17/2023 | 04/17/2023 |  | 2023-05-05T14:54:27.110 | Dehnke, Josh | Site Set Up
22-1020-EOC | WO00017, Complete | Design and Planning | 2023-03-13T11:34:00.000 | WO | 0 | 0 | 8 | 1251 | 0 |  | 100 |  | 03/13/2023 | 03/13/2023 |  | 2023-03-13T10:34:25.170 | Dehnke, Josh | PLN
22-1020-EOC | WO00018, Complete | Framing Labor | 2023-05-05T15:56:00.000 | WO | 0 | 1000 | 8 | 1000 | 100 |  | 0 |  | 05/05/2023 | 05/05/2023 |  | 2023-08-21T08:18:57.503 | Dehnke, Josh | FRM
22-1021-IR
22-1023-IR | WO0001 | Cabinets Labor | 2023-07-31T08:27:30.000 | WO | 0 | 4500.0007 | 76.52 | 9736.51 | 4500 |  | 53.7822 |  | 07/31/2023 | 08/07/2023 |  |  |  | CAB
22-1023-IR | WO0004, Complete | Demo / Contents | 2023-07-31T08:27:31.000 | WO | 0 | 1799.9997 | 47.43 | 4334.56 | 1800 |  | 58.4733 |  | 07/31/2023 | 08/02/2023 |  | 2023-08-24T09:35:03.167 | Dehnke, Josh | DMO
22-1023-IR | WO0005, Complete | Drywall and Paint Labor/Materials | 2023-07-31T08:27:31.000 | WO | 0 | 5274.144 | 50.2 | 8790.24 | 60 |  | 40 |  | 07/31/2023 | 08/02/2023 |  | 2023-08-24T09:35:08.370 | Dehnke, Josh | DRY
22-1023-IR | WO0007 | Carpet Labor and materials | 2023-07-31T08:27:31.000 | WO | 0 | 3500.0011 | 26.28 | 8842.54 | 3500 |  | 60.4186 |  | 07/31/2023 | 08/03/2023 |  |  |  | FCC
22-1023-IR | WO0008 | Tile Labor | 2023-07-31T08:27:31.000 | WO | 0 | 4634.357 | 44.1 | 7129.78 | 65 |  | 35 |  | 07/31/2023 | 08/03/2023 |  |  |  | FCT
22-1023-IR | WO0009, Complete | Finish Carpentry Labor | 2023-07-31T08:27:31.000 | WO | 0 | 1484.796 | 19.68 | 2474.66 | 60 |  | 40 |  | 07/31/2023 | 08/01/2023 |  | 2023-08-24T09:35:32.073 | Dehnke, Josh | FNC
22-1023-IR | WO00014 | Plumbing Labor | 2023-07-31T08:27:32.000 | WO | 0 | 6002.703 | 32.08 | 8575.29 | 70 |  | 30 |  | 07/31/2023 | 08/02/2023 |  |  |  | PLM
22-1023-IR | WO00025, Complete | Engineered Wood Floor | 2023-07-31T08:43:38.000 | WO | 0 | 15503.0054 | 33.57 | 11334.86 | 15503 |  | -36.7728 |  | 07/31/2023 | 08/03/2023 |  | 2023-08-24T09:35:16.333 | Dehnke, Josh | FCW
22-1023-IR | WO00029 | Electric Labor | 2023-07-31T08:43:39.000 | WO | 0 | 468.68 | 2.83 | 468.68 | 100 |  | 0 |  | 07/31/2023 | 07/31/2023 |  |  |  | LIT
22-1023-IR | WO00033, Complete | Mitigation (Sota) | 2023-07-31T08:43:40.000 | WO | 0 | 9323.517 | 116.53 | 13319.31 | 70 |  | 30 |  | 07/31/2023 | 08/16/2023 |  | 2023-08-24T09:35:21.687 | Dehnke, Josh | WTR
22-1023-IR | WO00035, Complete | Tile Materials | 2023-07-31T09:50:33.000 | WO | 0 | 2624.5197 |  | 3117.34 | 2624.52 |  | 15.809 |  |  |  |  | 2023-08-24T09:35:43.580 | Dehnke, Josh | TIL
22-1023-IR | WO00036, Complete | Cabinet Materials | 2023-07-31T09:51:15.000 | WO | 0 | 21392.9931 |  | 15819.3 | 21393 |  | -35.2335 |  |  |  |  | 2023-08-24T09:35:38.820 | Dehnke, Josh | Material Work Order
22-1023-IR | WO00037 | FNC Materials | 2023-07-31T09:53:26.000 | WO | 0 | 684.76 |  | 855.95 | 80 |  | 20 | [6 empty] | FNC
22-1025-D | WO0002 | Cleaning | 2023-02-10T11:43:55.000 | WO | 0 | 285.37 | 0.53 | 285.37 | 100 |  | 0 |  | 02/10/2023 | 02/10/2023 |  |  |  | CLN
22-1025-D | WO0003, Complete | CON | 2023-02-10T11:43:55.000 | WO | 0 | 284.9998 | 3.77 | 473.79 | 285 |  | 39.8468 |  | 02/10/2023 | 02/10/2023 |  | 2023-03-07T09:32:48.013 | Olson, Jonathon | CON
22-1025-D | WO0004, Complete | Demo | 2023-02-10T11:43:56.000 | WO | 0 | 149.9999 | 1.98 | 364.15 | 150 |  | 58.8082 |  | 02/10/2023 | 02/10/2023 |  | 2023-03-07T09:32:48.033 | Olson, Jonathon | DMO
22-1025-D | WO0006, Complete | Drywall & Paint | 2023-02-10T11:43:56.000 | WO | 0 | 3299.9978 | 45.92 | 6402.33 | 3300 |  | 48.4563 |  | 02/10/2023 | 02/17/2023 |  | 2023-03-07T09:32:48.033 | Olson, Jonathon | DRY
22-1025-D | WO0007, Complete | Carpet | 2023-02-10T11:43:56.000 | WO | 0 | 700.0001 | 4.6 | 737.89 | 700 |  | 5.1349 |  | 02/10/2023 | 02/10/2023 |  | 2023-05-19T09:13:58.313 | Olson, Jonathon | FCC
22-1025-D | WO0008, Complete | Trim, door, Baseboard and FNC | 2023-02-10T11:43:56.000 | WO | 0 | 500.0003 | 8.57 | 1023.05 | 500 |  | 51.1265 |  | 02/10/2023 | 02/10/2023 |  | 2023-03-12T22:39:25.133 | Olson, Jonathon | FNC
22-1025-D | WO00013, Complete | LAB | 2023-02-10T11:43:57.000 | WO | 0 | 0 | 0 | 0.1 | 0 |  | 100 |  | 02/10/2023 | 02/10/2023 |  | 2023-05-19T09:13:58.297 | Olson, Jonathon | LAB
22-1025-D | WO00014, Complete | Plumbing | 2023-02-10T11:43:57.000 | WO | 0 | 163.65 | 4.75 | 1091 | 15 |  | 85 |  | 02/10/2023 | 02/10/2023 |  | 2023-03-07T09:32:48.043 | Olson, Jonathon | PLM
22-1025-D | WO00016, Complete | Materials | 2023-02-10T11:48:00.000 | WO | 0 | 2409.5676 | 8 | 3650.86 | 66 |  | 34 |  | 02/10/2023 | 02/10/2023 |  | 2023-03-12T22:39:25.150 | Olson, Jonathon | Materials
22-1029-IR | WO0001, Complete | Design and Planning | 2023-03-13T11:37:00.000 | WO | 0 | 0 | 8 | 600 | 0 |  | 100 |  | 03/13/2023 | 03/13/2023 |  | 2023-03-13T10:38:47.780 | Dehnke, Josh | Design and Planning
22-1029-IR | WO0002, Complete | Materials | 2023-03-13T11:38:00.000 | WO | 0 | 2528 | 8 | 3160 | 80 |  | 20 |  | 03/13/2023 | 03/13/2023 |  | 2023-03-13T10:38:47.797 | Dehnke, Josh | MAT
22-1029-IR | WO0003, Complete | Site Set Up | 2023-03-13T11:39:00.000 | WO | 0 | 500 | 8 | 1000 | 50 |  | 50 |  | 03/13/2023 | 03/13/2023 |  | 2023-05-23T14:02:44.240 | Dehnke, Josh | Site Set Up
22-1029-IR | WO0004, Complete | Demo | 2023-03-13T11:39:00.000 | WO | 0 | 720 | 8 | 1200 | 60 |  | 40 |  | 03/13/2023 | 03/13/2023 |  | 2023-05-23T14:02:44.257 | Dehnke, Josh | Demo
22-1029-IR | WO0005, Complete | Framing | 2023-03-13T11:40:00.000 | WO | 0 | 673.4 | 8 | 1036 | 65 |  | 35 |  | 03/13/2023 | 03/13/2023 |  | 2023-05-26T13:36:47.760 | Dehnke, Josh | FRM
22-1029-IR | WO0006, Complete | Electrical Labor | 2023-03-13T11:41:00.000 | WO | 0 | 1500 | 8 | 2500 | 60 |  | 40 |  | 03/13/2023 | 03/13/2023 |  | 2023-06-05T13:18:21.847 | Dehnke, Josh | Electrical
22-1029-IR | WO0007, Complete | Plumbing Labor | 2023-03-13T11:41:00.000 | WO | 0 | 3578.0008 | 8 | 6475 | 3578 |  | 44.7413 |  | 03/13/2023 | 03/13/2023 |  | 2023-06-05T13:18:21.860 | Dehnke, Josh | PLM
22-1029-IR | WO0008, Complete | Drywall Labor | 2023-03-13T11:42:00.000 | WO | 0 | 540 | 8 | 900 | 60 |  | 40 |  | 03/13/2023 | 03/13/2023 |  | 2023-06-05T13:18:21.877 | Dehnke, Josh | Drywall
22-1029-IR | WO0009, Complete | Cabinetry Labor | 2023-03-13T11:42:00.000 | WO | 0 | 249 | 8 | 415 | 60 |  | 40 |  | 03/13/2023 | 03/13/2023 |  | 2023-06-19T09:46:53.127 | Dehnke, Josh | Cabinetry
22-1029-IR | WO00010, Complete | LVP Labor / Shiplap | 2023-03-13T11:44:00.000 | WO | 0 | 654.6 | 8 | 1091 | 60 |  | 40 |  | 03/13/2023 | 03/13/2023 |  | 2023-06-19T09:46:53.167 | Dehnke, Josh | FLR
22-1029-IR | WO00011, Complete | Millwork Labor | 2023-03-13T11:45:00.000 | WO | 0 | 429 | 8 | 715 | 60 |  | 40 |  | 03/13/2023 | 03/13/2023 |  | 2023-06-19T09:46:53.193 | Dehnke, Josh | FNC
22-1029-IR | WO00012, Complete | Painting Labor | 2023-03-13T11:46:00.000 | WO | 0 | 343.8 | 8 | 573 | 60 |  | 40 |  | 03/13/2023 | 03/13/2023 |  | 2023-06-19T09:46:53.210 | Dehnke, Josh | PNT
22-1029-IR | WO00013 | Final Clean | 2023-03-13T11:47:00.000 | WO | 0 | 500 | 8 | 1000 | 50 |  | 50 |  | 03/13/2023 | 03/13/2023 |  |  |  | CLN
22-1029-IR | WO00014 | Overhead and Admin | 2023-03-13T11:47:00.000 | WO | 0 | 0 | 8 | 1990 | 0 |  | 100 |  | 03/13/2023 | 03/13/2023 |  |  |  | Overhead and Admin
22-1029-IR | WO00015, Complete | Profit 1 of 2 | 2023-03-13T11:48:00.000 | WO | 0 | 0 | 8 | 1492 | 0 |  | 100 |  | 03/13/2023 | 03/13/2023 |  | 2023-05-26T13:36:47.770 | Dehnke, Josh | Profit
22-1029-IR | WO00016 | Profit 2 of 2 | 2023-03-13T11:48:00.000 | WO | 0 | 0 | 8 | 1492 | 0 |  | 100 |  | 03/13/2023 | 03/13/2023 |  |  |  | Profit
22-1032-EOC
22-1035-ER
22-1036-IR | WO0003 | Drywall/Paint Labor | 2023-04-25T10:51:14.000 | WO | 0 | 1000.0006 | 10 | 1365.94 | 1000 |  | 26.7903 |  | 04/25/2023 | 04/26/2023 |  |  |  | DRY
22-1036-IR | WO0007 | Drywall/Paint Materials | 2023-04-25T09:53:13.000 | WO | 0 | 0 |  | 233.53 | 0 |  | 100 | [6 empty] | Material Work Order
22-1039-IR
22-1041-ER | WO0002, Complete | CLN | 2023-05-15T14:43:56.073 | WO | 0 | 330.76 | 4.22 | 330.76 | 100 |  | 0 |  | 05/15/2023 | 05/15/2023 |  | 2023-08-07T19:00:40.743 | Burrell, Bianca | CLN
22-1041-ER | WO0003, Complete | CON | 2023-05-15T14:43:56.000 | WO | 0 | 691.4996 | 20.35 | 2086.11 | 691.5 |  | 66.8522 |  | 05/15/2023 | 05/16/2023 |  | 2023-07-17T08:53:21.453 | Burrell, Bianca | CON
22-1041-ER | WO0005, Complete | DMO | 2023-05-15T14:43:56.683 | WO | 0 | 241.75 | 1.98 | 241.75 | 100 |  | 0 |  | 05/15/2023 | 05/15/2023 |  | 2023-06-20T13:04:54.047 | Burrell, Bianca | DMO
22-1041-ER | WO0006, Complete | DOR | 2023-05-15T14:43:56.740 | WO | 0 | 283.64 | 2.5 | 283.64 | 100 |  | 0 |  | 05/15/2023 | 05/15/2023 |  | 2023-06-30T10:17:53.183 | Burrell, Bianca | DOR
22-1041-ER | WO0007, Complete | DRY/PNT - Rob | 2023-05-15T14:43:56.000 | WO | 0 | 2154.173 | 18.92 | 3077.39 | 70 |  | 30 |  | 05/15/2023 | 05/16/2023 |  | 2023-06-20T13:04:49.397 | Burrell, Bianca | DRY
22-1041-ER | WO0008, Complete | FCW | 2023-05-15T14:43:56.000 | WO | 0 | 4840.498 | 35.37 | 7376.93 | 4840.5 |  | 34.3833 |  | 06/18/2023 | 06/22/2023 |  | 2023-06-30T10:15:56.900 | Burrell, Bianca | FCW
22-1041-ER | WO0009, Complete | Trim | 2023-05-15T14:43:56.000 | WO | 0 | 505.81 | 4.52 | 505.81 | 100 |  | 0 |  | 05/15/2023 | 05/15/2023 |  | 2023-08-07T19:00:40.730 | Burrell, Bianca | FNC
22-1041-ER | WO00010, Complete | FRM | 2023-05-15T14:43:57.060 | WO | 0 | 23.19 | 0.12 | 23.19 | 100 |  | 0 |  | 05/15/2023 | 05/15/2023 |  | 2023-06-20T13:03:30.387 | Burrell, Bianca | FRM
22-1041-ER | WO00011, Complete | INS | 2023-05-15T14:43:57.000 | WO | 0 | 178.311 | 1.07 | 254.73 | 70 |  | 30 |  | 05/15/2023 | 05/15/2023 |  | 2023-06-20T13:03:30.387 | Burrell, Bianca | INS
22-1041-ER | WO00012, Complete | Trim Paint | 2023-05-31T10:03:00.000 | WO | 0 | 316.421 | 11.08 | 452.03 | 70 |  | 30 |  | 05/15/2023 | 05/31/2023 |  | 2023-08-07T19:00:40.697 | Burrell, Bianca
22-1041-ER | WO00013 | Additional Insulation- Change Order | 2023-07-17T09:55:00.000 | WO | 0 | 0 | 8 | 0 | 0 |  | 0 |  | 07/17/2023 | 07/17/2023
22-1049-D
23-0005-IR | WO0001, Complete | Cabinet Labor | 2023-03-03T15:10:05.000 | WO | 0 | 5342.58 | 64.8 | 10685.16 | 50 |  | 50 |  | 03/03/2023 | 03/14/2023 |  | 2023-05-02T18:01:27.163 | Sleem, Michael | CAB
23-0005-IR | WO0002 | DOR | 2023-03-03T15:10:05.000 | WO | 0 | 9600.5 | 1.09 | 13715 | 70 |  | 30 |  | 03/07/2023 | 03/07/2023 |  |  |  | DOR
23-0005-IR | WO0003 | Carpet Install Labor | 2023-03-03T15:10:05.000 | WO | 0 | 2647.11 | 26.47 | 4411.85 | 60 |  | 40 |  | 03/03/2023 | 03/08/2023 |  |  |  | FCC
23-0005-IR | WO0004, Complete | Bathroom Tile | 2023-03-03T15:10:05.000 | WO | 0 | 7500.0015 | 39.47 | 18025.34 | 7500 |  | 58.3919 |  | 03/03/2023 | 03/08/2023 |  | 2023-05-02T18:01:00.870 | Sleem, Michael | FCT
23-0005-IR | WO0005, Complete | Plank Flooring Install Labor | 2023-03-03T15:10:05.000 | WO | 0 | 2550.002 | 45.57 | 5086.19 | 2550 |  | 49.8642 |  | 03/03/2023 | 03/10/2023 |  | 2023-03-30T08:00:22.530 | Olson, Jonathon | FCV
23-0005-IR | WO0006, Complete | Finish Carpentry Labor | 2023-03-03T15:10:05.000 | WO | 0 | 4490.2785 | 36.74 | 6285.39 | 71.4399 |  | 28.5601 |  | 03/03/2023 | 03/08/2023 |  | 2023-05-02T18:01:00.847 | Sleem, Michael | FNC
23-0005-IR | WO00010, Complete | Trim, Door, wall Painting | 2023-03-03T15:10:06.000 | WO | 0 | 10233.324 | 113.47 | 17055.54 | 60 |  | 40 |  | 03/03/2023 | 03/21/2023 |  | 2023-05-02T18:01:00.887 | Sleem, Michael | PNT
23-0005-IR | WO00011, Complete | Stone Veneer | 2023-03-16T09:39:00.000 | WO | 0 | 2299.9988 | 23.75 | 2367.06 | 2300 |  | 2.8331 |  | 03/03/2023 | 03/16/2023 |  | 2023-05-02T18:01:00.860 | Sleem, Michael | Stone Veneer
23-0005-IR | WO00012, Complete | Stairway Railings | 2023-05-11T10:28:00.000 | WO | 0 | 7280 | 8 | 10400 | 70 |  | 30 |  | 05/11/2023 | 05/11/2023 |  | 2023-05-11T09:29:59.497 | Olson, Jonathon | Stairway Railings
23-0006-IR | WO00010 | CAB | 2023-08-29T15:27:46.517 | WO | 0 | -2013.22 | -12.9 | -2013.22 | 0 |  | 0 |  | 08/29/2023 | 08/29/2023 |  |  |  | CAB
23-0006-IR | WO00014 | Demo, Insulation, Drywall, Texture, Paint | 2023-08-29T15:27:47.000 | WO | 0 | 2132.5717 | 22.58 | 3397.27 | 2132.57 |  | 37.2269 |  | 08/29/2023 | 08/29/2023 |  |  |  | DRY
23-0006-IR | WO00015 | Finish Carpentry | 2023-08-29T15:27:47.000 | WO | 0 | 350.0005 | 15.82 | 1871.4 | 350 |  | 81.2974 |  | 08/29/2023 | 08/29/2023 |  |  |  | FNC
23-0006-IR | WO00019 | Soffit Replacement and Painting | 2023-08-29T15:27:48.000 | WO | 0 | 999.9997 | 5.62 | 1677.88 | 1000 |  | 40.401 |  | 08/29/2023 | 08/29/2023 |  |  |  | SDG
23-0006-IR | WO00023 | Anderson | 2023-08-29T15:27:49.000 | WO | 0 | 18482.9924 | 8.38 | 30574.81 | 18483 |  | 39.5483 |  | 08/29/2023 | 08/29/2023 |  |  |  | WDV
23-0008-IR | WO0002 | Drywall and Paint Labor | 2023-08-09T11:50:47.000 | WO | 0 | 1038.3505 | 21.67 | 1887.91 | 55 |  | 45 |  | 08/09/2023 | 08/10/2023 |  |  |  | DRY
23-0008-IR | WO0003 | FEE | 2023-08-09T11:50:47.150 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | FEE
23-0008-IR | WO0004 | Demo and Window and tile Labor | 2023-08-09T11:50:47.000 | WO | 0 | 1281.31 | 25.98 | 2562.62 | 50 |  | 50 |  | 08/09/2023 | 08/10/2023 |  |  |  | FRM
23-0008-IR | WO00011 | Window Materials | 2023-08-09T11:50:48.000 | WO | 0 | 903.0703 |  | 1170 | 903.07 |  | 22.8145 | [6 empty] | WDV
23-0008-IR | WO00012 | Material Work Order | 2023-08-10T08:56:32.000 | WO | 0 | 214.89 |  | 358.15 | 60 |  | 40 | [6 empty] | Material Work Order
23-0011-IR | WO0004, Complete | Contents Labor | 2023-03-09T12:06:34.000 | WO | 0 | 584.568 | 14.27 | 974.28 | 60 |  | 40 |  | 03/27/2023 | 03/27/2023 |  | 2023-04-18T13:12:47.490 | Dehnke, Josh | CON
23-0011-IR | WO0006, Complete | Door Labor | 2023-03-09T12:06:34.000 | WO | 0 | 543.984 | 17.27 | 906.64 | 60 |  | 40 |  | 03/28/2023 | 03/29/2023 |  | 2023-04-18T13:12:47.503 | Dehnke, Josh | DOR
23-0011-IR | WO0007, Complete | Drywall, texture, paint Labor | 2023-03-09T12:06:34.000 | WO | 1 | 3999.9992 | 113.4 | 7250.71 | 4000 |  | 44.833 |  | 03/08/2023 | 03/24/2023 |  | 2023-03-16T07:58:02.327 | Dehnke, Josh | DRY
23-0011-IR | WO0009, Complete | Carpet Labor | 2023-03-09T12:06:34.000 | WO | 1 | 0 | 12.22 | 1515.39 | 0 |  | 100 |  | 03/30/2023 | 03/31/2023 |  | 2023-06-09T09:12:44.937 | Dehnke, Josh | FCC
23-0011-IR | WO00013, Complete | Insulation Labor | 2023-03-09T12:06:35.000 | WO | 0 | 57.515 | 1.02 | 115.03 | 50 |  | 50 |  | 03/08/2023 | 03/08/2023 |  | 2023-03-16T07:58:02.340 | Dehnke, Josh | INS
23-0011-IR | WO00016, Complete | USR | 2023-03-09T12:06:35.530 | WO | 0 | 0 |  | 0 | 0 |  | 0 |  |  |  |  | 2023-06-09T09:12:50.113 | Dehnke, Josh | USR
23-0011-IR | WO00017, Complete | Door Materials | 2023-03-09T11:07:31.000 | WO | 0 | 1453.777 |  | 2236.58 | 65 |  | 35 |  |  |  |  | 2023-04-18T13:12:47.550 | Dehnke, Josh | DOR
23-0011-IR | WO00018, Complete | Drywall/Paint Materials | 2023-03-09T11:09:36.000 | WO | 0 | 930.787 |  | 1431.98 | 65 |  | 35 |  |  |  |  | 2023-04-18T13:12:47.583 | Dehnke, Josh | DRY
23-0011-IR | WO00019, Complete | Carpet Materials | 2023-03-09T11:15:27.000 | WO | 0 | 6022.066 |  | 9632.1 | 6022.07 |  | 37.4792 |  |  |  |  | 2023-06-09T09:12:40.570 | Dehnke, Josh | FCC
23-0011-IR | WO00020, Complete | FNC Materials | 2023-03-09T11:16:49.000 | WO | 0 | 190.2095 |  | 292.63 | 65 |  | 35 |  |  |  |  | 2023-04-18T13:12:47.613 | Dehnke, Josh | FNC
23-0011-IR | WO00021, Complete | Insulation Materials | 2023-03-09T11:17:51.000 | WO | 0 | 73.6905 |  | 113.37 | 65 |  | 35 |  |  |  |  | 2023-04-18T13:12:47.630 | Dehnke, Josh | INS
23-0011-IR | WO00023, Complete | Rubber Floor and Trim | 2023-06-09T10:12:00.000 | WO | 0 | 1319.868 | 16.65 | 2199.78 | 60 |  | 40 |  | 03/28/2023 | 06/09/2023 |  | 2023-06-19T09:49:28.220 | Dehnke, Josh | FLR
23-0015-IR | WO0001 | CON | 2023-07-05T10:23:00.953 | WO | 0 | 269.31 | 0 | 269.31 | 100 |  | 0 |  | 07/05/2023 | 07/05/2023 |  |  |  | CON
23-0015-IR | WO0002 | DMO | 2023-07-05T10:23:01.093 | WO | 0 | 371.55 | 0 | 371.55 | 100 |  | 0 |  | 07/05/2023 | 07/05/2023 |  |  |  | DMO
23-0015-IR | WO0003 | DRY | 2023-07-05T10:23:01.187 | WO | 0 | 984.42 | 0 | 984.42 | 100 |  | 0 |  | 07/05/2023 | 07/06/2023 |  |  |  | DRY
23-0015-IR | WO0004 | FNC | 2023-07-05T10:23:01.327 | WO | 0 | 232.72 | 0 | 232.72 | 100 |  | 0 |  | 07/05/2023 | 07/05/2023 |  |  |  | FNC
23-0015-IR | WO0005 | FRM | 2023-07-05T10:23:01.420 | WO | 0 | 1549.44 | 0 | 1549.44 | 100 |  | 0 |  | 07/05/2023 | 07/10/2023 |  |  |  | FRM
23-0015-IR | WO0006 | INS | 2023-07-05T10:23:01.513 | WO | 0 | 185.88 | 0 | 185.88 | 100 |  | 0 |  | 07/05/2023 | 07/05/2023 |  |  |  | INS
23-0015-IR | WO0007 | SDG | 2023-07-05T10:23:01.000 | WO | 0 | 2512.398 | 0 | 3589.14 | 70 |  | 30 |  | 07/05/2023 | 07/07/2023 |  |  |  | SDG
23-0015-IR | WO0008 | SFG | 2023-07-05T10:23:01.733 | WO | 0 | 241.17 | 0 | 241.17 | 100 |  | 0 |  | 07/05/2023 | 07/05/2023 |  |  |  | SFG
23-0015-IR | WO0009 | Siding Material | 2023-08-06T18:40:00.000 | WO | 0 | 0 | 8 | 0 | 100 |  | 0 |  | 08/06/2023 | 08/06/2023
23-0017-IR
23-0018-IR | WO0001, Complete | APP | 2023-03-27T09:16:36.170 | WO | 0 | 124.04 | 0 | 124.04 | 100 |  | 0 |  | 03/27/2023 | 03/27/2023 |  | 2023-05-15T09:13:27.360 | Burrell, Bianca | APP
23-0018-IR | WO0003 | Final Clean | 2023-03-27T09:16:36.000 | WO | 0 | 283.68 | 0 | 283.68 | 100 |  | 0 |  | 03/27/2023 | 04/04/2023 |  |  |  | CLN
23-0018-IR | WO0004 | CON | 2023-03-27T09:16:36.740 | WO | 0 | 939.4 | 0 | 939.4 | 100 |  | 0 |  | 03/27/2023 | 03/31/2023 |  |  |  | CON
23-0018-IR | WO0005, Complete | DMO | 2023-03-27T09:16:36.000 | WO | 0 | 245.52 | 0 | 245.52 | 100 |  | 0 |  | 05/15/2023 | 05/15/2023 |  | 2023-05-15T09:20:13.227 | Burrell, Bianca | DMO
23-0018-IR | WO0008, Complete | ELE | 2023-03-27T09:16:37.257 | WO | 0 | 1437.15 | 0 | 1437.15 | 100 |  | 0 |  | 03/27/2023 | 03/27/2023 |  | 2023-05-15T09:19:40.547 | Burrell, Bianca | ELE
23-0018-IR | WO0009 | Flooring Needs - George | 2023-03-27T09:16:37.000 | WO | 0 | 551.383 | 0 | 787.69 | 70 |  | 30 |  | 03/27/2023 | 03/30/2023 |  |  |  | FCC
23-0018-IR | WO00011, Complete | FNC - Beacon | 2023-03-27T09:16:37.000 | WO | 0 | 1274.0485 | 0 | 1904.57 | 66.8943 |  | 33.1057 |  | 03/27/2023 | 05/05/2023 |  | 2023-05-15T08:56:00.577 | Burrell, Bianca | FNC
23-0018-IR | WO00012 | Small items | 2023-03-27T09:16:38.000 | WO | 0 | 602.44 | 0 | 602.44 | 100 |  | 0 |  | 03/27/2023 | 03/31/2023 |  |  |  | FNH
23-0018-IR | WO00017, Complete | MPR | 2023-03-27T09:16:38.820 | WO | 0 | 19.33 | 0 | 19.33 | 100 |  | 0 |  | 03/27/2023 | 03/27/2023 |  | 2023-05-15T09:25:06.337 | Burrell, Bianca | MPR
23-0018-IR | WO00018 | PLM - Young Plumbing | 2023-03-27T09:16:38.000 | WO | 0 | 1179.304 | 0 | 1684.72 | 70 |  | 30 |  | 03/27/2023 | 04/02/2023 |  |  |  | PLM
23-0018-IR | WO00019, Complete | PNT - Rob | 2023-03-27T09:16:39.000 | WO | 0 | 3073.815 | 0 | 6147.63 | 50 |  | 50 |  | 03/27/2023 | 04/30/2023 |  | 2023-05-15T09:26:13.167 | Burrell, Bianca | PNT
23-0018-IR | WO00021, Complete | Base Stain | 2023-03-27T10:47:00.000 | WO | 0 | 757.0892 | 28 | 2907.71 | 757.09 |  | 73.9627 |  | 05/11/2023 | 05/16/2023 |  | 2023-05-15T09:51:37.050 | Burrell, Bianca
23-0018-IR | WO00022, Complete | Floor Material - Laundry | 2023-03-27T11:34:00.000 | WO | 0 | 250.4198 | 28 | 394.47 | 250.42 |  | 36.5174 |  | 05/10/2023 | 05/15/2023 |  | 2023-05-15T09:36:01.873 | Burrell, Bianca
23-0018-IR | WO00024, Complete | Bath Vanity | 2023-05-15T10:12:00.000 | WO | 0 | 431.347 | 8 | 616.21 | 70 |  | 30 |  | 03/27/2023 | 05/22/2023 |  | 2023-06-20T12:57:33.787 | Burrell, Bianca
23-0018-IR | WO00025, Complete | Carpet Clean | 2023-05-15T10:14:00.000 | WO | 0 | 101.205 | 8 | 337.35 | 30 |  | 70 |  | 03/28/2023 | 05/15/2023 |  | 2023-06-20T12:57:33.770 | Burrell, Bianca
23-0021-ER | WO0001 | Ceiling Panels | 2023-04-20T09:29:35.000 | WO | 0 | 0 | 8.13 | 1486.48 | 0 |  | 100 |  | 04/20/2023 | 04/20/2023 |  |  |  | ACT
23-0021-ER | WO0005 | Drywall and Paint | 2023-04-20T09:29:36.000 | WO | 0 | 2744.904 | 27.53 | 4574.84 | 60 |  | 40 |  | 04/20/2023 | 04/24/2023 |  |  |  | DRY
23-0021-ER | WO0007 | Stair Carpet and LVP Labor | 2023-04-20T09:29:36.000 | WO | 0 | 2000.0003 | 28.65 | 2506.31 | 2000 |  | 20.2014 |  | 04/20/2023 | 04/21/2023 |  |  |  | FCC
23-0021-ER | WO0008 | FEE | 2023-04-20T09:29:36.673 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | FEE
23-0021-ER | WO0009 | Doors, Waynes Coat, Trim | 2023-04-20T09:29:36.000 | WO | 0 | 2197.464 | 18.8 | 3662.44 | 60 |  | 40 |  | 04/20/2023 | 04/24/2023 |  |  |  | FNC
23-0021-ER | WO00012 | Carpet Materials | 2023-04-20T08:59:45.000 | WO | 0 | 2682.4098 |  | 3129.39 | 2682.41 |  | 14.2833 | [6 empty] | FCC
23-0021-ER | WO00013 | Paneling Labor/Materials | 2023-05-17T14:26:00.000 | WO | 0 | 0 | 21.73 | 1907.47 | 0 |  | 100 |  | 04/20/2023 | 05/17/2023 |  |  |  | PNL
23-0023-IR | WO0004 | LAB | 2023-06-21T09:45:37.007 | WO | 0 | 269.83 | 0 | 269.83 | 100 |  | 0 |  | 06/21/2023 | 06/21/2023 |  |  |  | LAB
23-0023-IR | WO0005 | Fence Labor and Materials | 2023-06-21T09:45:37.000 | WO | 0 | 7000 | 0 | 14362.02 | 7000 |  | 51.2603 |  | 06/21/2023 | 06/21/2023 |  |  |  | ORI
23-0025-ER | WO0001 | APP | 2023-04-19T14:25:24.197 | WO | 0 |  |  |  | 0 |  | 0 | [6 empty] | APP
23-0025-ER | WO0002 | CAB | 2023-04-19T14:25:24.337 | WO | 0 |  |  |  | 0 |  | 0 | [6 empty] | CAB
23-0025-ER | WO0003 | CLN | 2023-04-19T14:25:24.413 | WO | 0 | 298.32 | 4.37 | 298.32 | 100 |  | 0 |  | 04/19/2023 | 04/19/2023 |  |  |  | CLN
23-0025-ER | WO0004 | DMO | 2023-04-19T14:25:24.507 | WO | 0 | 560.08 |  | 560.08 | 100 |  | 0 | [6 empty] | DMO
23-0025-ER | WO0005 | DOR | 2023-04-19T14:25:24.570 | WO | 0 |  |  |  | 0 |  | 0 | [6 empty] | DOR
23-0025-ER | WO0006 | DRY | 2023-04-19T14:25:24.633 | WO | 0 | 200.45 |  | 200.45 | 100 |  | 0 | [6 empty] | DRY
23-0025-ER | WO0007 | ELE | 2023-04-19T14:25:24.727 | WO | 0 |  |  |  | 0 |  | 0 | [6 empty] | ELE
23-0025-ER | WO0008 | FCT | 2023-04-19T14:25:24.803 | WO | 0 | 428.46 |  | 428.46 | 100 |  | 0 | [6 empty] | FCT
23-0025-ER | WO0009 | FCV | 2023-04-19T14:25:24.867 | WO | 0 | 799.82 | 3.07 | 799.82 | 100 |  | 0 |  | 04/19/2023 | 04/19/2023 |  |  |  | FCV
23-0025-ER | WO00010 | FCW | 2023-04-19T14:25:24.000 | WO | 0 | 6499.9998 | 41.62 | 9072.7 | 6500 |  | 28.3565 |  | 04/19/2023 | 04/25/2023 |  |  |  | FCW
23-0025-ER | WO00011 | FEE | 2023-04-19T14:25:25.053 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | FEE
23-0025-ER | WO00012 | FNC | 2023-04-19T14:25:25.130 | WO | 0 | 1005.13 |  | 1005.13 | 100 |  | 0 | [6 empty] | FNC
23-0025-ER | WO00013 | FNH | 2023-04-19T14:25:25.240 | WO | 0 |  |  |  | 0 |  | 0 | [6 empty] | FNH
23-0025-ER | WO00014 | FRM | 2023-04-19T14:25:25.000 | WO | 0 | 320 |  | 251.45 | 320 |  | -27.2619 | [6 empty] | FRM
23-0025-ER | WO00015 | HVC | 2023-04-19T14:25:25.413 | WO | 0 |  |  |  | 0 |  | 0 | [6 empty] | HVC
23-0025-ER | WO00016 | INS | 2023-04-19T14:25:25.490 | WO | 0 | 90.42 |  | 90.42 | 100 |  | 0 | [6 empty] | INS
23-0025-ER | WO00017 | LAB | 2023-04-19T14:25:25.000 | WO | 0 | 0 | 10 | 1033.46 | 0 |  | 100 |  | 04/19/2023 | 04/20/2023 |  |  |  | LAB
23-0025-ER | WO00018 | LIT | 2023-04-19T14:25:25.727 | WO | 0 |  |  |  | 0 |  | 0 | [6 empty] | LIT
23-0025-ER | WO00019 | MPR | 2023-04-19T14:25:25.860 | WO | 0 | 62.23 |  | 62.23 | 100 |  | 0 | [6 empty] | MPR
23-0025-ER | WO00020 | MSD | 2023-04-19T14:25:25.957 | WO | 0 |  |  |  | 0 |  | 0 | [6 empty] | MSD
23-0025-ER | WO00021 | PLM | 2023-04-19T14:25:26.063 | WO | 0 | 4955.17 | 18 | 4955.17 | 100 |  | 0 |  | 04/19/2023 | 04/21/2023 |  |  |  | PLM
23-0025-ER | WO00022 | PNT | 2023-04-19T14:25:26.220 | WO | 0 | 540.88 |  | 540.88 | 100 |  | 0 | [6 empty] | PNT
23-0025-ER | WO00023 | WDT | 2023-04-19T14:25:26.610 | WO | 0 |  |  |  | 0 |  | 0 | [6 empty] | WDT
23-0025-ER | WO00024, Complete | marlon | 2023-04-19T14:25:00.000 | WO | 0 | 6499.9993 | 81.95 | 10861.79 | 6500 |  | 40.1572 |  | 04/19/2023 | 04/24/2023 |  | 2023-05-01T10:45:30.913 | Trevino, Jeovani | marlon work orders
23-0025-ER | WO00025, Complete | Val tile labor | 2023-07-18T19:41:00.000 | WO | 0 | 774.9995 | 14.43 | 1128.97 | 775 |  | 31.3534 |  | 04/19/2023 | 07/18/2023 |  | 2023-07-21T08:14:38.527 | Trevino, Jeovani | Val tile labor
23-0025-ER | WO00026 | Flooring and baseboard labor | 2023-08-10T08:56:00.000 | WO | 0 | 217.7633 | 9.77 | 289.14 | 75.3141 |  | 24.6859 |  | 04/19/2023 | 08/10/2023 |  |  |  | Flooring and baseboard Labor
23-0026-D | WO0001 | Window - Material | 2023-08-23T11:07:00.000 | WO | 0 | 692.04 |  | 692.04 | 692.04 |  | 0
23-0026-D | WO0002 | Window | 2023-08-23T11:11:00.000 | WO | 0 | 614.445 | 13 | 1228.89 | 50 |  | 50 | Keil, Norbert | 09/12/2023 | 09/13/2023
23-0036-EOC
23-0038-IR
23-0039-IR | WO0001 | APP | 2023-04-19T10:32:15.887 | WO | 0 |  |  |  | 0 |  | 0 | [6 empty] | APP
23-0039-IR | WO0002 | CLN | 2023-04-19T10:32:16.013 | WO | 0 | 927.28 | 13.55 | 927.28 | 100 |  | 0 |  | 04/19/2023 | 04/20/2023 |  |  |  | CLN
23-0039-IR | WO0003, Complete | CON | 2023-04-19T10:32:16.073 | WO | 0 | 1011.9509 | 25.3 | 1701.41 | 59.4772 |  | 40.5228 |  | 04/19/2023 | 04/21/2023 |  | 2023-06-26T10:35:25.480 | Trevino, Jeovani | CON
23-0039-IR | WO0004 | DMO | 2023-04-19T10:32:16.153 | WO | 0 | 111.2 |  | 111.2 | 100 |  | 0 | [6 empty] | DMO
23-0039-IR | WO0005 | DOR | 2023-04-19T10:32:16.217 | WO | 0 |  |  |  | 0 |  | 0 | [6 empty] | DOR
23-0039-IR | WO0006, Complete | DRY | 2023-04-19T10:32:16.297 | WO | 0 | 534.93 |  | 534.93 | 100 |  | 0 |  |  |  |  | 2023-06-26T10:35:30.967 | Trevino, Jeovani | DRY
23-0039-IR | WO0007 | ELE | 2023-04-19T10:32:16.377 | WO | 0 |  |  |  | 0 |  | 0 | [6 empty] | ELE
23-0039-IR | WO0008, Complete | carpet labor | 2023-04-19T10:32:16.000 | WO | 0 | 1900 | 20.85 | 2637.85 | 1900 |  | 27.9716 |  | 04/19/2023 | 04/24/2023 |  | 2023-06-26T10:35:17.177 | Trevino, Jeovani | FCC
23-0039-IR | WO0009 | FCV | 2023-04-19T10:32:16.000 | WO | 0 | 399.9997 | 0.06 | 676.57 | 400 |  | 40.8783 |  | 04/19/2023 | 04/19/2023 |  |  |  | FCV
23-0039-IR | WO00010 | FNC | 2023-04-19T10:32:17.270 | WO | 0 | 225.53 |  | 225.53 | 100 |  | 0 | [6 empty] | FNC
23-0039-IR | WO00011 | FNH | 2023-04-19T10:32:17.320 | WO | 0 |  |  |  | 0 |  | 0 | [6 empty] | FNH
23-0039-IR | WO00012 | HVC | 2023-04-19T10:32:17.383 | WO | 0 |  |  |  | 0 |  | 0 | [6 empty] | HVC
23-0039-IR | WO00013, Complete | INS | 2023-04-19T10:32:17.430 | WO | 0 | 424.88 |  | 424.88 | 100 |  | 0 |  |  |  |  | 2023-05-15T11:43:22.887 | Trevino, Jeovani | INS
23-0039-IR | WO00014 | LIT | 2023-04-19T10:32:17.503 | WO | 0 |  |  |  | 0 |  | 0 | [6 empty] | LIT
23-0039-IR | WO00015, Complete | PNT | 2023-04-19T10:32:17.550 | WO | 0 | 720.48 |  | 720.48 | 100 |  | 0 |  |  |  |  | 2023-05-15T11:43:22.887 | Trevino, Jeovani | PNT
23-0039-IR | WO00016 | WDT | 2023-04-19T10:32:17.650 | WO | 0 |  |  |  | 0 |  | 0 | [6 empty] | WDT
23-0039-IR | WO00017, Complete | carpet materials | 2023-04-19T10:33:00.000 | WO | 0 | 2955.37 | 8 | 2955.37 | 100 |  | 0 |  | 04/19/2023 | 04/19/2023 |  | 2023-06-26T10:35:49.590 | Trevino, Jeovani | carpet material
23-0039-IR | WO00018, Complete | marlon | 2023-04-19T13:43:00.000 | WO | 0 | 7300 | 95.88 | 11338.06 | 7300 |  | 35.6151 |  | 04/19/2023 | 04/25/2023 |  | 2023-05-15T11:43:22.903 | Trevino, Jeovani | marlon work orders
23-0039-IR | WO00019 | Tile labor | 2023-08-10T09:05:00.000 | WO | 0 | 459.97 | 11.26 | 459.97 | 100 |  | 0 |  | 04/19/2023 | 08/10/2023 |  |  |  | Tile labor
23-0039-IR | WO00020 | carpet install | 2023-08-17T09:32:00.000 | WO | 0 | 56.2533 | 13.57 | 739.73 | 56.2533 |  | 92.3954 |  | 04/19/2023 | 08/17/2023 |  |  |  | carpet install
23-0040-IR | WO0001 | CLN | 2023-06-05T11:57:36.000 | WO | 0 | 0 | 2.5 | 172.21 | 0 |  | 100 |  | 06/05/2023 | 06/05/2023 |  |  |  | CLN
23-0040-IR | WO0002 | CON | 2023-06-05T11:57:36.000 | WO | 0 | 0 | 4 | 268.8 | 0 |  | 100 |  | 06/05/2023 | 06/05/2023 |  |  |  | CON
23-0040-IR | WO0003 | DMO | 2023-06-05T11:57:37.000 | WO | 0 | 0 | 1.98 | 245.89 | 0 |  | 100 |  | 06/05/2023 | 06/05/2023 |  |  |  | DMO
23-0040-IR | WO0004 | DOR | 2023-06-05T11:57:37.110 | WO | 0 |  |  |  | 0 |  | 0 | [6 empty] | DOR
23-0040-IR | WO0005 | DRY | 2023-06-05T11:57:37.000 | WO | 0 | 0 |  | 41.29 | 0 |  | 100 | [6 empty] | DRY
23-0040-IR | WO0006 | FCW | 2023-06-05T11:57:37.000 | WO | 0 | 1550 |  | 2148.74 | 1550 |  | 27.8647 | [6 empty] | FCW
23-0040-IR | WO0007 | FNC | 2023-06-05T11:57:37.000 | WO | 0 | 0 |  | 42.66 | 0 |  | 100 | [6 empty] | FNC
23-0040-IR | WO0008 | FRM | 2023-06-05T11:57:37.000 | WO | 0 | 0 |  | 165.16 | 0 |  | 100 | [6 empty] | FRM
23-0040-IR | WO0009 | INS | 2023-06-05T11:57:37.000 | WO | 0 | 0 |  | 13.55 | 0 |  | 100 | [6 empty] | INS
23-0040-IR | WO00010 | LAB | 2023-06-05T11:57:37.000 | WO | 0 | 0 | 0 | -757.55 | 0 |  | 100 |  | 06/05/2023 | 06/05/2023 |  |  |  | LAB
23-0040-IR | WO00011 | PNT | 2023-06-05T11:57:37.000 | WO | 0 | 0 |  | 357.85 | 0 |  | 100 | [6 empty] | PNT
23-0040-IR | WO00012 | SFG | 2023-06-05T11:57:38.093 | WO | 0 | 820.12 | 3.37 | 820.12 | 100 |  | 0 |  | 06/05/2023 | 06/05/2023 |  |  |  | SFG
23-0040-IR | WO00013 | marlon work order | 2023-06-05T11:58:00.000 | WO | 0 | 3750.0029 | 58.07 | 5857.97 | 3750 |  | 35.9846 |  | 06/05/2023 | 06/07/2023 |  |  |  | marlon work order
23-0048-IR | WO0001 | APP | 2023-04-24T15:26:28.333 | WO | 0 | 648.37 | 3.95 | 648.37 | 100 |  | 0 |  | 04/24/2023 | 04/24/2023 |  |  |  | APP
23-0048-IR | WO0002 | CON | 2023-04-24T15:26:28.450 | WO | 0 | 132.48 | 2 | 132.48 | 100 |  | 0 |  | 04/24/2023 | 04/24/2023 |  |  |  | CON
23-0048-IR | WO0003 | DMO | 2023-04-24T15:26:28.560 | WO | 0 | 126.21 |  | 126.21 | 100 |  | 0 | [6 empty] | DMO
23-0048-IR | WO0004 | DRY | 2023-04-24T15:26:28.687 | WO | 0 | 132.52 |  | 132.52 | 100 |  | 0 | [6 empty] | DRY
23-0048-IR | WO0005 | FCC | 2023-04-24T15:26:28.840 | WO | 0 | 2727.11 |  | 2727.11 | 100 |  | 0 | [6 empty] | FCC
23-0048-IR | WO0006 | FCV | 2023-04-24T15:26:28.993 | WO | 0 | 2245.12 | 14.43 | 2245.12 | 100 |  | 0 |  | 04/24/2023 | 04/25/2023 |  |  |  | FCV
23-0048-IR | WO0007 | FNC | 2023-04-24T15:26:29.077 | WO | 0 | 322.92 |  | 322.92 | 100 |  | 0 | [6 empty] | FNC
23-0048-IR | WO0008 | FRM | 2023-04-24T15:26:29.163 | WO | 0 | 55.12 |  | 55.12 | 100 |  | 0 | [6 empty] | FRM
23-0048-IR | WO0009 | INS | 2023-04-24T15:26:29.443 | WO | 0 | 39.88 |  | 39.88 | 100 |  | 0 | [6 empty] | INS
23-0048-IR | WO00010 | LAB | 2023-04-24T15:26:29.570 | WO | 0 | 217.95 | 0 | 217.95 | 100 |  | 0 |  | 04/24/2023 | 04/24/2023 |  |  |  | LAB
23-0048-IR | WO00011 | LIT | 2023-04-24T15:26:29.650 | WO | 0 |  |  |  | 0 |  | 0 | [6 empty] | LIT
23-0048-IR | WO00012 | PNT | 2023-04-24T15:26:29.753 | WO | 0 | 440.79 |  | 440.79 | 100 |  | 0 | [6 empty] | PNT
23-0048-IR | WO00013, Complete | marlon | 2023-04-24T15:27:00.000 | WO | 0 | 2599.9995 | 44.07 | 4455.51 | 2600 |  | 41.6453 |  | 04/24/2023 | 04/25/2023 |  | 2023-05-15T11:44:23.097 | Trevino, Jeovani | marlon
23-0048-IR | WO00014 | carpet labor | 2023-06-16T15:10:00.000 | WO | 0 | 499.9999 | 16.87 | 1086.68 | 500 |  | 53.9883 |  | 04/24/2023 | 06/16/2023 |  |  |  | George carpet labor
23-0049-IR | WO0001, Complete | APP | 2023-05-30T17:07:17.803 | WO | 0 | 72.08 | 1.07 | 72.08 | 100 |  | 0 |  | 05/30/2023 | 05/30/2023 |  | 2023-06-22T09:11:08.447 | Burrell, Bianca | APP
23-0049-IR | WO0002, Complete | CON | 2023-05-30T17:07:17.000 | WO | 0 | 221.826 | 50.5 | 369.71 | 60 |  | 40 |  | 05/23/2023 | 05/30/2023 |  | 2023-06-22T09:11:08.400 | Burrell, Bianca | CON
23-0049-IR | WO0003, Complete | DMO | 2023-05-30T17:07:18.000 | WO | 0 | 184.65 | 3.08 | 369.3 | 50 |  | 50 |  | 06/21/2023 | 06/21/2023 |  | 2023-06-22T09:11:08.430 | Burrell, Bianca | DMO
23-0049-IR | WO0005, Complete | FNC | 2023-05-30T17:07:18.527 | WO | 0 | 91.91 | 0.45 | 91.91 | 100 |  | 0 |  | 05/30/2023 | 05/30/2023 |  | 2023-08-07T19:04:04.030 | Burrell, Bianca | FNC
23-0049-IR | WO0006, Complete | INS | 2023-05-30T17:07:18.667 | WO | 0 | 12.85 | 0.05 | 12.85 | 100 |  | 0 |  | 05/30/2023 | 05/30/2023 |  | 2023-08-07T19:04:04.017 | Burrell, Bianca | INS
23-0049-IR | WO0007, Complete | PNT | 2023-05-30T17:07:18.000 | WO | 0 | 2501.356 | 26.02 | 3848.24 | 65 |  | 35 |  | 06/21/2023 | 06/23/2023 |  | 2023-06-22T09:11:08.460 | Burrell, Bianca | PNT
23-0054-IR | WO0001 | CLN | 2023-03-27T10:51:40.020 | WO | 0 | 49.39 | 0.62 | 49.39 | 100 |  | 0 |  | 03/27/2023 | 03/27/2023 |  |  |  | CLN
23-0054-IR | WO0002 | DMO | 2023-03-27T10:51:40.117 | WO | 0 | 32.5 | 0.3 | 32.5 | 100 |  | 0 |  | 03/27/2023 | 03/27/2023 |  |  |  | DMO
23-0054-IR | WO0003, Complete | DRY/PNT/INS - Rob | 2023-03-27T10:51:40.000 | WO | 0 | 1199.9996 | 12.52 | 1383.43 | 1200 |  | 13.2591 |  | 04/06/2023 | 04/07/2023 |  | 2023-04-09T17:31:43.720 | Burrell, Bianca | DRY
23-0054-IR | WO0004 | FNC | 2023-03-27T10:51:40.323 | WO | 0 | 23.89 | 0.07 | 23.89 | 100 |  | 0 |  | 03/27/2023 | 03/27/2023 |  |  |  | FNC
23-0057-WAR | WO0001 | CLN | 2023-04-03T13:08:44.233 | WO | 0 |  |  |  | 0 |  | 0 | [6 empty] | CLN
23-0057-WAR | WO0002 | CON | 2023-04-03T13:08:44.330 | WO | 0 |  |  |  | 0 |  | 0 | [6 empty] | CON
23-0057-WAR | WO0003 | DMO | 2023-04-03T13:08:44.440 | WO | 0 | 27.06 |  | 27.06 | 100 |  | 0 | [6 empty] | DMO
23-0057-WAR | WO0004 | DOR | 2023-04-03T13:08:44.513 | WO | 0 |  |  |  | 0 |  | 0 | [6 empty] | DOR
23-0057-WAR | WO0005, Complete | FCV | 2023-04-03T13:08:44.000 | WO | 0 | 180.0001 |  | 314.23 | 180 |  | 42.7171 |  |  |  |  | 2023-04-24T09:54:48.593 | Trevino, Jeovani | FCV
23-0057-WAR | WO0006 | FNC | 2023-04-03T13:08:44.693 | WO | 0 | 17.42 |  | 17.42 | 100 |  | 0 | [6 empty] | FNC
23-0057-WAR | WO0007 | FNH | 2023-04-03T13:08:44.790 | WO | 0 |  |  |  | 0 |  | 0 | [6 empty] | FNH
23-0057-WAR | WO0008, Complete | LAB | 2023-04-03T13:08:44.000 | WO | 0 | 0 | 1 | 67.2 | 0 |  | 100 |  | 04/03/2023 | 04/03/2023 |  | 2023-04-12T13:58:51.450 | Trevino, Jeovani | LAB
23-0057-WAR | WO0009 | PNT | 2023-04-03T13:08:44.953 | WO | 0 | 214.96 | 1.26 | 214.96 | 100 |  | 0 |  | 04/03/2023 | 04/03/2023 |  |  |  | PNT
23-0057-WAR | WO00010 | marlon work orders | 2023-04-12T14:30:00.000 | WO | 0 | 1110.0007 | 23.98 | 1849.36 | 1110 |  | 39.9792 |  | 04/03/2023 | 04/12/2023 |  |  |  | marlon work orders
23-0058-IR
23-0059-IR | WO0001 | APP | 2023-05-10T07:15:18.867 | WO | 0 | 1184.84 | 6.32 | 1184.84 | 100 |  | 0 |  | 05/10/2023 | 05/10/2023 |  |  |  | APP
23-0059-IR | WO0002 | CAB | 2023-05-10T07:15:19.020 | WO | 0 | 26747.6 | 74.77 | 26747.6 | 100 |  | 0 |  | 05/10/2023 | 05/22/2023 |  |  |  | CAB
23-0059-IR | WO0003 | CLN | 2023-05-10T07:15:19.127 | WO | 0 | 1456.18 | 21.28 | 1456.18 | 100 |  | 0 |  | 05/10/2023 | 05/12/2023 |  |  |  | CLN
23-0059-IR | WO0004 | DMO | 2023-05-10T07:15:19.197 | WO | 0 | 670.22 |  | 670.22 | 100 |  | 0 | [6 empty] | DMO
23-0059-IR | WO0005 | DOR | 2023-05-10T07:15:19.250 | WO | 0 | 2247.31 | 9.9 | 2247.31 | 100 |  | 0 |  | 05/10/2023 | 05/11/2023 |  |  |  | DOR
23-0059-IR | WO0006, Complete | DRY - Rob | 2023-05-10T07:15:19.000 | WO | 0 | 11361.575 | 121.37 | 22723.15 | 50 |  | 50 |  | 05/10/2023 | 05/29/2023 |  | 2023-08-06T18:32:15.710 | Burrell, Bianca | DRY
23-0059-IR | WO0007 | ELE | 2023-05-10T07:15:19.460 | WO | 0 | 702.88 | 3.1 | 702.88 | 100 |  | 0 |  | 05/10/2023 | 05/10/2023 |  |  |  | ELE
23-0059-IR | WO0009 | Tile Labor & Grout | 2023-05-10T07:15:19.000 | WO | 0 | 14720.0047 | 84.66 | 16790.05 | 14720 |  | 12.329 |  | 05/10/2023 | 05/23/2023 |  |  |  | FCT
23-0059-IR | WO00010 | FCW - Labor | 2023-05-10T07:15:19.000 | WO | 0 | 11572.0011 | 84.63 | 10015.58 | 11572 |  | -15.54 |  | 05/10/2023 | 05/23/2023 |  |  |  | FCW
23-0059-IR | WO00011 | FNC | 2023-05-10T07:15:20.027 | WO | 0 | 8649.25 | 43.9 | 8649.25 | 100 |  | 0 |  | 05/10/2023 | 05/16/2023 |  |  |  | FNC
23-0059-IR | WO00012 | FNH | 2023-05-10T07:15:20.163 | WO | 0 | 303.88 | 3.3 | 303.88 | 100 |  | 0 |  | 05/10/2023 | 05/10/2023 |  |  |  | FNH
23-0059-IR | WO00013 | FRM | 2023-05-10T07:15:20.233 | WO | 0 | 1816.31 | 7.5 | 1816.31 | 100 |  | 0 |  | 05/10/2023 | 05/10/2023 |  |  |  | FRM
23-0059-IR | WO00014 | HVC | 2023-05-10T07:15:20.310 | WO | 0 | 476.56 | 0.47 | 476.56 | 100 |  | 0 |  | 05/10/2023 | 05/10/2023 |  |  |  | HVC
23-0059-IR | WO00015, Complete | Insulation Material | 2023-05-10T07:15:20.000 | WO | 0 | 617.425 |  | 1234.85 | 50 |  | 50 |  |  |  |  | 2023-08-06T18:32:15.727 | Burrell, Bianca | INS
23-0059-IR | WO00016 | LAB | 2023-05-10T07:15:20.507 | WO | 0 | -221.35 | 0 | -221.35 | 100 |  | 0 |  | 05/10/2023 | 05/10/2023 |  |  |  | LAB
23-0059-IR | WO00017 | LIT | 2023-05-10T07:15:20.560 | WO | 0 | 2549.8 | 11.27 | 2549.8 | 100 |  | 0 |  | 05/10/2023 | 05/11/2023 |  |  |  | LIT
23-0059-IR | WO00018 | MSD | 2023-05-10T07:15:20.627 | WO | 0 | 555.51 | 2.3 | 555.51 | 100 |  | 0 |  | 05/10/2023 | 05/10/2023 |  |  |  | MSD
23-0059-IR | WO00019 | PLM | 2023-05-10T07:15:20.000 | WO | 0 | 3027.401 | 17.3 | 4657.54 | 65 |  | 35 |  | 05/10/2023 | 05/12/2023 |  |  |  | PLM
23-0059-IR | WO00020, Complete | PNT - Rob | 2023-05-10T07:15:20.000 | WO | 0 | 6997.005 | 99.64 | 13994.01 | 50 |  | 50 |  | 05/10/2023 | 05/29/2023 |  | 2023-08-14T11:07:34.490 | Burrell, Bianca | PNT
23-0059-IR | WO00021 | WDT | 2023-05-10T07:15:20.947 | WO | 0 | 327.6 | 3.57 | 327.6 | 100 |  | 0 |  | 05/10/2023 | 05/10/2023 |  |  |  | WDT
23-0059-IR | WO00022 | WPR | 2023-05-10T07:15:21.010 | WO | 0 | 3547.91 | 23.07 | 3547.91 | 100 |  | 0 |  | 05/10/2023 | 05/12/2023 |  |  |  | WPR
23-0059-IR | WO00023 | Random Electric | 2023-05-10T07:19:00.000 | WO | 0 | 0 | 8 | 0 | 100 |  | 0 |  | 05/10/2023 | 05/10/2023
23-0059-IR | WO00024, Complete | Insulation Labor | 2023-06-09T10:06:00.000 | WO | 0 | 844.524 | 20.9 | 1407.54 | 60 |  | 40 |  | 05/10/2023 | 06/09/2023 |  | 2023-08-06T18:32:15.697 | Burrell, Bianca
23-0059-IR | WO00025 | Wood Materials | 2023-06-09T10:13:00.000 | WO | 0 | 8662.5136 | 8 | 14479.61 | 8662.52 |  | 40.1744 |  | 06/09/2023 | 06/09/2023
23-0059-IR | WO00026, Complete | Tile Material | 2023-06-09T10:14:00.000 | WO | 0 | 2318.5609 | 8 | 3105.63 | 2318.56 |  | 25.3433 |  | 06/09/2023 | 06/09/2023 |  | 2023-08-14T11:08:10.993 | Burrell, Bianca
23-0059-IR | WO00027 | Carpet Material | 2023-06-09T10:21:00.000 | WO | 0 | 272.76 | 8 | 340.95 | 80 |  | 20 |  | 06/09/2023 | 06/09/2023
23-0059-IR | WO00028 | Carpet Pad | 2023-06-09T10:26:00.000 | WO | 0 | 147.032 | 8 | 183.79 | 80 |  | 20 |  | 06/09/2023 | 06/09/2023
23-0059-IR | WO00029 | Trim Staining | 2023-07-13T12:28:00.000 | WO | 0 | 3223.895 | 55.71 | 6447.79 | 50 |  | 50 |  | 05/11/2023 | 07/13/2023
23-0059-IR | WO00030 | Workout Room | 2023-08-08T10:25:00.000 | WO | 0 | 1096.698 | 11.01 | 1443.64 | 75.9676 |  | 24.0324 |  | 05/10/2023 | 08/08/2023
23-0062-IR
23-0065-IR | WO0001 | APP | 2023-06-08T11:48:53.860 | WO | 0 | 250.38 | 3.7 | 250.38 | 100 |  | 0 |  | 06/08/2023 | 06/08/2023 |  |  |  | APP
23-0065-IR | WO0002 | CAB | 2023-06-08T11:48:54.030 | WO | 0 | 8972.45 | 41.2 | 8972.45 | 100 |  | 0 |  | 06/08/2023 | 06/14/2023 |  |  |  | CAB
23-0065-IR | WO0003 | CON | 2023-06-08T11:48:54.187 | WO | 0 | 403.2 | 6 | 403.2 | 100 |  | 0 |  | 06/08/2023 | 06/08/2023 |  |  |  | CON
23-0065-IR | WO0004 | DMO | 2023-06-08T11:48:54.390 | WO | 0 | 369.76 | 3.08 | 369.76 | 100 |  | 0 | Burrell, Bianca | 06/08/2023 | 06/08/2023 |  |  |  | DMO
23-0065-IR | WO0005 | DRY | 2023-06-08T11:48:54.627 | WO | 0 | 1337.83 | 7.5 | 1337.83 | 100 |  | 0 |  | 06/08/2023 | 06/08/2023 |  |  |  | DRY
23-0065-IR | WO0006 | Hard Surface labor | 2023-06-08T11:48:54.000 | WO | 0 | 1690.632 | 24.75 | 2817.72 | 60 |  | 40 |  | 06/08/2023 | 06/12/2023 |  |  |  | FCW
23-0065-IR | WO0007 | FNC | 2023-06-08T11:48:54.923 | WO | 0 | 608.65 | 2.7 | 608.65 | 100 |  | 0 |  | 06/08/2023 | 06/08/2023 |  |  |  | FNC
23-0065-IR | WO0008 | PLM | 2023-06-08T11:48:55.047 | WO | 0 | 598.1 | 2.03 | 598.1 | 100 |  | 0 |  | 06/08/2023 | 06/08/2023 |  |  |  | PLM
23-0065-IR | WO0009 | PNT | 2023-06-08T11:48:55.140 | WO | 0 | 2074.61 | 14.07 | 2074.61 | 100 |  | 0 |  | 06/08/2023 | 06/09/2023 |  |  |  | PNT
23-0065-IR | WO00010 | Hard Surface Material | 2023-06-08T11:49:00.000 | WO | 0 | 1077.188 | 8 | 1538.84 | 70 |  | 30 |  | 06/08/2023 | 06/08/2023
23-0065-IR | WO00011 |  | 2023-07-27T12:13:00.000 | WO | 0 | 0 | 8 | 0 | 100 |  | 0 | Viking Gypsum Floors | 07/27/2023 | 07/27/2023
23-0066-IR
23-0067-IR | WO0001, Complete | CLN | 2023-07-25T22:06:37.000 | WO | 0 | 0 | 1.85 | 196.72 | 0 |  | 100 |  | 07/25/2023 | 07/25/2023 |  | 2023-08-08T10:55:30.783 | Sleem, Michael | CLN
23-0067-IR | WO0002, Complete | CON | 2023-07-25T22:06:37.000 | WO | 0 | 0 | 2.93 | 197.86 | 0 |  | 100 |  | 07/25/2023 | 07/25/2023 |  | 2023-08-08T10:55:30.797 | Sleem, Michael | CON
23-0067-IR | WO0003, Complete | DMO | 2023-07-25T22:06:38.000 | WO | 0 | 0 | 1.1 | 102.82 | 0 |  | 100 |  | 07/25/2023 | 07/25/2023 |  | 2023-08-08T10:55:30.813 | Sleem, Michael | DMO
23-0067-IR | WO0005 | FNC | 2023-07-25T22:06:38.000 | WO | 0 | 208.098 | 1.11 | 378.36 | 55 |  | 45 |  | 07/25/2023 | 07/25/2023 |  |  |  | FNC
23-0067-IR | WO0006, Complete | PNTDRYINS | 2023-07-25T22:06:38.000 | WO | 0 | 1347.6106 | 9.56 | 2106.83 | 1347.61 |  | 36.0361 |  | 07/25/2023 | 07/25/2023 |  | 2023-08-08T10:55:07.140 | Sleem, Michael | INS
23-0067-IR | WO0007 | Finish Carpentry Materials | 2023-08-08T11:52:00.000 | WO | 0 | 50.6453 | 8 | 75.59 | 67 |  | 33 |  | 08/08/2023 | 08/08/2023
23-0068-IR | WO0003 | LVP Labor | 2023-05-23T14:02:50.000 | WO | 0 | 619.585 | 13.78 | 1239.17 | 50 |  | 50 |  | 05/23/2023 | 05/24/2023 |  |  |  | FCC
23-0068-IR | WO0004 | LVP Materials | 2023-06-07T12:43:39.000 | WO | 0 | 1098.79 |  | 1098.79 | 100 |  | 0 | [6 empty] | Material Work Order
23-0075-IR | WO0001 | APP | 2023-06-01T18:16:19.407 | WO | 0 | 530.13 | 2.08 | 530.13 | 100 |  | 0 |  | 06/01/2023 | 06/01/2023 |  |  |  | APP
23-0075-IR | WO0002 | Cabinet Labor | 2023-06-01T18:16:19.000 | WO | 0 | 3762.885 | 59.8 | 7525.77 | 50 |  | 50 |  | 06/01/2023 | 06/09/2023 |  |  |  | CAB
23-0075-IR | WO0003 | Cleaning Labor | 2023-06-01T18:16:19.000 | WO | 0 | 11663.4919 | 701.43 | 59374.02 | 11663.47 |  | 80.3559 |  | 06/01/2023 | 09/19/2023 |  |  |  | CLN
23-0075-IR | WO0004 | Fire Demo | 2023-06-01T18:16:20.000 | WO | 0 | 17585.0023 | 210.31 | 20412.43 | 17585 |  | 13.8515 |  | 06/01/2023 | 07/04/2023 |  |  |  | DMO
23-0075-IR | WO0005 | FNC (Doors, Trim, Knobs) Labor | 2023-06-01T18:16:20.000 | WO | 0 | 6305.576 | 120.67 | 15763.94 | 40 |  | 60 |  | 06/01/2023 | 06/13/2023 |  |  |  | DOR
23-0075-IR | WO0006 | Drywall and Paint Labor | 2023-06-01T18:16:20.000 | WO | 0 | 26727.8284 | 594.16 | 83302.93 | 26727.81 |  | 67.9149 |  | 06/01/2023 | 08/02/2023 |  |  |  | DRY
23-0075-IR | WO0007 | Electric Labor | 2023-06-01T18:16:21.000 | WO | 0 | 10987.758 | 100.75 | 18312.93 | 60 |  | 40 |  | 06/01/2023 | 06/13/2023 |  |  |  | ELE
23-0075-IR | WO0008 | Carpet Labor | 2023-06-01T18:16:21.000 | WO | 0 | 3227.51 | 40.75 | 5868.2 | 55 |  | 45 |  | 06/01/2023 | 06/07/2023 |  |  |  | FCC
23-0075-IR | WO00010 | Wood Floor Labor | 2023-06-01T18:16:21.000 | WO | 0 | 3347.22 | 38.52 | 5578.7 | 60 |  | 40 |  | 06/01/2023 | 06/07/2023 |  |  |  | FCW
23-0075-IR | WO00011 | FEE | 2023-06-01T18:16:21.627 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | FEE
23-0075-IR | WO00014 | Framing Labor | 2023-06-01T18:16:21.000 | WO | 0 | 15665.084 | 369.25 | 39162.71 | 40 |  | 60 |  | 06/01/2023 | 07/28/2023 |  |  |  | FRM
23-0075-IR | WO00015 | HVC Materials and Labor | 2023-06-01T18:16:22.000 | WO | 0 | 2722.209 | 13.67 | 3888.87 | 70 |  | 30 |  | 06/01/2023 | 06/02/2023 |  |  |  | HVC
23-0075-IR | WO00016 | Insulation Materials and Labor | 2023-06-01T18:16:22.000 | WO | 0 | 10693.709 | 76.67 | 16451.86 | 65 |  | 35 |  | 06/01/2023 | 06/13/2023 |  |  |  | INS
23-0075-IR | WO00018 | Masonry Labor | 2023-06-01T18:16:22.000 | WO | 0 | 3521.316 | 48.3 | 5868.86 | 60 |  | 40 |  | 06/01/2023 | 06/08/2023 |  |  |  | MAS
23-0075-IR | WO00021 | Bathroom FNC Labor | 2023-06-01T18:16:22.000 | WO | 0 | 599.44 | 14.85 | 1498.6 | 40 |  | 60 |  | 06/01/2023 | 06/02/2023 |  |  |  | MSD
23-0075-IR | WO00022 | Plumbing Labor | 2023-06-01T18:16:23.000 | WO | 0 | 11301.654 | 55.63 | 16145.22 | 70 |  | 30 |  | 06/01/2023 | 06/09/2023 |  |  |  | PLM
23-0075-IR | WO00024 | Roofing Labor | 2023-06-01T18:16:23.000 | WO | 0 | 12019.42 | 142.45 | 30048.55 | 40 |  | 60 |  | 06/01/2023 | 06/22/2023 |  |  |  | RFG
23-0075-IR | WO00025 | Siding/Soffit/Gutter Labor | 2023-06-01T18:16:23.000 | WO | 0 | 5488.075 | 60.45 | 10976.15 | 50 |  | 50 |  | 06/01/2023 | 06/09/2023 |  |  |  | SDG
23-0075-IR | WO00027 | Tile Labor | 2023-06-01T18:16:23.000 | WO | 0 | 7002.15 | 60.88 | 11670.25 | 60 |  | 40 |  | 06/01/2023 | 06/08/2023 |  |  |  | TIL
23-0075-IR | WO00028 | Board Up | 2023-06-01T18:16:23.000 | WO | 0 | 1698.864 | 1.85 | 2831.44 | 60 |  | 40 |  | 06/01/2023 | 06/01/2023 |  |  |  | TMP
23-0075-IR | WO00029 | Window Treatment Labor | 2023-06-01T18:16:24.000 | WO | 0 | 350.695 | 6.5 | 701.39 | 50 |  | 50 |  | 06/01/2023 | 06/01/2023 |  |  |  | WDT
23-0075-IR | WO00030 | Window Labor | 2023-06-01T18:16:24.000 | WO | 0 | 1494.036 | 19.4 | 2490.06 | 60 |  | 40 |  | 06/01/2023 | 06/05/2023 |  |  |  | WDW
23-0075-IR | WO00031 | Wall Paper Labor | 2023-06-01T18:16:24.000 | WO | 0 | 3892.0365 | 67.2 | 8648.97 | 45 |  | 55 |  | 06/01/2023 | 06/12/2023 |  |  |  | WPR
23-0075-IR | WO00032 | Drywall and Paint Materials | 2023-08-14T16:51:12.000 | WO | 0 | 9742.194 |  | 17713.08 | 55 |  | 45 | [6 empty] | Material Work Order
23-0075-IR | WO00033 | Cabinets/Counter top Materials | 2023-08-14T16:52:23.000 | WO | 0 | 13377.384 | 2.57 | 22295.64 | 60 |  | 40 |  | 06/01/2023 | 06/01/2023 |  |  |  | Material Work Order
23-0075-IR | WO00034 | FNC (doors, trim, knobs) Materials | 2023-08-14T16:56:30.000 | WO | 0 | 11131.989 |  | 20239.98 | 55 |  | 45 | [6 empty] | Material Work Order
23-0075-IR | WO00035 | Cleaning Materials | 2023-08-14T16:59:06.000 | WO | 0 | 558.684 |  | 931.14 | 60 |  | 40 | [6 empty] | Material Work Order
23-0075-IR | WO00036 | Electric Materials | 2023-08-14T17:00:20.000 | WO | 0 | 3055.241 |  | 4364.63 | 70 |  | 30 | [6 empty] | Material Work Order
23-0075-IR | WO00037 | Carpet Materials | 2023-08-14T17:01:58.000 | WO | 0 | 8405.229 |  | 12007.47 | 70 |  | 30 | [6 empty] | Material Work Order
23-0075-IR | WO00038 | Framing Materials | 2023-08-14T17:04:31.000 | WO | 0 | 19041.953 |  | 27202.79 | 70 |  | 30 | [6 empty] | Material Work Order
23-0075-IR | WO00039 | Siding/Soffit/Gutter Materials | 2023-08-14T17:07:35.000 | WO | 0 | 3087.07 |  | 4410.1 | 70 |  | 30 | [6 empty] | Material Work Order
23-0075-IR | WO00040 | Roofing Materials | 2023-08-14T17:08:34.000 | WO | 0 | 6940.619 |  | 9915.17 | 70 |  | 30 | [6 empty] | Material Work Order
23-0075-IR | WO00041 | Plumbing Materials | 2023-08-14T17:09:39.000 | WO | 0 | 3615.36 |  | 5164.8 | 70 |  | 30 | [6 empty] | Material Work Order
23-0075-IR | WO00042 | Window Treatment Materials | 2023-08-14T17:10:50.000 | WO | 0 | 368.081 |  | 525.83 | 70 |  | 30 | [6 empty] | Material Work Order
23-0075-IR | WO00043 | Wall Paper Materials | 2023-08-14T17:12:02.000 | WO | 0 | 1826.01 |  | 3043.35 | 60 |  | 40 | [6 empty] | Material Work Order
23-0075-IR | WO00044 | Window Materials | 2023-08-14T17:12:53.000 | WO | 0 | 6413.148 |  | 9161.64 | 70 |  | 30 | [6 empty] | Material Work Order
23-0075-IR | WO00046 | Bathroom FNC Materials | 2023-08-14T17:14:32.000 | WO | 0 | 963.536 |  | 1376.48 | 70 |  | 30 | [6 empty] | Material Work Order
23-0075-IR | WO00047 | Masonry Materials | 2023-08-14T17:15:47.000 | WO | 0 | 1623.314 |  | 2319.02 | 70 |  | 30 | [6 empty] | Material Work Order
23-0075-IR | WO00048 | Tile Materials | 2023-08-14T17:16:58.000 | WO | 0 | 3493.966 |  | 4991.38 | 70 |  | 30 | [6 empty] | Material Work Order
23-0075-IR | WO00049 | Wood Floor Materials | 2023-08-14T17:18:53.000 | WO | 0 | 654.577 |  | 935.11 | 70 |  | 30 | [6 empty] | Material Work Order
23-0076-IR | WO0001 | CLN | 2023-05-24T17:04:31.977 | WO | 0 | 722.99 | 8.92 | 722.99 | 100 |  | 0 |  | 05/24/2023 | 05/25/2023 |  |  |  | CLN
23-0076-IR | WO0002 | CON | 2023-05-24T17:04:32.267 | WO | 0 | 336 | 5 | 336 | 100 |  | 0 |  | 05/24/2023 | 05/24/2023 |  |  |  | CON
23-0076-IR | WO0003 | DMO | 2023-05-24T17:04:32.420 | WO | 0 | 245.89 | 1.98 | 245.89 | 100 |  | 0 |  | 05/24/2023 | 05/24/2023 |  |  |  | DMO
23-0076-IR | WO0004 | DOR | 2023-05-24T17:04:32.557 | WO | 0 | 1040.68 | 3.22 | 1040.68 | 100 |  | 0 |  | 05/24/2023 | 05/24/2023 |  |  |  | DOR
23-0076-IR | WO0005, Complete | FCC | 2023-05-24T17:04:32.000 | WO | 0 | 2343.9801 |  | 6292.26 | 2343.98 |  | 62.7482 |  |  |  |  | 2023-08-06T17:55:00.733 | Burrell, Bianca | FCC
23-0076-IR | WO0006, Complete | FCV | 2023-05-24T17:04:32.000 | WO | 0 | 282.074 | 0.37 | 433.96 | 65 |  | 35 |  | 05/24/2023 | 05/24/2023 |  | 2023-08-14T11:09:11.240 | Burrell, Bianca | FCV
23-0076-IR | WO0007 | FNC | 2023-05-24T17:04:32.997 | WO | 0 | 12.59 | 0.07 | 12.59 | 100 |  | 0 |  | 05/24/2023 | 05/24/2023 |  |  |  | FNC
23-0076-IR | WO0008 | FNH | 2023-05-24T17:04:33.270 | WO | 0 | 135.74 | 1.43 | 135.74 | 100 |  | 0 |  | 05/24/2023 | 05/24/2023 |  |  |  | FNH
23-0076-IR | WO0009 | LAB | 2023-05-24T17:04:33.497 | WO | 0 | -175.16 | 0 | -175.16 | 100 |  | 0 |  | 05/24/2023 | 05/24/2023 |  |  |  | LAB
23-0076-IR | WO00010 | PNL | 2023-05-24T17:04:33.687 | WO | 0 | 190.22 | 1.12 | 190.22 | 100 |  | 0 |  | 05/24/2023 | 05/24/2023 |  |  |  | PNL
23-0076-IR | WO00011 | PNT | 2023-05-24T17:04:33.843 | WO | 0 | 1196.06 | 8.05 | 1196.06 | 100 |  | 0 |  | 05/24/2023 | 05/25/2023 |  |  |  | PNT
23-0076-IR | WO00012 | TIL | 2023-05-24T17:04:34.017 | WO | 0 | 564.65 | 3.18 | 564.65 | 100 |  | 0 |  | 05/24/2023 | 05/24/2023 |  |  |  | TIL
23-0076-IR | WO00013, Complete | Flooring labor | 2023-05-24T17:05:00.000 | WO | 0 | 1491.76 | 19.35 | 1491.76 | 100 |  | 0 |  | 05/24/2023 | 05/25/2023 |  | 2023-08-14T11:09:00.247 | Burrell, Bianca
23-0078-IR | WO0001 | CAB | 2023-05-16T15:40:18.787 | WO | 0 | 1921.57 | 3.75 | 1921.57 | 100 |  | 0 |  | 05/16/2023 | 05/16/2023 |  |  |  | CAB
23-0078-IR | WO0002 | CON | 2023-05-16T15:40:18.910 | WO | 0 | 168 | 2.5 | 168 | 100 |  | 0 |  | 05/16/2023 | 05/16/2023 |  |  |  | CON
23-0078-IR | WO0003 | DMO | 2023-05-16T15:40:19.007 | WO | 0 | 84.14 |  | 84.14 | 100 |  | 0 | [6 empty] | DMO
23-0078-IR | WO0004 | DRY | 2023-05-16T15:40:19.287 | WO | 0 | 116.4 |  | 116.4 | 100 |  | 0 | [6 empty] | DRY
23-0078-IR | WO0005 | ELE | 2023-05-16T15:40:19.553 | WO | 0 | 159.02 | 0 | 159.02 | 100 |  | 0 |  | 05/16/2023 | 05/16/2023 |  |  |  | ELE
23-0078-IR | WO0006 | FCT | 2023-05-16T15:40:19.757 | WO | 0 | 480.28 |  | 480.28 | 100 |  | 0 | [6 empty] | FCT
23-0078-IR | WO0007 | FNC | 2023-05-16T15:40:19.880 | WO | 0 | 40.2 |  | 40.2 | 100 |  | 0 | [6 empty] | FNC
23-0078-IR | WO0008 | FRM | 2023-05-16T15:40:19.943 | WO | 0 | 43.09 |  | 43.09 | 100 |  | 0 | [6 empty] | FRM
23-0078-IR | WO0009 | HVC | 2023-05-16T15:40:20.120 | WO | 0 | 465.3 | 2.33 | 465.3 | 100 |  | 0 |  | 05/16/2023 | 05/16/2023 |  |  |  | HVC
23-0078-IR | WO00010 | LAB | 2023-05-16T15:40:20.197 | WO | 0 | -56.2 | 0 | -56.2 | 100 |  | 0 |  | 05/16/2023 | 05/16/2023 |  |  |  | LAB
23-0078-IR | WO00011 | LIT | 2023-05-16T15:40:20.310 | WO | 0 | 517.22 |  | 517.22 | 100 |  | 0 | [6 empty] | LIT
23-0078-IR | WO00012 | PLM | 2023-05-16T15:40:20.387 | WO | 0 | 1092.51 | 4.17 | 1092.51 | 100 |  | 0 |  | 05/16/2023 | 05/16/2023 |  |  |  | PLM
23-0078-IR | WO00013 | PNT | 2023-05-16T15:40:20.527 | WO | 0 | 310.37 |  | 310.37 | 100 |  | 0 | [6 empty] | PNT
23-0078-IR | WO00014 | DRY | 2023-05-16T15:40:41.030 | WO | 0 | 26.91 |  | 26.91 | 100 |  | 0 | [6 empty] | DRY
23-0078-IR | WO00015 | FRM | 2023-05-16T15:40:41.393 | WO | 0 |  |  |  | 0 |  | 0 | [6 empty] | FRM
23-0078-IR | WO00016 | MSD | 2023-05-16T15:40:41.803 | WO | 0 | 1432.28 |  | 1432.28 | 100 |  | 0 | [6 empty] | MSD
23-0078-IR | WO00017 | PLM | 2023-05-16T15:40:42.163 | WO | 0 | 3676.42 | 7.02 | 3676.42 | 100 |  | 0 |  | 05/16/2023 | 05/16/2023 |  |  |  | PLM
23-0078-IR | WO00018 | marlon work order | 2023-05-16T16:34:00.000 | WO | 0 | 2200 | 29.47 | 2572.79 | 2200 |  | 14.4897 |  | 05/16/2023 | 05/17/2023 |  |  |  | marlon work order
23-0078-IR | WO00019, Complete | Drywall work Angel | 2023-05-25T13:01:00.000 | WO | 0 | 1100 | 24.8 | 2374.95 | 1100 |  | 53.6832 |  | 05/16/2023 | 05/25/2023 |  | 2023-06-01T16:38:34.060 | Trevino, Jeovani | Angel work order
23-0078-IR | WO00020 | Val tile | 2023-07-17T15:03:00.000 | WO | 0 | 699.9995 | 15.83 | 1196.11 | 700 |  | 41.477 |  | 05/16/2023 | 07/17/2023 |  |  |  | val Tile
23-0081-ER | WO0001, Complete | CON | 2023-06-14T15:49:45.853 | WO | 0 | 247.31 | 4.4 | 247.31 | 100 |  | 0 |  | 06/14/2023 | 06/14/2023 |  | 2023-08-24T09:38:34.947 | Dehnke, Josh | CON
23-0081-ER | WO0002, Complete | DMO | 2023-06-14T15:49:46.133 | WO | 0 | 42.07 |  | 42.07 | 100 |  | 0 |  |  |  |  | 2023-08-24T09:38:34.933 | Dehnke, Josh | DMO
23-0081-ER | WO0003, Complete | DOR | 2023-06-14T15:49:46.273 | WO | 0 | 887.58 | 6.8 | 887.58 | 100 |  | 0 |  | 06/14/2023 | 06/14/2023 |  | 2023-08-24T09:38:34.917 | Dehnke, Josh | DOR
23-0081-ER | WO0004, Complete | FNC | 2023-06-14T15:49:46.383 | WO | 0 |  |  |  | 0 |  | 0 |  |  |  |  | 2023-08-24T09:38:34.900 | Dehnke, Josh | FNC
23-0081-ER | WO0005, Complete | FRM | 2023-06-14T15:49:46.477 | WO | 0 | 26.9 |  | 26.9 | 100 |  | 0 |  |  |  |  | 2023-08-24T09:38:34.883 | Dehnke, Josh | FRM
23-0081-ER | WO0006, Complete | MAS | 2023-06-14T15:49:46.570 | WO | 0 | 198.77 |  | 198.77 | 100 |  | 0 |  |  |  |  | 2023-08-24T09:38:34.870 | Dehnke, Josh | MAS
23-0081-ER | WO0007, Complete | PNT | 2023-06-14T15:49:46.650 | WO | 0 | 79.25 | 0.6 | 79.25 | 100 |  | 0 |  | 06/14/2023 | 06/14/2023 |  | 2023-08-24T09:38:34.870 | Dehnke, Josh | PNT
23-0081-ER | WO0008, Complete | SDG | 2023-06-14T15:49:46.773 | WO | 0 |  |  |  | 0 |  | 0 |  |  |  |  | 2023-08-24T09:38:34.853 | Dehnke, Josh | SDG
23-0081-ER | WO0009, Complete | Trim Labor | 2023-06-14T15:54:00.000 | WO | 0 | 637.1502 | 13.15 | 1925.21 | 637.15 |  | 66.9049 |  | 06/14/2023 | 06/14/2023 |  | 2023-08-24T09:38:34.837 | Dehnke, Josh
23-0086-D | WO0001 | CAB | 2023-05-23T13:13:33.130 | WO | 0 | 271.44 | 2.32 | 271.44 | 100 |  | 0 |  | 05/23/2023 | 05/23/2023 |  |  |  | CAB
23-0086-D | WO0002 | DMO | 2023-05-23T13:13:33.410 | WO | 0 | 35.45 | 0.22 | 35.45 | 100 |  | 0 |  | 05/23/2023 | 05/23/2023 |  |  |  | DMO
23-0086-D | WO0003 | DOR | 2023-05-23T13:13:33.723 | WO | 0 | 34.66 | 0.3 | 34.66 | 100 |  | 0 |  | 05/23/2023 | 05/23/2023 |  |  |  | DOR
23-0086-D | WO0004 | DRY | 2023-05-23T13:13:34.000 | WO | 0 | 665.93 | 4.5 | 665.93 | 100 |  | 0 |  | 05/23/2023 | 05/23/2023 |  |  |  | DRY
23-0086-D | WO0005 | MPR | 2023-05-23T13:13:34.163 | WO | 0 | 143.94 | 1.1 | 143.94 | 100 |  | 0 |  | 05/23/2023 | 05/23/2023 |  |  |  | MPR
23-0086-D | WO0006 | Plumbing Labor | 2023-05-23T13:13:34.000 | WO | 0 | 2848.28 | 12.43 | 2848.28 | 100 |  | 0 |  | 05/23/2023 | 05/24/2023 |  |  |  | PLM
23-0086-D | WO0007 | Shower materials | 2023-05-23T12:15:19.000 | WO | 0 | 2571.21 |  | 2571.21 | 100 |  | 0 | [6 empty] | Shower
23-0088-IR | WO0001, Complete | CLN | 2023-06-21T14:36:36.833 | WO | 0 | 388 | 4 | 388 | 100 |  | 0 |  | 06/21/2023 | 06/21/2023 |  | 2023-07-17T09:05:34.727 | Burrell, Bianca | CLN
23-0088-IR | WO0002, Complete | CON | 2023-06-21T14:36:36.960 | WO | 0 | 67.2 | 1 | 67.2 | 100 |  | 0 |  | 06/21/2023 | 06/21/2023 |  | 2023-08-06T17:51:46.647 | Burrell, Bianca | CON
23-0088-IR | WO0003, Complete | DMO | 2023-06-21T14:36:37.053 | WO | 0 | 97.84 | 1.98 | 97.84 | 100 |  | 0 |  | 06/21/2023 | 06/21/2023 |  | 2023-08-06T17:51:46.643 | Burrell, Bianca | DMO
23-0088-IR | WO0005, Complete | ELE | 2023-06-21T14:36:37.490 | WO | 0 | 150.36 | 0.52 | 150.36 | 100 |  | 0 |  | 06/21/2023 | 06/21/2023 |  | 2023-08-06T17:51:46.637 | Burrell, Bianca | ELE
23-0088-IR | WO0006 | FCC | 2023-06-21T14:36:37.773 | WO | 0 | 692.6 | 3.6 | 692.6 | 100 |  | 0 |  | 06/21/2023 | 06/21/2023 |  |  |  | FCC
23-0088-IR | WO0007 | INS | 2023-06-21T14:36:37.943 | WO | 0 | 329.28 | 0.5 | 329.28 | 100 |  | 0 |  | 06/21/2023 | 06/21/2023 |  |  |  | INS
23-0088-IR | WO0008, Complete | LIT | 2023-06-21T14:36:38.070 | WO | 0 | 259 | 1.85 | 259 | 100 |  | 0 |  | 06/21/2023 | 06/21/2023 |  | 2023-08-06T17:51:46.633 | Burrell, Bianca | LIT
23-0088-IR | WO0009, Complete | PNT | 2023-06-21T14:36:38.000 | WO | 0 | 909.517 | 8.13 | 1299.31 | 70 |  | 30 |  | 06/21/2023 | 06/21/2023 |  | 2023-08-06T17:51:46.627 | Burrell, Bianca | PNT
23-0092-IR
23-0093-ER | WO0001 | haul away debris | 2023-06-26T10:29:18.000 | WO | 0 | 110.862 | 1.98 | 246.36 | 45 |  | 55 |  | 06/26/2023 | 06/26/2023 |  |  |  | DMO
23-0093-ER | WO0002 | ELS | 2023-06-26T10:29:19.077 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | ELS
23-0093-ER | WO0003 | FEE | 2023-06-26T10:29:19.187 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | FEE
23-0093-ER | WO0004 | fireplace material | 2023-06-26T10:29:19.000 | WO | 0 | 122.312 |  | 152.89 | 80 |  | 20 | [6 empty] | FPL
23-0093-ER | WO0005 | roof labor | 2023-06-26T10:29:19.000 | WO | 0 | 6855.5305 | 62.76 | 10546.97 | 65 |  | 35 |  | 06/27/2023 | 07/06/2023 |  |  |  | RFG
23-0093-ER | WO0006 | fireplace labor | 2023-06-26T10:13:10.000 | WO | 0 | 163.57 | 0.6 | 297.4 | 55 |  | 45 |  | 06/26/2023 | 06/26/2023 |  |  |  | Labor Work Order
23-0093-ER | WO0008 | roofing material | 2023-06-26T10:16:09.000 | WO | 0 | 3282.824 |  | 4103.53 | 80 |  | 20 | [6 empty] | Material Work Order
23-0094-IR
23-0095-IR | WO0003 | Final Cleaning | 2023-08-04T13:10:42.000 | WO | 0 | 0 | 11.07 | 757.54 | 0 |  | 100 |  | 08/04/2023 | 08/07/2023 |  |  |  | CLN
23-0095-IR | WO0006, Complete | Drywall and Paint Labor | 2023-08-04T13:10:42.000 | WO | 0 | 7060 | 78.67 | 10810.34 | 7060 |  | 34.6922 |  | 08/04/2023 | 08/14/2023 |  | 2023-08-28T12:04:23.570 | Dehnke, Josh | DRY
23-0095-IR | WO0007 | Electrical Labor and Materials | 2023-08-04T13:10:42.000 | WO | 0 | 1598.44 | 9.98 | 1998.05 | 80 |  | 20 |  | 08/04/2023 | 08/04/2023 |  |  |  | ELE
23-0095-IR | WO0008 | Flooring Labor | 2023-08-04T13:10:42.000 | WO | 0 | 2499.9987 | 25.58 | 3560.06 | 2500 |  | 29.7765 |  | 08/04/2023 | 08/08/2023 |  |  |  | FCC
23-0095-IR | WO00010 | Carpentry (Trim, Doors, Window) Labor | 2023-08-04T13:10:43.000 | WO | 0 | 2223.21 | 32.33 | 3705.35 | 60 |  | 40 |  | 08/04/2023 | 08/07/2023 |  |  |  | FNC
23-0095-IR | WO00012, Complete | Framing and Insulation labor | 2023-08-04T13:10:43.000 | WO | 0 | 1147.416 | 9.8 | 1912.36 | 60 |  | 40 |  | 08/04/2023 | 08/04/2023 |  | 2023-08-24T09:33:20.133 | Dehnke, Josh | FRM
23-0095-IR | WO00019 | Plumbing Labor | 2023-08-04T13:10:43.000 | WO | 0 | 816.296 | 3.53 | 1020.37 | 80 |  | 20 |  | 08/04/2023 | 08/04/2023 |  |  |  | PLM
23-0095-IR | WO00021, Complete | FNC Materials | 2023-08-04T12:22:52.000 | WO | 0 | 3009.39 |  | 4663.48 | 3009.39 |  | 35.469 |  |  |  |  | 2023-08-28T12:04:23.583 | Dehnke, Josh | FNC
23-0095-IR | WO00022, Complete | Drywall and Paint Materials | 2023-08-04T12:26:09.000 | WO | 0 | 0 |  | 3125.4 | 0 |  | 100 |  |  |  |  | 2023-08-28T12:04:23.620 | Dehnke, Josh | Material Work Order
23-0095-IR | WO00023, Complete | Flooring Materials | 2023-08-04T12:28:56.000 | WO | 0 | 3199.9986 |  | 4669.99 | 3200 |  | 31.4774 |  |  |  |  | 2023-08-28T12:04:23.633 | Dehnke, Josh | Material Work Order
23-0095-IR | WO00024, Complete | Trim / Door Painting | 2023-08-25T11:47:00.000 | WO | 0 | 1800.0021 | 49.89 | 5054.78 | 1800 |  | 64.3901 |  | 08/08/2023 | 08/25/2023 |  | 2023-08-29T12:50:58.383 | Dehnke, Josh | PNT
23-0095-IR | WO00025 | Window Materials | 2023-08-25T14:31:00.000 | WO | 0 | 362.8598 | 8 | 460.51 | 362.86 |  | 21.2048 |  | 08/25/2023 | 08/25/2023 |  |  |  | WDW
23-0095-IR | WO00026 | Vanity Cabinet | 2023-08-25T14:43:00.000 | WO | 0 | 831.425 | 8 | 1662.85 | 50 |  | 50 |  | 08/25/2023 | 08/25/2023 |  |  |  | CAB
23-0095-IR | WO00027 | OOP Framing Labor | 2023-08-29T13:24:00.000 | WO | 0 | 500 | 14.91 | 1070.33 | 500 |  | 53.2854 |  | 08/08/2023 | 08/29/2023 |  |  |  | FRM
23-0099-ER | WO0001 | labor- deck and lattice | 2023-07-06T12:26:39.000 | WO | 0 | 1961.29 | 37.27 | 3922.58 | 50 |  | 50 |  | 07/06/2023 | 07/12/2023 |  |  |  | CNC
23-0099-ER | WO0004 | material- lattice | 2023-07-06T12:26:40.000 | WO | 0 | 92.768 |  | 115.96 | 80 |  | 20 | [6 empty] | FNC
23-0099-ER | WO0005 | material- deck | 2023-07-06T12:26:40.000 | WO | 0 | 2181.344 |  | 2726.68 | 80 |  | 20 | [6 empty] | FRM
23-0099-ER | WO0007 | material- seal/stain/paint deck | 2023-07-06T12:26:40.000 | WO | 0 | 119.88 |  | 149.85 | 80 |  | 20 | [6 empty] | PNT
23-0099-ER | WO0008, Complete | material- roof | 2023-07-06T12:26:40.000 | WO | 0 | 3030.9687 |  | 3059.06 | 3030.97 |  | 0.9183 |  |  |  |  | 2023-07-27T08:45:20.827 | Schmidt, Jeremy | RFG
23-0099-ER | WO00013 | labor- seal/stain/paint | 2023-07-06T11:36:57.000 | WO | 0 | 292.515 | 4.77 | 585.03 | 50 |  | 50 |  | 07/06/2023 | 07/06/2023 |  |  |  | Labor Work Order
23-0099-ER | WO00015 | material and labor- concrete | 2023-07-06T13:02:00.000 | WO | 0 | 611.95 | 12.7 | 611.95 | 100 |  | 0 |  | 07/06/2023 | 07/06/2023
23-0099-ER | WO00016, Complete | labor- roof, gutters and dump trailer | 2023-07-07T12:20:00.000 | WO | 0 | 3243.2009 | 706.22 | 8033.83 | 3243.2 |  | 59.6307 |  | 07/06/2023 | 10/23/2023 |  | 2023-07-27T08:45:06.873 | Schmidt, Jeremy
23-0101-IR | WO0004, Complete | Demo Labor | 2023-05-23T14:57:41.000 | WO | 0 | 411.65 | 7.8 | 823.3 | 50 |  | 50 |  | 05/23/2023 | 05/23/2023 |  | 2023-06-21T09:00:44.060 | Dehnke, Josh | DMO
23-0101-IR | WO0006 | Drywall and Paint Labor | 2023-05-23T14:57:42.000 | WO | 0 | 1199.9992 | 27.7 | 3699.18 | 1200 |  | 67.5604 |  | 05/23/2023 | 05/24/2023 |  |  |  | DRY
23-0101-IR | WO0007 | Light Labor | 2023-05-23T14:57:42.000 | WO | 0 | 204.68 | 0.77 | 409.36 | 50 |  | 50 |  | 05/23/2023 | 05/23/2023 |  |  |  | ELE
23-0101-IR | WO0008 | Vinyl Floor Labor | 2023-05-23T14:57:42.000 | WO | 0 | 268.16 | 2.17 | 536.32 | 50 |  | 50 |  | 05/23/2023 | 05/23/2023 |  |  |  | FCV
23-0101-IR | WO0009 | FEE | 2023-05-23T14:57:42.607 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | FEE
23-0101-IR | WO00010 | Finish Carpentry Labor (Doors, Trim, Vanity set) | 2023-05-23T14:57:42.000 | WO | 0 | 803.176 | 12.52 | 1460.32 | 55 |  | 45 |  | 05/23/2023 | 05/24/2023 |  |  |  | FNC
23-0101-IR | WO00011 | Framing and Insulation labor | 2023-05-23T14:57:42.000 | WO | 0 | 2318.155 | 41.43 | 4636.31 | 50 |  | 50 |  | 05/23/2023 | 05/29/2023 |  |  |  | FRM
23-0101-IR | WO00015 | Masonry and Brick Repair Labor | 2023-05-23T14:57:43.000 | WO | 0 | 2678.286 | 38.53 | 4463.81 | 60 |  | 40 |  | 05/23/2023 | 05/29/2023 |  |  |  | MAS
23-0101-IR | WO00017 | Shower Door Labor | 2023-05-23T14:57:43.000 | WO | 0 | 203.005 | 4.15 | 406.01 | 50 |  | 50 |  | 05/23/2023 | 05/23/2023 |  |  |  | MSD
23-0101-IR | WO00018 | Plumbing Labor | 2023-05-23T14:57:43.000 | WO | 0 | 2558.268 | 12.62 | 4263.78 | 60 |  | 40 |  | 05/23/2023 | 05/24/2023 |  |  |  | PLM
23-0101-IR | WO00020 | Siding Labor | 2023-05-23T14:57:43.000 | WO | 0 | 357.222 | 2.03 | 595.37 | 60 |  | 40 |  | 05/23/2023 | 05/23/2023 |  |  |  | SDG
23-0101-IR | WO00021 | Shower floor labor | 2023-05-23T14:57:43.000 | WO | 0 | 103.32 | 0.75 | 147.6 | 70 |  | 30 |  | 05/23/2023 | 05/23/2023 |  |  |  | TIL
23-0101-IR | WO00022 | Window Labor | 2023-05-23T14:57:44.000 | WO | 0 | 492.9905 | 6.05 | 703.87 | 70.04 |  | 29.96 |  | 05/23/2023 | 05/23/2023 |  |  |  | WDA
23-0101-IR | WO00023 | Window blind materials | 2023-05-23T14:57:44.000 | WO | 0 | 148.82 | 1.9 | 297.64 | 50 |  | 50 |  | 05/23/2023 | 05/23/2023 |  |  |  | WDT
23-0101-IR | WO00025 | Drywall and paint Materials | 2023-06-21T08:53:45.000 | WO | 0 | 499.704 |  | 624.63 | 80 |  | 20 | [6 empty] | Material Work Order
23-0101-IR | WO00026 | Vanity and Laundry Cabinet | 2023-06-21T08:54:40.000 | WO | 0 | 922.088 |  | 1152.61 | 80 |  | 20 | [6 empty] | Material Work Order
23-0101-IR | WO00027 | Door and Trim Materials | 2023-06-21T08:56:53.000 | WO | 0 | 396.8325 |  | 529.11 | 75 |  | 25 | [6 empty] | Material Work Order
23-0101-IR | WO00028 | Framing, Insulation, and window Materials | 2023-08-22T16:08:14.000 | WO | 0 | 1542.499 |  | 2203.57 | 70 |  | 30 | [6 empty] | Material Work Order
23-0101-IR | WO00029 | Masonry Materials | 2023-08-22T16:19:01.000 | WO | 0 | 839.321 |  | 1199.03 | 70 |  | 30 | [6 empty] | Material Work Order
23-0101-IR | WO00030 | Shower tile materials | 2023-08-22T16:20:33.000 | WO | 0 | 40.334 |  | 57.62 | 70 |  | 30 | [6 empty] | Material Work Order
23-0101-IR | WO00031 | Shower materials | 2023-08-22T16:25:39.000 | WO | 0 | 1133.152 |  | 1548.88 | 73.1594 |  | 26.8406 | [6 empty] | Material Work Order
23-0101-IR | WO00032 | Siding Materials | 2023-08-22T16:26:58.000 | WO | 0 | 108.7575 |  | 145.01 | 75 |  | 25 | [6 empty] | Material Work Order
23-0102-ER | WO0005 | FEN | 2023-05-26T14:39:03.173 | WO | 0 | 637.73 | 3.25 | 637.73 | 100 |  | 0 |  | 05/26/2023 | 05/26/2023 |  |  |  | FEN
23-0102-ER | WO0007 | MAS | 2023-05-26T14:39:03.000 | WO | 0 | 567.51 | 8.68 | 1135.02 | 50 |  | 50 |  | 05/26/2023 | 05/29/2023 |  |  |  | MAS
23-0102-ER | WO0009 | PNT | 2023-05-26T14:39:03.000 | WO | 0 | 2398.852 | 29.77 | 5997.13 | 40 |  | 60 |  | 05/26/2023 | 05/30/2023 |  |  |  | PNT
23-0102-ER | WO00010 | Flat Roof Labor | 2023-05-26T14:39:03.000 | WO | 0 | 6381.372 | 61.76 | 10635.62 | 60 |  | 40 |  | 05/26/2023 | 06/01/2023 |  |  |  | RFG
23-0102-ER | WO00015 | Flat Roof Materials | 2023-06-30T08:50:10.000 | WO | 0 | 3613.984 |  | 4517.48 | 80 |  | 20 | [6 empty] | Material Work Order
23-0106-IR | WO0001 | CLN | 2023-04-20T13:01:33.000 | WO | 0 | 350.0003 | 5.95 | 573.24 | 350 |  | 38.9435 |  | 04/20/2023 | 04/20/2023 |  |  |  | CLN
23-0106-IR | WO0002 | CON | 2023-04-20T13:01:34.000 | WO | 0 |  |  |  | 0 |  | 0 | [6 empty] | CON
23-0106-IR | WO0003 | DMO | 2023-04-20T13:01:34.000 | WO | 0 | 0 |  | 42.07 | 0 |  | 100 | [6 empty] | DMO
23-0106-IR | WO0004 | DOR | 2023-04-20T13:01:34.170 | WO | 0 |  |  |  | 0 |  | 0 | [6 empty] | DOR
23-0106-IR | WO0005, Complete | FCC | 2023-04-20T13:01:34.267 | WO | 0 | 398.15 |  | 398.15 | 100 |  | 0 |  |  |  |  | 2023-05-08T10:48:01.920 | Trevino, Jeovani | FCC
23-0106-IR | WO0006, Complete | FNC | 2023-04-20T13:01:34.000 | WO | 0 | 0 |  | 796.28 | 0 |  | 100 |  |  |  |  | 2023-05-22T11:29:43.773 | Trevino, Jeovani | FNC
23-0106-IR | WO0007, Complete | LAB | 2023-04-20T13:01:34.000 | WO | 0 | 0 | 0 | 33.71 | 0 |  | 100 |  | 04/20/2023 | 04/20/2023 |  | 2023-05-08T10:47:21.020 | Trevino, Jeovani | LAB
23-0106-IR | WO0008, Complete | PNT | 2023-04-20T13:01:34.000 | WO | 0 | 0 |  | 66.47 | 0 |  | 100 |  |  |  |  | 2023-05-08T10:51:21.227 | Trevino, Jeovani | PNT
23-0106-IR | WO0009, Complete | george work order | 2023-04-20T13:25:00.000 | WO | 0 | 1115.0005 | 23.05 | 1861.16 | 1115 |  | 40.0911 |  | 04/20/2023 | 04/20/2023 |  | 2023-05-08T10:46:13.103 | Trevino, Jeovani | george carpet
23-0106-IR | WO00010 | rob painting | 2023-06-13T11:49:00.000 | WO | 0 | 350.0003 | 13.58 | 683.8 | 350 |  | 48.8154 |  | 04/20/2023 | 06/13/2023 |  |  |  | Rob painting
22-0553-RET-ER | WO0001 | Gutter Labor | 2023-05-25T10:25:02.000 | WO | 0 | 799.9999 | 6.18 | 1615 | 800 |  | 50.4644 |  | 05/25/2023 | 05/25/2023 |  |  |  | DMO
23-0110-ER | WO0001 | DMO | 2023-04-26T15:24:40.883 | WO | 0 |  |  |  | 0 |  | 0 | [6 empty] | DMO
23-0110-ER | WO0002 | FRM | 2023-04-26T15:24:40.000 | WO | 0 | 1060.68 |  | 2651.7 | 40 |  | 60 | [6 empty] | FRM
23-0110-ER | WO0003 | Material Work Order | 2023-04-26T14:24:59.873 | WO | 0 | 6222.85 |  | 6222.85 | 100 |  | 0 | [6 empty] | Material Work Order
23-0110-ER | WO0004 | Labor | 2023-07-25T13:55:00.000 | WO | 0 | 2242.968 | 75.62 | 5607.42 | 40 |  | 60 |  | 04/26/2023 | 07/25/2023 |  |  |  | Labor
23-0111-IR | WO0001 | DMO | 2023-04-26T15:24:40.883 | WO | 0 |  |  |  | 0 |  | 0 | [6 empty] | DMO
23-0111-IR | WO0002 | FRM | 2023-04-26T15:24:40.000 | WO | 0 | 1060.68 |  | 2651.7 | 40 |  | 60 | [6 empty] | FRM
23-0111-IR | WO0003 | Material Work Order | 2023-04-26T14:24:59.873 | WO | 0 | 6222.85 |  | 6222.85 | 100 |  | 0 | [6 empty] | Material Work Order
23-0111-IR | WO0004 | Labor | 2023-07-25T13:55:00.000 | WO | 0 | 2242.968 | 75.62 | 5607.42 | 40 |  | 60 |  | 04/26/2023 | 07/25/2023 |  |  |  | Labor
23-0112-IR | WO0001 | Vanity Labor | 2023-06-01T12:13:34.000 | WO | 0 | 634.37 | 5.2 | 634.37 | 100 |  | 0 |  | 06/01/2023 | 06/01/2023 |  |  |  | CAB
23-0112-IR | WO0002 | CLN | 2023-06-01T12:13:35.123 | WO | 0 | 694.34 | 9.15 | 694.34 | 100 |  | 0 |  | 06/01/2023 | 06/02/2023 |  |  |  | CLN
23-0112-IR | WO0003 | CON | 2023-06-01T12:13:35.250 | WO | 0 | 741.44 | 11 | 741.44 | 100 |  | 0 |  | 06/02/2023 | 06/05/2023 |  |  |  | CON
23-0112-IR | WO0004, Complete | DMO | 2023-06-01T12:13:35.357 | WO | 0 | 246.36 | 1.98 | 246.36 | 100 |  | 0 |  | 06/01/2023 | 06/01/2023 |  | 2023-06-20T13:19:41.837 | Burrell, Bianca | DMO
23-0112-IR | WO0005 | DOR | 2023-06-01T12:13:35.483 | WO | 0 | 1565.62 | 8.57 | 1565.62 | 100 |  | 0 |  | 06/01/2023 | 06/02/2023 |  |  |  | DOR
23-0112-IR | WO0007, Complete | FCC - Material | 2023-06-01T12:13:35.000 | WO | 0 | 1916.3187 |  | 3808.87 | 1916.32 |  | 49.688 |  |  |  |  | 2023-07-17T09:07:15.150 | Burrell, Bianca | FCC
23-0112-IR | WO0008, Complete | FNC | 2023-06-01T12:13:35.000 | WO | 0 | 640.0004 | 7.03 | 1614.98 | 640 |  | 60.371 |  | 06/01/2023 | 06/01/2023 |  | 2023-06-20T13:19:27.647 | Burrell, Bianca | FNC
23-0112-IR | WO0009 | FNH | 2023-06-01T12:13:36.060 | WO | 0 | 252.85 | 2.5 | 252.85 | 100 |  | 0 |  | 06/01/2023 | 06/01/2023 |  |  |  | FNH
23-0112-IR | WO00010, Complete | INS | 2023-06-01T12:13:36.000 | WO | 0 | 200.6425 | 1.2 | 236.05 | 85 |  | 15 |  | 06/01/2023 | 06/01/2023 |  | 2023-06-20T13:16:24.003 | Burrell, Bianca | INS
23-0112-IR | WO00011 | LIT | 2023-06-01T12:13:36.250 | WO | 0 | 162.06 | 0.97 | 162.06 | 100 |  | 0 |  | 06/01/2023 | 06/01/2023 |  |  |  | LIT
23-0112-IR | WO00012, Complete | MBL | 2023-06-01T12:13:36.327 | WO | 0 | 175.68 | 0.92 | 175.68 | 100 |  | 0 |  | 06/01/2023 | 06/01/2023 |  | 2023-06-20T13:16:23.940 | Burrell, Bianca | MBL
23-0112-IR | WO00013, Complete | MSD | 2023-06-01T12:13:36.420 | WO | 0 | 60.62 | 0.63 | 60.62 | 100 |  | 0 |  | 06/01/2023 | 06/01/2023 |  | 2023-06-20T13:16:24.067 | Burrell, Bianca | MSD
23-0112-IR | WO00014 | PLM | 2023-06-01T12:13:36.500 | WO | 0 | 606.03 | 2.23 | 606.03 | 100 |  | 0 |  | 06/01/2023 | 06/01/2023 |  |  |  | PLM
23-0112-IR | WO00015 | PNL | 2023-06-01T12:13:36.593 | WO | 0 | 168.77 | 0.67 | 168.77 | 100 |  | 0 |  | 06/01/2023 | 06/01/2023 |  |  |  | PNL
23-0112-IR | WO00016, Complete | PNT/DRY | 2023-06-01T12:13:36.000 | WO | 0 | 4784.436 | 26.97 | 7974.06 | 60 |  | 40 |  | 06/06/2023 | 06/09/2023 |  | 2023-06-20T13:16:24.097 | Burrell, Bianca | PNT
23-0112-IR | WO00017, Complete | TIL | 2023-06-01T12:13:36.827 | WO | 0 | 366.97 | 0 | 366.97 | 100 |  | 0 |  | 06/01/2023 | 06/01/2023 |  | 2023-06-20T13:16:24.130 | Burrell, Bianca | TIL
23-0112-IR | WO00018, Complete | Trim | 2023-06-01T12:15:00.000 | WO | 0 | 698.13 | 16.42 | 1163.55 | 60 |  | 40 |  | 06/01/2023 | 06/07/2023 |  | 2023-06-20T13:16:24.177 | Burrell, Bianca
23-0112-IR | WO00019, Complete | Carpet Labor | 2023-06-06T15:08:00.000 | WO | 0 | 2006.655 | 38.08 | 2866.65 | 70 |  | 30 |  | 06/01/2023 | 06/06/2023 |  | 2023-07-17T09:07:15.163 | Burrell, Bianca
23-0112-IR | WO00020 | Vanity - Material | 2023-06-14T12:58:00.000 | WO | 0 | 1204.2 | 8 | 1505.25 | 80 |  | 20 |  | 06/14/2023 | 06/14/2023
23-0114-ER | WO0001 | CAB | 2023-05-08T09:59:45.000 | WO | 0 | 0 | 9.88 | 2312.7 | 0 |  | 100 |  | 05/08/2023 | 05/08/2023 |  |  |  | CAB
23-0114-ER | WO0005 | DOR | 2023-05-08T09:59:45.750 | WO | 0 | 184.78 | 2.72 | 184.78 | 100 |  | 0 |  | 05/08/2023 | 05/08/2023 |  |  |  | DOR
23-0114-ER | WO0006 | FCC | 2023-05-08T09:59:45.000 | WO | 0 | 749.9996 | 15.38 | 1583.42 | 750 |  | 52.6342 |  | 05/08/2023 | 05/08/2023 |  |  |  | FCC
23-0114-ER | WO00010 | FCC Materials | 2023-05-08T09:00:30.000 | WO | 0 | 1700.0004 |  | 1820.24 | 1700 |  | 6.6057 | [6 empty] | Material Work Order
23-0114-ER | WO00011 | Door Materials | 2023-05-09T10:10:22.000 | WO | 0 | 148.904 |  | 186.13 | 80 |  | 20 | [6 empty] | Material Work Order
23-0114-ER-HouseRoof | WO0001, Complete | dump trailer- haul away debris | 2023-07-11T16:33:03.000 | WO | 0 | 500.0004 | 10.9 | 1690.75 | 500 |  | 70.4273 |  | 07/11/2023 | 07/12/2023 |  | 2023-07-27T09:34:23.100 | Schmidt, Jeremy | DMO
23-0114-ER-HouseRoof | WO0002 | FEE | 2023-07-11T16:33:03.723 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | FEE
23-0114-ER-HouseRoof | WO0003, Complete | material and labor- painting carport ceiling and cover the floor | 2023-07-11T16:33:04.000 | WO | 0 | 286.6701 | 4.87 | 648.39 | 286.67 |  | 55.7874 |  | 07/11/2023 | 07/11/2023 |  | 2023-08-10T12:29:00.353 | Schmidt, Jeremy | PNT
23-0114-ER-HouseRoof | WO0004, Complete | material- carport roof | 2023-07-11T16:33:04.000 | WO | 0 | 977.6 |  | 650.31 | 977.6 |  | -50.3283 |  |  |  |  | 2023-07-27T09:34:23.113 | Schmidt, Jeremy | RFG
23-0114-ER-HouseRoof | WO0005 | labor- prep, cover floor and paint carport ceiling | 2023-07-11T15:34:17.000 | WO | 0 |  |  |  | 0 |  | 0 | [6 empty] | Labor Work Order
23-0114-ER-HouseRoof | WO0006 | paint carport ceiling | 2023-07-27T10:32:00.000 | WO | 0 | 0 | 8 | 0 | 100 |  | 0 |  | 07/27/2023 | 07/27/2023
23-0117-IR | WO0002 | FEE | 2023-07-10T15:08:15.000 | WO | 0 | 0 |  | 273.77 | 0 |  | 100 | [6 empty] | FEE
23-0117-IR | WO0003, Complete | material- roof | 2023-07-10T15:08:15.000 | WO | 0 | 3677.8387 |  | 3282 | 3677.84 |  | -12.0609 |  |  |  |  | 2023-07-27T09:35:06.350 | Schmidt, Jeremy | RFG
23-0117-IR | WO0006 | USR | 2023-07-10T15:08:16.140 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | USR
23-0117-IR | WO0007, Complete | labor- roof, fascia and haul away | 2023-07-10T14:09:43.000 | WO | 0 | 2500.0021 | 55.35 | 8173.2 | 2500 |  | 69.4122 |  | 07/10/2023 | 07/17/2023 |  | 2023-07-27T09:35:06.333 | Schmidt, Jeremy | Labor Work Order
23-0122-IR | WO0001 | Carpet Materials | 2023-06-26T13:19:00.000 | WO | 0 | 1100.0003 | 8 | 1700 | 1100 |  | 35.2941 |  | 06/26/2023 | 06/26/2023 |  |  |  | FCC
23-0122-IR | WO0002 | Carpet and LVP Labor | 2023-06-26T13:20:00.000 | WO | 0 | 1000 | 16 | 1000 | 1000 |  | 0 |  | 06/26/2023 | 06/26/2023 |  |  |  | FCC
23-0122-IR | WO0003 | LVP Materials | 2023-06-26T13:20:00.000 | WO | 0 | 0 | 8 | 250 | 0 |  | 100 |  | 06/26/2023 | 06/26/2023 |  |  |  | LVP
23-0122-IR | WO0005 | Drywall Labor/Materials | 2023-06-26T13:28:00.000 | WO | 0 | 400.0002 | 8 | 650 | 400 |  | 38.4615 |  | 06/26/2023 | 06/26/2023 |  |  |  | DRY
23-0138-ER | WO0003 | Construction Clean | 2023-06-15T14:13:00.000 | WO | 0 | 0 | 1.18 | 99.05 | 0 |  | 100 |  | 06/15/2023 | 06/15/2023 |  |  |  | CLN
23-0138-ER | WO0006 | Drywall, paint (Materials and Labor) | 2023-06-15T14:13:00.000 | WO | 0 | 2013.965 | 24.03 | 4027.93 | 50 |  | 50 |  | 06/15/2023 | 06/16/2023 |  |  |  | DRY
23-0138-ER | WO0007 | Electrical Labor | 2023-06-15T14:13:00.000 | WO | 0 | 329.416 | 0.97 | 411.77 | 80 |  | 20 |  | 06/15/2023 | 06/15/2023 |  |  |  | ELE
23-0138-ER | WO0008 | Vinyl floor labor and contents move | 2023-06-15T14:13:01.000 | WO | 0 | 738.045 | 15.62 | 1640.1 | 45 |  | 55 |  | 06/15/2023 | 06/15/2023 |  |  |  | FCV
23-0138-ER | WO0009 | Trim, Doors, Cabinets, knobs | 2023-06-15T14:13:01.000 | WO | 0 | 579.1095 | 7.63 | 1286.91 | 45 |  | 55 |  | 06/15/2023 | 06/15/2023 |  |  |  | FNC
23-0138-ER | WO00012 | Plumbing Labor | 2023-06-15T14:13:01.000 | WO | 0 | 1341.864 | 7.57 | 2236.44 | 60 |  | 40 |  | 06/15/2023 | 06/15/2023 |  |  |  | PLM
23-0138-ER | WO00014 | Tile Labor | 2023-06-15T14:13:02.000 | WO | 0 | 2542.825 | 27.63 | 5085.65 | 50 |  | 50 |  | 06/15/2023 | 06/20/2023 |  |  |  | TIL
23-0138-ER | WO00015 | Tile Materials | 2023-06-15T13:48:12.000 | WO | 0 | 575.848 |  | 885.92 | 65 |  | 35 | [6 empty] | TIL
23-0138-ER | WO00016 | Vinyl Materials | 2023-06-15T13:54:14.000 | WO | 0 | 1291.15 | 4.02 | 1389.42 | 1291.15 |  | 7.0727 |  | 06/15/2023 | 06/15/2023 |  |  |  | FCV
23-0139-ER | WO0001 | DMO | 2023-06-26T11:40:08.683 | WO | 0 |  |  |  | 0 |  | 0 | [6 empty] | DMO
23-0139-ER | WO0002 | FEE | 2023-06-26T11:40:09.040 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | FEE
23-0139-ER | WO0003, Complete | RFG | 2023-06-26T11:40:09.000 | WO | 0 | 4200.0012 |  | 3914.76 | 4200 |  | -7.2863 |  |  |  |  | 2023-06-28T12:03:50.010 | Trevino, Jeovani | RFG
23-0139-ER | WO0004 | SDG | 2023-06-26T11:40:09.387 | WO | 0 | 289.48 | 0.48 | 289.48 | 100 |  | 0 |  | 06/26/2023 | 06/26/2023 |  |  |  | SDG
23-0139-ER | WO0005 | SFG | 2023-06-26T11:40:09.000 | WO | 0 | 1500.0013 | 11.19 | 3035.77 | 1500 |  | 50.5891 |  | 06/26/2023 | 06/27/2023 |  |  |  | SFG
23-0139-ER | WO0006, Complete | Ramirez | 2023-06-26T11:40:00.000 | WO | 0 | 3650.008 | 60.98 | 9125.02 | 40 |  | 60 |  | 06/26/2023 | 07/03/2023 |  | 2023-06-28T12:03:49.997 | Trevino, Jeovani | Ramirez
23-0145-D | WO0001 | material- awning | 2023-07-20T13:56:59.000 | WO | 0 | 678.2103 |  | 864.32 | 678.21 |  | 21.5325 | [6 empty] | AWN
23-0145-D | WO0004 | FEE | 2023-07-20T13:56:59.687 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | FEE
23-0145-D | WO0005, Complete | material- roofing | 2023-07-20T13:56:59.000 | WO | 0 | 5380.0304 |  | 5087.48 | 5380.03 |  | -5.7504 |  |  |  |  | 2023-08-18T14:06:13.067 | Schmidt, Jeremy | RFG
23-0145-D | WO0006, Complete | material- window wrap and custom fascia | 2023-07-20T13:56:59.000 | WO | 0 | 754.6709 | 8 | 1934.28 | 754.67 |  | 60.9844 |  | 08/22/2023 | 08/22/2023 |  | 2023-08-22T10:27:29.083 | Schmidt, Jeremy | SDG
23-0145-D | WO0008 | material- window screen | 2023-07-20T13:57:00.000 | WO | 0 | 1078.9125 |  | 1438.55 | 75 |  | 25 | [6 empty] | WDR
23-0145-D | WO00010, Complete | labor- roofing | 2023-07-20T13:00:39.000 | WO | 0 | 2830.0062 | 10 | 12443.69 | 2830 |  | 77.2575 |  | 08/18/2023 | 08/18/2023 |  | 2023-08-18T14:06:27.863 | Schmidt, Jeremy | Labor Work Order
23-0145-D | WO00012, Complete | labor- window screen | 2023-07-20T13:43:34.000 | WO | 0 | 304.37 | 17 | 304.37 | 100 |  | 0 |  | 08/23/2023 | 08/24/2023 |  | 2023-08-22T10:19:51.570 | Schmidt, Jeremy | Labor Work Order
23-0145-D | WO00013 | window and door wraps- labor | 2023-08-03T10:49:00.000 | WO | 0 | 4277.4011 | 18 | 9720.35 | 4277.4 |  | 55.9954 |  | 08/23/2023 | 08/24/2023
23-0145-D | WO00014 | gutters and downspouts | 2023-08-03T10:51:00.000 | WO | 0 | 288 | 0 | 589.11 | 288 |  | 51.1127 |  | 08/23/2023 | 08/25/2023
23-0145-D | WO00015 | labor- awning | 2023-08-03T10:56:00.000 | WO | 0 | 307.4803 | 6 | 819.93 | 307.48 |  | 62.4992 |  | 08/24/2023 | 08/24/2023
23-0145-D | WO00016 | custom fascia wrap- labor | 2023-08-03T11:00:00.000 | WO | 0 | 465.5365 | 27 | 846.43 | 55 |  | 45 |  | 08/23/2023 | 08/25/2023
23-0145-D | WO00017 | painting wraps- material | 2023-08-15T12:48:17.000 | WO | 0 | 161.864 |  | 202.33 | 80 |  | 20 | [6 empty] | PNT
23-0145-D | WO00018 | painting wraps- labor | 2023-08-15T12:49:00.000 | WO | 0 | 669.545 | 12 | 1339.09 | 50 |  | 50 |  | 08/28/2023 | 08/29/2023
23-0146-D
23-0150-WAR
23-0152-IR
23-0153-IR | WO0001 | CLN | 2023-06-16T13:53:22.000 | WO | 0 | 399.9999 | 8.4 | 793.04 | 400 |  | 49.5612 |  | 06/30/2023 | 07/03/2023 |  |  |  | CLN
23-0153-IR | WO0002 | CON | 2023-06-16T13:53:22.000 | WO | 0 | 406.01 | 24 | 406.01 | 100 |  | 0 |  | 06/29/2023 | 07/03/2023 |  |  |  | CON
23-0153-IR | WO0003 | DMO | 2023-06-16T13:53:22.000 | WO | 0 | 0 |  | 95.45 | 0 |  | 100 | [6 empty] | DMO
23-0153-IR | WO0004 | DRY | 2023-06-16T13:53:22.763 | WO | 0 | 132.267 |  | 227.59 | 58.1164 |  | 41.8836 | [6 empty] | DRY
23-0153-IR | WO0005 | ELE | 2023-06-16T13:53:22.890 | WO | 0 | 417.73 | 1 | 417.73 | 100 |  | 0 |  | 06/16/2023 | 06/16/2023 |  |  |  | ELE
23-0153-IR | WO0006 | George carpet labor | 2023-06-16T13:53:23.000 | WO | 0 | 299.9998 | 21.3 | 555.44 | 300 |  | 45.9888 |  | 06/27/2023 | 06/29/2023 |  |  |  | FCC
23-0153-IR | WO0007 | FNC | 2023-06-16T13:53:23.000 | WO | 0 | 0 |  | 39.22 | 0 |  | 100 | [6 empty] | FNC
23-0153-IR | WO0008 | INS | 2023-06-16T13:53:23.000 | WO | 0 | 0 |  | 28.64 | 0 |  | 100 | [6 empty] | INS
23-0153-IR | WO0009 | LAB | 2023-06-16T13:53:23.000 | WO | 0 | 0 | 6 | 462.96 | 0 |  | 100 |  | 06/16/2023 | 06/16/2023 |  |  |  | LAB
23-0153-IR | WO00010 | PNT | 2023-06-16T13:53:23.000 | WO | 0 | 0 |  | 287.51 | 0 |  | 100 | [6 empty] | PNT
23-0153-IR | WO00011 | WTR | 2023-06-16T13:53:23.000 | WO | 0 | 0 | 0.87 | 99.66 | 0 |  | 100 |  | 06/16/2023 | 06/16/2023 |  |  |  | WTR
23-0153-IR | WO00012 | marlon labor | 2023-06-16T13:54:00.000 | WO | 0 | 1599.9997 | 20.92 | 2722.69 | 1600 |  | 41.2346 |  | 06/27/2023 | 06/29/2023 |  |  |  | marlon labor
23-0157-IR | WO0004 | DRY | 2023-05-26T14:41:07.000 | WO | 0 | 2689.122 | 17.22 | 4481.87 | 60 |  | 40 |  | 05/26/2023 | 06/26/2023 |  |  |  | DRY
23-0157-IR | WO0006 | FCW | 2023-05-26T14:41:08.000 | WO | 0 | 3031.7999 | 18 | 3286.39 | 3031.8 |  | 7.7468 |  | 05/26/2023 | 05/29/2023 |  |  |  | FCW
23-0157-IR | WO0008 | PLM | 2023-05-26T14:41:08.000 | WO | 0 | 0 | 2.5 | 713.7 | 0 |  | 100 |  | 05/26/2023 | 05/26/2023 |  |  |  | PLM
23-0143-IR | WO0001 | CAB | 2023-06-26T14:49:29.530 | WO | 0 | 1049.53 | 3.1 | 1049.53 | 100 |  | 0 |  | 06/26/2023 | 06/26/2023 |  |  |  | CAB
23-0143-IR | WO0002 | CLN | 2023-06-26T14:49:29.623 | WO | 0 | 172.66 | 1.52 | 172.66 | 100 |  | 0 |  | 06/26/2023 | 06/26/2023 |  |  |  | CLN
23-0143-IR | WO0003 | DMO | 2023-06-26T14:49:29.717 | WO | 0 | 245.89 | 1.98 | 245.89 | 100 |  | 0 |  | 06/26/2023 | 06/26/2023 |  |  |  | DMO
23-0143-IR | WO0004 | DOR | 2023-06-26T14:49:29.780 | WO | 0 | 69.5 | 0.6 | 69.5 | 100 |  | 0 |  | 06/26/2023 | 06/26/2023 |  |  |  | DOR
23-0143-IR | WO0005 | DRY | 2023-06-26T14:49:29.860 | WO | 0 | 1978.24 | 12.95 | 1978.24 | 100 |  | 0 |  | 06/26/2023 | 06/27/2023 |  |  |  | DRY
23-0143-IR | WO0006 | FCC | 2023-06-26T14:49:30.000 | WO | 0 | 289.48 | 1.95 | 289.48 | 100 |  | 0 |  | 06/26/2023 | 06/26/2023 |  |  |  | FCC
23-0143-IR | WO0007 | FCV | 2023-06-26T14:49:30.077 | WO | 0 | 652.66 | 2.47 | 652.66 | 100 |  | 0 |  | 06/26/2023 | 06/26/2023 |  |  |  | FCV
23-0143-IR | WO0008 | FCW | 2023-06-26T14:49:30.140 | WO | 0 | 1426.22 | 12.22 | 1426.22 | 100 |  | 0 |  | 06/26/2023 | 06/27/2023 |  |  |  | FCW
23-0143-IR | WO0009 | FNC | 2023-06-26T14:49:30.250 | WO | 0 | 687.57 | 2.73 | 687.57 | 100 |  | 0 |  | 06/26/2023 | 06/26/2023 |  |  |  | FNC
23-0143-IR | WO00010 | FNH | 2023-06-26T14:49:30.327 | WO | 0 | 57.06 | 0.6 | 57.06 | 100 |  | 0 |  | 06/26/2023 | 06/26/2023 |  |  |  | FNH
23-0143-IR | WO00011 | FRM | 2023-06-26T14:49:30.390 | WO | 0 | 315.74 | 1.05 | 315.74 | 100 |  | 0 |  | 06/26/2023 | 06/26/2023 |  |  |  | FRM
23-0143-IR | WO00012 | LIT | 2023-06-26T14:49:30.467 | WO | 0 | 88.56 | 0.53 | 88.56 | 100 |  | 0 |  | 06/26/2023 | 06/26/2023 |  |  |  | LIT
23-0143-IR | WO00013 | PLA | 2023-06-26T14:49:30.530 | WO | 0 | 3191.51 | 15.17 | 3191.51 | 100 |  | 0 |  | 06/26/2023 | 06/27/2023 |  |  |  | PLA
23-0143-IR | WO00014 | PLM | 2023-06-26T14:49:30.610 | WO | 0 | 1202.43 | 4.6 | 1202.43 | 100 |  | 0 |  | 06/26/2023 | 06/26/2023 |  |  |  | PLM
23-0143-IR | WO00015 | PNT | 2023-06-26T14:49:30.670 | WO | 0 | 1755.66 | 12.2 | 1755.66 | 100 |  | 0 |  | 06/26/2023 | 06/27/2023 |  |  |  | PNT
23-0143-IR | WO00016 | flooring material | 2023-06-26T14:50:00.000 | WO | 0 | 1137.04 | 8 | 1137.04 | 100 |  | 0 |  | 06/26/2023 | 06/26/2023 |  |  |  | Flooring material
23-0143-IR | WO00017 | Carpet material | 2023-06-26T14:57:00.000 | WO | 0 | 520.73 | 8 | 520.73 | 100 |  | 0 |  | 06/26/2023 | 06/26/2023 |  |  |  | Carpet material
23-0163-IR
23-0165-IR | WO0001, Complete | DMO | 2023-08-28T12:47:26.653 | WO | 0 | 246.81 | 1.98 | 246.81 | 100 |  | 0 |  | 08/28/2023 | 08/28/2023 |  | 2023-08-28T12:03:49.290 | Dehnke, Josh | DMO
23-0165-IR | WO0002 | ELE | 2023-08-28T12:47:26.747 | WO | 0 | 282.26 | 0 | 282.26 | 100 |  | 0 |  | 08/28/2023 | 08/28/2023 |  |  |  | ELE
23-0165-IR | WO0004 | FEE | 2023-08-28T12:47:26.967 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | FEE
23-0165-IR | WO0005 | FNC | 2023-08-28T12:47:27.000 | WO | 0 | 2346.22 | 13.49 | 2346.22 | 100 |  | 0 |  | 08/28/2023 | 08/29/2023 |  |  |  | FNC
23-0165-IR | WO0008 | HMR | 2023-08-28T12:47:27.417 | WO | 0 | 5651.87 | 0 | 5651.87 | 100 |  | 0 |  | 08/28/2023 | 08/28/2023 |  |  |  | HMR
23-0165-IR | WO0009 | HVC | 2023-08-28T12:47:27.513 | WO | 0 | 468.72 | 2.5 | 468.72 | 100 |  | 0 |  | 08/28/2023 | 08/28/2023 |  |  |  | HVC
23-0165-IR | WO00014 | SDG | 2023-08-28T12:47:28.200 | WO | 0 | 13171.53 | 51.71 | 13171.53 | 100 |  | 0 |  | 08/28/2023 | 08/31/2023 |  |  |  | SDG
23-0168-D | WO0001 | CLN | 2023-07-04T18:56:40.000 | WO | 0 | 0 | 3.72 | 261.23 | 0 |  | 100 |  | 07/04/2023 | 07/04/2023 |  |  |  | CLN
23-0168-D | WO0004 | Contents | 2023-07-04T18:56:40.000 | WO | 0 | 578.0006 | 13.3 | 1441.01 | 578 |  | 59.8892 |  | 07/04/2023 | 07/04/2023 |  |  |  | DOR
23-0168-D | WO0006 | FCW | 2023-07-04T18:56:40.000 | WO | 0 | 2547.9989 | 41.97 | 4318.73 | 2548 |  | 41.0012 |  | 07/04/2023 | 07/10/2023 |  |  |  | FCW
23-0168-D | WO0009, Complete | INSPNTDRY | 2023-07-04T18:56:40.000 | WO | 0 | 1512.21 | 10.01 | 2160.3 | 70 |  | 30 |  | 07/04/2023 | 07/05/2023 |  | 2023-08-28T15:50:06.583 | Burrell, Bianca | INS
23-0168-D | WO00010 | Shoe | 2023-07-04T18:56:40.000 | WO | 0 | 1861.2801 | 26.65 | 2778.03 | 67 |  | 33 |  | 07/04/2023 | 07/05/2023 |  |  |  | MPR
23-0168-D | WO00012, Complete | Hard Surface - Material | 2023-07-04T18:57:00.000 | WO | 0 | 2562.166 | 8 | 3135.7 | 81.7095 |  | 18.2905 |  | 07/04/2023 | 07/04/2023 |  | 2023-08-06T17:50:26.970 | Burrell, Bianca
23-0168-D | WO00014, Complete | CO - Flooring Material | 2023-08-28T16:52:00.000 | WO | 0 | 1134.9009 |  | 2021.4 | 1134.9 |  | 43.8557 |  |  |  |  | 2023-08-28T16:06:18.973 | Burrell, Bianca
23-0168-D | WO00015, Complete | CO - Vapor Barrier | 2023-08-28T16:53:00.000 | WO | 0 | 155.4 |  | 249.6 | 155.4 |  | 37.7404 |  |  |  |  | 2023-08-28T16:06:52.727 | Burrell, Bianca
23-0168-D | WO00016 | CO - Contents | 2023-08-28T16:53:00.000 | WO | 0 | 546.9 | 8 | 546.9 | 100 |  | 0 |  | 08/28/2023 | 08/28/2023
23-0168-D | WO00017 | CO - Shoe | 2023-08-28T16:54:00.000 | WO | 0 | 334.92 | 8 | 334.92 | 100 |  | 0 |  | 08/28/2023 | 08/28/2023
23-0168-D | WO00018, Complete | CO - LVP Install Office/Bedroom | 2023-08-28T16:54:00.000 | WO | 0 | 1430.001 | 8 | 2048.09 | 1430 |  | 30.1788 |  | 08/28/2023 | 08/28/2023 |  | 2023-08-28T16:13:14.320 | Burrell, Bianca
23-0168-D | WO00019, Complete | CO - Existing Removal | 2023-08-28T16:55:00.000 | WO | 0 | 276.2497 | 0 | 586.23 | 276.25 |  | 52.8769 |  | 08/29/2023 | 08/29/2023 |  | 2023-08-28T16:24:49.650 | Burrell, Bianca
22-0421-IR
23-0169-RET-ER
23-0170-D
23-0178-ER
23-0181-C
23-0182-ER | WO0001 | DMO | 2023-06-20T10:29:28.000 | WO | 0 | 0 | 1.98 | 246.81 | 0 |  | 100 |  | 06/20/2023 | 06/20/2023 |  |  |  | DMO
23-0182-ER | WO0002 | DRY | 2023-06-20T10:29:28.000 | WO | 0 | 0 |  | 88.03 | 0 |  | 100 | [6 empty] | DRY
23-0182-ER | WO0003 | FEE | 2023-06-20T10:29:28.263 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | FEE
23-0182-ER | WO0004 | FNC | 2023-06-20T10:29:28.000 | WO | 0 | 0 |  | 95.19 | 0 |  | 100 | [6 empty] | FNC
23-0182-ER | WO0005 | FRM | 2023-06-20T10:29:28.450 | WO | 0 | 283.69 |  | 283.69 | 100 |  | 0 | [6 empty] | FRM
23-0182-ER | WO0006 | INS | 2023-06-20T10:29:28.000 | WO | 0 | 0 |  | 97.51 | 0 |  | 100 | [6 empty] | INS
23-0182-ER | WO0007 | PNT | 2023-06-20T10:29:28.780 | WO | 0 | 186.05 |  | 186.05 | 100 |  | 0 | [6 empty] | PNT
23-0182-ER | WO0008 | WDW | 2023-06-20T10:29:28.920 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | WDW
23-0182-ER | WO0009 | Marlon labor | 2023-06-20T10:30:00.000 | WO | 0 | 1399.9996 | 27.53 | 2433.91 | 1400 |  | 42.4794 |  | 06/20/2023 | 06/20/2023 |  |  |  | Marlon Labor
23-0184-IR | WO0002 | Permit and Fees | 2023-08-10T11:26:49.000 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | FEE
23-0184-IR | WO0003 | Roof Replacement | 2023-08-10T11:26:49.000 | WO | 0 | 3314 | 70.85 | 11701.02 | 3314 |  | 71.6777 |  | 08/10/2023 | 08/21/2023 |  |  |  | RFG
23-0184-IR | WO0005 | Metals | 2023-08-10T11:26:50.000 | WO | 0 | 236.2 | 3.08 | 472.4 | 50 |  | 50 |  | 08/10/2023 | 08/10/2023 |  |  |  | SFG
23-0184-IR | WO0006 | Roofing Materials | 2023-08-10T11:30:00.000 | WO | 0 | 5908.2103 |  | 5191.79 | 5908.21 |  | -13.7991
23-0186-ER | WO0003 | Deconstruction and Clean | 2023-08-17T12:07:49.000 | WO | 1 | 227.45 | 25 | 454.9 | 50 |  | 50 | Felt, Rik | 08/31/2023 | 09/04/2023 |  |  |  | DMO
23-0186-ER | WO0004 | Drywall, Paint and Trim | 2023-08-17T12:07:49.000 | WO | 1 | 1011.575 | 25 | 2023.15 | 50 |  | 50 | Felt, Rik | 08/31/2023 | 09/04/2023 |  |  |  | DRY
23-0186-ER | WO0006 | FEE | 2023-08-17T12:07:49.787 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | FEE
23-0188-IR
22-1011-June21inspectiong-C | WO0001 | APP | 2023-07-18T09:34:55.000 | WO | 0 | 659.43 | 3.95 | 659.43 | 100 |  | 0 | Viking Gypsum Floors | 07/18/2023 | 07/18/2023 |  |  |  | APP
22-1011-June21inspectiong-C | WO0002 | CLN | 2023-07-18T09:34:55.723 | WO | 0 | 196.72 | 2.4 | 196.72 | 100 |  | 0 |  | 07/18/2023 | 07/18/2023 |  |  |  | CLN
22-1011-June21inspectiong-C | WO0003 | CON | 2023-07-18T09:34:55.910 | WO | 0 | 247.47 | 3.67 | 247.47 | 100 |  | 0 |  | 07/18/2023 | 07/18/2023 |  |  |  | CON
22-1011-June21inspectiong-C | WO0004 | DMO | 2023-07-18T09:34:56.067 | WO | 0 | 914.24 | 8.37 | 914.24 | 100 |  | 0 |  | 07/18/2023 | 07/19/2023 |  |  |  | DMO
22-1011-June21inspectiong-C | WO0005 | DOR | 2023-07-18T09:34:56.193 | WO | 0 | 34.66 | 0.3 | 34.66 | 100 |  | 0 |  | 07/18/2023 | 07/18/2023 |  |  |  | DOR
22-1011-June21inspectiong-C | WO0006 | FCW | 2023-07-18T09:34:56.300 | WO | 0 | 3796.47 | 20.88 | 3796.47 | 100 |  | 0 |  | 07/18/2023 | 07/20/2023 |  |  |  | FCW
22-1011-June21inspectiong-C | WO0007 | FNC | 2023-07-18T09:34:56.427 | WO | 0 | 343.73 | 2.55 | 343.73 | 100 |  | 0 |  | 07/18/2023 | 07/18/2023 |  |  |  | FNC
22-1011-June21inspectiong-C | WO0008 | PLM | 2023-07-18T09:34:56.537 | WO | 0 | 105.79 | 0 | 105.79 | 100 |  | 0 |  | 07/18/2023 | 07/18/2023 |  |  |  | PLM
22-1011-June21inspectiong-C | WO0009 | PNT | 2023-07-18T09:34:56.660 | WO | 0 | 499.43 | 3.62 | 499.43 | 100 |  | 0 |  | 07/18/2023 | 07/18/2023 |  |  |  | PNT
23-0192-Aery
23-0193-ER | WO0001 | Cabinet Installation | 2023-06-27T08:03:33.000 | WO | 1 | 937.1466 | 27.79 | 2402.94 | 39 |  | 61 |  | 06/27/2023 | 07/03/2023 |  |  |  | CAB
23-0193-ER | WO0002 | Final Construction & Window Cleaning | 2023-06-27T08:03:33.000 | WO | 0 | 269.37 | 7.42 | 538.74 | 50 |  | 50 |  | 06/27/2023 | 06/27/2023 |  |  |  | CLN
23-0193-ER | WO0003 | Demo and Debris Removal | 2023-06-27T08:03:33.000 | WO | 1 | 1532.394 | 20.87 | 3405.32 | 45 |  | 55 |  | 06/28/2023 | 06/30/2023 |  |  |  | DMO
23-0193-ER | WO0004 | Carpentry Labor (+ Framing) | 2023-06-27T08:03:33.000 | WO | 1 | 1538.928 | 6 | 3419.84 | 45 |  | 55 |  | 07/07/2023 | 07/07/2023 |  |  |  | DOR
23-0193-ER | WO0006 | Phase 1 Electrical | 2023-06-27T08:03:33.000 | WO | 1 | 1454.0715 | 11.05 | 2308.05 | 63 |  | 37 |  | 07/03/2023 | 07/04/2023 |  |  |  | ELE
23-0193-ER | WO0007 | Tile - Materials | 2023-06-27T08:03:34.000 | WO | 0 | 566.515 |  | 1133.03 | 50 |  | 50 | [6 empty] | FCT
23-0193-ER | WO0008 | Flooring (Labor and Materials) | 2023-06-27T08:03:34.000 | WO | 0 | 4351.578 | 37.22 | 7911.96 | 55 |  | 45 |  | 06/27/2023 | 07/03/2023 |  |  |  | FCV
23-0193-ER | WO0009 | Door & Bathroom Hardware | 2023-06-27T08:03:34.000 | WO | 0 | 185.875 |  | 371.75 | 50 |  | 50 | [6 empty] | FCW
23-0193-ER | WO00016 | Glass Shower Door | 2023-06-27T08:03:34.000 | WO | 0 | 883.484 |  | 1262.12 | 70 |  | 30 | [6 empty] | MSD
23-0193-ER | WO00017 | Phase 1 Plumbing | 2023-06-27T08:03:35.000 | WO | 1 | 2745.9004 | 9.37 | 7502.46 | 36.6 |  | 63.4 |  | 07/05/2023 | 07/06/2023 |  |  |  | PLM
23-0193-ER | WO00018 | Paint & Drywall | 2023-06-27T08:03:35.000 | WO | 1 | 6699.9956 | 81 | 15629.4 | 6700 |  | 57.1321 | Complete Painting LLC | 07/09/2023 | 07/19/2023 |  |  |  | PNT
23-0193-ER | WO00023 | Handyman Labor - Blinds, Bath Accessories | 2023-06-27T08:03:35.000 | WO | 0 | 636.1535 | 8.87 | 1091.27 | 58.2948 |  | 41.7052 |  | 06/27/2023 | 06/28/2023 |  |  |  | WDT
23-0193-ER | WO00024 | Window Replacement | 2023-06-27T08:03:35.000 | WO | 0 | 1302.3248 | 1.6 | 1933.38 | 67.36 |  | 32.64 |  | 06/27/2023 | 06/27/2023 |  |  |  | WDV
23-0193-ER | WO00025 | Cabinets - Materials | 2023-06-27T10:41:00.000 | WO | 0 | 3286.4692 |  | 5947.93 | 3286.47 |  | 44.746
23-0193-ER | WO00026 | Carpentry Materials | 2023-06-27T10:50:00.000 | WO | 0 | 1651.3858 | 0.32 | 1985.14 | 83.1874 |  | 16.8126 |  | 06/27/2023 | 06/27/2023
23-0193-ER | WO00027 | Garage Door Handle Install | 2023-06-27T10:51:00.000 | WO | 0 | 133.84 | 9 | 133.84 | 100 |  | 0 |  | 07/06/2023 | 07/06/2023
23-0193-ER | WO00028 | Tile Labor | 2023-06-27T10:57:00.000 | WO | 0 | 2262.69 | 31.65 | 5028.2 | 45 |  | 55 |  | 06/27/2023 | 06/30/2023
23-0193-ER | WO00029 | Vent Covers | 2023-06-27T11:32:00.000 | WO | 0 | 116.4573 |  | 140.31 | 83 |  | 17
23-0193-ER | WO00030 | Light Fixtures | 2023-06-27T11:39:00.000 | WO | 0 | 653.5932 |  | 837.94 | 78 |  | 22
23-0193-ER | WO00032 | Window Blinds | 2023-06-27T11:59:00.000 | WO | 0 | 290.31 |  | 290.31 | 100 |  | 0
23-0193-ER | WO00033 | Plumbing Fixtures | 2023-06-27T12:10:00.000 | WO | 0 | 671.7024 |  | 809.28 | 83 |  | 17
23-0193-ER | WO00034 | Kitchen Countertop Measure | 2023-06-27T12:33:00.000 | WO | 0 | 1697.88 | 23.78 | 3395.76 | 50 |  | 50 |  | 06/27/2023 | 07/03/2023
23-0193-ER | WO00035 | Appliances | 2023-06-27T14:11:18.000 | WO | 1 | 4424.1399 |  | 5308.97 | 4424.14 |  | 16.6667 | [6 empty] | APP
23-0193-ER | WO00037 | Hydroxyl | 2023-06-27T14:11:18.000 | WO | 0 | 324 |  | 648 | 50 |  | 50 | [6 empty] | CLN
23-0193-ER | WO00038 | Phase 2 Electrical | 2023-08-09T12:38:00.000 | WO | 1 | 1488.5829 | 26 | 2362.83 | 63 |  | 37 |  | 07/07/2023 | 07/12/2023
23-0194-ER | WO0001 | labor & material- custom built in cabinet | 2023-07-07T15:32:49.000 | WO | 0 | 2032.2225 | 0 | 2709.63 | 75 |  | 25 |  | 08/21/2023 | 08/21/2023 |  |  |  | CAB
23-0194-ER | WO0002 | final cleaning | 2023-07-07T15:32:49.000 | WO | 0 | 125 | 0.67 | 177.49 | 125 |  | 29.5735 |  | 08/30/2023 | 08/30/2023 |  |  |  | CLN
23-0194-ER | WO0004, Complete | haul away debris from covering floor and dust control | 2023-07-07T15:32:49.000 | WO | 0 | 75.0001 | 1.98 | 247.99 | 75 |  | 69.7568 |  | 08/31/2023 | 09/01/2023 |  | 2023-08-29T13:29:28.470 | Schmidt, Jeremy | DMO
23-0194-ER | WO0006, Complete | electrical - material and labor | 2023-07-07T15:32:50.000 | WO | 1 | 0 | 0.7 | 452.79 | 0 |  | 100 |  | 08/28/2023 | 08/28/2023 |  | 2023-08-22T10:22:59.910 | Schmidt, Jeremy | ELE
23-0194-ER | WO0007 | carpet- install some new pad and re-stretch in master bedroom | 2023-07-07T15:32:50.000 | WO | 0 | 285.677 | 3 | 408.11 | 70 |  | 30 |  | 08/28/2023 | 08/29/2023 |  |  |  | FCC
23-0194-ER | WO0009 | FEE | 2023-07-07T15:32:50.300 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | FEE
23-0194-ER | WO00010 | material- millwork | 2023-07-07T15:32:50.000 | WO | 0 | 123.272 |  | 154.09 | 80 |  | 20 | [6 empty] | FNC
23-0194-ER | WO00011, Complete | material- sheathing, framing, insulation/vapor barrier, dust confinement and floor protection etc | 2023-07-07T15:32:50.000 | WO | 0 | 762.728 | 8 | 953.41 | 80 |  | 20 |  | 08/28/2023 | 08/28/2023 |  | 2023-08-22T10:22:10.023 | Schmidt, Jeremy | FRM
23-0194-ER | WO00013 | LAB | 2023-07-07T15:32:50.000 | WO | 0 | 0 | 0 | 2.36 | 0 |  | 100 |  | 08/28/2023 | 08/28/2023 |  |  |  | LAB
23-0194-ER | WO00014 | MAS | 2023-07-07T15:32:50.707 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | MAS
23-0194-ER | WO00017 | RFG | 2023-07-07T15:32:50.970 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | RFG
23-0194-ER | WO00020 | clean carpet | 2023-07-07T15:37:00.000 | WO | 0 | 218.232 | 9 | 363.72 | 60 |  | 40 |  | 08/18/2023 | 08/18/2023
23-0194-ER | WO00022, Complete | labor and material- drywall | 2023-07-07T14:45:50.000 | WO | 0 | 708.1605 | 8.77 | 1573.69 | 45 |  | 55 |  | 08/29/2023 | 08/30/2023 |  | 2023-08-29T13:30:49.753 | Schmidt, Jeremy | Labor Work Order
23-0194-ER | WO00024, Complete | labor- framing and rough carpentry | 2023-07-07T14:55:04.000 | WO | 0 | 2468.0271 | 48.02 | 5036.79 | 49 |  | 51 |  | 08/21/2023 | 08/28/2023 |  | 2023-08-22T10:23:37.653 | Schmidt, Jeremy | Labor Work Order
23-0194-ER | WO00026, Complete | labor- painting (walls & trim) | 2023-07-07T15:00:34.000 | WO | 0 | 663.21 | 13.12 | 1473.8 | 45 |  | 55 |  | 08/30/2023 | 08/31/2023 |  | 2023-08-29T13:30:49.817 | Schmidt, Jeremy | Labor Work Order
23-0194-ER | WO00027 | Progress payment due | 2023-08-09T11:24:00.000 | WO | 1 | 0 | 8 | 0 | 100 |  | 0 |  | 08/09/2023 | 08/09/2023
23-0194-ER | WO00028, Complete | material- paint | 2023-08-24T10:56:00.000 | WO | 0 | 88.67 | 8 | 282.51 | 88.67 |  | 68.6135 |  | 08/24/2023 | 08/24/2023 |  | 2023-08-29T13:30:49.880 | Schmidt, Jeremy
23-0194-ER | WO00029 | cabinet labor | 2023-08-28T12:31:00.000 | WO | 0 | 200.565 | 11.18 | 401.13 | 50 |  | 50 |  | 08/21/2023 | 08/28/2023
23-0194-ER | WO00030 | cabinet- paint (labor and material) | 2023-08-28T12:43:00.000 | WO | 0 | 45 | 9.65 | 241.99 | 45 |  | 81.4042 |  | 08/28/2023 | 08/31/2023
23-0195-ER | WO0001 | concrete and block | 2023-07-20T13:52:59.000 | WO | 0 | 6038.557 | 34.1 | 8626.51 | 70 |  | 30 |  | 07/20/2023 | 07/24/2023 |  |  |  | CNC
23-0195-ER | WO0002 | dumpster | 2023-07-20T13:53:00.000 | WO | 0 | 550.0004 |  | 1452.15 | 550 |  | 62.1251 | [6 empty] | DMO
23-0195-ER | WO0003 | exterior door (insulated) | 2023-07-20T13:53:00.000 | WO | 0 | 324.27 |  | 540.45 | 60 |  | 40 | [6 empty] | DOR
23-0195-ER | WO0004 | material- drywall | 2023-07-20T13:53:00.000 | WO | 0 | 436.6593 |  | 567.09 | 77 |  | 23 | [6 empty] | DRY
23-0195-ER | WO0006 | material- lvp | 2023-07-20T13:53:00.000 | WO | 0 | 628.088 |  | 785.11 | 80 |  | 20 | [6 empty] | FCV
23-0195-ER | WO0007 | FEE | 2023-07-20T13:53:00.000 | WO | 0 | 0 |  | 2691 | 0 |  | 100 | [6 empty] | FEE
23-0195-ER | WO0008 | labor- chain link fence | 2023-07-20T13:53:01.000 | WO | 0 | 197.39 | 4 | 394.78 | 50 |  | 50 |  | 07/20/2023 | 07/20/2023 |  |  |  | FEN
23-0195-ER | WO0009 | material- baseboard and casing | 2023-07-20T13:53:01.000 | WO | 0 | 388.8346 |  | 504.98 | 77 |  | 23 | [6 empty] | FNC
23-0195-ER | WO00010 | material- door lockset and dead bolt | 2023-07-20T13:53:01.000 | WO | 0 | 224.2725 |  | 263.85 | 85 |  | 15 | [6 empty] | FNH
23-0195-ER | WO00011 | material- lumber | 2023-07-20T13:53:01.000 | WO | 0 | 6466.568 | 45.95 | 8083.21 | 80 |  | 20 |  | 07/20/2023 | 07/27/2023 |  |  |  | FRM
23-0195-ER | WO00012 | hvac | 2023-07-20T13:53:01.000 | WO | 0 | 3037.286 | 15.53 | 4338.98 | 70 |  | 30 |  | 07/20/2023 | 07/21/2023 |  |  |  | HVC
23-0195-ER | WO00013 | insulation- material and labor | 2023-07-20T13:53:02.000 | WO | 0 | 2051.203 | 13.53 | 2930.29 | 70 |  | 30 |  | 07/20/2023 | 07/21/2023 |  |  |  | INS
23-0195-ER | WO00014 | material- ceiling fan w/ light and exterior light | 2023-07-20T13:53:02.000 | WO | 0 | 297.464 |  | 371.83 | 80 |  | 20 | [6 empty] | LIT
23-0195-ER | WO00016 | material- caulking and moldable tape(sill flashing) | 2023-07-20T13:53:02.000 | WO | 0 | 121.1826 |  | 157.38 | 77 |  | 23 | [6 empty] | MPR
23-0195-ER | WO00017 | material- paint | 2023-07-20T13:53:02.000 | WO | 0 | 131.8779 |  | 171.27 | 77 |  | 23 | [6 empty] | PNT
23-0195-ER | WO00018 | material- roof | 2023-07-20T13:53:03.000 | WO | 0 | 954.009 |  | 1060.01 | 90 |  | 10 | [6 empty] | RFG
23-0195-ER | WO00019 | material- siding | 2023-07-20T13:53:03.000 | WO | 0 | 1121.1277 |  | 1456.01 | 77 |  | 23 | [6 empty] | SDG
23-0195-ER | WO00020 | gutters- material and labor | 2023-07-20T13:53:03.000 | WO | 0 | 504.0002 | 2.33 | 1122.82 | 504 |  | 55.113 |  | 07/20/2023 | 07/20/2023 |  |  |  | SFG
23-0195-ER | WO00021 | electrician | 2023-07-20T13:53:03.000 | WO | 0 | 1744.708 | 10.5 | 2492.44 | 70 |  | 30 |  | 07/20/2023 | 07/20/2023 |  |  |  | TMP
23-0195-ER | WO00022 | material- windows | 2023-07-20T13:53:03.000 | WO | 0 | 8393.8855 |  | 10901.15 | 77 |  | 23 | [6 empty] | WDV
23-0195-ER | WO00023 | material- window ext jambs | 2023-07-20T13:53:04.000 | WO | 0 | 776.0214 |  | 1007.82 | 77 |  | 23 | [6 empty] | WDW
23-0195-ER | WO00024 | demo deck | 2023-07-20T13:51:03.000 | WO | 0 | 1540.3995 | 38.47 | 3423.11 | 45 |  | 55 |  | 07/20/2023 | 07/26/2023 |  |  |  | Labor Work Order
23-0195-ER | WO00025 | labor- exterior door | 2023-07-20T13:52:26.000 | WO | 0 | 125 | 1.18 | 335.25 | 125 |  | 62.7144 |  | 07/20/2023 | 07/20/2023 |  |  |  | Labor Work Order
23-0195-ER | WO00026 | labor- drywall, paint, finish trim (base/casing), window ext jambs | 2023-07-20T13:54:57.000 | WO | 0 | 2184.85 | 28.35 | 4369.7 | 50 |  | 50 |  | 07/20/2023 | 07/21/2023 |  |  |  | Labor Work Order
23-0195-ER | WO00027 | labor- lvp | 2023-07-20T13:57:04.000 | WO | 0 | 602.364 | 7.83 | 1003.94 | 60 |  | 40 |  | 07/20/2023 | 07/20/2023 |  |  |  | Labor Work Order
23-0195-ER | WO00029 | labor- door lockset and lock set | 2023-07-20T14:02:14.000 | WO | 0 | 50 | 0.45 | 262.62 | 50 |  | 80.9611 |  | 07/20/2023 | 07/20/2023 |  |  |  | Labor Work Order
23-0195-ER | WO00031 | labor- caulking and moldable tape (sill flashing) | 2023-07-20T14:10:11.000 | WO | 0 | 307.8585 | 5.1 | 684.13 | 45 |  | 55 |  | 07/20/2023 | 07/20/2023 |  |  |  | Labor Work Order
23-0195-ER | WO00033 | labor -roof | 2023-07-20T14:13:51.000 | WO | 0 | 199.9994 | 7.35 | 1996.68 | 200 |  | 89.9834 |  | 07/20/2023 | 07/21/2023 |  |  |  | Labor Work Order
23-0195-ER | WO00034 | labor- siding | 2023-07-20T14:19:07.000 | WO | 0 | 1117.096 | 13.55 | 2792.74 | 40 |  | 60 |  | 07/20/2023 | 07/21/2023 |  |  |  | Labor Work Order
23-0195-ER | WO00035 | labor- install windows | 2023-07-20T14:22:43.000 | WO | 0 | 602.745 | 9.12 | 1205.49 | 50 |  | 50 |  | 07/20/2023 | 07/21/2023 |  |  |  | Labor Work Order
23-0195-ER | WO00037 | material- sheathing 1/2" cdx | 2023-07-20T14:47:17.000 | WO | 0 | 347.4317 |  | 451.21 | 77 |  | 23
23-0195-ER | WO00038 | labor- sheathing 1/2 cdx | 2023-07-20T15:57:00.000 | WO | 0 | 444.6675 | 11.65 | 988.15 | 45 |  | 55 |  | 07/20/2023 | 07/20/2023
23-0195-ER | WO00039 | material- fascia and soffit | 2023-08-04T15:15:00.000 | WO | 0 | 253.1144 | 8 | 328.72 | 77 |  | 23 |  | 08/04/2023 | 08/04/2023
23-0195-ER | WO00040 | labor- fascia and soffit | 2023-08-04T15:17:00.000 | WO | 0 | 271.278 | 10.72 | 602.84 | 45 |  | 55 |  | 07/20/2023 | 08/04/2023
23-0198-ER
23-0202-ER
23-0203-ER
23-0204-ER
23-0206-D
23-0207-IR
23-0208-IR | WO0001 | CLN | 2023-07-19T10:11:43.000 | WO | 0 | 0 | 4.72 | 335.36 | 0 |  | 100 |  | 07/19/2023 | 07/19/2023 |  |  |  | CLN
23-0208-IR | WO0002 | DMO | 2023-07-19T10:11:44.000 | WO | 0 | 0 | 2.87 | 380.75 | 0 |  | 100 |  | 07/19/2023 | 07/19/2023 |  |  |  | DMO
23-0208-IR | WO0003 | Insulation, Drywall, Paint (Materials and Labor) | 2023-07-19T10:11:44.000 | WO | 0 | 3000.0008 | 32.92 | 5719.68 | 3000 |  | 47.5495 |  | 07/19/2023 | 07/20/2023 |  |  |  | DRY
23-0208-IR | WO0004 | FEE | 2023-07-19T10:11:44.737 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | FEE
22-1011-July-C
23-0209-Aery
23-0212-ER
23-0216-D
23-0217-IR
23-0221-Aery | WO0001 | CON | 2023-08-22T11:02:25.793 | WO | 0 | 102.25 | 1.47 | 102.25 | 100 |  | 0 |  | 08/22/2023 | 08/22/2023 |  |  |  | CON
23-0221-Aery | WO0002 | DMO | 2023-08-22T11:02:25.903 | WO | 0 | 248.54 | 1.98 | 248.54 | 100 |  | 0 |  | 08/22/2023 | 08/22/2023 |  |  |  | DMO
23-0221-Aery | WO0003 | DOR | 2023-08-22T11:02:25.980 | WO | 0 | 1094.94 | 9.07 | 1094.94 | 100 |  | 0 |  | 08/22/2023 | 08/23/2023 |  |  |  | DOR
23-0221-Aery | WO0004 | FCV | 2023-08-22T11:02:26.060 | WO | 0 | 1426.69 | 5.75 | 1426.69 | 100 |  | 0 |  | 08/22/2023 | 08/22/2023 |  |  |  | FCV
23-0221-Aery | WO0005 | FEE | 2023-08-22T11:02:26.217 | WO | 0 | 628.8 |  | 628.8 | 100 |  | 0 | [6 empty] | FEE
23-0221-Aery | WO0006 | FNC | 2023-08-22T11:02:26.293 | WO | 0 | 197.07 | 0.65 | 197.07 | 100 |  | 0 |  | 08/22/2023 | 08/22/2023 |  |  |  | FNC
23-0221-Aery | WO0007 | FRM | 2023-08-22T11:02:26.403 | WO | 0 | 1933.16 | 14.23 | 1933.16 | 100 |  | 0 |  | 08/22/2023 | 08/23/2023 |  |  |  | FRM
23-0221-Aery | WO0008 | INS | 2023-08-22T11:02:26.497 | WO | 0 | 532.15 | 2.83 | 532.15 | 100 |  | 0 |  | 08/22/2023 | 08/22/2023 |  |  |  | INS
23-0221-Aery | WO0009 | LAB | 2023-08-22T11:02:26.577 | WO | 0 | 610.27 | 6 | 610.27 | 100 |  | 0 |  | 08/22/2023 | 08/22/2023 |  |  |  | LAB
23-0221-Aery | WO00010 | MPR | 2023-08-22T11:02:26.670 | WO | 0 | 398.86 | 2.47 | 398.86 | 100 |  | 0 |  | 08/22/2023 | 08/22/2023 |  |  |  | MPR
23-0221-Aery | WO00011 | PNL | 2023-08-22T11:02:26.763 | WO | 0 | 707.42 | 3.78 | 707.42 | 100 |  | 0 |  | 08/22/2023 | 08/22/2023 |  |  |  | PNL
23-0221-Aery | WO00012 | PNT | 2023-08-22T11:02:26.890 | WO | 0 | 327.48 | 2.22 | 327.48 | 100 |  | 0 |  | 08/22/2023 | 08/22/2023 |  |  |  | PNT
23-0221-Aery | WO00013 | SDG | 2023-08-22T11:02:27.093 | WO | 0 | 878.77 | 4.58 | 878.77 | 100 |  | 0 |  | 08/22/2023 | 08/22/2023 |  |  |  | SDG
23-0221-Aery | WO00014 | WDP | 2023-08-22T11:02:27.250 | WO | 0 | 9697.03 | 2.97 | 9697.03 | 100 |  | 0 |  | 08/22/2023 | 08/22/2023 |  |  |  | WDP
23-0221-Aery | WO00015 | WDW | 2023-08-22T11:02:27.467 | WO | 0 | 70.8 | 0.58 | 70.8 | 100 |  | 0 |  | 08/22/2023 | 08/22/2023 |  |  |  | WDW
23-0222-Aery
23-0225-IR
23-0222-C
23-0226-IR
23-0227-C | WO0002 | Cabinetry | 2023-08-18T11:24:25.000 | WO | 0 | 2076.675 | 8.88 | 4153.35 | 50 |  | 50 |  | 09/14/2023 | 09/15/2023 |  |  |  | CAB
23-0227-C | WO0003 | Cleaning | 2023-08-18T11:24:25.000 | WO | 0 | 195.89 | 5.5 | 391.78 | 50 |  | 50 |  | 09/28/2023 | 09/28/2023 |  |  |  | CLN
23-0227-C | WO0004 | Deck | 2023-08-18T11:24:25.000 | WO | 0 | 13947.108 | 35.9 | 23245.18 | 60 |  | 40 |  | 09/04/2023 | 09/08/2023 |  |  |  | CNC
23-0227-C | WO0005 | Demo and Debris | 2023-08-18T11:24:25.000 | WO | 0 | 1200.485 | 9.5 | 2400.97 | 50 |  | 50 |  | 08/28/2023 | 08/29/2023 |  |  |  | DMO
23-0227-C | WO0006 | Drywall and Paint | 2023-08-18T11:24:25.000 | WO | 0 | 807.705 | 50.73 | 1615.41 | 50 |  | 50 |  | 08/30/2023 | 09/06/2023 |  |  |  | DRY
23-0227-C | WO0007 | Electrical Phase 2 | 2023-08-18T11:24:26.000 | WO | 0 | 554.6457 | 7 | 880.39 | 63 |  | 37 |  | 09/18/2023 | 09/18/2023 |  |  |  | ELE
23-0227-C | WO0009 | Tile | 2023-08-18T11:24:26.000 | WO | 0 | 2575.881 | 14.43 | 4683.42 | 55 |  | 45 |  | 09/11/2023 | 09/13/2023 |  |  |  | FCT
23-0227-C | WO00010 | FEE | 2023-08-18T11:24:26.343 | WO | 0 | 1800 |  | 1800 | 100 |  | 0 | [6 empty] | FEE
23-0227-C | WO00011 | Carpentry | 2023-08-18T11:24:26.000 | WO | 0 | 627.095 | 16.06 | 1254.19 | 50 |  | 50 |  | 09/19/2023 | 09/21/2023 |  |  |  | FNC
23-0227-C | WO00013 | Radiant floor | 2023-08-18T11:24:26.000 | WO | 0 | 3329.781 | 12.8 | 5122.74 | 65 |  | 35 |  | 09/07/2023 | 09/08/2023 |  |  |  | HVC
23-0227-C | WO00014 | LAB | 2023-08-18T11:24:26.953 | WO | 0 | 2934.38 | 212 | 2934.38 | 100 |  | 0 |  | 08/28/2023 | 09/28/2023 |  |  |  | LAB
23-0227-C | WO00015 | Siding | 2023-08-18T11:24:27.000 | WO | 0 | 10788.825 | 57.09 | 21577.65 | 50 |  | 50 |  | 08/30/2023 | 09/21/2023 |  |  |  | LIT
23-0227-C | WO00016 | Plumbing | 2023-08-18T11:24:27.000 | WO | 0 | 670.8114 | 4.35 | 1064.78 | 63 |  | 37 |  | 09/27/2023 | 09/27/2023 |  |  |  | PLM
23-0227-C | WO00022 | Cabinetry - Materials | 2023-08-18T11:32:00.000 | WO | 0 | 6073.19 |  | 12146.38 | 50 |  | 50
23-0227-C | WO00023 | Countertop | 2023-08-18T11:33:00.000 | WO | 0 | 3763.585 | 7.8 | 7527.17 | 50 |  | 50 |  | 09/22/2023 | 09/22/2023
23-0227-C | WO00024 | Deck - Materials | 2023-08-18T11:38:00.000 | WO | 0 | 4349.755 |  | 8699.51 | 50 |  | 50
23-0227-C | WO00025 | Tile - Materials | 2023-08-18T12:35:00.000 | WO | 0 | 1227.1615 |  | 2447.01 | 50.1494 |  | 49.8506
23-0227-C | WO00026 | Carpentry - Materials | 2023-08-18T12:37:00.000 | WO | 0 | 54.02 |  | 108.04 | 50 |  | 50
23-0227-C | WO00027 | Plumbing - Materials | 2023-08-18T13:17:00.000 | WO | 0 | 395.872 |  | 494.84 | 80 |  | 20
23-0227-C | WO00028 | Siding - Material | 2023-08-18T15:03:00.000 | WO | 0 | 6226.4735 |  | 9579.19 | 65 |  | 35
23-0227-C | WO00029 | Electrical Phase 1 | 2023-08-21T17:33:00.000 | WO | 0 | 619.1388 | 2 | 982.76 | 63 |  | 37 |  | 08/30/2023 | 08/30/2023
23-0227-C | WO00030 | Dumpster | 2023-08-30T09:15:00.000 | WO | 0 | 673.24 |  | 1346.48 | 50 |  | 50
23-0227-C | WO00031 | Tile Phase 2 | 2023-08-30T09:17:00.000 | WO | 0 | 1051.974 | 18 | 1912.68 | 55 |  | 45 |  | 09/25/2023 | 09/26/2023
23-0228-Aery
23-0229-C
23-0231-Aery
23-0232-Aery | WO0001 | Appliances | 2023-07-31T16:51:39.000 | WO | 0 | 344.32 | 4.95 | 860.8 | 40 |  | 60 |  | 07/31/2023 | 08/01/2023 |  |  |  | APP
23-0232-Aery | WO0002 | Carpentry | 2023-07-31T16:51:40.000 | WO | 0 | 1440.015 | 25.23 | 2880.03 | 50 |  | 50 |  | 07/31/2023 | 08/01/2023 |  |  |  | CAB
23-0232-Aery | WO0003 | Final Clean | 2023-07-31T16:51:40.000 | WO | 0 | 129.79 | 3.8 | 259.58 | 50 |  | 50 |  | 07/31/2023 | 07/31/2023 |  |  |  | CLN
23-0232-Aery | WO0004 | Debris Removal | 2023-07-31T16:51:40.000 | WO | 0 | 122.945 | 1.98 | 245.89 | 50 |  | 50 |  | 07/31/2023 | 07/31/2023 |  |  |  | DMO
23-0232-Aery | WO0006 | Insulation, Paint & Drywall | 2023-07-31T16:51:40.000 | WO | 0 | 2804.035 | 39.38 | 5608.07 | 50 |  | 50 |  | 07/31/2023 | 08/02/2023 |  |  |  | DRY
23-0232-Aery | WO0008 | Tile | 2023-07-31T16:51:41.000 | WO | 0 | 1730.927 | 18.13 | 3147.14 | 55 |  | 45 |  | 07/31/2023 | 08/02/2023 |  |  |  | FCT
23-0232-Aery | WO0009 | Vinyl Floor | 2023-07-31T16:51:41.000 | WO | 0 | 380.886 | 2.88 | 692.52 | 55 |  | 45 |  | 07/31/2023 | 07/31/2023 |  |  |  | FCV
23-0232-Aery | WO00010 | Engineered Wood Flooring | 2023-07-31T16:51:41.000 | WO | 0 | 2336.6205 | 22.5 | 5192.49 | 45 |  | 55 |  | 07/31/2023 | 08/02/2023 |  |  |  | FCW
23-0232-Aery | WO00017 | ASK ESTIMATOR | 2023-07-31T16:51:42.000 | WO | 0 | -163.76 | 0 | -163.76 | 100 |  | 0 |  | 07/31/2023 | 07/31/2023 |  |  |  | LAB
23-0232-Aery | WO00021 | Plumbing | 2023-07-31T16:51:43.000 | WO | 0 | 3349.3085 | 28.82 | 5178.79 | 64.6736 |  | 35.3264 |  | 07/31/2023 | 08/02/2023 |  |  |  | PLM
23-0232-Aery | WO00047 | Tile - Materials | 2023-08-01T11:51:00.000 | WO | 0 | 595.12 | 8 | 1190.24 | 50 |  | 50 |  | 08/01/2023 | 08/01/2023
23-0232-Aery | WO00048 | Oak Flooring | 2023-08-01T12:01:00.000 | WO | 0 | 468.745 | 12.89 | 937.49 | 50 |  | 50 |  | 07/31/2023 | 08/02/2023
23-0232-Aery | WO00049 | Carpentry Materials | 2023-08-01T12:09:00.000 | WO | 0 | 705.27 | 8 | 1175.45 | 60 |  | 40 |  | 08/01/2023 | 08/01/2023
23-0232-Aery | WO00050 | Plumbing - Materials | 2023-08-01T12:44:00.000 | WO | 0 | 109.545 |  | 365.15 | 30 |  | 70
23-0233-ER | WO0001 | Cabinetry | 2023-08-16T17:50:38.000 | WO | 0 | 10518.55 | 64.8 | 10518.55 | 100 |  | 0 |  | 08/16/2023 | 08/25/2023 |  |  |  | CAB
23-0233-ER | WO0002 | Doors | 2023-08-16T17:50:38.000 | WO | 0 | 686.19 | 4.12 | 686.19 | 100 |  | 0 |  | 08/16/2023 | 08/16/2023 |  |  |  | DOR
23-0233-ER | WO0003 | FCC | 2023-08-16T17:50:38.840 | WO | 0 | 4411.85 | 26.47 | 4411.85 | 100 |  | 0 |  | 08/16/2023 | 08/21/2023 |  |  |  | FCC
23-0233-ER | WO0004 | FCT | 2023-08-16T17:50:38.997 | WO | 0 | 6005.42 | 11.57 | 6005.42 | 100 |  | 0 |  | 08/16/2023 | 08/17/2023 |  |  |  | FCT
23-0233-ER | WO0005 | FCV | 2023-08-16T17:50:39.107 | WO | 0 | 5086.19 | 45.57 | 5086.19 | 100 |  | 0 |  | 08/16/2023 | 08/23/2023 |  |  |  | FCV
23-0233-ER | WO0006 | FNC | 2023-08-16T17:50:39.247 | WO | 0 | 28557.7 | 26.95 | 28557.7 | 100 |  | 0 |  | 08/16/2023 | 08/21/2023 |  |  |  | FNC
23-0233-ER | WO0007 | FNH | 2023-08-16T17:50:39.420 | WO | 0 | 628.56 | 3.32 | 628.56 | 100 |  | 0 |  | 08/16/2023 | 08/16/2023 |  |  |  | FNH
23-0233-ER | WO0008 | MAS | 2023-08-16T17:50:39.513 | WO | 0 | 2367.06 | 15.75 | 2367.06 | 100 |  | 0 |  | 08/16/2023 | 08/17/2023 |  |  |  | MAS
23-0233-ER | WO0009 | MSD | 2023-08-16T17:50:39.623 | WO | 0 | 413.55 | 2.85 | 413.55 | 100 |  | 0 |  | 08/16/2023 | 08/16/2023 |  |  |  | MSD
23-0233-ER | WO00010 | PNT | 2023-08-16T17:50:39.717 | WO | 0 | 17055.54 | 113.47 | 17055.54 | 100 |  | 0 |  | 08/16/2023 | 09/01/2023 |  |  |  | PNT
23-0233-ER | WO00011 | TIL | 2023-08-16T17:50:39.920 | WO | 0 | 12134.31 | 28.5 | 12134.31 | 100 |  | 0 |  | 08/16/2023 | 08/21/2023 |  |  |  | TIL
23-0233-ER | WO00012 | Cabinetry - Materials | 2023-08-17T11:45:00.000 | WO | 0 | 166.61 | 8 | 166.61 | 100 |  | 0 |  | 08/17/2023 | 08/17/2023
23-0234-D | WO0002 | FEE | 2023-08-07T14:14:47.787 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | FEE
23-0234-D | WO0003 | sheathing- material | 2023-08-07T14:14:47.000 | WO | 0 | 27.104 |  | 33.88 | 80 |  | 20 | [6 empty] | FRM
23-0234-D | WO0004 | paint- material | 2023-08-07T14:14:48.000 | WO | 0 | 65.936 |  | 82.42 | 80 |  | 20 | [6 empty] | PNT
23-0234-D | WO0005 | roof- material | 2023-08-07T14:14:48.000 | WO | 0 | 1477.431 |  | 1641.59 | 90 |  | 10 | [6 empty] | RFG
23-0234-D | WO0006 | siding- labor | 2023-08-07T14:14:48.000 | WO | 0 | 157.235 | 0 | 314.47 | 50 |  | 50 |  | 08/07/2023 | 08/07/2023 |  |  |  | SDG
23-0234-D | WO0007 | soffit & fascia- wood 1" overhang- material | 2023-08-07T14:14:48.000 | WO | 0 | 73.816 |  | 92.27 | 80 |  | 20 | [6 empty] | SFG
23-0234-D | WO0008 | sheathing- labor | 2023-08-07T14:16:00.000 | WO | 0 | 117.225 | 8.8 | 234.45 | 50 |  | 50 |  | 08/07/2023 | 08/07/2023
23-0234-D | WO0009 | painting- labor | 2023-08-07T14:19:00.000 | WO | 0 | 302.155 | 13.75 | 604.31 | 50 |  | 50 |  | 08/07/2023 | 08/07/2023
23-0234-D | WO00010 | roof- labor | 2023-08-07T14:20:00.000 | WO | 0 | 1095.0001 | 29.2 | 3286.66 | 1095 |  | 66.6835 |  | 08/07/2023 | 08/09/2023
23-0234-D | WO00011 | soffit & fascia- wood 1" overhang- labor | 2023-08-07T14:23:00.000 | WO | 0 | 88.6 | 9.22 | 177.2 | 50 |  | 50 |  | 08/07/2023 | 08/07/2023
23-0236-Aery
23-0237-IR | WO0001 | Appliances - Materials | 2023-08-02T09:21:16.000 | WO | 0 | 4247.176 |  | 5308.97 | 80 |  | 20 | [6 empty] | APP
23-0237-IR | WO0003 | Cleaning | 2023-08-02T09:21:16.000 | WO | 0 | 586.055 | 5.42 | 1172.11 | 50 |  | 50 |  | 09/29/2023 | 09/29/2023 |  |  |  | CLN
23-0237-IR | WO0004 | Deconstruction and Debris Removal | 2023-08-02T09:21:16.000 | WO | 0 | 1857.2615 | 23.03 | 3405.32 | 54.54 |  | 45.46 |  | 08/21/2023 | 08/23/2023 |  |  |  | DMO
23-0237-IR | WO0006 | Drywall and Paint Phase 1 | 2023-08-02T09:21:17.000 | WO | 0 | 5039.365 | 48.1 | 10078.73 | 50 |  | 50 |  | 08/31/2023 | 09/06/2023 |  |  |  | DRY
23-0237-IR | WO0007 | Electrical Phase 1 | 2023-08-02T09:21:17.000 | WO | 0 | 460.0449 | 12.73 | 730.23 | 63 |  | 37 |  | 08/28/2023 | 08/28/2023 |  |  |  | ELE
23-0237-IR | WO0008 | Tile | 2023-08-02T09:21:17.000 | WO | 0 | 2626.745 | 16 | 4775.9 | 55 |  | 45 |  | 09/14/2023 | 09/15/2023 |  |  |  | FCT
23-0237-IR | WO0009 | Vinyl Floor | 2023-08-02T09:21:17.000 | WO | 0 | 2260.5 | 10.22 | 4110 | 55 |  | 45 |  | 09/07/2023 | 09/08/2023 |  |  |  | FCV
23-0237-IR | WO00011 | Permits | 2023-08-02T09:21:17.000 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | FEE
23-0237-IR | WO00012 | Carpentry Phase 2 | 2023-08-02T09:21:17.000 | WO | 0 | 1602.945 | 20.68 | 3205.89 | 50 |  | 50 |  | 09/18/2023 | 09/20/2023 |  |  |  | FNC
23-0237-IR | WO00018 | Plumbing Phase 1 | 2023-08-02T09:21:18.000 | WO | 0 | 3048.7464 | 6.6 | 4839.28 | 63 |  | 37 |  | 08/24/2023 | 08/25/2023 |  |  |  | PLM
23-0237-IR | WO00020 | Window Replacement | 2023-08-02T09:21:18.000 | WO | 0 | 1502.697 | 7 | 2146.71 | 70 |  | 30 |  | 09/19/2023 | 09/19/2023 |  |  |  | SDG
23-0237-IR | WO00028 | Tile - Materials | 2023-08-03T09:10:00.000 | WO | 0 | 478.16 |  | 956.32 | 50 |  | 50 | [6 empty] | FCT
23-0237-IR | WO00029 | Vinyl Floor - Materials | 2023-08-03T09:13:00.000 | WO | 0 | 1285.668 |  | 3214.17 | 40 |  | 60 | [6 empty] | FCV
23-0237-IR | WO00030 | Carpentry - Materials | 2023-08-03T09:27:00.000 | WO | 0 | 2178.53 |  | 4357.06 | 50 |  | 50
23-0237-IR | WO00031 | Electrical - Materials | 2023-08-03T09:57:00.000 | WO | 0 | 349.056 |  | 775.68 | 45 |  | 55
23-0237-IR | WO00032 | Plumbing - Materials | 2023-08-03T10:08:00.000 | WO | 0 | 379.63 |  | 759.26 | 50 |  | 50
23-0237-IR | WO00033 | Kitchen Counters | 2023-08-09T17:49:00.000 | WO | 0 | 944.955 | 7 | 1889.91 | 50 |  | 50 |  | 09/12/2023 | 09/12/2023
23-0237-IR | WO00034 | Cabinetry | 2023-08-09T17:53:00.000 | WO | 0 | 3475.805 | 17 | 6951.61 | 50 |  | 50 |  | 09/11/2023 | 09/12/2023
23-0237-IR | WO00035 | Plumbing Phase 2 | 2023-08-14T16:32:00.000 | WO | 0 | 1267.6419 | 17.12 | 2012.13 | 63 |  | 37 |  | 09/25/2023 | 09/26/2023
23-0237-IR | WO00036 | Electrical Phase 2 | 2023-08-14T16:43:00.000 | WO | 0 | 2275.1253 | 17 | 3611.31 | 63 |  | 37 |  | 09/27/2023 | 09/28/2023
23-0237-IR | WO00037 | Carpentry Phase 1 | 2023-08-14T16:50:00.000 | WO | 0 | 251.455 | 16 | 502.91 | 50 |  | 50 |  | 08/29/2023 | 08/30/2023
23-0237-IR | WO00038 | Counter Top Material | 2023-08-14T16:55:00.000 | WO | 0 | 696.99 | 8 | 1393.98 | 50 |  | 50 |  | 08/24/2023 | 08/24/2023
23-0237-IR | WO00039 | Drywall and Paint Phase 2 | 2023-08-14T17:03:00.000 | WO | 0 | 2263.055 | 12.27 | 4526.11 | 50 |  | 50 |  | 09/21/2023 | 09/22/2023
23-0237-IR | WO00040 | Handyman | 2023-08-14T17:37:00.000 | WO | 0 | 539.245 | 7 | 1078.49 | 50 |  | 50 |  | 09/29/2023 | 09/29/2023
23-0238-ER
23-0239-IR
23-0241-ER
23-0242-IR
23-0245-IR
23-0246-ER
23-0247-IR
23-0249-ER
23-0250-IR | WO0001 | Dumpster | 2023-08-28T14:52:58.000 | WO | 0 | 103.56 | 1 | 103.56 | 100 |  | 0 |  | 08/28/2023 | 08/28/2023 |  |  |  | DMO
23-0250-IR | WO0002 | FEE | 2023-08-28T14:52:58.413 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | FEE
23-0250-IR | WO0003 | Roof | 2023-08-28T14:52:58.000 | WO | 0 | 2183.82 | 13.83 | 2183.82 | 100 |  | 0 |  | 08/28/2023 | 08/29/2023 |  |  |  | RFG
23-0250-IR | WO0004 | Gutter | 2023-08-28T14:52:58.000 | WO | 0 | 77.5 | 0.47 | 77.5 | 100 |  | 0 |  | 08/28/2023 | 08/28/2023 |  |  |  | SFG
23-0250-IR | WO0005 | Materials | 2023-08-28T14:54:00.000 | WO | 0 | 1117.27 | 8 | 1117.27 | 100 |  | 0 |  | 08/28/2023 | 08/28/2023
23-0251-IR
23-0253-ER
23-0254-ER | WO0001 | HVC | 2023-08-24T10:00:21.587 | WO | 0 | 116.45 | 0.65 | 116.45 | 100 |  | 0 |  | 08/24/2023 | 08/24/2023 |  |  |  | HVC
23-0254-ER | WO0002 | RFG | 2023-08-24T10:00:22.523 | WO | 0 | 10492.69 | 49.32 | 10492.69 | 100 |  | 0 |  | 08/24/2023 | 08/31/2023 |  |  |  | RFG
23-0254-ER | WO0003 | HVC | 2023-08-24T10:01:31.080 | WO | 0 | 116.45 | 0.65 | 116.45 | 100 |  | 0 |  | 08/24/2023 | 08/24/2023 |  |  |  | HVC
23-0254-ER | WO0004 | RFG | 2023-08-24T10:01:31.173 | WO | 0 | 10492.69 | 49.32 | 10492.69 | 100 |  | 0 |  | 08/24/2023 | 08/31/2023 |  |  |  | RFG
23-0258-ER
23-0259-IR
23-0260-ER
23-0261-ER
23-0262-IR
23-0263-ER
23-0264-ER
23-0265-IR
23-0266-ER
23-0267-ER
23-0268-ER
23-0270-ER
23-0272-ER
23-0273-ER
23-0274-ER | WO0001 | DMO | 2023-08-30T09:09:13.847 | WO | 0 | 299.93 | 3.12 | 299.93 | 100 |  | 0 |  | 08/30/2023 | 08/30/2023 |  |  |  | DMO
23-0274-ER | WO0002 | overhead door weather stop-labor | 2023-08-30T09:09:13.000 | WO | 0 | 126.8775 | 1.38 | 281.95 | 45 |  | 55 |  | 08/30/2023 | 08/30/2023 |  |  |  | DOR
23-0274-ER | WO0003 | caulking- labor | 2023-08-30T09:09:14.000 | WO | 0 | 90.73 | 1.77 | 181.46 | 50 |  | 50 |  | 08/30/2023 | 08/30/2023 |  |  |  | MPR
23-0274-ER | WO0004 | wrap garage door frame- labor | 2023-08-30T09:09:14.000 | WO | 0 | 431.188 | 7.78 | 1077.97 | 40 |  | 60 |  | 08/30/2023 | 08/30/2023 |  |  |  | SDG
23-0274-ER | WO0005 | fascia and soffit- labor | 2023-08-30T09:09:14.000 | WO | 0 | 624.16 | 8.1 | 1248.32 | 50 |  | 50 |  | 08/30/2023 | 08/31/2023 |  |  |  | SFG
23-0274-ER | WO0006 | overhead door weather stop- material | 2023-08-30T09:14:00.000 | WO | 0 | 68.12 | 8 | 68.12 | 100 |  | 0 |  | 08/30/2023 | 08/30/2023
23-0274-ER | WO0007 | caulking- material | 2023-08-30T09:16:00.000 | WO | 0 | 11.73 | 8 | 11.73 | 100 |  | 0 |  | 08/30/2023 | 08/30/2023
23-0274-ER | WO0008 | wrap garage door frame- material | 2023-08-30T09:17:00.000 | WO | 0 | 148.744 | 8 | 185.93 | 80 |  | 20 |  | 08/30/2023 | 08/30/2023
23-0274-ER | WO0009 | gutters/downspouts- labor and material | 2023-08-30T09:18:00.000 | WO | 0 | 623.9698 | 11.65 | 983.28 | 623.97 |  | 36.542 |  | 08/30/2023 | 08/30/2023
23-0274-ER | WO00010 | fascia and soffit- material | 2023-08-30T09:19:00.000 | WO | 0 | 423.168 | 8 | 528.96 | 80 |  | 20 |  | 08/30/2023 | 08/30/2023
23-0275-IR
23-0276-IR
23-0277-IR
22-0869-IR
23-0278-IR
23-0279-IR
23-0280-ER
23-0281-ER
23-0282-ER
23-0283-ER
23-0284-ER
23-1011-C
23-0286-D
23-0287-ER
23-0288-ER
23-0499-ER
23-0242-ER
23-0289-IR
23-0290-ER
23-0291-ER
23-0292-Aery
22-0260-ER
22-0179-ER
22-0201-C
22-0202-C
22-0211-C
22-0213-C
22-0149-ER
22-0043-ER
22-0379-IR
22-0483-ER
22-0425-RET-ER
22-0542-ER
22-0539-ER
22-0567-ER
22-0527-ER
22-0511-ER
22-0510-ER
22-0591-ER
22-0597-ER
22-0626-ER
22-0501-ER
22-0485-ER
22-0487-ER
22-0608-ER
22-0529-ER
22-0634-ER
22-0651-ER
22-0496-ER
22-0518-ER
22-0519-ER
22-0615-ER
22-0605-ER
22-0593-ER
22-0564-ER
22-0522-ER
22-0672-ER
22-0670-ER
22-0644-ER
22-0566-ER
22-0637-ER
22-0646-ER
22-0666-ER
22-0705-ER
22-0578-ER
22-0607-ER
22-0740-ER
22-0592-ER
22-0631-ER
22-0659-ER
22-0671-ER
22-0596-ER
22-0716-ER
22-0715-ER
22-0624-ER
22-0675-ER
22-0676-ER
22-0663-ER
22-0667-ER
22-0656-ER
22-0658-ER
22-0704-ER
22-0703-ER
22-0745-ER
22-0691-IR
22-0628-ER
22-0550-ER
22-0528-ER
22-0751-ER
22-0633-ER
22-0612-ER
22-0665-ER
22-0791-ER
22-0789-ER
22-0575-ER
22-0632-ER
22-0654-ER
22-0660-ER
22-0146-D
22-0680-EST
22-0486-ER
22-0502-ER
22-0541-ER
22-0582-ER
22-0552-ER
22-0538-ER
22-0537-ER
22-0526-ER
22-0649-ER
22-0643-ER
22-0488-ER
22-0503-ER
22-0816-ER
22-0743-C
22-0795-ER
22-0811-ER
22-0807-ER
22-0609-ER
22-0823-ER
22-0824-ER
22-0820-ER
22-0642-ER
22-0625-ER
22-0602-ER
22-0540-ER
22-0563-ER
22-0581-ER
22-0799-ER
22-0639-ER
22-0710-ER
22-0604-ER
22-0794-ER
22-0819-ER
22-0555-ER
22-0825-ER
22-0838-ER
22-0839-ER
22-0861-ER
22-0863-ER
22-0744-C
22-0821-ER
22-0919-ER
22-0790-ER
22-0638-ER
22-0712-ER
22-0495-ER
22-0733-ER
22-0770-ER
22-0808-ER-2-ER
22-0736-WAR
22-0928-ER
22-0945-ER
22-0792-ER
22-0948-ER
22-0865-ER
22-0931-ER
22-0929-ER
22-0927-ER
22-0782-ER
22-0840-ER
22-0850-ER
22-0853-ER
22-0878-ER
22-0886-ER
22-0887-ER
22-0890-ER
22-0911-ER
22-0912-ER
22-0920-ER
22-0961-ER
22-0941-ER
22-0947-ER
22-0949-ER
22-0982-ER
22-0980-ER
22-0708-ER
22-0841-ER
22-0588-ER
22-0601-RET-ER
22-0725-ER
22-0894-ER
22-0769-ER
22-0862-ER
22-0965-ER
22-0921-ER
22-0851-ER
22-0899-ER
22-0925-ER
22-0781-ER
22-0876-ER
22-0937-ER
22-0576-RET-ER
22-0924-ER
22-0984-ER
22-0854-ER
22-0909-ER
22-0932-ER
22-0939-ER
22-0944-ER
22-0955-ER
22-0964-ER
22-0974-ER
22-0993-ER
22-0994-ER
22-0531-ER
22-0571-ER
22-0998-ER
22-0780-ER
22-0852-ER
22-1007-ER
22-1006-ER
22-0647-ER
22-0648-ER
22-0677-ER
22-0812-ER
22-0762-ER
22-0804-ER
22-0864-ER
22-0866-ER
22-0891-ER
22-0893-ER
22-0907-ER
22-0913-ER
22-0914-ER
22-0699-ER
22-0999-ER
22-0889-ER
22-0956-ER
22-0657-ER
22-0662-ER
22-0747-ER
22-0635-ER
22-0764-ER
22-0877-ER
22-0806-ER
22-0805-ER
22-0750-ER
22-0723-ER
22-0981-ER
22-0722-ER
22-0755-WAR | WO0001 | Deck Materials and Labor for brackets | 2022-07-28T11:58:00.000 | WO | 0 | 700 | 8 | 700 | 100 |  | 0 |  | 07/28/2022 | 07/28/2022 |  |  |  | FRM
22-0661-ER | WO0001 | Roofing Labor | 2022-08-01T15:58:00.000 | WO | 0 | 5500 | 8 | 5500 | 100 |  | 0 |  | 08/01/2022 | 08/01/2022 |  |  |  | RFG
22-0799-WAR
22-0730-WAR | WO0001 | equipment | 2022-08-15T13:34:00.000 | WO | 0 | 225 | 8 | 225 | 100 |  | 0 |  | 08/15/2022 | 08/15/2022 |  |  |  | equipment
22-0735-WAR | WO0001, Complete | window film | 2022-08-29T16:03:00.000 | WO | 0 | 1517 | 1 | 1517 | 0 |  | 0 |  | 08/29/2022 | 08/29/2022 |  | 2022-08-29T15:04:41.683 | Deville , Jard | Window film
22-0735-WAR | WO0002, Complete | Security system | 2022-08-29T16:05:00.000 | WO | 0 | 750 | 1 | 750 | 750 |  | 0 |  | 08/29/2022 | 08/29/2022 |  | 2022-08-29T15:06:17.140 | Deville , Jard | Security system
22-0917-IR | WO0001 | Roofing Labor | 2022-09-06T11:22:00.000 | WO | 0 | 5500 | 8 | 5500 | 100 |  | 0 |  | 09/06/2022 | 09/06/2022 |  |  |  | RFG
22-0917-IR | WO0002 | Roofing Materials | 2022-09-06T11:23:00.000 | WO | 0 | 0 | 8 | 0 | 100 |  | 0 |  | 09/06/2022 | 09/06/2022 |  |  |  | MAT
22-0917-IR | WO0003 | Gutter Guards (LeafFilter) | 2022-09-06T11:59:00.000 | WO | 0 | 2935 | 8 | 2935 | 100 |  | 0 |  | 09/06/2022 | 09/06/2022 |  |  |  | SFG
22-0917-IR | WO0004 | Solar Midwest (Skylights) | 2022-09-06T12:00:00.000 | WO | 0 | 2570 | 8 | 2570 | 100 |  | 0 |  | 09/06/2022 | 09/06/2022 |  |  |  | WDW
22-0973-ER
22-0788-EOC
22-0934-C
22-1005-ER
22-0975-IR
22-0972-ER
22-0972-IR
22-0968-ER
22-0957-D
22-0680--ER
22-0832-D
22-0655-ER
22-0963-RET-IR
22-0618-IR
22-1024-D
22-1038-ER
23-0070-EST
23-0072-IR
23-0085-ER
23-0045-D
23-0010-WAR
22-1030-WAR
22-0652-C
22-1044-IR
23-0160-WAR
22-1012-WAR
22-0580-RET-ER
23-0028-WAR | WO0003 | Gutter Labor | 2022-10-03T11:24:00.000 | WO | 0 | 415.5865 | 15.82 | 1187.39 | 35 |  | 65 |  | 10/03/2022 | 10/03/2022 |  |  |  | Gutter Labor
23-0028-WAR | WO0004, Complete | Gutter Material | 2022-10-03T11:24:00.000 | WO | 0 | 463.29 | 8 | 463.29 | 100 |  | 0 |  | 10/03/2022 | 10/03/2022 |  | 2022-10-03T10:33:05.947 | Olson, Jonathon | Gutter Material
23-0821-ER
22-0453-IR
22-1031-EST
22-1002-WAR
23-0159-WAR | WO0001, Complete | Warranty | 2023-05-08T22:38:00.000 | WO | 0 | 500 | 8 | 500 | 100 |  | 0 |  | 05/08/2023 | 05/08/2023 |  | 2023-05-08T21:39:09.693 | Olson, Jonathon | Warranty
23-0107-ER
22-0808-ER-2
22-0908-ER
22-0775-WAR
23-0269-ER
23-0252-ER
23-0205-ER
23-0224-WAR
22-0454-WAR
23-0174-WAR
23-0189-WAR
23-0052-WAR
22-1027-WAR
23-0134-WAR
23-0180-WAR
23-0166-IR
23-0080-WAR
22-0884-RET-ER
22-0315-D
22-1026-D | WO0002 | Site Set Up | 2022-05-18T14:27:00.000 | WO | 0 | 850 | 8 | 1062.5 | 850 |  | 20 |  | 05/18/2022 | 05/18/2022
22-1026-D | WO0003 | Framing | 2022-05-18T14:29:00.000 | WO | 0 | 180.0001 | 0 | 251.97 | 180 |  | 28.5629 |  | 05/18/2022 | 05/18/2022
22-1026-D | WO0004 | Drywall | 2022-05-18T14:30:00.000 | WO | 0 | 1100 | 8 | 2200 | 1100 |  | 50 |  | 05/18/2022 | 05/18/2022
22-1026-D | WO0005 | Flooring | 2022-05-18T14:31:00.000 | WO | 0 | 2149.9988 | 8 | 2787.5 | 2150 |  | 22.87 |  | 05/18/2022 | 05/18/2022
22-1026-D | WO0006 | Millwork | 2022-05-18T14:37:00.000 | WO | 0 | 200 | 8 | 250 | 200 |  | 20 |  | 05/18/2022 | 05/18/2022
22-1026-D | WO0007 | O&P | 2022-05-18T14:38:00.000 | WO | 0 | 0 | 0 | 1650 | 0 |  | 100 |  | 05/18/2022 | 05/18/2022
22-0012-D
22-0786-D | WO0001, Complete | Design | 2022-08-23T15:02:00.000 | WO | 0 | 300 | 8 | 300 | 100 |  | 0 |  | 08/23/2022 | 08/23/2022 |  | 2022-08-23T14:24:40.527 | Dehnke, Josh | Design
22-0786-D | WO0002, Complete | Planning | 2022-08-23T15:03:00.000 | WO | 0 | 0 | 8 | 0 | 100 |  | 0 |  | 08/23/2022 | 08/23/2022 |  | 2022-08-23T14:24:40.510 | Dehnke, Josh | Planning
22-0786-D | WO0003, Complete | Site Set Up | 2022-08-23T15:05:00.000 | WO | 0 | 300 | 8 | 300 | 100 |  | 0 |  | 08/23/2022 | 08/23/2022 |  | 2022-08-23T14:24:40.497 | Dehnke, Josh | Site Set Up
22-0786-D | WO0004, Complete | Demo | 2022-08-23T15:06:00.000 | WO | 0 | 700 | 8 | 700 | 100 |  | 0 |  | 08/23/2022 | 08/23/2022 |  | 2022-08-23T14:24:40.463 | Dehnke, Josh | Demo
22-0786-D | WO0005, Complete | Framing Labor | 2022-08-23T15:06:00.000 | WO | 0 | 313 | 8 | 313 | 100 |  | 0 |  | 08/23/2022 | 08/23/2022 |  | 2022-09-19T07:37:12.530 | Dehnke, Josh | Framing
22-0786-D | WO0006, Complete | Electrical | 2022-08-23T15:08:00.000 | WO | 0 | 3006 | 8 | 3006 | 100 |  | 0 |  | 08/23/2022 | 08/23/2022 |  | 2022-08-23T14:24:40.417 | Dehnke, Josh | Electrical
22-0786-D | WO0007, Complete | Plumbing | 2022-08-23T15:09:00.000 | WO | 0 | 2974.9992 | 8 | 4719 | 2975 |  | 36.957 |  | 08/23/2022 | 08/23/2022 |  | 2022-09-12T13:42:29.490 | Dehnke, Josh | Plumbing
22-0786-D | WO0008, Complete | HVAC | 2022-08-23T15:12:00.000 | WO | 0 | 181 | 8 | 181 | 100 |  | 0 |  | 08/23/2022 | 08/23/2022 |  | 2022-09-12T13:42:29.557 | Dehnke, Josh | HVAC
22-0786-D | WO00010, Complete | Drywall | 2022-08-23T15:15:00.000 | WO | 0 | 1080.5 | 16 | 2161 | 50 |  | 50 |  | 08/23/2022 | 08/23/2022 |  | 2022-09-19T07:37:12.547 | Dehnke, Josh | Drywall
22-0786-D | WO00012, Complete | Finish Carpentry | 2022-08-23T15:18:00.000 | WO | 0 | 456 | 16 | 912 | 50 |  | 50 |  | 08/23/2022 | 08/23/2022 |  | 2022-10-17T09:21:37.563 | Dehnke, Josh | Carpentry/Millwork
22-0786-D | WO00013, Complete | Tiling Labor | 2022-08-23T15:19:00.000 | WO | 0 | 2319.75 | 16 | 3093 | 75 |  | 25 |  | 08/23/2022 | 08/23/2022 |  | 2022-09-28T08:27:08.840 | Dehnke, Josh | Tiling
22-0786-D | WO00015, Complete | Overhead and Admin | 2022-08-23T15:21:00.000 | WO | 0 | 0 | 8 | 1392 | 0 |  | 100 |  | 08/23/2022 | 08/23/2022 |  | 2022-09-23T14:30:05.200 | Dehnke, Josh | O&P
22-0786-D | WO00016, Complete | Profit | 2022-08-23T15:21:00.000 | WO | 0 | 0 | 8 | 2087 | 0 |  | 100 |  | 08/23/2022 | 08/23/2022 |  | 2022-10-17T09:21:37.610 | Dehnke, Josh | Profit
22-0124-D
22-0951-D | WO0001, Complete | Drywall, Texture, Paint (Ceiling) | 2022-05-23T15:07:00.000 | WO | 0 | 5400.0028 | 40 | 8190 | 5400 |  | 34.0659 |  | 06/27/2022 | 07/01/2022 |  | 2022-07-01T08:14:14.390 | Dehnke, Josh | DRY
22-0951-D | WO0002, Complete | Doors (Mat/Lab) | 2022-05-23T15:14:00.000 | WO | 0 | 5714.4 | 17 | 5714.4 | 100 |  | 0 |  | 07/12/2022 | 07/13/2022 |  | 2022-06-24T13:17:31.673 | Dehnke, Josh | Carp/Wind/Doors
22-0951-D | WO0003, Complete | Door and Trim Labor | 2022-07-15T09:56:00.000 | WO | 0 | 1904.8 | 8 | 3809.6 | 50 |  | 50 |  | 07/15/2022 | 07/15/2022 |  | 2022-09-06T09:58:51.303 | Dehnke, Josh | FNC
22-0951-D | WO0004, Complete | Finish Materials | 2022-07-15T09:59:00.000 | WO | 0 | 2625 | 8 | 3500 | 75 |  | 25 |  | 07/15/2022 | 07/15/2022 |  | 2022-07-15T14:01:28.610 | Dehnke, Josh | FNC
22-0951-D | WO0005, Complete | Site Clean Up | 2022-07-15T15:04:00.000 | WO | 0 | 600 | 8 | 1000 | 60 |  | 40 |  | 07/15/2022 | 07/15/2022 |  | 2022-07-15T14:05:22.767 | Dehnke, Josh | CLN
22-0014-D
22-0749-D | WO0001, Complete | Design | 2022-05-04T12:58:00.000 | WO | 0 | 120 | 8 | 300 | 120 |  | 60 |  | 05/13/2022 | 05/13/2022 |  | 2022-05-09T10:42:42.157 | Sleem, Michael
22-0749-D | WO0002, Complete | Job Site Setup | 2022-05-04T14:17:00.000 | WO | 0 | 525 | 8 | 800 | 525 |  | 34.375 |  | 05/11/2022 | 05/12/2022 |  | 2022-07-25T13:54:47.010 | Dehnke, Josh
22-0749-D | WO0003, Complete | Demo | 2022-05-04T14:18:00.000 | WO | 0 | 599.9999 | 8 | 1176 | 600 |  | 48.9796 |  | 05/09/2022 | 05/10/2022 |  | 2022-07-25T13:54:47.027 | Dehnke, Josh
22-0749-D | WO0004, Complete | Insulation and Vapor Barrier | 2022-05-04T14:21:00.000 | WO | 0 | 400.0001 | 8 | 615.38 | 400 |  | 34.9995 |  | 05/04/2022 | 05/04/2022 |  | 2022-07-25T13:54:47.073 | Dehnke, Josh
22-0749-D | WO0005, Complete | Electrical | 2022-05-04T14:24:00.000 | WO | 0 | 1090.0002 | 8 | 1816.67 | 1090 |  | 40.0001 |  | 05/16/2022 | 05/16/2022 |  | 2022-07-25T13:54:47.120 | Dehnke, Josh
22-0749-D | WO0006, Complete | Plumbing | 2022-05-04T14:32:00.000 | WO | 0 | 4160.0015 | 0 | 5012.05 | 4160 |  | 17 |  | 05/03/2022 | 05/03/2022 |  | 2022-07-25T13:54:47.150 | Dehnke, Josh
22-0749-D | WO0007, Complete | Cabinetry Install | 2022-05-04T14:33:00.000 | WO | 0 | 300 | 8 | 375 | 300 |  | 20 |  | 05/04/2022 | 05/05/2022 |  | 2023-02-13T08:23:09.303 | Dehnke, Josh
22-0749-D | WO0008, Complete | Tile | 2022-05-04T14:35:00.000 | WO | 0 | 2199.9996 | 8 | 3384.62 | 2200 |  | 35.0001 |  | 05/06/2022 | 05/09/2022 |  | 2022-07-25T13:54:47.183 | Dehnke, Josh
22-0749-D | WO0009, Complete | Final Cleaning | 2022-05-04T14:36:00.000 | WO | 0 | 150 | 8 | 150 | 150 |  | 0 |  | 05/05/2022 | 05/06/2022 |  | 2023-02-13T08:23:09.317 | Dehnke, Josh
22-0749-D | WO00010, Complete | O & P | 2022-05-04T14:37:00.000 | WO | 0 | 0 | 8 | 1379 | 0 |  | 100 |  | 05/10/2022 | 05/11/2022 |  | 2023-01-03T09:14:36.727 | Dehnke, Josh
22-0749-D | WO00011, Complete | Profit | 2022-05-04T14:38:00.000 | WO | 0 | 0 | 8 | 2069 | 0 |  | 100 |  | 05/12/2022 | 05/13/2022 |  | 2023-01-03T09:14:36.680 | Dehnke, Josh
22-0749-D | WO00013, Complete | Sub Floor Replacement | 2022-05-19T14:42:00.000 | WO | 0 | 500 | 8 | 625 | 500 |  | 20 |  | 05/19/2022 | 05/19/2022 |  | 2023-01-03T09:14:36.633 | Dehnke, Josh
22-0015-D
22-0283-D
22-0180-D
22-0370-C
22-0728-C
22-0506-C
22-0505-C
22-0650-C
22-0504-C
22-0166-IR
22-0155-IR | WO00010, Complete | punch list | 2022-08-22T11:11:36.000 | WO | 0 | 0 |  | 1420.26 | 0 |  | 100 |  |  |  |  | 2022-12-02T14:24:15.253 | Trevino, Jeovani | PNT
22-0155-IR | WO00011, Complete | RFG | 2022-08-22T11:11:37.000 | WO | 0 | 3399.9982 | 15.78 | 6384.05 | 3400 |  | 46.7423 |  | 09/10/2022 | 09/11/2022 |  | 2022-09-30T12:01:34.267 | Trevino, Jeovani | RFG
22-0155-IR | WO00012, Complete | interior labor | 2022-11-11T09:12:00.000 | WO | 0 | 3249.998 | 52.77 | 5222.08 | 3250 |  | 37.7643 |  | 08/22/2022 | 11/11/2022 |  | 2022-12-02T14:24:15.210 | Trevino, Jeovani | interior labor
22-0155-IR | WO00013, Complete | sub floor | 2022-12-15T10:24:00.000 | WO | 0 | 499.9999 | 8 | 367.28 | 500 |  | -36.1359 |  | 12/15/2022 | 12/15/2022 |  | 2022-12-16T09:48:15.697 | Trevino, Jeovani | sub floor
22-0686-IR | WO0001, Complete | CAB | 2022-10-13T12:44:22.217 | WO | 0 | 5652.25 |  | 5652.25 | 100 |  | 0 |  |  |  |  | 2022-10-17T08:41:24.347 | Dehnke, Josh | CAB
22-0686-IR | WO0002, Complete | CON | 2022-10-13T12:44:22.340 | WO | 0 | 136.2 | 2.2 | 136.2 | 100 |  | 0 |  | 10/13/2022 | 10/13/2022 |  | 2022-10-17T08:41:24.330 | Dehnke, Josh | CON
22-0686-IR | WO0003, Complete | DOR | 2022-10-13T12:44:22.623 | WO | 0 | 638.1 | 1.67 | 638.1 | 100 |  | 0 |  | 10/13/2022 | 10/13/2022 |  | 2022-10-17T08:41:24.487 | Dehnke, Josh | DOR
22-0686-IR | WO0004, Complete | DRY | 2022-10-13T12:44:22.000 | WO | 0 | 1770.894 | 19.7 | 2951.49 | 60 |  | 40 |  | 10/13/2022 | 10/14/2022 |  | 2022-10-17T08:41:24.377 | Dehnke, Josh | DRY
22-0686-IR | WO0005, Complete | FCC | 2022-10-13T12:44:23.077 | WO | 0 | 6086.85 | 17.57 | 6086.85 | 100 |  | 0 |  | 10/13/2022 | 10/17/2022 |  | 2022-10-17T08:41:24.470 | Dehnke, Josh | FCC
22-0686-IR | WO0006, Complete | FCT | 2022-10-13T12:44:23.530 | WO | 0 | 208.01 | 0.98 | 208.01 | 100 |  | 0 |  | 10/13/2022 | 10/13/2022 |  | 2022-10-17T08:41:24.440 | Dehnke, Josh | FCT
22-0686-IR | WO0007, Complete | FCV | 2022-10-13T12:44:23.763 | WO | 0 | 2188.32 | 12.38 | 2188.32 | 100 |  | 0 |  | 10/13/2022 | 10/14/2022 |  | 2022-10-17T08:41:24.410 | Dehnke, Josh | FCV
22-0686-IR | WO0008, Complete | FNC | 2022-10-13T12:44:23.903 | WO | 0 | 215 | 1.32 | 215 | 100 |  | 0 |  | 10/13/2022 | 10/13/2022 |  | 2022-10-17T08:41:24.363 | Dehnke, Josh | FNC
22-0686-IR | WO0009, Complete | FNH | 2022-10-13T12:44:24.000 | WO | 0 | 81.76 | 0 | 81.76 | 100 |  | 0 |  | 11/17/2022 | 11/17/2022 |  | 2022-11-11T15:25:46.707 | Burrell, Bianca | FNH
22-0686-IR | WO00010, Complete | MBL | 2022-10-13T12:44:24.153 | WO | 0 | 1467.69 | 4.17 | 1467.69 | 100 |  | 0 |  | 10/13/2022 | 10/13/2022 |  | 2022-10-17T08:41:24.457 | Dehnke, Josh | MBL
22-0686-IR | WO00011, Complete | PLM | 2022-10-13T12:44:24.263 | WO | 0 | 612.87 | 1.6 | 612.87 | 100 |  | 0 |  | 10/13/2022 | 10/13/2022 |  | 2022-10-17T08:41:24.457 | Dehnke, Josh | PLM
22-0686-IR | WO00012, Complete | PNT | 2022-10-13T12:44:24.390 | WO | 0 | 193.7 | 1.45 | 193.7 | 100 |  | 0 |  | 10/14/2022 | 10/17/2022 |  | 2022-10-17T08:41:24.393 | Dehnke, Josh | PNT
22-0232-ER | WO0006, Complete | leo | 2022-09-01T15:51:00.000 | WO | 0 | 2400.0013 | 34 | 3502.91 | 2400 |  | 31.4855 |  | 09/06/2022 | 09/09/2022 |  | 2022-09-12T07:58:11.013 | Trevino, Jeovani | leo
22-0554-ER | WO0001, Complete | Ground anchor | 2022-06-28T16:15:11.000 | WO | 0 | 549.98 | 4.13 | 549.98 | 100 |  | 0 |  | 06/28/2022 | 06/28/2022 |  | 2022-11-08T12:06:13.423 | Burrell, Bianca | ACC
22-0554-ER | WO0002, Complete | Fence | 2022-06-28T16:15:11.000 | WO | 0 | 1440.18 | 36.15 | 1440.18 | 100 |  | 0 |  | 11/14/2022 | 11/18/2022 |  | 2022-11-15T04:59:08.537 | Burrell, Bianca | FEN
22-0554-ER | WO0003, Complete | Shed Repair | 2022-06-28T16:15:11.000 | WO | 0 | 248.46 | 4 | 414.1 | 60 |  | 40 |  | 06/28/2022 | 06/28/2022 |  | 2022-11-08T12:05:05.807 | Burrell, Bianca | FRM
22-0554-ER | WO0004, Complete | carpenter | 2022-06-28T16:15:11.000 | WO | 0 | 1656.38 | 25 | 1656.38 | 100 |  | 0 |  | 09/28/2022 | 09/30/2022 |  | 2022-11-08T12:05:05.823 | Burrell, Bianca | STR
22-0767-IR | WO0002, Complete | House and Garage Labor | 2022-09-30T10:00:30.000 | WO | 0 | 4999.9973 | 66.77 | 9479.89 | 5000 |  | 47.2568 |  | 09/30/2022 | 10/10/2022 |  | 2022-10-13T11:51:46.280 | Hicks, Dave | RFG
22-0767-IR | WO0005 | USR | 2022-09-30T10:00:31.037 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | USR
22-0767-IR | WO0006, Complete | Materials | 2022-09-30T10:01:00.000 | WO | 0 | 2928.11 | 8 | 2928.11 | 100 |  | 0 |  | 09/30/2022 | 09/30/2022 |  | 2022-10-10T15:34:52.897 | Hicks, Dave
22-0767-IR | WO0007, Complete | Window and Door Materials | 2022-09-30T10:05:00.000 | WO | 0 | 208.61 | 8 | 208.61 | 100 |  | 0 |  | 09/30/2022 | 09/30/2022 |  | 2022-10-10T15:35:13.503 | Hicks, Dave
22-0767-IR | WO0008, Complete | Gutter Materials | 2022-09-30T10:07:00.000 | WO | 0 | 107.22 | 8 | 107.22 | 100 |  | 0 |  | 09/30/2022 | 09/30/2022 |  | 2022-10-10T15:35:28.913 | Hicks, Dave
22-0915-ER
22-0757-IR
22-0846-IR | WO0001, Complete | CON | 2022-08-29T15:55:16.423 | WO | 0 | 139.65 | 2.2 | 139.65 | 100 |  | 0 |  | 08/29/2022 | 08/29/2022 |  | 2022-10-17T08:24:59.427 | Trevino, Jeovani | CON
22-0846-IR | WO00010, Complete | Labor | 2023-02-07T14:35:00.000 | WO | 0 | 1178.6993 | 27.73 | 2428.14 | 1178.7 |  | 51.4567 |  | 02/07/2023 | 08/30/2022 |  | 2023-02-07T13:50:18.633 | Trevino, Jeovani | inhouse labor
22-0846-IR | WO00011, Complete | material | 2023-02-07T14:40:00.000 | WO | 0 | 277.9301 | 8 | 419.45 | 277.93 |  | 33.7394 |  | 02/07/2023 | 02/07/2023 |  | 2023-02-07T13:50:18.680 | Trevino, Jeovani | material
22-0248-IR | WO0002, Complete | CON | 2022-09-27T09:33:18.000 | WO | 0 | 100.436 | 4 | 251.09 | 40 |  | 60 |  | 09/27/2022 | 09/27/2022 |  | 2022-12-11T19:09:22.460 | Burrell, Bianca | CON
22-0248-IR | WO0003, Complete | Drywall & Paint | 2022-09-27T09:33:19.000 | WO | 0 | 912.26 | 15.07 | 2280.65 | 40 |  | 60 |  | 09/27/2022 | 09/27/2022 |  | 2022-12-11T19:09:22.433 | Burrell, Bianca | DRY
22-0248-IR | WO0005, Complete | FNC | 2022-09-27T09:33:19.000 | WO | 0 | 279.28 | 12.12 | 698.2 | 40 |  | 60 |  | 12/07/2022 | 12/08/2022 |  | 2022-12-11T19:09:22.453 | Burrell, Bianca | FNC
22-0248-IR | WO0008, Complete | Carpet - Completed by Homeowner | 2022-09-27T09:37:00.000 | WO | 0 | 0 | 15.47 | 3088.64 | 0 |  | 100 |  | 09/27/2022 | 09/27/2022 |  | 2022-12-11T19:09:22.450 | Burrell, Bianca
22-0902-RET-IR | WO0001, Complete | Dumpster | 2022-06-16T09:10:30.000 | WO | 0 | 0 | 1.98 | 227.91 | 0 |  | 100 |  | 06/16/2022 | 06/16/2022 |  | 2022-10-21T12:36:24.373 | Dehnke, Josh | DMO
22-0902-RET-IR | WO0002, Complete | Drywall, Paint, Insulation, Vapor barrier | 2022-06-16T09:10:30.000 | WO | 0 | 824.275 | 4.08 | 1648.55 | 50 |  | 50 |  | 06/16/2022 | 06/16/2022 |  | 2022-10-21T12:36:24.357 | Dehnke, Josh | DRY
22-0902-RET-IR | WO0006, Complete | Roof labor | 2022-06-16T09:10:31.000 | WO | 0 | 938.172 | 4.72 | 1563.62 | 60 |  | 40 |  | 06/16/2022 | 06/16/2022 |  | 2022-10-21T12:36:24.357 | Dehnke, Josh | RFG
22-0902-RET-IR | WO0007 | Downspout and Screens | 2022-06-16T09:10:31.000 | WO | 0 | 355.565 | 1.62 | 711.13 | 50 |  | 50 |  | 06/16/2022 | 06/16/2022 |  |  |  | SFG
22-0688-IR | WO0001, Complete | CLN | 2022-09-21T16:15:38.760 | WO | 0 | 261.22 | 0.72 | 261.22 | 100 |  | 0 |  | 09/21/2022 | 09/21/2022 |  | 2023-02-20T11:00:02.643 | Trevino, Jeovani | CLN
22-0688-IR | WO0002, Complete | DRY labor | 2022-09-21T16:15:39.000 | WO | 0 | 750.0002 | 8.48 | 1263.32 | 750 |  | 40.6326 |  | 09/21/2022 | 09/21/2022 |  | 2022-10-17T08:06:12.850 | Trevino, Jeovani | DRY
22-0688-IR | WO0006, Complete | PLM | 2022-09-21T16:15:39.527 | WO | 0 | 1977.57 |  | 1977.57 | 100 |  | 0 |  |  |  |  | 2023-01-02T09:17:36.093 | Trevino, Jeovani | PLM
22-0688-IR | WO0008, Complete | drywall materials | 2022-10-20T10:26:00.000 | WO | 0 | 924.09 | 8 | 924.09 | 100 |  | 0 |  | 10/20/2022 | 10/20/2022 |  | 2022-12-20T12:17:43.003 | Trevino, Jeovani | Drywall materials
22-0688-IR | WO0009, Complete | shower materials | 2022-12-01T19:04:00.000 | WO | 0 | 1693.1905 | 8 | 1607.35 | 1693.19 |  | -5.3405 |  | 12/01/2022 | 12/01/2022 |  | 2023-01-02T09:17:36.153 | Trevino, Jeovani | shower materials
22-0688-IR | WO00010, Complete | shower labor | 2022-12-20T13:13:00.000 | WO | 0 | 900.0005 | 16.08 | 1498.43 | 900 |  | 39.9371 |  | 09/21/2022 | 12/20/2022 |  | 2023-01-02T09:17:36.107 | Trevino, Jeovani | shower unit instalment
22-0843-ER-ER | WO0001, Complete | APP | 2022-08-19T11:22:37.200 | WO | 0 | 351.83 | 1.43 | 351.83 | 100 |  | 0 |  | 08/19/2022 | 08/19/2022 |  | 2022-10-17T08:14:55.773 | Trevino, Jeovani | APP
22-0843-ER-ER | WO0002, Complete | CAB | 2022-08-19T11:22:37.513 | WO | 0 | 389.6156 |  | 1499.25 | 25.9874 |  | 74.0126 |  |  |  |  | 2022-10-24T08:43:30.263 | Trevino, Jeovani | CAB
22-0843-ER-ER | WO0003, Complete | CON | 2022-08-19T11:22:37.670 | WO | 0 | 276.36 | 4.4 | 276.36 | 100 |  | 0 |  | 08/19/2022 | 08/19/2022 |  | 2022-10-17T08:14:55.693 | Trevino, Jeovani | CON
22-0843-ER-ER | WO0004, Complete | DMO | 2022-08-19T11:22:37.763 | WO | 0 | 560.08 |  | 560.08 | 100 |  | 0 |  |  |  |  | 2022-10-17T08:14:55.740 | Trevino, Jeovani | DMO
22-0843-ER-ER | WO0006, Complete | FCS | 2022-08-19T11:22:38.013 | WO | 0 | 238.17 | 0.97 | 238.17 | 100 |  | 0 |  | 08/19/2022 | 08/19/2022 |  | 2023-01-03T13:27:20.710 | Dehnke, Josh | FCS
22-0843-ER-ER | WO0007, Complete | FCT | 2022-08-19T11:22:38.173 | WO | 0 | 295.84 |  | 295.84 | 100 |  | 0 |  |  |  |  | 2023-01-03T13:27:20.727 | Dehnke, Josh | FCT
22-0843-ER-ER | WO0008, Complete | FNC | 2022-08-19T11:22:38.297 | WO | 0 | 37.64 |  | 37.64 | 100 |  | 0 |  |  |  |  | 2023-02-20T10:50:27.823 | Trevino, Jeovani | FNC
22-0843-ER-ER | WO0009, Complete | HVC | 2022-08-19T11:22:38.483 | WO | 0 | 53.83 | 0.3 | 53.83 | 100 |  | 0 |  | 08/19/2022 | 08/19/2022 |  | 2023-01-03T13:27:20.760 | Dehnke, Josh | HVC
22-0843-ER-ER | WO00010, Complete | INS | 2022-08-19T11:22:38.640 | WO | 0 | 27.94 | 0.17 | 27.94 | 100 |  | 0 |  | 08/19/2022 | 08/19/2022 |  | 2023-01-03T13:27:20.773 | Dehnke, Josh | INS
22-0843-ER-ER | WO00011, Complete | LIT | 2022-08-19T11:22:38.830 | WO | 0 |  |  |  | 0 |  | 0 |  |  |  |  | 2023-02-20T10:50:27.953 | Trevino, Jeovani | LIT
22-0843-ER-ER | WO00012, Complete | MPR | 2022-08-19T11:22:38.940 | WO | 0 | 42.26 | 0.33 | 42.26 | 100 |  | 0 |  | 08/19/2022 | 08/19/2022 |  | 2023-02-20T10:50:27.863 | Trevino, Jeovani | MPR
22-0843-ER-ER | WO00013, Complete | PLM | 2022-08-19T11:22:39.067 | WO | 0 | 473.73 | 1.92 | 473.73 | 100 |  | 0 |  | 08/19/2022 | 08/19/2022 |  | 2023-01-03T13:27:20.773 | Dehnke, Josh | PLM
22-0843-ER-ER | WO00015, Complete | TIL | 2022-08-19T11:22:39.483 | WO | 0 | 921.01 |  | 921.01 | 100 |  | 0 |  |  |  |  | 2022-10-17T08:14:55.630 | Trevino, Jeovani | TIL
22-0843-ER-ER | WO00016, Complete | Drywall and Paint | 2022-09-08T17:15:00.000 | WO | 0 | 2699.9989 | 36.58 | 4150.39 | 2700 |  | 34.9459 |  | 08/19/2022 | 09/08/2022 |  | 2022-09-19T13:38:24.647 | Trevino, Jeovani | Leo
22-0843-ER-ER | WO00017, Complete | Beacon | 2022-10-25T17:46:00.000 | WO | 0 | 1700 | 41.9 | 5060.37 | 1700 |  | 66.4056 |  | 08/19/2022 | 10/25/2022 |  | 2023-01-02T09:15:05.847 | Trevino, Jeovani | beacon labor
22-0843-ER-ER | WO00018, Complete | marlon | 2023-02-13T16:36:00.000 | WO | 0 | 350 | 10.17 | 255.47 | 350 |  | -37.0024 |  | 02/13/2023 | 08/19/2022 |  | 2023-02-20T10:50:27.973 | Trevino, Jeovani | counter top install
22-0845-IR | WO0003, Complete | Materials | 2022-12-09T11:05:00.000 | WO | 0 | 353.81 | 8 | 353.81 | 100 |  | 0 |  | 12/09/2022 | 12/09/2022 |  | 2023-01-23T09:32:28.587 | Olson, Jonathon | Materials
22-0845-IR | WO0004, Complete | Labor | 2022-12-09T11:05:00.000 | WO | 0 | 1357.224 | 23.6 | 3393.06 | 40 |  | 60 |  | 12/05/2022 | 12/09/2022 |  | 2023-01-23T09:32:28.603 | Olson, Jonathon | Labor
22-0868-IR | WO0001, Complete | CON | 2022-09-29T09:09:51.000 | WO | 0 | 1069.488 | 28 | 1782.48 | 60 |  | 40 |  | 09/29/2022 | 10/04/2022 |  | 2022-10-24T09:56:44.833 | Burrell, Bianca | CON
22-0868-IR | WO0002, Complete | Paint (base & trim) | 2022-09-29T09:09:51.000 | WO | 0 | 458 | 31.02 | 1145 | 40 |  | 60 |  | 12/13/2022 | 12/16/2022 |  | 2022-12-19T12:10:10.447 | Burrell, Bianca | DRY
22-0868-IR | WO0003, Complete | Carpet - Labor | 2022-09-29T09:09:51.000 | WO | 0 | 1856.82 | 40.5 | 3094.7 | 60 |  | 40 |  | 12/12/2022 | 12/16/2022 |  | 2022-12-19T12:10:10.427 | Burrell, Bianca | FCC
22-0868-IR | WO0004, Complete | Vinyl - Labor | 2022-09-29T09:09:52.000 | WO | 0 | 212.744 | 40.12 | 531.86 | 40 |  | 60 |  | 12/12/2022 | 12/16/2022 |  | 2022-12-19T12:10:10.473 | Burrell, Bianca | FCV
22-0868-IR | WO0005, Complete | Finish Carpentry | 2022-09-29T09:09:52.000 | WO | 0 | 651.376 | 36.57 | 1628.44 | 40 |  | 60 |  | 12/12/2022 | 12/16/2022 |  | 2022-12-19T12:10:10.493 | Burrell, Bianca | FNC
22-0868-IR | WO0007, Complete | Paint & Drywall | 2022-09-29T09:09:53.000 | WO | 0 | 1549.524 | 34.45 | 3873.81 | 40 |  | 60 |  | 11/01/2022 | 11/04/2022 |  | 2022-11-01T11:08:31.070 | Burrell, Bianca | PNT
22-0868-IR | WO0009, Complete | Vinyl - Material | 2022-10-09T21:33:00.000 | WO | 0 | 334.602 | 44 | 557.67 | 60 |  | 40 |  | 11/14/2022 | 11/18/2022 |  | 2022-11-15T04:47:49.110 | Burrell, Bianca
22-0868-IR | WO00010, Complete | Carpet - Material LR/BED/BHALL/OFFICE | 2022-10-09T21:41:00.000 | WO | 0 | 0 | 33.39 | 0 | 0 |  | 0 |  | 11/15/2022 | 11/18/2022 |  | 2022-11-15T04:47:49.247 | Burrell, Bianca
22-0868-IR | WO00011, Complete | Carpet Materials | 2022-11-29T12:12:00.000 | WO | 0 | 4751.2009 | 20.5 | 6709.39 | 4751.2 |  | 29.1858 |  | 12/04/2022 | 12/06/2022 |  | 2022-12-11T19:28:45.757 | Burrell, Bianca | CPT
22-0868-IR | WO00012, Complete | Trim - George | 2022-12-12T08:50:00.000 | WO | 0 | 233.92 | 34 | 584.8 | 40 |  | 60 |  | 12/13/2022 | 12/16/2022 |  | 2022-12-19T12:10:10.513 | Burrell, Bianca
22-0868-IR | WO00013, Complete | Change Order | 2023-01-03T11:54:00.000 | WO | 0 | 4404 | 8 | 4404 | 100 |  | 0 |  | 01/03/2023 | 01/03/2023 |  | 2023-01-03T10:55:26.197 | Dehnke, Josh | CO
22-0902-IR | WO0002, Complete | CAB | 2022-09-29T09:18:08.000 | WO | 0 | 1897.064 | 51.4 | 4742.66 | 40 |  | 60 |  | 11/08/2022 | 11/15/2022 |  | 2022-11-15T04:43:16.230 | Burrell, Bianca | CAB
22-0902-IR | WO0004, Complete | DRY | 2022-09-29T09:18:08.000 | WO | 0 | 277.776 | 48.93 | 694.44 | 40 |  | 60 |  | 11/08/2022 | 11/15/2022 |  | 2022-11-15T04:43:16.433 | Burrell, Bianca | DRY
22-0902-IR | WO0005, Complete | ELE | 2022-09-29T09:18:08.000 | WO | 0 | 406.35 | 0.72 | 406.35 | 100 |  | 0 |  | 11/23/2022 | 11/23/2022 |  | 2022-11-22T12:44:52.633 | Burrell, Bianca | ELE
22-0902-IR | WO0006, Complete | Floor Removal | 2022-09-29T09:18:09.000 | WO | 0 | 1369.41 | 38.07 | 2282.35 | 60 |  | 40 |  | 09/29/2022 | 10/26/2022 |  | 2022-10-24T09:27:29.513 | Burrell, Bianca | FCR
22-0902-IR | WO0007, Complete | Vinyl Tile - Material | 2022-09-29T09:18:09.000 | WO | 0 | 311.268 | 4.59 | 469.41 | 66.3105 |  | 33.6895 |  | 10/24/2022 | 10/24/2022 |  | 2022-10-24T09:27:29.543 | Burrell, Bianca | FCV
22-0902-IR | WO0008, Complete | Wood Floor & Vinyl Install | 2022-09-29T09:18:09.000 | WO | 0 | 1349.9992 | 26.74 | 1792.78 | 1350 |  | 24.698 |  | 10/24/2022 | 10/27/2022 |  | 2022-10-24T09:27:29.570 | Burrell, Bianca | FCW
22-0902-IR | WO0009, Complete | FNC | 2022-09-29T09:18:09.000 | WO | 0 | 216.824 | 2.6 | 542.06 | 40 |  | 60 |  | 01/12/2023 | 01/12/2023 |  | 2023-01-16T20:34:02.673 | Burrell, Bianca | FNC
22-0902-IR | WO00011, Complete | Kitchen PLB Reset | 2022-09-29T09:18:09.000 | WO | 0 | 381.416 | 48.8 | 953.54 | 40 |  | 60 |  | 11/08/2022 | 11/15/2022 |  | 2022-11-15T04:43:52.497 | Burrell, Bianca | PLM
22-0902-IR | WO00012, Complete | Stain - Base & QTR | 2022-09-29T09:18:10.000 | WO | 0 | 169.76 | 48.33 | 424.4 | 40 |  | 60 |  | 11/08/2022 | 11/15/2022 |  | 2022-11-15T04:43:16.543 | Burrell, Bianca | PNT
22-0902-IR | WO00013, Complete | W//D Detach | 2022-09-29T09:18:10.000 | WO | 0 | 94.476 | 1.62 | 236.19 | 40 |  | 60 |  | 09/29/2022 | 09/29/2022 |  | 2022-11-15T04:43:16.510 | Burrell, Bianca | WTR
22-0902-IR | WO00014, Complete | Floor Covering Wood - Material | 2022-10-13T12:56:00.000 | WO | 0 | 2377.7097 | 8 | 3104.7 | 2377.71 |  | 23.4158 |  | 10/14/2022 | 10/14/2022 |  | 2022-10-14T14:17:52.150 | Burrell, Bianca
22-0902-IR | WO00015, Complete | Wood Floor Sanding | 2022-10-13T13:06:00.000 | WO | 0 | 1784.293 | 38.67 | 2548.99 | 70 |  | 30 |  | 10/23/2022 | 10/27/2022 |  | 2022-11-08T08:06:45.507 | Burrell, Bianca
22-0902-IR | WO00016, Complete | Sub Floor Replacement | 2022-10-13T13:59:00.000 | WO | 0 | 159.616 | 52 | 399.04 | 40 |  | 60 |  | 11/08/2022 | 11/15/2022 |  | 2022-11-15T04:43:16.573 | Burrell, Bianca
22-0752-IR | WO0002, Complete | DRY Labor | 2022-09-21T16:03:33.000 | WO | 0 | 2500.0019 | 36.03 | 4160.99 | 2500 |  | 39.9181 |  | 09/21/2022 | 09/23/2022 |  | 2022-10-17T08:04:46.013 | Trevino, Jeovani | DRY
22-0752-IR | WO0003, Complete | FCC | 2022-09-21T16:03:33.000 | WO | 0 | 63.546 |  | 105.91 | 60 |  | 40 |  |  |  |  | 2022-12-28T09:09:43.243 | Trevino, Jeovani | FCC
22-0752-IR | WO0008, Complete | flooring material | 2022-10-02T11:39:00.000 | WO | 0 | 5197.0704 | 8 | 4572.31 | 5197.07 |  | -13.664 |  | 10/02/2022 | 10/02/2022 |  | 2022-10-02T10:48:36.997 | Trevino, Jeovani | flooring material
22-0752-IR | WO0009, Complete | material | 2022-10-20T10:12:00.000 | WO | 0 | 338.48 | 8 | 338.48 | 100 |  | 0 |  | 10/20/2022 | 10/20/2022 |  | 2022-12-28T09:09:24.533 | Trevino, Jeovani | material
22-0752-IR | WO00010, Complete | george carpet | 2022-12-21T16:16:00.000 | WO | 0 | 905.0003 | 20.28 | 1511.46 | 905 |  | 40.1241 |  | 09/21/2022 | 12/21/2022 |  | 2022-12-28T09:09:04.020 | Trevino, Jeovani | george carpet
22-0687-IR | WO0003, Complete | Dumpster | 2022-09-21T14:02:58.000 | WO | 0 | 420.06 |  | 560.08 | 75 |  | 25 |  |  |  |  | 2022-10-17T09:10:52.253 | Dehnke, Josh | DMO
22-0687-IR | WO0004, Complete | Inso Drywall and paint | 2022-09-21T14:02:58.000 | WO | 0 | 1451.254 | 19.12 | 4119.14 | 35.232 |  | 64.768 |  | 10/03/2022 | 12/16/2022 |  | 2022-10-17T09:10:52.160 | Dehnke, Josh | DRY
22-0687-IR | WO0005, Complete | Cabinets Flooring trim | 2022-09-21T14:02:58.000 | WO | 0 | 3200 | 20.24 | 3346.54 | 3200 |  | 4.3789 |  | 10/04/2022 | 12/19/2022 |  | 2022-12-13T10:27:47.230 | Hicks, Dave | FCW
22-0687-IR | WO0008, Complete | Plumbing | 2022-09-21T14:02:58.000 | WO | 0 | 1892.9997 | 11.1 | 730.34 | 1893 |  | -159.1943 |  | 11/21/2022 | 11/22/2022 |  | 2023-01-20T08:23:27.367 | Hicks, Dave | PLM
22-0687-IR | WO00010, Complete | Cabinet Materials | 2022-09-21T14:05:00.000 | WO | 0 | 0 | 0.7 | 0 | 0 |  | 0 |  | 10/04/2022 | 10/04/2022 |  | 2022-10-17T09:10:51.973 | Dehnke, Josh | cab
22-0687-IR | WO00011, Complete | Flooring Materials | 2022-09-21T14:06:00.000 | WO | 0 | 576.608 | 8 | 720.76 | 80 |  | 20 |  | 10/04/2022 | 10/04/2022 |  | 2022-10-04T12:48:39.547 | Hicks, Dave | Flooring
22-0687-IR | WO00012, Complete | Materials | 2022-09-21T14:08:00.000 | WO | 0 | 678.27 | 8 | 678.27 | 100 |  | 0 |  | 10/04/2022 | 10/04/2022 |  | 2022-10-04T12:48:39.513 | Hicks, Dave | Materials
22-0687-IR | WO00013, Complete | Countertop | 2022-12-12T20:05:00.000 | WO | 0 | 699.999 | 40.6 | 2065.04 | 700 |  | 66.1024 |  | 12/12/2022 | 12/16/2022 |  | 2023-01-03T09:10:28.240 | Hicks, Dave
22-0687-IR | WO00014, Complete | Cabinet Materials | 2023-01-03T15:11:00.000 | WO | 0 | 5850.3 | 8 | 5850.3 | 100 |  | 0 |  | 01/03/2023 | 01/03/2023 |  | 2023-01-03T14:12:54.223 | Dehnke, Josh | CAB
22-0818-IR | WO0003, Complete | Drywall and Paint Labor | 2022-08-17T10:54:56.000 | WO | 0 | 2399.505 | 44.54 | 4799.01 | 50 |  | 50 |  | 08/17/2022 | 08/26/2022 |  | 2022-10-21T11:57:04.853 | Dehnke, Josh | DRY
22-0818-IR | WO0006, Complete | Plank flooring and Carpet Labor | 2022-08-17T10:54:56.000 | WO | 0 | 1799.9989 | 26.9 | 2615.54 | 1800 |  | 31.1806 |  | 08/17/2022 | 08/24/2022 |  | 2023-01-16T08:08:46.103 | Dehnke, Josh | FCV
22-0818-IR | WO0008, Complete | Finish Carpentry Labor | 2022-08-17T10:54:57.000 | WO | 0 | 499.9997 | 10.22 | 1405.2 | 500 |  | 64.4179 |  | 08/17/2022 | 08/17/2022 |  | 2022-12-16T10:06:42.267 | Dehnke, Josh | FNC
22-0818-IR | WO00012, Complete | Pumbing Labor, Tub and Toilet | 2022-08-17T10:54:57.000 | WO | 0 | 1669.48 | 9.07 | 3338.96 | 50 |  | 50 |  | 08/17/2022 | 08/18/2022 |  | 2022-12-16T10:06:42.283 | Dehnke, Josh | PLM
22-0818-IR | WO00014, Complete | Tile Labor | 2022-08-17T10:54:57.000 | WO | 0 | 999.9997 | 15.63 | 2475.21 | 1000 |  | 59.5994 |  | 08/17/2022 | 08/18/2022 |  | 2022-12-16T10:06:42.283 | Dehnke, Josh | TIL
22-0818-IR | WO00015, Complete | Materials | 2022-08-24T09:05:00.000 | WO | 0 | 2489.4319 | 8 | 3715.57 | 67 |  | 33 |  | 08/24/2022 | 08/24/2022 |  | 2022-10-21T11:57:04.883 | Dehnke, Josh | MAT
22-0818-IR | WO00016, Complete | LVP Materials | 2022-08-24T09:15:00.000 | WO | 0 | 1418.1153 | 8 | 2116.59 | 67 |  | 33 |  | 08/24/2022 | 08/24/2022 |  | 2022-10-21T11:57:04.917 | Dehnke, Josh | LVP
22-0818-IR | WO00017, Complete | Tile Materials | 2022-10-18T12:50:00.000 | WO | 0 | 665.6115 | 8 | 993.45 | 67 |  | 33 |  | 10/18/2022 | 10/18/2022 |  | 2022-10-21T11:57:04.957 | Dehnke, Josh | TIL
22-0818-IR | WO00018, Complete | Insulation, Drywall Partial Labor | 2022-12-08T10:20:00.000 | WO | 0 | 1897.5536 | 27.03 | 2693.88 | 70.4394 |  | 29.5606 |  | 08/17/2022 | 12/08/2022 |  | 2022-12-16T10:06:42.313 | Dehnke, Josh | INS
22-0858-IR | WO0001, Complete | washer and dryer | 2022-09-09T09:26:59.000 | WO | 0 | 184.99 | 1.12 | 184.99 | 100 |  | 0 |  | 09/09/2022 | 09/09/2022 |  | 2022-10-17T08:53:18.127 | Dehnke, Josh | APP
22-0858-IR | WO0002, Complete | Contents | 2022-09-09T09:27:00.000 | WO | 0 | 92.65 | 1.47 | 92.65 | 100 |  | 0 |  | 09/09/2022 | 09/09/2022 |  | 2022-10-17T08:53:18.143 | Dehnke, Josh | CON
22-0858-IR | WO0003, Complete | Drywall and Paint | 2022-09-09T09:27:00.000 | WO | 0 | 1700 | 28.32 | 2287.97 | 1700 |  | 25.6983 |  | 09/29/2022 | 10/02/2022 |  | 2022-10-17T08:53:18.157 | Dehnke, Josh | DRY
22-0858-IR | WO0004 | Carpentry | 2022-09-09T09:27:00.000 | WO | 0 | 275.68 | 0.42 | 275.68 | 100 |  | 0 |  | 09/09/2022 | 09/09/2022 |  |  |  | FNC
22-0858-IR | WO0005 | Caulking | 2022-09-09T09:27:00.000 | WO | 0 | 86.59 | 0.77 | 86.59 | 100 |  | 0 |  | 09/09/2022 | 09/09/2022 |  |  |  | MPR
22-0858-IR | WO0006, Complete | Plumbing | 2022-09-09T09:27:00.000 | WO | 0 | 466.53 | 0 | 466.53 | 100 |  | 0 |  | 09/09/2022 | 09/09/2022 |  | 2022-10-17T08:53:18.190 | Dehnke, Josh | PLM
22-0858-IR | WO0007, Complete | Materials | 2022-09-23T13:34:00.000 | WO | 0 | 223.8555 | 8 | 286.56 | 78.1182 |  | 21.8818 |  | 09/23/2022 | 09/23/2022 |  | 2022-09-23T12:36:15.210 | Dehnke, Josh | MAT
22-0262-IR | WO0001, Complete | CON | 2022-09-28T11:10:06.197 | WO | 0 | 464.14 | 8.8 | 464.14 | 100 |  | 0 |  | 09/28/2022 | 09/29/2022 |  | 2022-10-24T09:40:39.653 | Burrell, Bianca | CON
22-0262-IR | WO0002, Complete | DOR | 2022-09-28T11:10:06.397 | WO | 0 | 45.81 | 0.42 | 45.81 | 100 |  | 0 |  | 09/28/2022 | 09/28/2022 |  | 2022-10-31T10:58:36.410 | Dehnke, Josh | DOR
22-0262-IR | WO0003, Complete | Drywall & Paint | 2022-09-28T11:10:06.000 | WO | 0 | 4530.282 | 28.6 | 7550.47 | 60 |  | 40 |  | 10/24/2022 | 10/27/2022 |  | 2022-10-24T09:40:23.047 | Burrell, Bianca | DRY
22-0262-IR | WO0004, Complete | FNC | 2022-09-28T11:10:06.000 | WO | 0 | 116.172 | 1.75 | 193.62 | 60 |  | 40 |  | 09/28/2022 | 09/28/2022 |  | 2022-10-31T10:58:36.440 | Dehnke, Josh | FNC
22-0262-IR | WO0005, Complete | INS | 2022-09-28T11:10:06.000 | WO | 0 | 63.912 | 45.55 | 106.52 | 60 |  | 40 |  | 10/17/2022 | 10/24/2022 |  | 2022-10-24T09:40:27.037 | Burrell, Bianca | INS
22-0262-IR | WO0006, Complete | LIT | 2022-09-28T11:10:07.013 | WO | 0 | 339.44 | 2.13 | 339.44 | 100 |  | 0 |  | 09/28/2022 | 09/28/2022 |  | 2022-10-31T10:58:36.457 | Dehnke, Josh | LIT
22-0619-IR | WO0007, Complete | Contents | 2022-08-22T11:04:53.000 | WO | 0 | 200.0001 | 8 | 494.98 | 200 |  | 59.5943 |  | 08/22/2022 | 08/22/2022 |  | 2022-09-02T10:50:03.227 | Deville , Jard | CON
22-0619-IR | WO0008, Complete | Drywall and paint/jost | 2022-08-22T11:04:53.000 | WO | 0 | 1991.8708 | 29.23 | 4256.68 | 1991.87 |  | 53.206 |  | 08/22/2022 | 08/24/2022 |  | 2022-08-22T10:11:22.860 | Deville , Jard | DRY
22-0619-IR | WO0009, Complete | Carpet Labor | 2022-08-22T11:04:53.000 | WO | 0 | 1300.0005 | 8.97 | 1300.02 | 1300 |  | 0.0015 |  | 08/22/2022 | 08/23/2022 |  | 2022-09-02T10:50:03.163 | Deville , Jard | FCC
22-0619-IR | WO00010, Complete | Carpenter | 2022-08-22T11:04:53.000 | WO | 0 | 307.2403 | 12.67 | 1487.4 | 307.24 |  | 79.3438 |  | 09/06/2022 | 09/07/2022 |  | 2022-09-08T14:20:58.857 | Deville , Jard | FNC
22-0619-IR | WO00011, Complete | Carpet Materials | 2022-08-22T11:08:00.000 | WO | 0 | 1963.63 | 8 | 3330.51 | 1963.63 |  | 41.0412 |  | 08/22/2022 | 08/22/2022 |  | 2022-08-22T10:11:26.257 | Deville , Jard | Carpet Materials
22-0778-IR | WO0001, Complete | CON | 2022-09-23T12:40:46.000 | WO | 0 | 125.54 | 38 | 125.54 | 100 |  | 0 |  | 11/07/2022 | 11/11/2022 |  | 2022-11-14T09:16:59.197 | Burrell, Bianca | CON
22-0778-IR | WO0002, Complete | Drywall & Paint | 2022-09-23T12:40:46.000 | WO | 0 | 1127.997 | 11.99 | 1735.38 | 65 |  | 35 |  | 09/23/2022 | 09/23/2022 |  | 2022-10-18T16:48:18.750 | Burrell, Bianca | DRY
22-0778-IR | WO0003, Complete | ELE | 2022-09-23T12:40:46.000 | WO | 0 | 82.3 | 27.52 | 82.3 | 100 |  | 0 |  | 11/10/2022 | 11/15/2022 |  | 2022-11-14T09:18:38.577 | Burrell, Bianca | ELE
22-0778-IR | WO0005, Complete | INS | 2022-09-23T12:40:47.390 | WO | 0 | 327.43 | 0.77 | 327.43 | 100 |  | 0 |  | 09/23/2022 | 09/23/2022 |  | 2022-10-24T09:24:42.520 | Burrell, Bianca | INS
22-0778-IR | WO0006 | LIT | 2022-09-23T12:40:47.620 | WO | 0 | 302.68 | 1.91 | 302.68 | 100 |  | 0 |  | 09/23/2022 | 09/23/2022 |  |  |  | LIT
22-0843-EST
22-0827-ER
22-0395-C
22-0813-IR | WO0001, Complete | Veneer Brick Materials | 2022-07-13T12:54:00.000 | WO | 0 | 1350 | 8 | 1687.5 | 80 |  | 20 |  | 07/15/2022 | 07/15/2022 |  | 2022-07-15T14:11:11.440 | Dehnke, Josh | FNC
22-0813-IR | WO0002, Complete | Veneer Brick Labor | 2022-07-13T12:55:00.000 | WO | 0 | 500.0001 | 8 | 562.5 | 500 |  | 11.1111 |  | 07/25/2022 | 07/25/2022 |  | 2022-09-28T08:41:05.910 | Dehnke, Josh | FNC
22-0813-IR | WO0003, Complete | Metal Materials | 2022-07-13T12:56:00.000 | WO | 0 | 408 | 8 | 510 | 80 |  | 20 |  | 07/15/2022 | 07/15/2022 |  | 2022-07-15T14:11:11.423 | Dehnke, Josh | FNC
22-0813-IR | WO0004, Complete | Metal Labor | 2022-07-13T12:56:00.000 | WO | 0 | 170 | 8 | 340 | 50 |  | 50 |  | 07/15/2022 | 07/15/2022 |  | 2022-07-15T14:11:11.470 | Dehnke, Josh | FNC
22-0469-ER | WO0001, Complete | Cleaning | 2022-08-26T10:37:34.000 | WO | 0 | 215.55 | 2.9 | 215.55 | 100 |  | 0 |  | 08/26/2022 | 08/26/2022 |  | 2022-09-19T07:49:58.030 | Dehnke, Josh | CLN
22-0469-ER | WO0002, Complete | Content | 2022-08-26T10:37:34.000 | WO | 0 | 494.98 | 8 | 494.98 | 100 |  | 0 |  | 08/26/2022 | 08/26/2022 |  | 2022-09-19T07:49:58.047 | Dehnke, Josh | CON
22-0469-ER | WO0004, Complete | Framing/Drywall/Insulation | 2022-08-26T10:37:34.000 | WO | 0 | 9968.7108 | 18 | 16360.87 | 9968.71 |  | 39.0698 |  | 09/07/2022 | 09/09/2022 |  | 2022-09-19T07:49:58.063 | Dehnke, Josh | FRM
22-0857-IR | WO0002, Complete | Haul Debris | 2022-09-23T14:09:26.000 | WO | 0 | 228.75 | 1.98 | 228.75 | 100 |  | 0 |  | 09/23/2022 | 09/23/2022 |  | 2022-10-17T09:00:34.277 | Dehnke, Josh | DMO
22-0857-IR | WO0003, Complete | Garage Door Labor | 2022-09-23T14:09:27.000 | WO | 0 | 494.78 | 4.25 | 494.78 | 100 |  | 0 |  | 09/23/2022 | 09/23/2022 |  | 2022-10-17T09:00:34.307 | Dehnke, Josh | DOR
22-0857-IR | WO00010 | PNT | 2022-09-23T14:09:28.050 | WO | 0 | 122.13 | 0.83 | 122.13 | 100 |  | 0 |  | 09/23/2022 | 09/23/2022 |  |  |  | PNT
22-0857-IR | WO00011 | SDG | 2022-09-23T14:09:28.130 | WO | 0 | 652.54 | 3.4 | 652.54 | 100 |  | 0 |  | 09/23/2022 | 09/23/2022 |  |  |  | SDG
22-0857-IR | WO00013, Complete | Materials | 2022-09-23T14:09:00.000 | WO | 0 | 717.1 | 8 | 717.1 | 100 |  | 0 |  | 09/23/2022 | 09/23/2022 |  | 2022-10-17T09:00:34.323 | Dehnke, Josh | MAT
22-0857-IR | WO00014, Complete | Labor | 2022-09-30T13:07:00.000 | WO | 0 | 3633.6 | 35.23 | 3633.6 | 100 |  | 0 |  | 09/23/2022 | 09/30/2022 |  | 2022-10-17T09:00:34.340 | Dehnke, Josh
22-0014-RET-ER | WO0005, Complete | Drywall/ Painting Materials | 2022-09-21T15:37:16.000 | WO | 0 | 259.11 |  | 575.8 | 45 |  | 55 |  |  |  |  | 2022-10-21T13:38:15.273 | Dehnke, Josh | DRY
22-0014-RET-ER | WO0006, Complete | Carpet/Pad Labor | 2022-09-21T15:37:16.000 | WO | 0 | 1499.9994 | 12.81 | 7574.76 | 1500 |  | 80.1974 |  | 09/21/2022 | 09/22/2022 |  | 2022-11-18T07:27:00.450 | Hicks, Dave | FCC
22-0014-RET-ER | WO0007, Complete | Tile Materials | 2022-09-21T15:37:16.000 | WO | 0 | 213.246 |  | 355.41 | 60 |  | 40 |  |  |  |  | 2022-10-21T13:38:15.327 | Dehnke, Josh | FCT
22-0014-RET-ER | WO00012, Complete | Plumbing | 2022-09-21T15:37:17.000 | WO | 0 | 281.156 | 11.63 | 702.89 | 40 |  | 60 |  | 11/21/2022 | 11/22/2022 |  | 2022-11-29T14:10:03.837 | Hicks, Dave | PLM
22-0014-RET-ER | WO00013, Complete | Materials | 2022-09-21T15:37:17.000 | WO | 0 | 455.5485 |  | 1012.33 | 45 |  | 55 |  |  |  |  | 2022-10-21T13:38:15.360 | Dehnke, Josh | PNT
22-0014-RET-ER | WO00015, Complete | USR | 2022-09-21T15:37:17.763 | WO | 0 | 670.72 |  | 670.72 | 100 |  | 0 |  |  |  |  | 2022-10-21T13:38:15.383 | Dehnke, Josh | USR
22-0014-RET-ER | WO00016, Complete | Carpet/Pad Materials | 2022-09-26T13:24:00.000 | WO | 0 | 650 | 9.71 | 2272.77 | 650 |  | 71.4005 |  | 09/21/2022 | 09/26/2022 |  | 2022-10-21T13:38:15.403 | Dehnke, Josh
22-0014-RET-ER | WO00017, Complete | LABOR | 2022-10-10T09:06:00.000 | WO | 0 | 4000.0011 | 55.72 | 6244.45 | 4000 |  | 35.9431 |  | 09/21/2022 | 10/10/2022 |  | 2022-11-18T07:27:13.877 | Hicks, Dave
22-0966-ER | WO0005, Complete | Materials | 2022-10-13T14:41:00.000 | WO | 0 | 6556.33 | 8 | 6556.33 | 100 |  | 0 |  | 10/13/2022 | 10/13/2022 |  | 2022-10-17T10:39:30.827 | Olson, Jonathon | Materials
22-0966-ER | WO0006, Complete | Roofing Labor | 2022-10-13T14:54:00.000 | WO | 0 | 4099.995 | 24.83 | 11657.98 | 4100 |  | 64.831 |  | 10/19/2022 | 10/21/2022 |  | 2022-10-21T12:17:58.730 | Dehnke, Josh | Roofing Labor
22-0697-IR | WO0002, Complete | Framing Labor | 2022-12-01T15:53:10.000 | WO | 0 | 8069.4884 | 122.43 | 14968.5 | 8069.49 |  | 46.0902 |  | 12/01/2022 | 12/20/2022 |  | 2023-01-03T10:11:45.823 | Dehnke, Josh | FRM
22-0697-IR | WO0004, Complete | USR | 2022-12-01T15:53:11.253 | WO | 0 | 0 |  | 0 | 0 |  | 0 |  |  |  |  | 2023-01-03T10:11:45.860 | Dehnke, Josh | USR
22-0697-IR | WO0005, Complete | Materials | 2022-12-01T15:53:00.000 | WO | 0 | 1773.55 | 8 | 3935.1 | 45.07 |  | 54.93 |  | 12/01/2022 | 12/01/2022 |  | 2023-01-03T10:11:45.873 | Dehnke, Josh | MAT
22-0829-EST | WO0008 | labor | 2022-08-01T16:57:00.000 | WO | 0 | 2100.0004 | 43 | 3248.16 | 2100 |  | 35.348 |  | 08/08/2022 | 08/12/2022 |  |  |  | labor
22-0829-EST | WO0009 | mitigation | 2022-08-24T16:28:00.000 | WO | 0 | 3299.9983 | 8 | 4130.75 | 3300 |  | 20.1114 |  | 08/24/2022 | 08/24/2022 |  |  |  | mitigation
22-0355-C
22-0381-C
22-0468-EST
22-0546-C
22-0547-C
22-0681-IR
22-0101-ER | WO0001 | ELE | 2022-08-16T11:14:21.197 | WO | 0 | 153.69 | 0 | 153.69 | 100 |  | 0 |  | 08/16/2022 | 08/16/2022 |  |  |  | ELE
22-0101-ER | WO0002 | FNC | 2022-08-16T11:14:21.397 | WO | 0 | 30.47 |  | 30.47 | 100 |  | 0 | [6 empty] | FNC
22-0101-ER | WO0003 | LIT | 2022-08-16T11:14:21.590 | WO | 0 | 44.43 |  | 44.43 | 100 |  | 0 | [6 empty] | LIT
22-0101-ER | WO0004 | MPR | 2022-08-16T11:14:21.830 | WO | 0 | 6.65 |  | 6.65 | 100 |  | 0 | [6 empty] | MPR
22-0101-ER | WO0005 | PLA | 2022-08-16T11:14:21.990 | WO | 0 | 229.48 |  | 229.48 | 100 |  | 0 | [6 empty] | PLA
22-0101-ER | WO0006 | PNT | 2022-08-16T11:14:22.180 | WO | 0 | 11.68 |  | 11.68 | 100 |  | 0 | [6 empty] | PNT
22-0101-ER | WO0007 | WPR | 2022-08-16T11:14:22.340 | WO | 0 | 674.64 | 3.9 | 674.64 | 100 |  | 0 |  | 08/16/2022 | 08/16/2022 |  |  |  | WPR
22-0101-ER | WO0008 | D/P Labor | 2022-12-13T11:56:00.000 | WO | 0 | 1300.001 | 22.22 | 2040.52 | 1300 |  | 36.2907 |  | 08/16/2022 | 12/13/2022 |  |  |  | Dry wall and paint
22-0148-EST | WO0001, Complete | window materials | 2022-07-01T12:01:00.000 | WO | 0 | 1196.1204 | 0 | 1200 | 1196.12 |  | 0.3233 |  | 07/01/2022 | 07/01/2022 |  | 2022-07-01T11:05:04.870 | Dehnke, Josh | wdw
22-0148-EST | WO0002, Complete | Window Labor | 2022-07-01T12:02:00.000 | WO | 0 | 350.0003 | 17 | 650 | 350 |  | 46.1538 |  | 09/13/2022 | 09/14/2022 |  | 2022-09-20T09:09:58.300 | Trevino, Jeovani | wdw
22-0732-IR
22-0409-ER | WO0001 | APP | 2022-09-14T09:49:03.557 | WO | 0 | 534.89 | 3.95 | 534.89 | 100 |  | 0 |  | 09/14/2022 | 09/14/2022 |  |  |  | APP
22-0409-ER | WO0002 | CAB | 2022-09-14T09:49:03.760 | WO | 0 | 1623.148 | 16.16 | 1734.66 | 93.5715 |  | 6.4285 |  | 09/14/2022 | 09/15/2022 |  |  |  | CAB
22-0409-ER | WO0003 | CLN | 2022-09-14T09:49:03.920 | WO | 0 | 13.12 | 0.2 | 13.12 | 100 |  | 0 |  | 09/14/2022 | 09/14/2022 |  |  |  | CLN
22-0409-ER | WO0004, Complete | CON | 2022-09-14T09:49:04.000 | WO | 0 | 187.398 | 14.87 | 312.33 | 60 |  | 40 |  | 10/11/2022 | 10/12/2022 |  | 2022-10-12T15:33:58.500 | Burrell, Bianca | CON
22-0409-ER | WO0005, Complete | Floor Covering Labor | 2022-09-14T09:49:04.000 | WO | 0 | 2549.466 | 26.36 | 4249.11 | 60 |  | 40 |  | 09/14/2022 | 10/13/2022 |  | 2022-10-12T09:21:51.437 | Burrell, Bianca | FCW
22-0409-ER | WO0006 | Shoe - Labor & Material | 2022-09-14T09:49:04.000 | WO | 0 | 444.912 | 7.9 | 741.52 | 60 |  | 40 |  | 09/14/2022 | 09/14/2022 |  |  |  | FNC
22-0409-ER | WO0007 | LAB | 2022-09-14T09:49:04.857 | WO | 0 | 374.25 | 4 | 374.25 | 100 |  | 0 |  | 09/14/2022 | 09/14/2022 |  |  |  | LAB
22-0409-ER | WO00010, Complete | Floor Covering Material | 2022-09-14T12:52:00.000 | WO | 0 | 1489.602 | 5.12 | 2482.67 | 60 |  | 40 |  | 10/02/2022 | 10/02/2022 |  | 2022-10-12T09:22:23.367 | Burrell, Bianca
22-0888-EST | WO0001, Complete | ELS | 2022-07-06T11:00:08.000 | WO | 0 | 0 | 9.92 | 47.82 | 0 |  | 100 |  | 07/26/2022 | 07/27/2022 |  | 2022-08-01T07:41:01.083 | Deville , Jard | ELS
22-0888-EST | WO0002, Complete | RFG | 2022-07-06T11:00:08.000 | WO | 0 | 7812.0009 | 11.03 | 23091.66 | 7812 |  | 66.1696 |  | 07/26/2022 | 07/27/2022 |  | 2022-08-01T07:41:01.053 | Deville , Jard | RFG
22-0888-EST | WO0003, Complete | RFG Material | 2022-07-13T10:33:00.000 | WO | 0 | 11400.0003 | 8 | 6832.98 | 11400 |  | -66.8379 |  | 07/13/2022 | 07/13/2022 |  | 2022-07-15T15:15:30.427 | Deville , Jard | RFG Material
22-0888-EST | WO0004, Complete | PLYWOOD | 2022-07-15T15:55:00.000 | WO | 0 | 2149.9968 | 8 | 8138.44 | 2150 |  | 73.5822 |  | 07/15/2022 | 07/15/2022 |  | 2022-07-15T15:30:21.657 | Deville , Jard | PLYWOOD
22-0888-EST | WO0005, Complete | FEE | 2022-08-01T11:10:00.000 | WO | 0 | 0 | 8 | 0 | 195 |  | 0 |  | 08/01/2022 | 08/01/2022 |  | 2022-08-01T10:10:47.807 | Deville , Jard | FEE
22-0247-ER
22-0115-C | WO0008, Complete | Roofing LABOR | 2022-08-17T15:19:36.000 | WO | 0 | 3595.56 | 45.25 | 8988.9 | 40 |  | 60 |  | 08/17/2022 | 08/22/2022 |  | 2022-10-21T12:34:13.550 | Dehnke, Josh | RFG
22-0115-C | WO00011, Complete | ROOFING MATERIAL | 2022-08-19T12:04:00.000 | WO | 0 | 2546.8612 | 8 | 2718.65 | 2546.86 |  | 6.3189 |  | 08/19/2022 | 08/19/2022 |  | 2022-08-19T11:12:52.590 | Deville , Jard | ROOFING MATERIAL
22-0115-C | WO00012, Complete | Extra Materials | 2022-09-23T13:09:00.000 | WO | 0 | 765.4 | 8 | 765.4 | 100 |  | 0 |  | 09/23/2022 | 09/23/2022 |  | 2022-09-23T12:10:44.047 | Dehnke, Josh | MAT
22-0967-ER
22-0759-IR
22-0970-IR | WO0002, Complete | CON | 2022-09-12T10:40:27.223 | WO | 0 | 300.98 | 5.5 | 300.98 | 100 |  | 0 |  | 09/12/2022 | 09/12/2022 |  | 2022-10-17T08:01:57.783 | Trevino, Jeovani | CON
22-0970-IR | WO0003, Complete | DOR | 2022-09-12T10:40:27.333 | WO | 0 | 460.52 | 1.47 | 460.52 | 100 |  | 0 |  | 09/12/2022 | 09/12/2022 |  | 2022-10-21T11:09:36.667 | Dehnke, Josh | DOR
22-0970-IR | WO0004, Complete | DRY | 2022-09-12T10:40:27.000 | WO | 0 | 1530.977 | 15.1 | 2187.11 | 70 |  | 30 |  | 09/12/2022 | 09/13/2022 |  | 2022-09-19T14:10:07.047 | Trevino, Jeovani | DRY
22-0970-IR | WO0005, Complete | FCC | 2022-09-12T10:40:27.553 | WO | 0 | 1118.7 |  | 1118.7 | 100 |  | 0 |  |  |  |  | 2022-10-09T21:44:21.407 | Trevino, Jeovani | FCC
22-0970-IR | WO0006, Complete | FCT | 2022-09-12T10:40:27.697 | WO | 0 | 1821.17 | 10.17 | 1821.17 | 100 |  | 0 |  | 09/12/2022 | 09/13/2022 |  | 2022-10-21T11:09:36.683 | Dehnke, Josh | FCT
22-0970-IR | WO0007, Complete | FNC | 2022-09-12T10:40:27.837 | WO | 0 | 731.27 | 3.25 | 731.27 | 100 |  | 0 |  | 09/12/2022 | 09/12/2022 |  | 2022-10-17T08:01:57.840 | Trevino, Jeovani | FNC
22-0970-IR | WO0008, Complete | MBL | 2022-09-12T10:40:27.947 | WO | 0 | 491.96 | 2.85 | 491.96 | 100 |  | 0 |  | 09/12/2022 | 09/12/2022 |  | 2022-10-21T11:09:36.750 | Dehnke, Josh | MBL
22-0970-IR | WO0009, Complete | MPR | 2022-09-12T10:40:28.030 | WO | 0 | 85.95 | 0.72 | 85.95 | 100 |  | 0 |  | 09/12/2022 | 09/12/2022 |  | 2022-10-21T11:09:36.780 | Dehnke, Josh | MPR
22-0970-IR | WO00010, Complete | PLM | 2022-09-12T10:40:28.140 | WO | 0 | 635.38 | 2.1 | 635.38 | 100 |  | 0 |  | 09/12/2022 | 09/12/2022 |  | 2022-10-21T11:09:36.813 | Dehnke, Josh | PLM
22-0970-IR | WO00011, Complete | PNT | 2022-09-12T10:40:28.000 | WO | 0 | 0 | 4.02 | 511.95 | 0 |  | 100 |  | 09/12/2022 | 09/13/2022 |  | 2022-09-23T11:58:36.897 | Dehnke, Josh | PNT
22-0970-IR | WO00012 | TIL | 2022-09-12T10:40:28.470 | WO | 0 | 25.03 | 0 | 25.03 | 100 |  | 0 |  | 09/12/2022 | 09/12/2022 |  |  |  | TIL
22-0970-IR | WO00013, Complete | carpet labor | 2022-11-07T11:04:00.000 | WO | 0 | 560.0001 | 12.1 | 486.46 | 560 |  | -15.1174 |  | 09/12/2022 | 11/07/2022 |  | 2022-11-21T10:43:40.573 | Trevino, Jeovani | carpet labor
22-0970-IR | WO00014 | Vanity Labor | 2023-01-03T11:49:00.000 | WO | 0 | 637.596 | 11.05 | 1593.99 | 40 |  | 60 |  | 01/03/2023 | 09/12/2022 |  |  |  | CAB
22-0742-IR | WO0001, Complete | CAB | 2023-02-23T13:53:42.000 | WO | 0 | 1495.6801 | 19.6 | 1799.23 | 1495.68 |  | 16.8711 |  | 02/20/2023 | 02/22/2023 |  | 2023-02-24T10:13:34.420 | Burrell, Bianca | CAB
22-0742-IR | WO0003 | FCV | 2023-02-23T13:53:43.137 | WO | 0 | 395.14 | 2.37 | 395.14 | 100 |  | 0 |  | 02/23/2023 | 02/23/2023 |  |  |  | FCV
22-0742-IR | WO0004 | FNC | 2023-02-23T13:53:43.213 | WO | 0 | 29.26 |  | 29.26 | 100 |  | 0 | [6 empty] | FNC
22-0742-IR | WO0008 | PLM | 2023-02-23T13:53:43.433 | WO | 0 | 220.95 |  | 220.95 | 100 |  | 0 | [6 empty] | PLM
22-0742-IR | WO00010, Complete | PNT/DRY KTLR - Rob | 2023-02-24T09:52:47.000 | WO | 0 | 1647.85 | 28.01 | 3902.41 | 1647.85 |  | 57.7735 |  | 02/13/2023 | 02/16/2023 |  | 2023-02-24T10:08:57.483 | Burrell, Bianca | Labor Work Order
22-0742-IR | WO00012 | Paint - Bathroom | 2023-02-24T10:56:00.000 | WO | 0 | 49.29 | 8 | 49.29 | 100 |  | 0 |  | 02/24/2023 | 02/24/2023
22-0742-IR | WO00013 | Vinyl - material | 2023-02-24T10:05:30.000 | WO | 0 | 165.56 |  | 165.56 | 100 |  | 0 | [6 empty] | Material Work Order
22-0742-IR | WO00014 | In House - Bath Labor | 2023-02-24T11:10:00.000 | WO | 0 | 1588.842 | 23.92 | 2648.07 | 60 |  | 40 |  | 02/23/2023 | 02/27/2023
22-0223-IR
22-0967-IR | WO0002, Complete | Labor | 2022-07-15T15:56:56.000 | WO | 0 | 3275.23 | 19.1 | 7414.71 | 3275.23 |  | 55.8279 |  | 11/14/2022 | 11/18/2022 |  | 2022-10-02T11:07:35.120 | Trevino, Jeovani | CAB
22-0967-IR | WO00014, Complete | material | 2022-07-18T14:15:00.000 | WO | 0 | 10138.58 | 35.89 | 10428.75 | 10138.58 |  | 2.7824 |  | 08/03/2022 | 11/15/2022 |  | 2022-09-23T11:13:04.033 | Dehnke, Josh | material
22-0967-IR | WO00015, Complete | Cabinet Door Materials | 2022-10-18T11:55:00.000 | WO | 0 | 1890.525 | 19.96 | 5401.5 | 35 |  | 65 |  | 10/18/2022 | 11/15/2022 |  | 2022-12-30T08:36:30.140 | Dehnke, Josh | CAB
22-0967-IR | WO00016 | Punch list | 2022-12-02T15:31:00.000 | WO | 0 | 500 | 8.75 | 326.22 | 500 |  | -53.2708 |  | 11/14/2022 | 12/02/2022 |  |  |  | bathroom door/ trainsiton strips / paint
22-0245-IR | WO0001, Complete | Contents | 2022-12-21T11:34:39.000 | WO | 0 | 85.494 | 4.4 | 284.98 | 30 |  | 70 |  | 12/21/2022 | 12/21/2022 |  | 2023-01-24T10:31:26.867 | Hicks, Dave | CON
22-0245-IR | WO0002, Complete | Drywall, Paintin labor and materials | 2022-12-21T11:34:39.000 | WO | 0 | 4600 | 87.82 | 13023.54 | 4600 |  | 64.6793 |  | 01/04/2023 | 12/26/2022 |  | 2023-01-24T10:31:26.833 | Hicks, Dave | DRY
22-0245-IR | WO0003, Complete | wood floor labor and materials | 2022-12-21T11:34:39.000 | WO | 0 | 2050.0006 | 27.07 | 5080.32 | 2050 |  | 59.6482 |  | 12/21/2022 | 12/26/2022 |  | 2023-01-24T10:31:26.813 | Hicks, Dave | FCW
22-0245-IR | WO0004, Complete | Base labor and materials | 2022-12-21T11:34:39.000 | WO | 0 |  |  |  | 0 |  | 0 |  |  |  |  | 2023-01-24T10:31:26.853 | Hicks, Dave | FNC
22-0245-IR | WO0005, Complete | Framework Labor and materials | 2022-12-21T11:34:39.000 | WO | 0 | 6000.0046 | 101.55 | 12373.95 | 6000 |  | 51.511 |  | 01/02/2023 | 12/21/2022 |  | 2022-12-28T06:38:01.200 | Hicks, Dave | FRM
22-0245-IR | WO0006 | Insulation | 2022-12-21T11:34:39.000 | WO | 0 | 757.884 | 13.97 | 1894.71 | 40 |  | 60 |  | 12/21/2022 | 12/22/2022 |  |  |  | INS
22-0245-IR | WO0007 | pnt | 2023-01-04T15:39:00.000 | WO | 0 |  |  |  | 37.3979 |  | 0
22-0896-IR | WO0001, Complete | Vanity | 2022-12-01T13:52:54.000 | WO | 0 | 190.784 | 4.25 | 476.96 | 40 |  | 60 |  | 12/01/2022 | 12/01/2022 |  | 2022-12-01T13:13:06.713 | Dehnke, Josh | CAB
22-0896-IR | WO0004, Complete | Insulation, Drywall, Paint | 2022-12-01T13:52:55.000 | WO | 0 | 3194.93 | 41.18 | 6793.01 | 3194.93 |  | 52.9674 |  | 12/01/2022 | 12/05/2022 |  | 2022-12-01T13:13:06.730 | Dehnke, Josh | DRY
22-0896-IR | WO0005, Complete | Electrical | 2022-12-01T13:52:55.000 | WO | 0 | 394.77 | 1.07 | 394.77 | 100 |  | 0 |  | 12/01/2022 | 12/01/2022 |  | 2022-12-01T13:13:06.763 | Dehnke, Josh | ELE
22-0896-IR | WO0006, Complete | Wood Floor Install | 2022-12-01T13:52:55.000 | WO | 0 | 749.9995 | 17.73 | 1803.33 | 750 |  | 58.4103 |  | 12/01/2022 | 12/01/2022 |  | 2022-12-08T11:20:28.260 | Dehnke, Josh | FCC
22-0896-IR | WO0007, Complete | Tile Materials | 2022-12-01T13:52:56.000 | WO | 0 | 3760.0001 | 19.12 | 4421.61 | 3760 |  | 14.9631 |  | 12/01/2022 | 12/02/2022 |  | 2022-12-01T13:13:06.783 | Dehnke, Josh | FCT
22-0896-IR | WO0008 | Fence Repair | 2022-12-01T13:52:56.000 | WO | 0 | 508.824 | 39.75 | 636.03 | 80 |  | 20 |  | 04/03/2023 | 04/07/2023 |  |  |  | FEN
22-0896-IR | WO00010, Complete | Shower Glass | 2022-12-01T13:52:56.000 | WO | 0 | 999.999 |  | 2220 | 1000 |  | 54.955 |  |  |  |  | 2023-02-22T10:42:21.760 | Dehnke, Josh | GLS
22-0896-IR | WO00015, Complete | Plumbing | 2022-12-01T13:52:56.000 | WO | 0 | 661.784 | 3.17 | 827.23 | 80 |  | 20 |  | 12/01/2022 | 12/01/2022 |  | 2023-01-03T09:23:15.423 | Dehnke, Josh | PLM
22-0896-IR | WO00017, Complete | Tile Labor | 2022-12-01T13:52:57.000 | WO | 0 | 7200.0027 |  | 9900 | 7200 |  | 27.2727 |  |  |  |  | 2022-12-08T11:21:37.237 | Dehnke, Josh | TIL
22-0896-IR | WO00018, Complete | Materials | 2022-12-01T14:04:00.000 | WO | 0 | 2181.744 | 8 | 2727.18 | 80 |  | 20 |  | 12/01/2022 | 12/01/2022 |  | 2022-12-01T13:13:06.817 | Dehnke, Josh | MAT
22-0828-IR | WO0001, Complete | CON | 2023-02-28T12:25:26.000 | WO | 0 | 281.262 | 16.47 | 468.77 | 60 |  | 40 |  | 03/07/2023 | 03/08/2023 |  | 2023-03-13T11:08:48.540 | Burrell, Bianca | CON
22-0828-IR | WO0002, Complete | DRY | 2023-02-28T12:25:26.000 | WO | 0 | 1118.436 | 16.35 | 1864.06 | 60 |  | 40 |  | 03/07/2023 | 03/08/2023 |  | 2023-03-13T11:08:48.510 | Burrell, Bianca | DRY
22-0828-IR | WO0003, Complete | FNC | 2023-02-28T12:25:26.587 | WO | 0 | 71.09 | 0.6 | 71.09 | 100 |  | 0 |  | 02/28/2023 | 02/28/2023 |  | 2023-03-13T11:08:48.527 | Burrell, Bianca | FNC
22-0828-IR | WO0004, Complete | MAS | 2023-02-28T12:25:26.727 | WO | 0 | 0 |  | 0 | 0 |  | 0 |  |  |  |  | 2023-03-13T11:08:48.540 | Burrell, Bianca | MAS
22-0895-IR | WO0001, Complete | CAB | 2022-09-19T14:11:52.323 | WO | 0 | 838.12 |  | 838.12 | 100 |  | 0 |  |  |  |  | 2022-10-17T08:02:47.313 | Trevino, Jeovani | CAB
22-0895-IR | WO0002, Complete | CON | 2022-09-19T14:11:52.513 | WO | 0 | 138.18 | 2.2 | 138.18 | 100 |  | 0 |  | 09/19/2022 | 09/19/2022 |  | 2022-12-02T16:01:32.650 | Trevino, Jeovani | CON
22-0895-IR | WO0003, Complete | DRY | 2022-09-19T14:11:52.000 | WO | 0 | 372.555 | 3.78 | 496.74 | 75 |  | 25 |  | 09/19/2022 | 09/19/2022 |  | 2022-10-09T21:39:42.737 | Trevino, Jeovani | DRY
22-0895-IR | WO0004, Complete | FCC | 2022-09-19T14:11:52.000 | WO | 0 | 1820 | 20.35 | 2480.01 | 1820 |  | 26.6132 |  | 09/19/2022 | 09/21/2022 |  | 2022-10-17T07:58:50.343 | Trevino, Jeovani | FCC
22-0895-IR | WO0005, Complete | FCR | 2022-09-19T14:11:53.297 | WO | 0 | 1263.37 | 6.95 | 1263.37 | 100 |  | 0 |  | 09/19/2022 | 09/19/2022 |  | 2023-01-23T11:22:57.623 | Dehnke, Josh | FCR
22-0895-IR | WO0006, Complete | FCV | 2022-09-19T14:11:53.473 | WO | 0 | 81.07 | 0.52 | 81.07 | 100 |  | 0 |  | 09/19/2022 | 09/19/2022 |  | 2022-12-02T16:01:32.713 | Trevino, Jeovani | FCV
22-0895-IR | WO0007, Complete | FNC | 2022-09-19T14:11:53.633 | WO | 0 | 87.15 | 0.73 | 87.15 | 100 |  | 0 |  | 09/19/2022 | 09/19/2022 |  | 2022-12-02T16:01:32.683 | Trevino, Jeovani | FNC
22-0895-IR | WO0008, Complete | MBL | 2022-09-19T14:11:53.000 | WO | 0 | 329.4 | 10.82 | 329.4 | 100 |  | 0 |  | 04/04/2023 | 04/05/2023 |  | 2023-05-01T11:10:44.157 | Dehnke, Josh | MBL
22-0895-IR | WO0009, Complete | MPR | 2022-09-19T14:11:53.897 | WO | 0 | 48.28 | 0.38 | 48.28 | 100 |  | 0 |  | 09/19/2022 | 09/19/2022 |  | 2022-12-02T16:01:32.730 | Trevino, Jeovani | MPR
22-0895-IR | WO00010, Complete | PLM | 2022-09-19T14:11:54.000 | WO | 0 | 566.89 | 2.1 | 566.89 | 100 |  | 0 |  | 04/03/2023 | 04/03/2023 |  | 2023-05-01T11:10:44.190 | Dehnke, Josh | PLM
22-0895-IR | WO00012, Complete | flooring materials | 2022-10-02T12:01:00.000 | WO | 0 | 5048.62 | 8 | 5048.62 | 100 |  | 0 |  | 10/02/2022 | 10/02/2022 |  | 2022-10-02T11:02:51.257 | Trevino, Jeovani | flooring materials
22-0895-IR | WO00013, Complete | wall touch up work | 2022-11-30T18:30:00.000 | WO | 0 | 250 | 8 | 49.39 | 250 |  | -406.1753 |  | 11/30/2022 | 11/30/2022 |  | 2022-12-02T15:56:57.420 | Trevino, Jeovani | wall touch up work
22-0570-IR | WO0001, Complete | CON | 2023-02-27T12:35:01.627 | WO | 0 | 313.86 | 5 | 313.86 | 100 |  | 0 |  | 02/27/2023 | 02/27/2023 |  | 2023-03-13T11:06:33.543 | Burrell, Bianca | CON
22-0570-IR | WO0005, Complete | Flooring Labor | 2023-02-27T12:35:02.000 | WO | 0 | 2171.508 | 10.82 | 3619.18 | 60 |  | 40 |  | 04/06/2023 | 04/07/2023 |  | 2023-04-10T08:59:27.950 | Burrell, Bianca | FCV
22-0570-IR | WO0006, Complete | FNC | 2023-02-27T12:35:02.000 | WO | 0 | 303.94 | 9.22 | 303.94 | 100 |  | 0 |  | 04/20/2023 | 04/21/2023 |  | 2023-05-02T13:31:23.633 | Burrell, Bianca | FNC
22-0570-IR | WO0007, Complete | FRM | 2023-02-27T12:35:02.000 | WO | 0 | 2624.136 | 36.38 | 6560.34 | 40 |  | 60 |  | 02/27/2023 | 03/03/2023 |  | 2023-03-06T09:18:56.247 | Burrell, Bianca | FRM
22-0570-IR | WO0008, Complete | INS | 2023-02-27T12:35:02.000 | WO | 0 | 751.46 | 38.23 | 1878.65 | 40 |  | 60 |  | 02/27/2023 | 03/03/2023 |  | 2023-03-06T09:20:26.820 | Burrell, Bianca | INS
22-0570-IR | WO00010, Complete | PNT/DRY - Rob | 2023-02-27T12:35:02.000 | WO | 0 | 6648.0008 | 32.89 | 7665.92 | 6648 |  | 13.2785 |  | 03/08/2023 | 03/13/2023 |  | 2023-03-13T11:06:26.173 | Burrell, Bianca | PNT
22-0570-IR | WO00011, Complete | USR | 2023-02-27T12:35:02.693 | WO | 0 | 10.68 |  | 10.68 | 100 |  | 0 |  |  |  |  | 2023-03-06T09:21:15.817 | Burrell, Bianca | USR
22-0570-IR | WO00012, Complete | Flooring Material | 2023-03-06T10:21:00.000 | WO | 0 | 2926.74 | 17 | 3902.32 | 75 |  | 25 |  | 03/01/2023 | 03/02/2023 |  | 2023-03-06T09:39:22.240 | Burrell, Bianca
22-0296-C | WO0001, Complete | CON | 2022-10-07T15:06:57.000 | WO | 0 | 498.34 | 8 | 498.34 | 100 |  | 0 |  | 03/27/2023 | 03/27/2023 |  | 2023-05-02T13:13:42.397 | Sleem, Michael | CON
22-0296-C | WO0002, Complete | DMO | 2022-10-07T15:06:57.000 | WO | 0 | 155.02 | 28.55 | 387.55 | 40 |  | 60 |  | 03/28/2023 | 03/31/2023 |  | 2023-04-24T08:15:19.603 | Burrell, Bianca | DMO
22-0296-C | WO0003, Complete | DRY | 2022-10-07T15:06:57.000 | WO | 0 | 248.416 | 2.13 | 354.88 | 70 |  | 30 |  | 10/07/2022 | 10/07/2022 |  | 2022-10-24T09:48:02.547 | Burrell, Bianca | DRY
22-0296-C | WO0004, Complete | FCC | 2022-10-07T15:06:57.000 | WO | 0 | 1011.942 | 0 | 1686.57 | 60 |  | 40 |  | 04/17/2023 | 04/17/2023 |  | 2023-04-24T08:15:09.920 | Burrell, Bianca | FCC
22-0296-C | WO0005, Complete | FNC | 2022-10-07T15:06:58.000 | WO | 0 | 273.9555 | 1.62 | 421.47 | 65 |  | 35 |  | 10/07/2022 | 10/07/2022 |  | 2023-04-24T08:15:09.920 | Burrell, Bianca | FNC
22-0296-C | WO0006, Complete | FRM | 2022-10-07T15:06:58.000 | WO | 0 | 110.388 | 0.3 | 275.97 | 40 |  | 60 |  | 10/07/2022 | 10/07/2022 |  | 2023-04-24T08:15:09.933 | Burrell, Bianca | FRM
22-0296-C | WO0007, Complete | PNT | 2022-10-07T15:06:58.000 | WO | 0 | 2771.02 | 34.37 | 5542.04 | 50 |  | 50 |  | 03/16/2023 | 03/21/2023 |  | 2023-03-27T08:45:39.087 | Burrell, Bianca | PNT
22-0296-C | WO0008 | USR | 2022-10-07T15:06:58.460 | WO | 0 | -9.78 |  | -9.78 | 100 |  | 0 | [6 empty] | USR
22-0296-C | WO0009, Complete | Floor Covering - Materials | 2022-10-18T17:28:00.000 | WO | 0 | 3379.0515 | 15.17 | 3514.08 | 3379.05 |  | 3.8425 |  | 03/01/2023 | 03/02/2023 |  | 2023-03-06T10:16:42.693 | Burrell, Bianca
22-0875-IR | WO0001, Complete | material | 2022-07-27T16:45:00.000 | WO | 0 | 3263.23 |  | 3263.23 | 3263.23 |  | 0 |  |  |  |  | 2022-08-02T12:05:57.560 | Dehnke, Josh | mat
22-0875-IR | WO0002, Complete | Pillar Labor | 2022-08-02T13:01:00.000 | WO | 0 | 3200.003 | 44 | 12442.03 | 3200 |  | 74.2807 |  | 08/01/2022 | 08/05/2022 |  | 2022-08-15T08:40:10.713 | Trevino, Jeovani | LAB
22-0875-IR | WO0003, Complete | Boom Lift | 2022-08-02T13:02:00.000 | WO | 0 | 3655.8492 | 8 | 2268.42 | 3655.85 |  | -61.1628 |  | 08/02/2022 | 08/02/2022 |  | 2022-08-02T12:05:57.607 | Dehnke, Josh | EQU
22-0905-IR
22-0133-IR/D
22-0897-IR | WO0002, Complete | Cabinets | 2022-05-09T14:05:07.000 | WO | 0 | 264.48 | 3.1 | 264.48 | 100 |  | 0 |  | 05/10/2022 | 05/10/2022 |  | 2022-06-27T07:56:45.613 | Feltmann, Brandon | CAB
22-0897-IR | WO0005, Complete | Door | 2022-05-09T14:05:07.000 | WO | 0 | 134.28 | 1.48 | 134.28 | 100 |  | 0 |  | 05/09/2022 | 05/09/2022 |  | 2022-06-27T07:56:45.627 | Feltmann, Brandon | DOR
22-0897-IR | WO00010, Complete | FNH | 2022-05-09T14:05:08.490 | WO | 0 | 64.77 | 0.62 | 64.77 | 100 |  | 0 |  | 05/09/2022 | 05/09/2022 |  | 2022-06-27T07:56:45.637 | Feltmann, Brandon | FNH
22-0897-IR | WO00011, Complete | PLM | 2022-05-09T14:05:08.697 | WO | 0 | 323.54 | 1.98 | 323.54 | 100 |  | 0 |  | 05/09/2022 | 05/09/2022 |  | 2022-06-27T07:56:45.647 | Feltmann, Brandon | PLM
22-0897-IR | WO00012, Complete | PNT | 2022-05-09T14:05:08.000 | WO | 0 | 690.632 | 8.5 | 863.29 | 80 |  | 20 |  | 05/09/2022 | 05/10/2022 |  | 2022-06-27T07:56:45.657 | Feltmann, Brandon | PNT
22-0897-IR | WO00013, Complete | Flooring labor | 2022-05-09T17:45:00.000 | WO | 0 | 3212.6444 | 79.73 | 5445.16 | 59 |  | 41 |  | 05/09/2022 | 05/13/2022 |  | 2022-06-27T07:56:45.667 | Feltmann, Brandon | Flooring labor
22-0897-IR | WO00014, Complete | Material | 2022-05-17T13:34:00.000 | WO | 0 | 4742.05 | 19.77 | 4742.05 | 100 |  | 0 |  | 05/09/2022 | 05/17/2022 |  | 2022-06-27T07:56:45.677 | Feltmann, Brandon | Material
22-0901-IR
22-0915-IR
22-0514-ER
22-0230-IR | WO0001 | CNC | 2022-07-14T12:22:20.827 | WO | 0 | 1452.65 | 8.3 | 1452.65 | 100 |  | 0 |  | 07/14/2022 | 07/15/2022 |  |  |  | CNC
22-0230-IR | WO0002 | CON | 2022-07-14T12:22:21.127 | WO | 0 | 93.38 | 1.47 | 93.38 | 100 |  | 0 |  | 07/14/2022 | 07/14/2022 |  |  |  | CON
22-0230-IR | WO0003 | DMO | 2022-07-14T12:22:21.280 | WO | 0 | 463.07 | 3.88 | 463.07 | 100 |  | 0 |  | 07/14/2022 | 07/14/2022 |  |  |  | DMO
22-0230-IR | WO0004 | DOR | 2022-07-14T12:22:21.397 | WO | 0 | 632.18 | 1.65 | 632.18 | 100 |  | 0 |  | 07/14/2022 | 07/14/2022 |  |  |  | DOR
22-0230-IR | WO0005 | EXC | 2022-07-14T12:22:21.530 | WO | 0 | 708.12 | 11.12 | 708.12 | 100 |  | 0 |  | 07/14/2022 | 07/15/2022 |  |  |  | EXC
22-0230-IR | WO0006 | FCW | 2022-07-14T12:22:21.617 | WO | 0 | 1849.85 | 13.5 | 1849.85 | 100 |  | 0 |  | 07/14/2022 | 07/15/2022 |  |  |  | FCW
22-0230-IR | WO0007 | FNH | 2022-07-14T12:22:21.717 | WO | 0 | 265.84 | 0.62 | 265.84 | 100 |  | 0 |  | 07/14/2022 | 07/14/2022 |  |  |  | FNH
22-0230-IR | WO0008 | FRM | 2022-07-14T12:22:21.807 | WO | 0 | 1251.96 | 8.32 | 1251.96 | 100 |  | 0 |  | 07/14/2022 | 07/15/2022 |  |  |  | FRM
22-0230-IR | WO0009 | LAB | 2022-07-14T12:22:21.910 | WO | 0 | 2.14 | 0 | 2.14 | 100 |  | 0 |  | 07/14/2022 | 07/14/2022 |  |  |  | LAB
22-0230-IR | WO00010 | LND | 2022-07-14T12:22:22.030 | WO | 0 | 404.53 | 2.85 | 404.53 | 100 |  | 0 |  | 07/14/2022 | 07/14/2022 |  |  |  | LND
22-0230-IR | WO00011 | MAS | 2022-07-14T12:22:22.120 | WO | 0 | 3984.64 | 31.43 | 3984.64 | 100 |  | 0 |  | 07/14/2022 | 07/19/2022 |  |  |  | MAS
22-0230-IR | WO00012 | MPR | 2022-07-14T12:22:22.220 | WO | 0 | 152.47 | 1.3 | 152.47 | 100 |  | 0 |  | 07/14/2022 | 07/14/2022 |  |  |  | MPR
22-0230-IR | WO00013 | PNL | 2022-07-14T12:22:22.300 | WO | 0 | 733.42 | 4.62 | 733.42 | 100 |  | 0 |  | 07/14/2022 | 07/14/2022 |  |  |  | PNL
22-0230-IR | WO00014 | PNT | 2022-07-14T12:22:22.377 | WO | 0 | 713.94 | 5.42 | 713.94 | 100 |  | 0 |  | 07/14/2022 | 07/14/2022 |  |  |  | PNT
22-0230-IR | WO00015 | SDG | 2022-07-14T12:22:22.467 | WO | 0 | 781.66 | 3.85 | 781.66 | 100 |  | 0 |  | 07/14/2022 | 07/14/2022 |  |  |  | SDG
22-0183-ER | WO0001, Complete | CON | 2022-06-07T12:33:03.000 | WO | 0 | 0 | 2 | 123.74 | 0 |  | 100 |  | 06/07/2022 | 06/07/2022 |  | 2022-06-14T11:36:47.803 | Burrell, Bianca | CON
22-0183-ER | WO0003, Complete | RFG | 2022-06-07T12:33:03.000 | WO | 0 | 6150.0041 | 70.67 | 11298.55 | 6150 |  | 45.5682 |  | 06/07/2022 | 06/16/2022 |  | 2022-06-20T08:23:58.040 | Deville , Jard | RFG
22-0183-ER | WO0004, Complete | RFG Materials | 2022-06-08T08:48:00.000 | WO | 0 | 5003.8885 | 7.55 | 5687.73 | 5003.89 |  | 12.0231 |  | 06/07/2022 | 06/07/2022 |  | 2022-06-20T08:23:58.047 | Deville , Jard | RFG Materials
22-0199-IR | WO0002, Complete | Door | 2022-06-02T10:37:58.000 | WO | 0 | 2568.0005 | 7.87 | 2668.79 | 2568 |  | 3.7766 |  | 06/02/2022 | 06/02/2022 |  | 2022-06-27T07:58:29.600 | Feltmann, Brandon | DOR
22-0199-IR | WO0003, Complete | SDG | 2022-06-02T10:37:58.000 | WO | 0 | 156.65 | 0.35 | 68.8 | 156.65 |  | -127.689 |  | 06/02/2022 | 06/02/2022 |  | 2022-06-14T18:47:15.657 | Sleem, Michael | SDG
22-0871-IR | WO0001, Complete | Cabinets | 2022-07-06T16:46:24.000 | WO | 0 | 789.9996 | 1.6 | 1138.2 | 790 |  | 30.5922 |  | 07/06/2022 | 07/06/2022 |  | 2022-07-11T07:12:13.007 | Deville , Jard | CAB
22-0871-IR | WO0002, Complete | Contents | 2022-07-06T16:46:24.000 | WO | 0 | 0 | 5.87 | 302.7 | 0 |  | 100 |  | 07/06/2022 | 07/06/2022 |  | 2022-07-14T12:02:22.330 | Deville , Jard | CON
22-0871-IR | WO0003, Complete | Doors/Finish Carpentry | 2022-07-06T16:46:24.000 | WO | 0 | 491.796 | 67.52 | 1092.88 | 45 |  | 55 | Deville , Jard | 08/14/2022 | 08/21/2022 |  | 2022-08-19T11:50:42.530 | Deville , Jard | DOR
22-0871-IR | WO0004, Complete | Drywall/Painting | 2022-07-06T16:46:24.000 | WO | 0 | 2732.8905 | 25.5 | 6073.09 | 2732.89 |  | 55 |  | 07/06/2022 | 07/11/2022 |  | 2022-07-14T11:59:28.427 | Deville , Jard | DRY
22-0871-IR | WO0006, Complete | Hardware | 2022-07-06T16:46:25.000 | WO | 0 | 149.03 | 62.67 | 149.03 | 100 |  | 0 | Deville , Jard | 08/14/2022 | 08/21/2022 |  | 2022-09-13T13:15:35.237 | Sleem, Michael | FNH
22-0871-IR | WO0008, Complete | Mirror install | 2022-07-06T16:46:25.000 | WO | 0 | 0 | 61.53 | 47.64 | 0 |  | 100 | Deville , Jard | 08/14/2022 | 08/21/2022 |  | 2022-09-08T14:10:47.647 | Deville , Jard | MSD
22-0871-IR | WO0009, Complete | Plumbing | 2022-07-06T16:46:25.000 | WO | 0 | 566.9469 | 12.65 | 848.85 | 66.79 |  | 33.21 | Deville , Jard | 07/06/2022 | 08/05/2022 |  | 2022-08-04T12:35:15.510 | Deville , Jard | PLM
22-0871-IR | WO00010, Complete | Carpentry Materials | 2022-07-22T13:12:00.000 | WO | 0 | 512.6797 | 8 | 1410.79 | 512.68 |  | 63.6601 |  | 07/22/2022 | 07/22/2022 |  | 2022-07-22T12:19:06.303 | Deville , Jard | DOR/FNC Mat
22-0900-IR
22-0766-EST
22-0718-RET-ER
22-0573-EST
22-0373-ER-EST
22-0976-IR
22-0122-D
22-0388-ER | WO0001, Complete | Tile Labor | 2022-06-15T12:47:00.000 | WO | 0 | 1999.9996 | 30.97 | 2664.68 | 2000 |  | 24.9441 |  | 06/24/2022 | 06/29/2022 |  | 2022-06-23T14:45:35.783 | Dehnke, Josh | FCT
22-0388-ER | WO0002, Complete | Tile Materials | 2022-06-15T12:47:00.000 | WO | 0 | 449.0002 |  | 657.32 | 449 |  | 31.6923 |  |  |  |  | 2022-06-23T14:45:49.683 | Dehnke, Josh | TIL
22-0281-ER
22-0586-ER | WO0001 | FEN | 2022-09-01T12:33:44.000 | WO | 0 | 1802.08 | 29.18 | 4505.2 | 40 |  | 60 |  | 09/01/2022 | 09/06/2022 |  |  |  | FEN
22-0586-ER | WO0003 | Roofing Labor | 2022-09-01T12:33:45.000 | WO | 0 | 5807.2635 | 68.27 | 12905.03 | 45 |  | 55 |  | 09/01/2022 | 09/09/2022 |  |  |  | RFG
22-0586-ER | WO0004 | SFG | 2022-09-01T12:33:45.000 | WO | 0 | 913.329 | 7.62 | 2029.62 | 45 |  | 55 |  | 09/01/2022 | 09/01/2022 |  |  |  | SFG
22-0586-ER | WO0005 | USR | 2022-09-01T12:33:46.160 | WO | 0 | 659.97 |  | 659.97 | 100 |  | 0 | [6 empty] | USR
22-0586-ER | WO0006, Complete | Roofing Material | 2022-09-01T12:55:00.000 | WO | 0 | 4828.138 | 8 | 4545.73 | 4828.14 |  | -6.2126 |  | 09/01/2022 | 09/01/2022 |  | 2022-09-02T10:05:00.903 | Deville , Jard | Roofing Material
22-0147-IR | WO0001 | Material | 2022-07-19T11:30:25.000 | WO | 0 | 4119.94 |  | 4119.94 | 100 |  | 0 | [6 empty] | HVC
22-0147-IR | WO0002 | RFG | 2022-07-19T11:30:25.950 | WO | 0 | 199.57 |  | 199.57 | 100 |  | 0 | [6 empty] | RFG
22-0147-IR | WO0003 | Labor | 2022-07-19T11:30:26.000 | WO | 0 | 10024.09 | 84.33 | 10024.09 | 100 |  | 0 |  | 07/19/2022 | 08/01/2022 |  |  |  | SDG
22-0333-IR | WO0003, Complete | DRY | 2022-08-18T09:30:15.000 | WO | 0 | 6306.248 | 0 | 9701.92 | 65 |  | 35 |  | 08/18/2022 | 09/08/2022 |  | 2022-08-18T08:33:35.257 | Dehnke, Josh | DRY
22-0333-IR | WO0004, Complete | FRM | 2022-08-18T09:30:15.000 | WO | 0 | 68.701 | 0 | 149.35 | 46 |  | 54 |  | 08/18/2022 | 08/18/2022 |  | 2022-08-18T08:33:35.287 | Dehnke, Josh | FRM
22-0333-IR | WO0005, Complete | PNT | 2022-08-18T09:30:16.000 | WO | 0 | 1881.745 | 0 | 3763.49 | 50 |  | 50 |  | 08/18/2022 | 09/01/2022 |  | 2022-08-18T08:33:35.303 | Dehnke, Josh | PNT
22-0462-C | WO0001, Complete | APP | 2022-06-09T15:54:41.000 | WO | 0 | 0 | 10.83 | 114.36 | 0 |  | 100 |  | 07/01/2022 | 07/04/2022 |  | 2022-07-14T12:05:04.213 | Deville , Jard | APP
22-0462-C | WO0002, Complete | CLN | 2022-06-09T15:54:42.000 | WO | 0 | 0 | 1.9 | 284.43 | 0 |  | 100 |  | 07/04/2022 | 07/04/2022 |  | 2022-07-18T09:42:09.530 | Deville , Jard | CLN
22-0462-C | WO0003, Complete | CON | 2022-06-09T15:54:42.000 | WO | 0 | 696.2799 |  | 514.03 | 696.28 |  | -35.4551 |  | 07/12/2022 |  |  | 2022-07-14T12:05:44.100 | Deville , Jard | CON
22-0462-C | WO0004, Complete | CPS | 2022-06-09T15:54:42.000 | WO | 0 | 341.62 |  | 222.82 | 341.62 |  | -53.3166 |  |  |  |  | 2022-07-14T12:05:34.550 | Deville , Jard | CPS
22-0462-C | WO0005, Complete | DMO | 2022-06-09T15:54:42.000 | WO | 0 | 271.41 | 1.98 | 339.26 | 271.41 |  | 19.9994 |  | 06/29/2022 | 06/29/2022 |  | 2022-07-01T09:42:39.050 | Dehnke, Josh | DMO
22-0462-C | WO0006, Complete | FNC,MPR,DOR/LAB | 2022-06-09T15:54:43.000 | WO | 0 | 2350.5791 | 18.07 | 2226.72 | 2350.58 |  | -5.5624 |  | 07/20/2022 | 07/22/2022 |  | 2022-07-22T10:04:30.717 | Deville , Jard | DOR
22-0462-C | WO0008, Complete | FCC LAB | 2022-06-09T15:54:43.000 | WO | 0 |  |  |  | 130.9 |  | 0 |  |  |  |  | 2022-07-18T09:41:52.163 | Deville , Jard | FCC
22-0462-C | WO0009, Complete | FEE | 2022-06-09T15:54:43.857 | WO | 0 | 0 |  | 0 | 0 |  | 0 |  |  |  |  | 2022-07-18T09:41:42.517 | Deville , Jard | FEE
22-0462-C | WO00011, Complete | FNH | 2022-06-09T15:54:44.000 | WO | 0 | 0 | 18.8 | 222.58 | 0 |  | 100 |  | 08/14/2022 | 08/16/2022 |  | 2022-08-12T09:07:16.840 | Deville , Jard | FNH
22-0462-C | WO00014, Complete | PNT/DRY/INS | 2022-06-09T15:54:44.000 | WO | 0 | 3843.345 | 21.82 | 6987.9 | 55 |  | 45 |  | 06/29/2022 | 07/01/2022 | 2022-06-28T08:49:59.770 | 2022-07-01T08:53:36.190 | Deville , Jard | PNT
22-0462-C | WO00015, Complete | FNC AND MPR MAT | 2022-06-09T16:23:00.000 | WO | 0 | 903.138 | 8 | 1505.23 | 60 |  | 40 |  | 06/30/2022 | 06/30/2022 |  | 2022-07-01T09:42:39.063 | Dehnke, Josh | FNC AND MPR MAT
22-0462-C | WO00016, Complete | LVP | 2022-06-28T14:02:00.000 | WO | 0 | 1996.1093 |  | 3942.27 | 1996.11 |  | 49.3665 |  |  |  |  | 2022-07-12T09:08:03.830 | Deville , Jard | FCC
22-0462-C | WO00017, Complete | LVP labor | 2022-07-07T11:39:00.000 | WO | 0 | 1599.9997 | 8 | 966.24 | 1600 |  | -65.5903 |  | 07/07/2022 | 07/15/2022 |  | 2022-07-18T09:41:33.817 | Deville , Jard | LVP
22-0156-IR | WO0001, Complete | Unit 7616, 7619, 7622, 7635, 7652, 7649 Deck Labor | 2022-07-13T15:57:00.000 | WO | 0 | 24000.012 | 264 | 36000 | 24000 |  | 33.3333 |  | 07/18/2022 | 07/22/2022 |  | 2022-07-22T09:33:03.633 | Dehnke, Josh | FRM
22-0156-IR | WO0002, Complete | Unit 7616, 7619, 7622, 7635, 7652, 7649 Deck Materials | 2022-07-13T15:59:00.000 | WO | 0 | 7524.3 | 48 | 7524.3 | 100 |  | 0 |  | 07/15/2022 | 07/15/2022 |  | 2022-07-15T12:47:58.197 | Dehnke, Josh | FRM
22-0156-IR | WO00013, Complete | Unit 7656, 7649, 7658, 7667 Deck Labor | 2022-07-14T08:48:00.000 | WO | 0 | 16000.008 | 176 | 24000 | 16000 |  | 33.3333 |  | 07/25/2022 | 07/29/2022 |  | 2022-08-08T08:11:08.433 | Dehnke, Josh | FRM
22-0156-IR | WO00014, Complete | Unit 7656, 7663, 7658, 7667 Deck Materials | 2022-07-14T08:58:00.000 | WO | 0 | 5016.2 | 32 | 5016.2 | 100 |  | 0 |  | 07/15/2022 | 07/15/2022 |  | 2022-07-15T12:47:58.213 | Dehnke, Josh | FRM
22-0156-IR | WO00021, Complete | Unit 7745, 7742, 7748 Deck Labor | 2022-07-14T09:34:00.000 | WO | 0 | 12000.006 | 132 | 18000 | 12000 |  | 33.3333 |  | 08/01/2022 | 08/05/2022 |  | 2022-08-08T08:11:08.413 | Dehnke, Josh | FRM
22-0156-IR | WO00022, Complete | Unit 7745, 7742, 7748 Deck Materials | 2022-07-14T09:50:00.000 | WO | 0 | 3762.15 | 24 | 3762.15 | 100 |  | 0 |  | 07/15/2022 | 07/15/2022 |  | 2022-07-15T12:47:58.230 | Dehnke, Josh | FRM
22-0156-IR | WO00027, Complete | Unit 7785, 7791, 7781, 7623 Deck Labor | 2022-07-14T09:58:00.000 | WO | 0 | 16000.008 | 176 | 24000 | 16000 |  | 33.3333 |  | 08/08/2022 | 08/12/2022 |  | 2022-08-08T08:11:08.400 | Dehnke, Josh | FRM
22-0156-IR | WO00028, Complete | Unit 7785, 7791, 7781, 7623 Deck Materials | 2022-07-14T09:58:00.000 | WO | 0 | 5016.2 | 32 | 5016.2 | 100 |  | 0 |  | 07/15/2022 | 07/15/2022 |  | 2022-07-15T12:47:58.243 | Dehnke, Josh | FRM
22-0267-ER | WO00012, Complete | Materials | 2022-08-26T12:22:00.000 | WO | 0 | 1683.75 | 8 | 1683.75 | 100 |  | 0 |  | 08/26/2022 | 08/26/2022 |  | 2022-09-09T10:57:22.183 | Dehnke, Josh | MAT
22-0267-ER | WO00017, Complete | FEE | 2022-08-30T11:00:41.490 | WO | 0 | 0 |  | 0 | 0 |  | 0 |  |  |  |  | 2022-09-19T07:39:42.533 | Dehnke, Josh | FEE
22-0267-ER | WO00020, Complete | Boilet System detach and reset | 2022-08-30T11:00:41.000 | WO | 0 | 2034.63 | 21.07 | 3391.05 | 60 |  | 40 |  | 08/30/2022 | 09/01/2022 |  | 2022-09-19T07:39:42.643 | Dehnke, Josh | HVC
22-0267-ER | WO00023, Complete | Insulation, Drywall, Crack fix, texture, prep for paint, clean, install window, framing | 2022-08-30T11:00:41.000 | WO | 0 | 10911.2389 | 107.4 | 18449.69 | 10911.24 |  | 40.8595 |  | 08/30/2022 | 09/07/2022 |  | 2022-09-09T10:56:58.383 | Dehnke, Josh | PLA
22-0267-ER | WO00024, Complete | PNT | 2022-08-30T11:00:41.000 | WO | 0 | 15130.08 | 127.88 | 18912.6 | 80 |  | 20 |  | 08/30/2022 | 09/19/2022 |  | 2022-09-19T07:39:42.690 | Dehnke, Josh | PNT
22-0267-ER | WO00026, Complete | STU | 2022-08-30T11:00:42.000 | WO | 0 | 1313.136 | 9.72 | 1641.42 | 80 |  | 20 |  | 08/30/2022 | 08/31/2022 |  | 2022-09-19T07:39:42.720 | Dehnke, Josh | STU
22-0870-IR | WO0002, Complete | Garage Door material/labor | 2022-06-20T13:09:53.000 | WO | 0 | 1618.99 | 27 | 1618.99 | 100 |  | 0 | Dehnke, Josh | 08/01/2022 | 08/03/2022 |  | 2022-08-17T10:32:51.227 | Dehnke, Josh | DOR
22-0870-IR | WO0003, Complete | Garage door trim labor | 2022-06-20T13:09:53.000 | WO | 0 | 199.9999 | 18 | 277.03 | 200 |  | 27.8057 | Dehnke, Josh | 07/27/2022 | 07/28/2022 |  | 2022-07-25T14:00:38.170 | Dehnke, Josh | FNC
22-0870-IR | WO0005, Complete | roofing material/labor | 2022-06-20T13:09:54.000 | WO | 0 | 737.295 | 18 | 983.06 | 75 |  | 25 | Dehnke, Josh | 07/27/2022 | 07/28/2022 |  | 2022-08-17T10:32:51.273 | Dehnke, Josh | RFG
22-0870-IR | WO0007, Complete | Materials | 2022-07-01T09:35:00.000 | WO | 0 | 1706.94 | 8 | 3413.88 | 50 |  | 50 |  | 07/15/2022 | 07/15/2022 |  | 2022-07-15T14:10:46.057 | Dehnke, Josh | Materials
22-0870-IR | WO0008, Complete | Framing Labor | 2022-07-13T14:42:00.000 | WO | 0 | 700.0002 | 18 | 1386.43 | 700 |  | 49.5106 |  | 07/25/2022 | 07/26/2022 |  | 2022-07-25T14:00:38.233 | Dehnke, Josh | FRM
22-0870-IR | WO0009, Complete | Painting Labor | 2022-07-13T14:45:00.000 | WO | 0 | 800.0004 | 27 | 1154.74 | 800 |  | 30.7203 |  | 07/25/2022 | 07/27/2022 |  | 2022-08-01T11:53:26.130 | Dehnke, Josh | PNT
22-0848-IR | WO0001 | Vanity Install Labor | 2022-09-16T10:35:20.000 | WO | 0 | 575.26 | 4.97 | 575.26 | 100 |  | 0 |  | 09/16/2022 | 09/16/2022 |  |  |  | CAB
22-0848-IR | WO0002 | DRY | 2022-09-16T10:35:20.827 | WO | 0 | 2001.09 | 12.85 | 2001.09 | 100 |  | 0 |  | 09/16/2022 | 09/19/2022 |  |  |  | DRY
22-0848-IR | WO0003 | Floor Tile Material | 2022-09-16T10:35:20.000 | WO | 0 | 591.396 |  | 985.66 | 60 |  | 40 | [6 empty] | FCT
22-0848-IR | WO0004 | FNC | 2022-09-16T10:35:21.030 | WO | 0 | 85.53 | 0.28 | 85.53 | 100 |  | 0 |  | 09/16/2022 | 09/16/2022 |  |  |  | FNC
22-0848-IR | WO0005 | FRM | 2022-09-16T10:35:21.107 | WO | 0 | 805.07 | 5.92 | 805.07 | 100 |  | 0 |  | 09/16/2022 | 09/16/2022 |  |  |  | FRM
22-0848-IR | WO0006 | HVC | 2022-09-16T10:35:21.200 | WO | 0 | 395.96 | 2.05 | 395.96 | 100 |  | 0 |  | 09/16/2022 | 09/16/2022 |  |  |  | HVC
22-0848-IR | WO0007 | INS | 2022-09-16T10:35:21.300 | WO | 0 | 205.63 | 1.62 | 205.63 | 100 |  | 0 |  | 09/16/2022 | 09/16/2022 |  |  |  | INS
22-0848-IR | WO0008 | LIT | 2022-09-16T10:35:21.377 | WO | 0 | 88.38 | 0.53 | 88.38 | 100 |  | 0 |  | 09/16/2022 | 09/16/2022 |  |  |  | LIT
22-0848-IR | WO0009 | MSD | 2022-09-16T10:35:21.470 | WO | 0 | 5073.71 | 24.7 | 5073.71 | 100 |  | 0 |  | 09/16/2022 | 09/20/2022 |  |  |  | MSD
22-0848-IR | WO00010 | PLM | 2022-09-16T10:35:21.550 | WO | 0 | 3231 | 11.9 | 3231 | 100 |  | 0 |  | 09/16/2022 | 09/19/2022 |  |  |  | PLM
22-0848-IR | WO00011 | PNT | 2022-09-16T10:35:21.643 | WO | 0 | 592.75 | 4.37 | 592.75 | 100 |  | 0 |  | 09/16/2022 | 09/16/2022 |  |  |  | PNT
22-0848-IR | WO00012 | Tile Labor | 2022-09-16T10:35:21.000 | WO | 0 | 6678.308 | 43.27 | 9889.46 | 67.5296 |  | 32.4704 |  | 09/16/2022 | 09/21/2022 |  |  |  | TIL
22-0848-IR | WO00013 | Bathtub - Material | 2022-09-16T10:42:00.000 | WO | 0 | 2524.404 | 8 | 4207.34 | 60 |  | 40 |  | 09/16/2022 | 09/16/2022
22-0848-IR | WO00014 | Tile Material | 2022-09-16T10:53:00.000 | WO | 0 | 3132.792 | 8 | 5221.32 | 60 |  | 40 |  | 09/16/2022 | 09/16/2022
22-0848-IR | WO00015 | Vanity | 2022-09-16T11:00:00.000 | WO | 0 | 1266.6 | 8 | 1266.6 | 100 |  | 0 |  | 09/16/2022 | 09/16/2022
22-0916-IR
22-0227-EST
22-0164-EST | WO0001 | APP | 2022-06-15T11:01:32.417 | WO | 0 | 712.75 | 3.52 | 712.75 | 100 |  | 0 |  | 06/15/2022 | 06/15/2022 |  |  |  | APP
22-0164-EST | WO0002 | CAB | 2022-06-15T11:01:32.590 | WO | 0 | 2780.72 | 9.95 | 2780.72 | 100 |  | 0 |  | 06/15/2022 | 06/16/2022 |  |  |  | CAB
22-0164-EST | WO0003 | PLM | 2022-06-15T11:01:32.813 | WO | 0 | 400.94 | 1.95 | 400.94 | 100 |  | 0 |  | 06/15/2022 | 06/15/2022 |  |  |  | PLM
22-0641-IR
22-0692-ER
22-0445-IR | WO0002 | FEN | 2022-08-18T12:32:27.000 | WO | 0 | 184.0755 | 5.82 | 525.93 | 35 |  | 65 |  | 08/18/2022 | 08/18/2022 |  |  |  | FEN
22-0445-IR | WO0003 | materials | 2022-09-22T23:10:00.000 | WO | 0 | 194.81 | 8 | 194.81 | 100 |  | 0 |  | 09/22/2022 | 09/22/2022 |  |  |  | materials
22-0836-IR | WO0001 | CON | 2022-08-16T10:59:54.413 | WO | 0 | 249.16 | 4 | 249.16 | 100 |  | 0 |  | 08/16/2022 | 08/16/2022 |  |  |  | CON
22-0836-IR | WO0002 | DMO | 2022-08-16T10:59:54.477 | WO | 0 | 243.64 | 1.63 | 243.64 | 100 |  | 0 |  | 08/16/2022 | 08/16/2022 |  |  |  | DMO
22-0836-IR | WO0003 | DRY | 2022-08-16T10:59:54.537 | WO | 0 | 2718.47 | 16.72 | 2718.47 | 100 |  | 0 |  | 08/16/2022 | 08/17/2022 |  |  |  | DRY
22-0836-IR | WO0004 | ELE | 2022-08-16T10:59:54.600 | WO | 0 | 36.06 | 0 | 36.06 | 100 |  | 0 |  | 08/16/2022 | 08/16/2022 |  |  |  | ELE
22-0836-IR | WO0005 | FCW | 2022-08-16T10:59:54.647 | WO | 0 | 2860.11 | 16.45 | 2860.11 | 100 |  | 0 |  | 08/16/2022 | 08/17/2022 |  |  |  | FCW
22-0836-IR | WO0006 | FNC | 2022-08-16T10:59:54.693 | WO | 0 | 828.1 | 4.97 | 828.1 | 100 |  | 0 |  | 08/16/2022 | 08/16/2022 |  |  |  | FNC
22-0836-IR | WO0007 | HVC | 2022-08-16T10:59:54.757 | WO | 0 | 403.21 | 2.33 | 403.21 | 100 |  | 0 |  | 08/16/2022 | 08/16/2022 |  |  |  | HVC
22-0836-IR | WO0008 | LIT | 2022-08-16T10:59:54.820 | WO | 0 | 551.36 | 2.48 | 551.36 | 100 |  | 0 |  | 08/16/2022 | 08/16/2022 |  |  |  | LIT
22-0836-IR | WO0009 | PLA | 2022-08-16T10:59:54.880 | WO | 0 | 10218.63 | 69.42 | 10218.63 | 100 |  | 0 |  | 08/16/2022 | 08/25/2022 |  |  |  | PLA
22-0836-IR | WO00010 | PNT | 2022-08-16T10:59:54.930 | WO | 0 | 1997.82 | 14.18 | 1997.82 | 100 |  | 0 |  | 08/16/2022 | 08/17/2022 |  |  |  | PNT
22-0726-ER
22-0679-IR
22-0325-IR
22-0874-IR | WO0001 | CLN | 2022-07-18T13:46:15.083 | WO | 0 | 658.95 | 8.6 | 658.95 | 100 |  | 0 |  | 07/18/2022 | 07/19/2022 |  |  |  | CLN
22-0874-IR | WO0002 | CON | 2022-07-18T13:46:15.213 | WO | 0 | 866.21 | 14 | 866.21 | 100 |  | 0 |  | 07/18/2022 | 07/19/2022 |  |  |  | CON
22-0874-IR | WO0003 | DRY | 2022-07-18T13:46:15.440 | WO | 0 | 1155.37 | 6.07 | 1155.37 | 100 |  | 0 |  | 07/18/2022 | 07/18/2022 |  |  |  | DRY
22-0874-IR | WO0004 | FCC | 2022-07-18T13:46:15.760 | WO | 0 | 5885.31 | 12.23 | 5885.31 | 100 |  | 0 |  | 07/18/2022 | 07/19/2022 |  |  |  | FCC
22-0874-IR | WO0005 | FNC | 2022-07-18T13:46:16.283 | WO | 0 | 277.95 | 0.37 | 277.95 | 100 |  | 0 |  | 07/18/2022 | 07/18/2022 |  |  |  | FNC
22-0874-IR | WO0006 | PNT | 2022-07-18T13:46:16.710 | WO | 0 | 2506.71 | 16.85 | 2506.71 | 100 |  | 0 |  | 07/18/2022 | 07/19/2022 |  |  |  | PNT
22-0103-D | WO0001 | APP | 2022-09-30T13:41:37.507 | WO | 0 | 372.42 | 2.27 | 372.42 | 100 |  | 0 |  | 09/30/2022 | 09/30/2022 |  |  |  | APP
22-0103-D | WO0002 | CAB | 2022-09-30T13:41:37.630 | WO | 0 | 283.32 | 1.55 | 283.32 | 100 |  | 0 |  | 09/30/2022 | 09/30/2022 |  |  |  | CAB
22-0103-D | WO0003 | CON | 2022-09-30T13:41:37.710 | WO | 0 | 782.88 | 12 | 782.88 | 100 |  | 0 |  | 09/30/2022 | 10/03/2022 |  |  |  | CON
22-0103-D | WO0004 | FCC | 2022-09-30T13:41:37.787 | WO | 0 | 2171.99 | 5.7 | 2171.99 | 100 |  | 0 |  | 09/30/2022 | 09/30/2022 |  |  |  | FCC
22-0103-D | WO0005 | FCV | 2022-09-30T13:41:37.877 | WO | 0 | 1258.15 | 4.75 | 1258.15 | 100 |  | 0 |  | 09/30/2022 | 09/30/2022 |  |  |  | FCV
22-0103-D | WO0006 | PLM | 2022-09-30T13:41:37.947 | WO | 0 | 537.82 | 2.1 | 537.82 | 100 |  | 0 |  | 09/30/2022 | 09/30/2022 |  |  |  | PLM
22-0103-D | WO0007 | PNL | 2022-09-30T13:41:38.050 | WO | 0 | 523.76 | 2.22 | 523.76 | 100 |  | 0 |  | 09/30/2022 | 09/30/2022 |  |  |  | PNL
22-0103-D | WO0008 | PNT | 2022-09-30T13:41:38.130 | WO | 0 | 915.59 | 6.82 | 915.59 | 100 |  | 0 |  | 09/30/2022 | 09/30/2022 |  |  |  | PNT
22-0098-ER
22-0136-D | WO0001, Complete | SDG MAT | 2022-05-31T13:47:00.000 | WO | 0 | 1500 | 0 | 2500 | 60 |  | 40 |  | 08/01/2022 | 08/01/2022 |  | 2022-06-22T11:46:37.670 | Burrell, Bianca | SDG
22-0136-D | WO0002, Complete | SDG Labor | 2022-05-31T13:48:00.000 | WO | 0 | 1991.4 | 24 | 3319 | 60 |  | 40 |  | 08/03/2022 | 08/05/2022 |  | 2022-07-26T12:36:36.180 | Trevino, Jeovani | SDG
22-0860-IR | WO0001, Complete | DRY | 2022-06-09T18:12:48.000 | WO | 0 | 1204.62 | 21.85 | 1606.16 | 75 |  | 25 |  | 06/27/2022 | 06/29/2022 |  | 2022-06-28T16:01:08.947 | Trevino, Jeovani | DRY
22-0448-IR
22-0523-IR | WO0001, Complete | CLN | 2022-08-03T11:24:58.000 | WO | 0 | 0 | 11.12 | 187.55 | 0 |  | 100 |  | 08/10/2022 | 08/11/2022 |  | 2022-08-15T12:43:35.263 | Deville , Jard | CLN
22-0523-IR | WO0002, Complete | CON | 2022-08-03T11:24:58.000 | WO | 0 | 0 | 11.2 | 136.2 | 0 |  | 100 |  | 08/10/2022 | 08/11/2022 |  | 2022-08-15T12:43:38.983 | Deville , Jard | CON
22-0523-IR | WO0004, Complete | DRY | 2022-08-03T11:24:58.000 | WO | 0 | 1912.086 | 8.77 | 3186.81 | 60 |  | 40 |  | 08/10/2022 | 08/11/2022 |  | 2022-08-15T12:43:42.090 | Deville , Jard | DRY
22-0523-IR | WO0005, Complete | ELE | 2022-08-03T11:27:00.000 | WO | 0 | 0 | 17 | 217.6 | 0 |  | 100 |  | 08/10/2022 | 08/11/2022 |  | 2022-08-15T12:43:44.663 | Deville , Jard | ELE
22-0844-ER | WO0001 | DMO | 2022-07-18T14:04:57.667 | WO | 0 | 228.75 | 1.98 | 228.75 | 100 |  | 0 |  | 07/18/2022 | 07/18/2022 |  |  |  | DMO
22-0844-ER | WO0002 | FRM | 2022-07-18T14:04:58.250 | WO | 0 | 415.78 | 4 | 415.78 | 100 |  | 0 |  | 07/18/2022 | 07/18/2022 |  |  |  | FRM
22-0844-ER | WO0003 | SDG | 2022-07-18T14:04:58.330 | WO | 0 | 871.75 | 4.75 | 871.75 | 100 |  | 0 |  | 07/18/2022 | 07/18/2022 |  |  |  | SDG
22-0844-ER | WO0004 | SFG | 2022-07-18T14:04:58.397 | WO | 0 | 1079.74 | 2.88 | 1079.74 | 100 |  | 0 |  | 07/18/2022 | 07/18/2022 |  |  |  | SFG
22-0753-EST
22-0684-IR
22-0826-ER
22-0595-ER
22-0682-RET-ER
22-0714-IR
22-0760-IR
22-0694-ER
22-0198-IR
22-0678-IR | WO0001, Complete | CLN | 2022-06-01T14:34:19.000 | WO | 0 | 0 | 4 | 20.25 | 0 |  | 100 |  | 07/15/2022 | 07/15/2022 |  | 2022-07-15T14:16:05.657 | Deville , Jard | CLN
22-0678-IR | WO0002, Complete | CON | 2022-06-01T14:34:20.000 | WO | 0 | 0 | 2 | 58.14 | 0 |  | 100 |  | 07/11/2022 | 07/11/2022 |  | 2022-07-15T14:16:03.350 | Deville , Jard | CON
22-0678-IR | WO0003, Complete | DRY,PNT,MAT | 2022-06-01T14:34:20.000 | WO | 0 | 689.9996 | 17 | 934.15 | 690 |  | 26.1361 |  | 06/29/2022 | 06/30/2022 |  | 2022-07-01T08:55:41.267 | Deville , Jard | DRY
22-0678-IR | WO0004, Complete | FCC | 2022-06-01T14:34:20.000 | WO | 0 | 250 | 18 | 223.23 | 250 |  | -11.9921 |  | 07/11/2022 | 07/12/2022 |  | 2022-07-15T14:16:16.293 | Deville , Jard | FCC
22-0678-IR | WO0005, Complete | FNC | 2022-06-01T14:34:20.000 | WO | 0 | 161 | 18 | 251.64 | 161 |  | 36.0197 |  | 07/13/2022 | 07/14/2022 |  | 2022-07-19T11:29:55.773 | Deville , Jard | FNC
22-0678-IR | WO0008, Complete | FCC Materials | 2022-06-01T14:49:00.000 | WO | 1 | 780.0004 | 17 | 1203.01 | 780 |  | 35.1626 |  | 07/06/2022 | 07/07/2022 |  | 2022-07-11T07:11:24.200 | Deville , Jard | FCC
22-0490-C
22-0695-D
22-0268-RET-ER
22-0343-C
22-0200-EST | WO0009, Complete | Bernabe | 2022-06-08T17:12:00.000 | WO | 0 | 11969.608 | 117.15 | 17099.44 | 70 |  | 30 |  | 05/31/2022 | 06/10/2022 |  | 2022-06-27T07:57:59.713 | Feltmann, Brandon | Bernabe
22-0558-IR
22-0696-EST
22-0701-ER
22-0768-IR
22-0254-ER
22-0549-IR
22-0203-IR
22-0246-IR | WO0001, Complete | DOR | 2022-06-03T15:39:42.113 | WO | 0 | 36.08 | 0.42 | 36.08 | 100 |  | 0 |  | 06/03/2022 | 06/03/2022 |  | 2022-06-14T13:11:25.763 | Burrell, Bianca | DOR
22-0246-IR | WO0002, Complete | DRY | 2022-06-03T15:39:42.270 | WO | 0 | 467.77 | 2.82 | 467.77 | 100 |  | 0 |  | 06/03/2022 | 06/03/2022 |  | 2022-06-14T13:11:25.793 | Burrell, Bianca | DRY
22-0246-IR | WO0003, Complete | ELE | 2022-06-03T15:39:42.427 | WO | 0 | 255.48 | 0 | 255.48 | 100 |  | 0 |  | 06/03/2022 | 06/03/2022 |  | 2022-06-14T13:11:25.827 | Burrell, Bianca | ELE
22-0246-IR | WO0004, Complete | FNC | 2022-06-03T15:39:42.553 | WO | 0 | 533.66 | 6.27 | 533.66 | 100 |  | 0 |  | 06/03/2022 | 06/03/2022 |  | 2022-06-14T13:11:25.840 | Burrell, Bianca | FNC
22-0246-IR | WO0005, Complete | LIT | 2022-06-03T15:39:42.630 | WO | 0 | 69.58 | 0.53 | 69.58 | 100 |  | 0 |  | 06/03/2022 | 06/03/2022 |  | 2022-06-14T13:11:25.887 | Burrell, Bianca | LIT
22-0246-IR | WO0006, Complete | PNT | 2022-06-03T15:39:42.693 | WO | 0 | 231.29 | 1.85 | 231.29 | 100 |  | 0 |  | 06/03/2022 | 06/03/2022 |  | 2022-06-14T13:11:25.717 | Burrell, Bianca | PNT
22-0246-IR | WO0007, Complete | CLN | 2022-07-01T09:46:22.000 | WO | 0 | 191.54 |  | 191.54 | 100 |  | 0 |  |  |  |  | 2022-07-08T08:33:54.067 | Trevino, Jeovani | CLN
22-0258-IR | WO0002, Complete | Steve | 2022-05-20T14:21:04.000 | WO | 0 | 670.894 | 8.37 | 958.42 | 70 |  | 30 |  | 05/20/2022 | 05/20/2022 |  | 2022-06-27T07:57:36.740 | Feltmann, Brandon | ELE
22-0258-IR | WO0004, Complete | Plumbing | 2022-05-20T14:21:04.000 | WO | 0 | 980.592 | 6 | 1225.74 | 80 |  | 20 |  | 05/20/2022 | 05/20/2022 |  | 2022-06-27T07:57:36.770 | Feltmann, Brandon | PLM
22-0258-IR | WO0005, Complete | Drywall/paint | 2022-05-20T14:21:04.000 | WO | 0 | 2381.218 | 30.78 | 3401.74 | 70 |  | 30 |  | 05/20/2022 | 05/25/2022 |  | 2022-06-27T07:57:36.800 | Feltmann, Brandon | PNT
22-0258-IR | WO0006, Complete | Plumbing parts | 2022-05-20T15:15:00.000 | WO | 0 | 751.61 | 8.42 | 710.53 | 751.61 |  | -5.7816 |  | 05/20/2022 | 05/20/2022 |  | 2022-06-27T07:57:36.817 | Feltmann, Brandon | PLM
22-0180-IR | WO0004, Complete | tile/labor/beacon | 2022-06-03T15:20:38.000 | WO | 0 |  |  |  | 0 |  | 0 |  |  |  |  | 2022-06-22T08:41:05.573 | Burrell, Bianca | TIL
22-0180-IR | WO0005, Complete | drywall/paint | 2022-06-03T15:22:00.000 | WO | 0 | 1105.674 | 22.47 | 1842.79 | 60 |  | 40 |  | 06/03/2022 | 06/03/2022 |  | 2022-06-14T13:09:32.833 | Burrell, Bianca | drywall
22-0017-D
22-0373-IR
22-0269-ER
22-0214-IR
22-0224-ER
22-0256-ER
22-0261-ER
22-0265-IR
22-0187-IR
22-0186-IR
22-0105-ER
22-0175-EST
22-0175-IR
22-0263-EST | WO0004, Complete | Carpet | 2022-05-27T20:40:51.000 | WO | 0 | 966.834 | 13.87 | 1757.88 | 55 |  | 45 |  | 05/27/2022 | 05/27/2022 |  | 2022-06-27T07:57:13.700 | Feltmann, Brandon | FCC
22-0263-EST | WO0006, Complete | Baseboard | 2022-05-27T20:40:51.000 | WO | 0 | 1087.4797 | 19.22 | 2108.52 | 1087.48 |  | 48.4245 |  | 05/27/2022 | 05/27/2022 |  | 2022-06-27T07:57:13.710 | Feltmann, Brandon | FNC
22-0263-EST | WO0007, Complete | Plumbing | 2022-05-27T20:40:51.000 | WO | 0 | 525.06 | 1.98 | 525.06 | 100 |  | 0 |  | 05/27/2022 | 05/27/2022 |  | 2022-06-27T07:57:13.723 | Feltmann, Brandon | PLM
22-0264-EST
22-0149-IR
22-0407-IR
22-0107-ER
22-0215-IR
22-0226-D
22-0330-RET-ER
22-0719-ER
22-0139-IR
22-0683-IR | WO0001, Complete | CLN | 2022-06-06T15:25:10.670 | WO | 0 | 208.62 | 2.45 | 208.62 | 100 |  | 0 |  | 06/06/2022 | 06/06/2022 |  | 2022-06-14T18:38:59.830 | Sleem, Michael | CLN
22-0683-IR | WO0002, Complete | CON | 2022-06-06T15:25:10.787 | WO | 0 | 227.02 | 4.4 | 227.02 | 100 |  | 0 |  | 06/06/2022 | 06/06/2022 |  | 2022-06-14T18:38:59.970 | Sleem, Michael | CON
22-0683-IR | WO0003, Complete | DRY | 2022-06-06T15:25:10.877 | WO | 0 | 2563.91 | 2.35 | 2563.91 | 100 |  | 0 |  | 06/06/2022 | 06/06/2022 |  | 2022-06-14T18:39:00.057 | Sleem, Michael | DRY
22-0683-IR | WO0004, Complete | FCC | 2022-06-06T15:25:10.977 | WO | 0 | 331.05 | 0.35 | 331.05 | 100 |  | 0 |  | 06/06/2022 | 06/06/2022 |  | 2022-06-14T18:39:00.123 | Sleem, Michael | FCC
22-0683-IR | WO0005, Complete | FNC | 2022-06-06T15:25:11.107 | WO | 0 | 226.62 | 0.58 | 226.62 | 100 |  | 0 |  | 06/06/2022 | 06/06/2022 |  | 2022-06-14T18:39:00.177 | Sleem, Michael | FNC
22-0683-IR | WO0006, Complete | INS | 2022-06-06T15:25:11.207 | WO | 0 | 292.06 | 0.02 | 292.06 | 100 |  | 0 |  | 06/06/2022 | 06/06/2022 |  | 2022-06-14T18:39:00.200 | Sleem, Michael | INS
22-0683-IR | WO0007, Complete | PNT | 2022-06-06T15:25:11.370 | WO | 0 | 1068.61 | 9.4 | 1068.61 | 100 |  | 0 |  | 06/06/2022 | 06/07/2022 |  | 2022-06-14T18:39:00.260 | Sleem, Michael | PNT
22-0701-IR
22-0194-C
22-0373-ER
22-0270-ER
22-0269-IR | WO0001 | CON | 2022-06-16T14:00:28.973 | WO | 0 | 247.49 | 4 | 247.49 | 100 |  | 0 |  | 06/16/2022 | 06/16/2022 |  |  |  | CON
22-0269-IR | WO0002 | DRY | 2022-06-16T14:00:29.173 | WO | 0 | 1191.24 | 7.35 | 1191.24 | 100 |  | 0 |  | 06/16/2022 | 06/16/2022 |  |  |  | DRY
22-0269-IR | WO0003 | ELE | 2022-06-16T14:00:29.363 | WO | 0 | 36.05 | 0 | 36.05 | 100 |  | 0 |  | 06/16/2022 | 06/16/2022 |  |  |  | ELE
22-0269-IR | WO0004 | LIT | 2022-06-16T14:00:29.643 | WO | 0 | 550.25 | 2.48 | 550.25 | 100 |  | 0 |  | 06/16/2022 | 06/16/2022 |  |  |  | LIT
22-0269-IR | WO0005 | PNT | 2022-06-16T14:00:29.893 | WO | 0 | 1058.81 | 8.7 | 1058.81 | 100 |  | 0 |  | 06/16/2022 | 06/17/2022 |  |  |  | PNT
22-0197-IR | WO0001 | DRY | 2022-06-20T13:59:35.330 | WO | 0 | 683.26 | 3.85 | 683.26 | 100 |  | 0 |  | 06/20/2022 | 06/20/2022 |  |  |  | DRY
22-0197-IR | WO0002 | LIT | 2022-06-20T13:59:35.423 | WO | 0 | 300.96 | 1.9 | 300.96 | 100 |  | 0 |  | 06/20/2022 | 06/20/2022 |  |  |  | LIT
22-0197-IR | WO0003 | PNT | 2022-06-20T13:59:35.483 | WO | 0 | 800.79 | 5.67 | 800.79 | 100 |  | 0 |  | 06/20/2022 | 06/20/2022 |  |  |  | PNT
22-0197-IR | WO0004 | RFG | 2022-06-20T13:59:35.573 | WO | 0 | 446.45 | 2 | 446.45 | 100 |  | 0 |  | 06/20/2022 | 06/20/2022 |  |  |  | RFG
22-0197-IR | WO0005 | SDG | 2022-06-20T13:59:35.633 | WO | 0 | 143.73 | 0.7 | 143.73 | 100 |  | 0 |  | 06/20/2022 | 06/20/2022 |  |  |  | SDG
22-0270-IR | WO0003 | ELE | 2022-05-31T16:47:24.000 | WO | 0 | 0 | 0 | 258.57 | 0 |  | 100 |  | 05/31/2022 | 05/31/2022 |  |  |  | ELE
22-0270-IR | WO0008 | Plumber | 2022-05-31T16:47:25.000 | WO | 0 | 643.44 | 3.42 | 643.44 | 100 |  | 0 |  | 05/31/2022 | 05/31/2022 |  |  |  | PLM
22-0270-IR | WO0009 | Paneling | 2022-05-31T16:47:26.000 | WO | 0 | 1446.9146 | 13.85 | 1955.29 | 74 |  | 26 |  | 05/31/2022 | 05/31/2022 |  |  |  | PNL
22-0270-IR | WO00010 | Door/Trim | 2022-06-06T14:18:00.000 | WO | 0 | 499.264 | 8 | 624.08 | 80 |  | 20 |  | 06/06/2022 | 06/06/2022 |  |  |  | Door/trim
22-0231-EST
22-0433-ER
22-0265-ER
22-0349-ER
22-0139-IR;EST
22-0472-IR | WO0002 | Carpet Cleaning | 2022-05-19T10:51:29.000 | WO | 0 | 536.683 | 7.2 | 766.69 | 70 |  | 30 |  | 05/19/2022 | 05/19/2022 |  |  |  | CON
22-0472-IR | WO0003 | Ceiling tiles | 2022-05-19T10:51:29.000 | WO | 0 | 2000.0011 | 2.35 | 2563.91 | 2000 |  | 21.9941 |  | 05/19/2022 | 05/19/2022 |  |  |  | DRY
22-0472-IR | WO0005 | Trim | 2022-05-19T10:51:29.000 | WO | 0 | 226.62 | 0.58 | 226.62 | 100 |  | 0 |  | 05/19/2022 | 05/19/2022 |  |  |  | FNC
22-0472-IR | WO0007 | Drywall | 2022-05-19T10:51:29.000 | WO | 0 | 1369.11 | 9.48 | 1369.11 | 100 |  | 0 |  | 05/19/2022 | 05/20/2022 |  |  |  | PNT
22-0257-ER
22-0248-ER | WO0001 | RFG Labor | 2022-06-03T10:35:22.000 | WO | 0 | 5502.985 | 58.82 | 11005.97 | 50 |  | 50 |  | 06/03/2022 | 06/13/2022 |  |  |  | RFG
22-0248-ER | WO0002 | SFG Labor | 2022-06-03T10:35:22.000 | WO | 0 | 2235.704 | 31.8 | 5589.26 | 40 |  | 60 |  | 06/03/2022 | 06/08/2022 |  |  |  | SFG
22-0248-ER | WO0003 | RFG Materials | 2022-06-03T10:37:00.000 | WO | 0 | 2434.1845 | 8 | 4425.79 | 55 |  | 45 |  | 06/03/2022 | 06/03/2022 |  |  |  | RFG materials
22-0248-ER | WO0004 | SFG Materials | 2022-06-03T10:39:00.000 | WO | 0 | 1606.187 | 8 | 2920.34 | 55 |  | 45 |  | 06/03/2022 | 06/03/2022 |  |  |  | SFG Materials
22-0133-D
22-0372-ER
22-0446-ER
22-0482-IR
22-0210-C
22-0176-D
22-0121-D
22-0013-D
22-0016-D | WO0001, Complete | Materials | 2022-08-29T11:18:00.000 | WO | 0 | 12880 | 8 | 16100 | 80 |  | 20 |  | 08/29/2022 | 08/29/2022 |  | 2022-08-29T10:20:12.907 | Dehnke, Josh | MAT
22-0016-D | WO0002, Complete | Profit 1/2 | 2022-08-29T11:20:00.000 | WO | 0 | 0 | 8 | 3602 | 0 |  | 100 |  | 08/29/2022 | 08/29/2022 |  | 2022-10-21T14:50:32.230 | Dehnke, Josh | PROFIT
22-0016-D | WO0004, Complete | Overhead First 1/2 | 2022-08-29T11:22:00.000 | WO | 0 | 0 | 8 | 2401.5 | 0 |  | 100 |  | 08/29/2022 | 08/29/2022 |  | 2022-10-21T14:52:33.473 | Dehnke, Josh | Overhead
22-0016-D | WO0005, Complete | Design Fee | 2022-08-29T11:23:00.000 | WO | 0 | 0 | 8 | 1600 | 0 |  | 100 |  | 08/29/2022 | 08/29/2022 |  | 2022-10-21T14:50:32.200 | Dehnke, Josh | Design
22-0016-D | WO0006, Complete | Planning Fee | 2022-08-29T11:36:00.000 | WO | 0 | 1000 | 8 | 1000 | 100 |  | 0 |  | 08/29/2022 | 08/29/2022 |  | 2022-10-21T14:50:32.183 | Dehnke, Josh | Planning
22-0016-D | WO0008, Complete | Overhead Final 1/2 | 2022-10-21T15:52:00.000 | WO | 0 | 0 | 8 | 2401.5 | 0 |  | 100 |  | 03/29/2023 | 03/29/2023 |  | 2023-04-03T12:21:29.840 | Trevino, Jeovani | Overhead
22-0016-D | WO0009, Complete | Demo Labor | 2022-12-21T08:52:00.000 | WO | 0 | 2070 | 16 | 3450 | 60 |  | 40 |  | 08/29/2022 | 12/21/2022 |  | 2022-12-27T11:36:41.583 | Dehnke, Josh | DMO
22-0016-D | WO00010, Complete | Framing Labor | 2022-12-21T08:53:00.000 | WO | 0 | 3469 | 16 | 6938 | 50 |  | 50 |  | 12/21/2022 | 12/21/2022 |  | 2022-12-27T11:36:41.620 | Dehnke, Josh | FRM
22-0016-D | WO00011, Complete | Electrical Labor | 2022-12-21T08:57:00.000 | WO | 0 | 8222.4 | 8 | 10278 | 80 |  | 20 |  | 12/21/2022 | 12/21/2022 |  | 2023-01-16T07:56:09.803 | Dehnke, Josh | ELE
22-0016-D | WO00012, Complete | Plumbing/HVAC Labor | 2022-12-21T08:58:00.000 | WO | 0 | 3922.4 | 16 | 4903 | 80 |  | 20 |  | 12/21/2022 | 12/21/2022 |  | 2023-01-16T07:56:09.827 | Dehnke, Josh | PLM
22-0016-D | WO00015, Complete | Drywall Labor (Ready for Paint) | 2022-12-21T09:00:00.000 | WO | 0 | 3177 | 8 | 6354 | 50 |  | 50 |  | 12/21/2022 | 12/21/2022 |  | 2023-01-30T11:28:11.973 | Dehnke, Josh | DRY
22-0016-D | WO00016, Complete | Cabinetry Labor | 2022-12-21T09:00:00.000 | WO | 0 | 1802.8 | 8 | 4507 | 40 |  | 60 |  | 12/21/2022 | 12/21/2022 |  | 2023-02-06T10:15:29.633 | Dehnke, Josh | Cab
22-0016-D | WO00017, Complete | Countertop Labor | 2022-12-21T09:02:00.000 | WO | 0 | 4675.2 | 8 | 5844 | 80 |  | 20 |  | 12/21/2022 | 12/21/2022 |  | 2023-02-06T10:15:29.657 | Dehnke, Josh | CTOP
22-0016-D | WO00019, Complete | Flooring Labor | 2022-12-21T09:04:00.000 | WO | 0 | 1658.5 | 16 | 3317 | 50 |  | 50 |  | 12/21/2022 | 12/21/2022 |  | 2023-02-22T10:37:08.343 | Dehnke, Josh | FCW
22-0016-D | WO00021, Complete | Final Punch | 2022-12-21T09:08:00.000 | WO | 0 | 900.0002 | 26 | 3902 | 900 |  | 76.9349 |  | 03/21/2023 | 03/23/2023 |  | 2023-04-03T12:21:29.980 | Trevino, Jeovani | CLN
22-0016-D | WO00022, Complete | Paint Labor (Ceilings and Walls) | 2023-01-11T14:40:00.000 | WO | 0 | 1773.75 | 16 | 2365 | 75 |  | 25 |  | 01/11/2023 | 12/22/2022 |  | 2023-02-13T08:22:40.073 | Dehnke, Josh | PNT
22-0135-D | WO0001, Complete | Design/Planning | 2022-07-27T16:27:00.000 | WO | 0 | 0 | 8 | 2100 | 0 |  | 100 |  | 08/01/2022 | 08/01/2022 |  | 2022-08-01T13:08:26.517 | Dehnke, Josh | Design
22-0135-D | WO0004, Complete | Demo/ Site Set Up | 2022-08-01T10:42:00.000 | WO | 0 | 2280 | 25 | 3800 | 60 |  | 40 |  | 11/14/2022 | 11/21/2022 |  | 2022-10-21T14:44:20.087 | Dehnke, Josh | Demo
22-0135-D | WO0005, Complete | Electrical Labor | 2022-08-01T10:43:00.000 | WO | 0 | 8232 | 16 | 10290 | 80 |  | 20 |  | 11/18/2022 | 11/21/2022 |  | 2022-11-14T14:45:18.267 | Dehnke, Josh | Electrical
22-0135-D | WO0006, Complete | Plumbing Labor | 2022-08-01T10:45:00.000 | WO | 0 | 5460.8 | 16 | 6826 | 80 |  | 20 |  | 11/16/2022 | 11/21/2022 |  | 2022-11-21T07:54:02.247 | Dehnke, Josh | PLM
22-0135-D | WO0007, Complete | HVAC Labor | 2022-08-01T10:45:00.000 | WO | 0 | 800 | 8 | 1000 | 80 |  | 20 |  | 11/17/2022 | 11/17/2022 |  | 2022-11-21T07:54:02.297 | Dehnke, Josh | HVAC
22-0135-D | WO0008, Complete | Cabinetry Labor | 2022-08-01T10:48:00.000 | WO | 0 | 1799.9987 | 8 | 4449 | 1800 |  | 59.5415 |  | 08/01/2022 | 08/01/2022 |  | 2022-08-01T13:08:26.537 | Dehnke, Josh | CAB
22-0135-D | WO0009, Complete | Countertops Materials | 2022-08-01T10:49:00.000 | WO | 0 | 3390.4 | 17 | 4238 | 80 |  | 20 |  | 11/24/2022 | 11/25/2022 |  | 2022-08-08T08:04:13.433 | Dehnke, Josh | Countertops
22-0135-D | WO00010, Complete | Carpentry/Millwork | 2022-08-01T10:50:00.000 | WO | 0 | 593.4 | 26 | 989 | 60 |  | 40 |  | 12/05/2022 | 12/07/2022 |  | 2022-12-08T11:08:31.387 | Dehnke, Josh | FNC
22-0135-D | WO00011, Complete | Tiling Labor | 2022-08-01T10:51:00.000 | WO | 0 | 6040 | 42 | 12080 | 50 |  | 50 |  | 11/21/2022 | 11/30/2022 |  | 2023-02-06T10:04:24.193 | Dehnke, Josh | TIL
22-0135-D | WO00012, Complete | Flooring | 2022-08-01T10:52:00.000 | WO | 0 | 383.5 | 26 | 767 | 50 |  | 50 |  | 12/05/2022 | 12/07/2022 |  | 2022-12-16T09:51:36.223 | Dehnke, Josh | Flooring
22-0135-D | WO00015, Complete | O&P First 1/2 | 2022-08-01T10:53:00.000 | WO | 0 | 0 | 8 | 2083 | 0 |  | 100 |  | 12/09/2022 | 12/09/2022 |  | 2022-10-21T14:44:20.057 | Dehnke, Josh | O&A
22-0135-D | WO00016, Complete | Profit First 1/2 | 2022-08-01T10:54:00.000 | WO | 0 | 0 | 8 | 3124.5 | 0 |  | 100 |  | 12/09/2022 | 12/09/2022 |  | 2022-10-21T14:44:20.070 | Dehnke, Josh | Profit
22-0135-D | WO00018, Complete | Materials | 2022-08-01T10:55:00.000 | WO | 0 | 14888 | 16 | 18610 | 80 |  | 20 |  | 08/01/2022 | 11/21/2022 |  | 2022-08-01T13:08:26.547 | Dehnke, Josh | MAT
22-0135-D | WO00019, Complete | O&P Final 1/2 | 2022-10-21T15:42:00.000 | WO | 0 | 0 | 17 | 2083 | 0 |  | 100 |  | 03/23/2023 | 03/24/2023 |  | 2023-04-03T12:21:56.730 | Trevino, Jeovani | O&P
22-0135-D | WO00020, Complete | Profit Final 1/2 | 2022-10-21T15:43:00.000 | WO | 0 | 0 | 17 | 3124.5 | 0 |  | 100 |  | 03/23/2023 | 03/24/2023 |  | 2023-04-03T12:21:56.743 | Trevino, Jeovani | Profit
22-0135-D | WO00021, Complete | Bathroom Demo | 2022-11-21T08:58:00.000 | WO | 0 | 796.8 | 8 | 996 | 80 |  | 20 |  | 11/21/2022 | 11/21/2022 |  | 2022-11-21T09:57:46.977 | Dehnke, Josh | DMO
22-0135-D | WO00022, Complete | Patches, Texture and paint | 2023-03-16T16:46:00.000 | WO | 0 | 1000.0007 | 42 | 1859 | 1000 |  | 46.2076 |  | 12/01/2022 | 12/07/2022 |  | 2023-04-03T12:21:56.760 | Trevino, Jeovani | DRY
22-0120-D | WO0001, Complete | Materials | 2022-08-08T13:33:00.000 | WO | 0 | 10412 | 8 | 10412 | 100 |  | 0 |  | 08/08/2022 | 08/08/2022 |  | 2022-08-09T11:21:32.933 | Dehnke, Josh | MAT
22-0120-D | WO0002, Complete | Profit 1/2 | 2022-08-08T13:36:00.000 | WO | 0 | 0 | 8 | 2764.5 | 0 |  | 100 |  | 08/08/2022 | 08/08/2022 |  | 2022-08-17T19:00:01.403 | Dehnke, Josh | Profit
22-0120-D | WO0003, Complete | Profit Final 1/2 | 2022-08-08T13:36:00.000 | WO | 0 | 0 | 8 | 2764.5 | 0 |  | 100 |  | 08/08/2022 | 08/08/2022 |  | 2022-09-28T08:35:39.270 | Dehnke, Josh | Profit
22-0120-D | WO0004, Complete | Overhead 1/2 | 2022-08-08T13:37:00.000 | WO | 0 | 0 | 8 | 1843 | 0 |  | 100 |  | 08/08/2022 | 08/08/2022 |  | 2022-08-17T19:00:01.310 | Dehnke, Josh | Overhead
22-0120-D | WO0005, Complete | Overhead Final 1/2 | 2022-08-08T13:37:00.000 | WO | 0 | 0 | 8 | 1843 | 0 |  | 100 |  | 08/08/2022 | 08/08/2022 |  | 2022-10-17T09:22:45.817 | Dehnke, Josh | Overhead
22-0120-D | WO0006, Complete | Drywall - Paint Labor/Materials | 2022-08-08T13:43:00.000 | WO | 0 | 2356.75 | 8 | 4285 | 55 |  | 45 |  | 08/08/2022 | 08/08/2022 |  | 2022-09-23T14:31:16.827 | Dehnke, Josh | DRY
22-0120-D | WO0007, Complete | HVAC LABOR | 2022-08-08T13:44:00.000 | WO | 0 | 1807 | 8 | 1807 | 100 |  | 0 |  | 08/08/2022 | 08/08/2022 |  | 2022-09-19T07:39:03.213 | Dehnke, Josh | HVAC
22-0120-D | WO0008, Complete | Cabinet Labor | 2022-08-08T13:45:00.000 | WO | 0 | 1782.8 | 8 | 4457 | 40 |  | 60 |  | 08/08/2022 | 08/08/2022 |  | 2022-09-28T08:35:27.783 | Dehnke, Josh | CAB
22-0120-D | WO0009, Complete | Design-Planning | 2022-08-09T08:44:00.000 | WO | 0 | 0 | 8 | 950 | 0 |  | 100 |  | 08/09/2022 | 08/09/2022 |  | 2022-08-09T11:21:43.530 | Dehnke, Josh | Design
22-0120-D | WO00010, Complete | Site Set Up - Demo | 2022-08-09T08:45:00.000 | WO | 0 | 1400 | 8 | 2800 | 50 |  | 50 |  | 08/09/2022 | 08/09/2022 |  | 2022-09-15T08:03:05.910 | Dehnke, Josh | DMO
22-0120-D | WO00011, Complete | Fraiming Labor | 2022-08-09T08:49:00.000 | WO | 0 | 587.7 | 8 | 1306 | 45 |  | 55 |  | 08/09/2022 | 08/09/2022 |  | 2022-09-23T14:31:16.840 | Dehnke, Josh | FRM
22-0120-D | WO00012, Complete | Electrical Labor | 2022-08-09T08:50:00.000 | WO | 0 | 2775.0006 | 8 | 3419 | 2775 |  | 18.8359 |  | 08/09/2022 | 08/09/2022 |  | 2022-09-15T08:03:05.923 | Dehnke, Josh | ELE
22-0120-D | WO00013, Complete | Plumbing Labor | 2022-08-09T08:50:00.000 | WO | 0 | 4214.9985 | 8 | 5277 | 4215 |  | 20.1251 |  | 08/09/2022 | 08/09/2022 |  | 2022-09-15T08:03:05.940 | Dehnke, Josh | PLM
22-0120-D | WO00014, Complete | Countertop Labor | 2022-08-09T08:51:00.000 | WO | 0 | 2503 | 8 | 2503 | 100 |  | 0 |  | 08/09/2022 | 08/09/2022 |  | 2022-10-17T09:22:45.973 | Dehnke, Josh | CAB
22-0120-D | WO00015, Complete | Finish Carpentry | 2022-08-09T08:52:00.000 | WO | 0 | 248.05 | 8 | 451 | 55 |  | 45 |  | 08/09/2022 | 08/09/2022 |  | 2022-10-21T11:49:54.823 | Dehnke, Josh | FNC
22-0120-D | WO00016, Complete | Flooring Labor | 2022-08-09T08:53:00.000 | WO | 0 | 416.4 | 8 | 694 | 60 |  | 40 |  | 08/09/2022 | 08/09/2022 |  | 2022-10-17T09:22:45.863 | Dehnke, Josh | LVP
22-0120-D | WO00017, Complete | Final Clean | 2022-08-09T08:53:00.000 | WO | 0 | 150 | 8 | 300 | 50 |  | 50 |  | 08/09/2022 | 08/09/2022 |  | 2022-11-27T18:59:01.690 | Dehnke, Josh | CLN
22-0168-D | WO0001 | Design | 2022-05-16T11:47:00.000 | WO | 0 | 500 | 8 | 500 | 500 |  | 0 |  | 05/16/2022 | 05/16/2022
22-0168-D | WO0002 | Planning | 2022-05-16T11:48:00.000 | WO | 0 | 500 | 8 | 500 | 500 |  | 0 |  | 05/16/2022 | 05/16/2022
22-0168-D | WO0003 | Site Set Up | 2022-05-16T11:49:00.000 | WO | 0 | 1000 | 8 | 1000 | 1000 |  | 0 |  | 05/16/2022 | 05/16/2022
22-0168-D | WO0004 | Demo | 2022-05-16T11:56:00.000 | WO | 0 | 250 | 8 | 500 | 250 |  | 50 |  | 05/16/2022 | 05/16/2022
22-0168-D | WO0005 | Framing | 2022-05-16T11:58:00.000 | WO | 0 | 950.0001 | 8 | 1303.57 | 950 |  | 27.1232 |  | 05/16/2022 | 05/16/2022
22-0168-D | WO0006 | Electrical | 2022-05-16T12:05:00.000 | WO | 0 | 4199.9992 | 8 | 5060.24 | 4200 |  | 17 |  | 05/16/2022 | 05/16/2022
22-0168-D | WO0007 | HVAC | 2022-05-16T12:09:00.000 | WO | 0 | 849.9999 | 8 | 1024.1 | 850 |  | 17.0003 |  | 05/16/2022 | 05/16/2022
22-0168-D | WO0008 | Insulation | 2022-05-16T12:10:00.000 | WO | 0 | 1000.0004 | 8 | 1428.57 | 1000 |  | 29.9999 |  | 05/16/2022 | 05/16/2022
22-0168-D | WO0009 | Drywall | 2022-05-16T12:12:00.000 | WO | 0 | 2100 | 8 | 3500 | 2100 |  | 40 |  | 05/16/2022 | 05/16/2022
22-0168-D | WO00010 | CarpentryMillwork | 2022-05-16T12:45:00.000 | WO | 0 | 799.9997 | 8 | 1375 | 800 |  | 41.8182 |  | 05/16/2022 | 05/16/2022
22-0168-D | WO00011 | Doors/Windows | 2022-05-16T12:47:00.000 | WO | 0 | 3189.29 | 8 | 3189.29 | 2430 |  | 0 |  | 05/16/2022 | 05/16/2022
22-0168-D | WO00012 | Final Cleaning | 2022-05-16T12:53:00.000 | WO | 0 | 300 | 8 | 300 | 300 |  | 0 |  | 05/16/2022 | 05/16/2022
22-0168-D | WO00013 | O & P | 2022-05-16T12:55:00.000 | WO | 0 | 0 | 8 | 4722.77 | 0 |  | 100 |  | 05/16/2022 | 05/16/2022
22-0162-D | WO0001 | Design Services | 2022-05-11T14:24:00.000 | WO | 0 | 1000 | 0 | 1250 | 1000 |  | 20 |  | 05/11/2022 | 05/11/2022
22-0162-D | WO0002 | Planning/Building Permit | 2022-05-11T14:31:00.000 | WO | 0 | 500 | 8 | 625 | 500 |  | 20 |  | 05/11/2022 | 05/11/2022
22-0162-D | WO0003 | Job Site Set Up/Debris Removal | 2022-05-11T14:33:00.000 | WO | 0 | 1000 | 0 | 1250 | 1000 |  | 20 |  | 05/11/2022 | 05/11/2022
22-0162-D | WO0004 | Framing | 2022-05-11T17:13:00.000 | WO | 0 | 2750.0011 | 8 | 3883.93 | 2750 |  | 29.1954 |  | 05/11/2022 | 05/11/2022
22-0162-D | WO0005 | Electrical | 2022-05-11T17:15:00.000 | WO | 0 | 5649.9971 | 8 | 6827.56 | 5650 |  | 17.2472 |  | 05/11/2022 | 05/11/2022
22-0162-D | WO0006 | Plumbing | 2022-05-11T17:19:00.000 | WO | 0 | 6950.0036 | 8 | 8529.37 | 6950 |  | 18.5168 |  | 05/11/2022 | 05/11/2022
22-0162-D | WO0007 | HVAC | 2022-05-11T17:22:00.000 | WO | 0 | 849.9999 | 8 | 1024.1 | 850 |  | 17.0003 |  | 05/11/2022 | 05/11/2022
22-0162-D | WO0008 | Insulation | 2022-05-11T17:35:00.000 | WO | 0 | 2000.0009 | 8 | 2857.14 | 2000 |  | 29.9999 |  | 05/11/2022 | 05/11/2022
22-0162-D | WO0009 | Drywall | 2022-05-11T17:40:00.000 | WO | 0 | 3849.9996 | 8 | 5366.07 | 3850 |  | 28.2529 |  | 05/11/2022 | 05/11/2022
22-0162-D | WO00010 | Carpentry | 2022-05-11T17:42:00.000 | WO | 0 | 1300.0005 | 8 | 1732.14 | 1300 |  | 24.9483 |  | 05/11/2022 | 05/11/2022
22-0162-D | WO00011 | Flooring | 2022-05-11T17:44:00.000 | WO | 0 | 2980.0001 | 8 | 4195.83 | 2980 |  | 28.9771 |  | 05/11/2022 | 05/11/2022
22-0162-D | WO00012 | Doors & Windows | 2022-05-11T18:06:00.000 | WO | 0 | 2260.0003 | 8 | 3116.67 | 2260 |  | 27.4867 |  | 05/11/2022 | 05/11/2022
22-0162-D | WO00013 | Final Cleaning | 2022-05-11T18:16:00.000 | WO | 0 | 300 | 0 | 375 | 300 |  | 20 |  | 05/11/2022 | 05/11/2022
22-0162-D | WO00014 | O&P | 2022-05-11T18:27:00.000 | WO | 0 | 0 | 8 | 9597.03 | 0 |  | 100 |  | 05/11/2022 | 05/11/2022
22-0163-D
22-0165-D
22-0167-D
22-0169-D
22-0170-D
22-0171-D
22-0354-D
22-0123-D
22-0119-D | WO0001, Complete | Design | 2022-08-17T19:34:00.000 | WO | 0 | 0 | 8 | 1800 | 0 |  | 100 |  | 08/17/2022 | 08/17/2022 |  | 2022-08-17T18:59:14.263 | Dehnke, Josh | Design
22-0119-D | WO0003, Complete | Demo Labor/ Dumpster | 2022-08-17T19:36:00.000 | WO | 0 | 2447.5 | 16 | 4450 | 55 |  | 45 |  | 08/17/2022 | 08/17/2022 |  | 2022-11-14T14:48:40.767 | Dehnke, Josh | DMO
22-0119-D | WO0004, Complete | Electrical labor | 2022-08-17T19:36:00.000 | WO | 0 | 6816.8 | 8 | 8521 | 80 |  | 20 |  | 08/17/2022 | 08/17/2022 |  | 2022-11-14T14:48:40.797 | Dehnke, Josh | ELE
22-0119-D | WO0005, Complete | Plumbing Labor | 2022-08-17T19:37:00.000 | WO | 0 | 2544.8 | 8 | 3181 | 80 |  | 20 |  | 08/17/2022 | 08/17/2022 |  | 2022-11-21T10:03:55.257 | Dehnke, Josh | PLM
22-0119-D | WO0006, Complete | HVAC Labor | 2022-08-17T19:38:00.000 | WO | 0 | 1084.5 | 8 | 1446 | 75 |  | 25 |  | 08/17/2022 | 08/17/2022 |  | 2022-11-21T10:03:55.267 | Dehnke, Josh | HVAC
22-0119-D | WO0007, Complete | Insulation Labor | 2022-08-17T19:38:00.000 | WO | 0 | 0 | 8 | 714 | 0 |  | 100 |  | 08/17/2022 | 08/17/2022 |  | 2022-11-21T10:03:55.273 | Dehnke, Josh | INS
22-0119-D | WO0008, Complete | Framing Labor | 2022-08-17T19:39:00.000 | WO | 0 | 250 | 8 | 500 | 50 |  | 50 |  | 08/17/2022 | 08/17/2022 |  | 2022-11-21T10:03:55.293 | Dehnke, Josh | FRM
22-0119-D | WO0009, Complete | Drywall Labor | 2022-08-17T19:39:00.000 | WO | 0 | 1657.2 | 8 | 4143 | 40 |  | 60 |  | 08/17/2022 | 08/17/2022 |  | 2022-11-14T14:48:40.830 | Dehnke, Josh | DRY
22-0119-D | WO00010, Complete | Cabinet Labor | 2022-08-17T19:40:00.000 | WO | 0 | 2269.7509 | 8 | 4485 | 2269.75 |  | 49.3924 |  | 08/17/2022 | 08/17/2022 |  | 2022-11-27T18:48:29.307 | Dehnke, Josh | CAB
22-0119-D | WO00011, Complete | Carpentry Labor | 2022-08-17T19:41:00.000 | WO | 0 | 664.5 | 8 | 1329 | 50 |  | 50 |  | 08/17/2022 | 08/17/2022 |  | 2022-11-27T18:48:29.330 | Dehnke, Josh | FNC
22-0119-D | WO00012, Complete | Tile Labor | 2022-08-17T19:41:00.000 | WO | 0 | 1799.9996 | 8 | 2330 | 1800 |  | 22.7468 |  | 08/17/2022 | 08/17/2022 |  | 2023-01-16T08:06:58.097 | Dehnke, Josh | TIL
22-0119-D | WO00013, Complete | Flooring Labor | 2022-08-17T19:42:00.000 | WO | 0 | 1500.0003 | 8 | 3482 | 1500 |  | 56.9213 |  | 08/17/2022 | 08/17/2022 |  | 2022-12-08T11:12:08.183 | Dehnke, Josh | FCW
22-0119-D | WO00015, Complete | Door Install Labor | 2022-08-17T19:43:00.000 | WO | 0 | 462.15 | 8 | 1027 | 45 |  | 55 |  | 08/17/2022 | 08/17/2022 |  | 2022-11-27T18:48:29.320 | Dehnke, Josh | DOR
22-0119-D | WO00016, Complete | Final Clean | 2022-08-17T19:44:00.000 | WO | 0 | 0 | 8 | 300 | 0 |  | 100 |  | 08/17/2022 | 08/17/2022 |  | 2023-03-01T13:16:10.073 | Dehnke, Josh | CLN
22-0119-D | WO00017, Complete | Overhead/Admin first 1/2 | 2022-08-17T19:45:00.000 | WO | 0 | 0 | 8 | 3857.5 | 0 |  | 100 |  | 08/17/2022 | 08/17/2022 |  | 2022-10-21T14:10:40.350 | Dehnke, Josh | O&A
22-0119-D | WO00018, Complete | Overhead/Admin Final 1/2 | 2022-08-17T19:46:00.000 | WO | 0 | 0 | 8 | 3857.5 | 0 |  | 100 |  | 08/17/2022 | 08/17/2022 |  | 2023-03-01T13:16:10.030 | Dehnke, Josh | O&A
22-0119-D | WO00019, Complete | Profit First 1/2 | 2022-08-17T19:46:00.000 | WO | 0 | 0 | 8 | 5786.5 | 0 |  | 100 |  | 08/17/2022 | 08/17/2022 |  | 2022-10-21T14:10:40.370 | Dehnke, Josh | Profit
22-0119-D | WO00020, Complete | Profit Final 1/2 | 2022-08-17T19:47:00.000 | WO | 0 | 0 | 8 | 5786.5 | 0 |  | 100 |  | 08/17/2022 | 08/17/2022 |  | 2023-03-01T13:16:10.060 | Dehnke, Josh | Profit
22-0119-D | WO00021, Complete | Materials: Cabinets, Flooring, Trim, Doors, Tile, General | 2022-08-17T19:48:00.000 | WO | 0 | 18356.25 | 8 | 24475 | 75 |  | 25 |  | 08/17/2022 | 08/17/2022 |  | 2022-08-17T18:59:02.390 | Dehnke, Josh | Materials
22-0119-D | WO00022, Complete | Punch for countertop install | 2022-12-12T14:34:00.000 | WO | 0 | 1000 | 8 | 2000 | 50 |  | 50 |  | 12/12/2022 | 12/12/2022 |  | 2023-02-13T08:24:37.383 | Dehnke, Josh | CAB
22-0119-D | WO00023, Complete | Painting Labor | 2022-12-22T13:18:00.000 | WO | 0 | 1500 | 16 | 3750 | 40 |  | 60 |  | 08/17/2022 | 12/22/2022 |  | 2022-12-27T11:38:12.470 | Dehnke, Josh | PNT
22-0154-D | WO0001, Complete | Design | 2022-05-05T18:09:00.000 | WO | 0 | 0 | 8 | 1000 | 0 |  | 100 |  | 05/05/2022 | 05/05/2022 |  | 2022-07-25T12:16:09.223 | Dehnke, Josh
22-0154-D | WO0002, Complete | Building Permit | 2022-05-05T18:12:00.000 | WO | 0 | 500 | 8 | 500 | 500 |  | 0 |  | 07/25/2022 | 07/25/2022 |  | 2022-07-25T12:16:09.240 | Dehnke, Josh
22-0154-D | WO0003, Complete | Site Set Up | 2022-05-05T18:13:00.000 | WO | 0 | 1000 | 8 | 1000 | 1000 |  | 0 |  | 07/18/2022 | 07/18/2022 |  | 2022-07-25T12:16:09.257 | Dehnke, Josh
22-0154-D | WO0004, Complete | Framing | 2022-05-05T18:17:00.000 | WO | 0 | 2200.0012 | 26 | 2964.29 | 2200 |  | 25.7832 |  | 07/18/2022 | 07/20/2022 |  | 2022-07-25T12:16:09.270 | Dehnke, Josh
22-0154-D | WO0005, Complete | Electrical | 2022-05-08T12:19:00.000 | WO | 0 | 6099.9979 | 0 | 7362.95 | 6100 |  | 17.1528 |  | 07/25/2022 | 07/29/2022 |  | 2022-08-17T18:55:52.183 | Dehnke, Josh
22-0154-D | WO0006, Complete | Plumbing | 2022-05-08T12:33:00.000 | WO | 0 | 4000 | 0 | 8000 | 50 |  | 50 |  | 07/25/2022 | 07/25/2022 |  | 2022-08-01T13:25:52.633 | Dehnke, Josh
22-0154-D | WO0007, Complete | Shower Door / Finish Hardware | 2022-05-08T13:02:00.000 | WO | 0 | 937.5 | 17 | 1875 | 50 |  | 50 |  | 08/17/2022 | 08/18/2022 |  | 2022-12-16T09:53:43.203 | Dehnke, Josh
22-0154-D | WO0008, Complete | HVAC | 2022-05-08T13:06:00.000 | WO | 0 | 849.9999 | 8 | 1024.1 | 850 |  | 17.0003 |  | 07/27/2022 | 07/27/2022 |  | 2022-08-17T18:55:59.737 | Dehnke, Josh
22-0154-D | WO0009, Complete | Drywall and Painting | 2022-05-08T13:20:00.000 | WO | 0 | 4928.57 | 0 | 9857.14 | 50 |  | 50 |  | 08/04/2022 | 08/04/2022 |  | 2022-10-21T11:25:11.310 | Dehnke, Josh | DRY
22-0154-D | WO00014, Complete | Final Cleaning | 2022-05-09T15:58:00.000 | WO | 0 | 300 | 8 | 300 | 300 |  | 0 |  | 08/31/2022 | 08/31/2022 |  | 2023-02-06T10:14:23.713 | Dehnke, Josh
22-0154-D | WO00015, Complete | OVERHEAD/ADMIN FIRST 1/2 | 2022-05-09T15:59:00.000 | WO | 0 | 0 | 8 | 5462.5 | 0 |  | 100 |  | 08/31/2022 | 08/31/2022 |  | 2022-08-17T18:58:07.733 | Dehnke, Josh | O&A
22-0154-D | WO00016, Complete | overhead/admin final 1/2 | 2022-08-17T19:57:00.000 | WO | 0 | 0 | 8 | 5462.5 | 0 |  | 100 |  | 08/17/2022 | 08/17/2022 |  | 2023-02-06T10:14:23.727 | Dehnke, Josh | O&A
22-0154-D | WO00017, Complete | Framing Final Labor | 2022-08-18T10:06:00.000 | WO | 0 | 1000 | 8 | 2000 | 50 |  | 50 |  | 08/18/2022 | 08/18/2022 |  | 2022-08-18T09:09:35.870 | Dehnke, Josh | FRM
22-0154-D | WO00018, Complete | Materials | 2022-09-07T17:04:00.000 | WO | 0 | 3660 | 0 | 3660 | 0 |  | 0 |  | 09/07/2022 | 09/07/2022 |  | 2022-09-08T12:30:48.590 | Dehnke, Josh | MAT
22-0154-D | WO00019, Complete | LVP Bathroom Labor | 2022-11-15T18:41:00.000 | WO | 0 | 800 | 8 | 1000 | 800 |  | 20 |  | 11/15/2022 | 11/15/2022 |  | 2022-11-21T10:02:47.323 | Dehnke, Josh | LVP
22-0154-D | WO00020, Complete | Trim and Door Labor | 2022-11-15T18:47:00.000 | WO | 0 | 1103.57 | 26 | 2207.14 | 50 |  | 50 |  | 08/10/2022 | 08/12/2022 |  | 2022-11-21T10:02:47.340 | Dehnke, Josh | FNC
22-0154-D | WO00021, Complete | Punch List Items | 2023-01-09T13:23:00.000 | WO | 0 | 2417.556 | 8 | 4029.26 | 60 |  | 40 |  | 01/09/2023 | 01/09/2023 |  | 2023-02-06T10:14:23.717 | Dehnke, Josh | Punch
22-0301-D | WO0001, Complete | Design Services | 2022-10-21T09:45:00.000 | WO | 0 | 1875 | 8 | 1875 | 100 |  | 0 |  | 10/21/2022 | 10/21/2022 |  | 2022-10-21T09:06:10.393 | Dehnke, Josh | Design
22-0301-D | WO0002, Complete | Planning | 2022-10-21T09:46:00.000 | WO | 0 | 625 | 8 | 625 | 100 |  | 0 |  | 10/21/2022 | 10/21/2022 |  | 2022-10-21T09:06:10.417 | Dehnke, Josh | Planning
22-0301-D | WO0003, Complete | Site Set Up | 2022-10-21T09:49:00.000 | WO | 0 | 687.5 | 8 | 1375 | 50 |  | 50 |  | 10/21/2022 | 10/21/2022 |  | 2022-11-14T14:51:09.993 | Dehnke, Josh | Site Set Up
22-0301-D | WO0004, Complete | Demo | 2022-10-21T09:50:00.000 | WO | 0 | 893.75 | 8 | 1375 | 65 |  | 35 |  | 10/21/2022 | 10/21/2022 |  | 2022-11-14T14:51:10.033 | Dehnke, Josh | Demo
22-0301-D | WO0005, Complete | Framing | 2022-10-21T09:51:00.000 | WO | 0 | 1519.7 | 8 | 2338 | 65 |  | 35 |  | 10/21/2022 | 10/21/2022 |  | 2022-11-14T14:51:10.083 | Dehnke, Josh | Framing
22-0301-D | WO0006, Complete | Electrical Labor | 2022-10-21T09:51:00.000 | WO | 0 | 7214 | 8 | 7214 | 100 |  | 0 |  | 10/21/2022 | 10/21/2022 |  | 2022-11-14T14:51:10.110 | Dehnke, Josh | ELE
22-0301-D | WO0007, Complete | Plumbing Labor | 2022-10-21T09:52:00.000 | WO | 0 | 12000.0004 | 16 | 21194 | 12000 |  | 43.3802 |  | 10/21/2022 | 10/24/2022 |  | 2022-12-08T11:13:36.150 | Dehnke, Josh | Plumbing
22-0301-D | WO0009, Complete | Insulation Labor | 2022-10-21T09:53:00.000 | WO | 0 | 1259.7 | 8 | 1938 | 65 |  | 35 |  | 10/21/2022 | 10/21/2022 |  | 2023-01-12T14:08:26.083 | Dehnke, Josh | Insulation
22-0301-D | WO00010, Complete | Drywall Labor | 2022-10-21T09:54:00.000 | WO | 0 | 4062.5 | 8 | 8125 | 50 |  | 50 |  | 10/21/2022 | 10/21/2022 |  | 2023-02-22T10:39:55.253 | Dehnke, Josh | DRY
22-0301-D | WO00011, Complete | Finish Carpentry | 2022-10-21T09:54:00.000 | WO | 0 | 1351 | 44 | 1351 | 100 |  | 0 |  | 03/16/2023 | 03/22/2023 |  | 2023-04-03T12:20:58.227 | Trevino, Jeovani | FNC
22-0301-D | WO00012, Complete | LVP Floor Labor | 2022-10-21T09:55:00.000 | WO | 0 | 2683.2 | 8 | 2683.2 | 100 |  | 0 |  | 10/21/2022 | 10/21/2022 |  | 2023-03-09T09:54:57.143 | Dehnke, Josh | FCW
22-0301-D | WO00013, Complete | Painting Labor | 2022-10-21T09:55:00.000 | WO | 0 | 4642.8 | 8 | 7738 | 60 |  | 40 |  | 10/21/2022 | 10/21/2022 |  | 2023-03-09T09:54:57.157 | Dehnke, Josh | PNT
22-0301-D | WO00014, Complete | Door/Window Labor | 2022-10-21T09:56:00.000 | WO | 0 | 1078 | 8 | 1960 | 55 |  | 45 |  | 10/21/2022 | 10/21/2022 |  | 2023-03-09T09:54:57.167 | Dehnke, Josh | DOR
22-0301-D | WO00015, Complete | Final Cleaning | 2022-10-21T09:56:00.000 | WO | 0 | 375 | 8 | 375 | 100 |  | 0 |  | 03/23/2023 | 03/23/2023 |  | 2023-04-03T12:20:58.190 | Trevino, Jeovani | Final Cleaning
22-0301-D | WO00016, Complete | O&P First 1/2 | 2022-10-21T09:57:00.000 | WO | 0 | 0 | 8 | 3295.5 | 0 |  | 100 |  | 10/21/2022 | 10/21/2022 |  | 2022-10-21T09:06:10.437 | Dehnke, Josh | O&P
22-0301-D | WO00017, Complete | O&P Final 1/2 | 2022-10-21T09:58:00.000 | WO | 0 | 0 | 8 | 3295.5 | 0 |  | 100 |  | 03/24/2023 | 03/24/2023 |  | 2023-04-03T12:20:58.207 | Trevino, Jeovani | O&P
22-0301-D | WO00018, Complete | Profit First 1/2 | 2022-10-21T09:59:00.000 | WO | 0 | 0 | 8 | 4943 | 0 |  | 100 |  | 10/21/2022 | 10/21/2022 |  | 2022-10-21T09:06:10.457 | Dehnke, Josh | Profit
22-0301-D | WO00019, Complete | Profit Final 1/2 | 2022-10-21T10:00:00.000 | WO | 0 | 0 | 8 | 4943 | 0 |  | 100 |  | 03/24/2023 | 03/24/2023 |  | 2023-04-03T12:20:58.247 | Trevino, Jeovani | Profit
22-0301-D | WO00020, Complete | Materials | 2022-10-21T10:00:00.000 | WO | 0 | 13290 | 8 | 13290 | 100 |  | 0 |  | 10/21/2022 | 10/21/2022 |  | 2022-10-21T12:06:49.313 | Dehnke, Josh | MAT
22-0301-D | WO00021, Complete | Carpet Labor | 2023-03-08T09:21:00.000 | WO | 0 | 2012.4 | 8 | 4024.8 | 50 |  | 50 |  | 03/08/2023 | 03/08/2023 |  | 2023-03-09T09:54:57.177 | Dehnke, Josh | CPT
22-0302-D
22-0303-D
22-0304-D
22-0305-D
22-0306-D
22-0307-D
22-0316-D
22-0317-D
22-0318-D
22-0320-D
22-0321-D
22-0322-D
22-0323-D
22-0329-D
22-0159-D
22-0152-D | WO0001 | Design | 2022-05-16T16:03:00.000 | WO | 0 | 499.9999 | 8 | 588.24 | 500 |  | 15.0007 |  | 05/16/2022 | 05/16/2022
22-0152-D | WO0002 | Planning | 2022-05-16T16:04:00.000 | WO | 0 | 500 | 8 | 625 | 500 |  | 20 |  | 05/16/2022 | 05/16/2022
22-0152-D | WO0003 | Site Set Up | 2022-05-16T16:05:00.000 | WO | 0 | 1200.0003 | 8 | 1411.77 | 1200 |  | 15.0003 |  | 05/16/2022 | 05/16/2022
22-0152-D | WO0004 | Demo | 2022-05-16T16:07:00.000 | WO | 0 | 300 | 8 | 375 | 300 |  | 20 |  | 05/16/2022 | 05/16/2022
22-0152-D | WO0005 | Framing | 2022-05-16T16:12:00.000 | WO | 0 | 1049.9998 | 8 | 1419.64 | 1050 |  | 26.0376 |  | 05/16/2022 | 05/16/2022
22-0152-D | WO0006 | HVAC | 2022-05-16T16:21:00.000 | WO | 0 | 849.9999 | 8 | 1024.1 | 850 |  | 17.0003 |  | 05/16/2022 | 05/16/2022
22-0152-D | WO0007 | Insulation | 2022-05-16T16:48:00.000 | WO | 0 | 649.9999 | 8 | 928.57 | 650 |  | 29.9999 |  | 05/16/2022 | 05/16/2022
22-0152-D | WO0008 | Drywall | 2022-05-16T16:50:00.000 | WO | 0 | 4499.9974 | 8 | 5844.16 | 4500 |  | 23.0001 |  | 05/16/2022 | 05/16/2022
22-0152-D | WO0009 | Carpentry/Millwork | 2022-05-16T16:52:00.000 | WO | 0 | 1000.0005 | 8 | 1357.14 | 1000 |  | 26.3156 |  | 05/16/2022 | 05/16/2022
22-0152-D | WO00010 | Flooring | 2022-05-16T16:54:00.000 | WO | 0 | 1500.0009 | 8 | 2026.79 | 1500 |  | 25.9913 |  | 05/16/2022 | 05/16/2022
22-0152-D | WO00011 | Doors & Windows | 2022-05-16T16:57:00.000 | WO | 0 | 1554.9999 | 8 | 1812.5 | 1555 |  | 14.2069 |  | 05/16/2022 | 05/16/2022
22-0152-D | WO00012 | Final Cleaning | 2022-05-16T17:00:00.000 | WO | 0 | 300.0001 | 8 | 352.94 | 300 |  | 14.9997 |  | 05/16/2022 | 05/16/2022
22-0152-D | WO00013 | O&P | 2022-05-16T17:01:00.000 | WO | 0 | 0 | 0 | 6658 | 0 |  | 100 |  | 05/16/2022 | 05/16/2022
22-0152-D | WO00014 | Electrical | 2022-05-18T16:28:00.000 | WO | 0 | 4199.9992 | 8 | 5060.24 | 4200 |  | 17 |  | 05/18/2022 | 05/18/2022
22-0152-D | WO00015 | Painting | 2022-05-18T16:29:00.000 | WO | 0 | 3799.9975 | 8 | 5846.15 | 3800 |  | 35 |  | 05/18/2022 | 05/18/2022
22-0152-D | WO00016 | Finance Charge | 2022-05-18T16:31:00.000 | WO | 0 | 500 | 8 | 500 | 500 |  | 0 |  | 05/18/2022 | 05/18/2022
22-0273-D | WO0001 | Design | 2022-05-17T14:54:00.000 | WO | 0 | 1200 | 8 | 1500 | 1200 |  | 20 |  | 05/17/2022 | 05/17/2022
22-0273-D | WO0002 | Planning | 2022-05-17T15:43:00.000 | WO | 0 | 500 | 8 | 500 | 500 |  | 0 |  | 05/17/2022 | 05/17/2022
22-0273-D | WO0003 | Site Set Up | 2022-05-17T15:44:00.000 | WO | 0 | 1099.9994 | 8 | 1294.12 | 1100 |  | 15.0002 |  | 05/17/2022 | 05/17/2022
22-0273-D | WO0004 | Framing | 2022-05-17T15:47:00.000 | WO | 0 | 2099.9993 | 8 | 3142.86 | 2100 |  | 33.1819 |  | 05/17/2022 | 05/17/2022
22-0273-D | WO0005 | Electrical | 2022-05-17T15:48:00.000 | WO | 0 | 6299.9998 | 8 | 7603.92 | 6300 |  | 17.148 |  | 05/17/2022 | 05/17/2022
22-0273-D | WO0006 | Plumbing | 2022-05-17T15:52:00.000 | WO | 0 | 12300.0008 | 8 | 15058.73 | 12300 |  | 18.3198 |  | 05/17/2022 | 05/17/2022
22-0273-D | WO0007 | Shower Door | 2022-05-17T15:56:00.000 | WO | 0 | 1500 | 8 | 1875 | 1500 |  | 20 |  | 05/17/2022 | 05/17/2022
22-0273-D | WO0008 | HVAC | 2022-05-17T15:58:00.000 | WO | 0 | 1400.0008 | 8 | 1686.75 | 1400 |  | 17.0001 |  | 05/17/2022 | 05/17/2022
22-0273-D | WO0009 | Insulation | 2022-05-17T16:07:00.000 | WO | 0 | 3000 | 8 | 3750 | 3000 |  | 20 |  | 05/17/2022 | 05/17/2022
22-0273-D | WO00010 | Drywall | 2022-05-17T16:09:00.000 | WO | 0 | 5500 | 8 | 6875 | 5500 |  | 20 |  | 05/17/2022 | 05/17/2022
22-0273-D | WO00011 | Carpentry/Millwork | 2022-05-17T16:10:00.000 | WO | 0 | 1800.0002 | 8 | 2392.86 | 1800 |  | 24.7762 |  | 05/17/2022 | 05/17/2022
22-0273-D | WO00012 | Flooring | 2022-05-17T16:13:00.000 | WO | 0 | 5800.0036 | 8 | 7240.42 | 5800 |  | 19.8941 |  | 05/17/2022 | 05/17/2022
22-0273-D | WO00013 | Doors & Windows | 2022-05-17T16:21:00.000 | WO | 0 | 2325.001 | 8 | 3062.5 | 2325 |  | 24.0816 |  | 05/17/2022 | 05/17/2022
22-0273-D | WO00014 | Final Cleaning | 2022-05-17T16:23:00.000 | WO | 0 | 300 | 8 | 375 | 300 |  | 20 |  | 05/17/2022 | 05/17/2022
22-0273-D | WO00015 | O & P | 2022-05-17T16:24:00.000 | WO | 0 | 0 | 8 | 16425 | 0 |  | 100 |  | 05/17/2022 | 05/17/2022
22-0274-D
22-0275-D
22-0276-D
22-0277-D | WO0001 | Design | 2022-05-18T10:29:00.000 | WO | 0 | 1800 | 8 | 1800 | 1800 |  | 0 |  | 05/18/2022 | 05/18/2022
22-0277-D | WO0002 | Planning | 2022-05-18T10:30:00.000 | WO | 0 | 500 | 8 | 500 | 500 |  | 0 |  | 05/18/2022 | 05/18/2022
22-0277-D | WO0003 | Site Set Up | 2022-05-18T10:31:00.000 | WO | 0 | 1000 | 8 | 1000 | 1000 |  | 0 |  | 05/18/2022 | 05/18/2022
22-0277-D | WO0004 | Framing | 2022-05-18T10:33:00.000 | WO | 0 | 4300.002 | 8 | 6000 | 4300 |  | 28.3333 |  | 05/18/2022 | 05/18/2022
22-0277-D | WO0005 | Electrical | 2022-05-18T10:34:00.000 | WO | 0 | 10150.002 | 8 | 12249.24 | 10150 |  | 17.1377 |  | 05/18/2022 | 05/18/2022
22-0277-D | WO0006 | Plumbing | 2022-05-18T10:44:00.000 | WO | 0 | 7999.9986 | 8 | 9828.31 | 8000 |  | 18.6025 |  | 05/18/2022 | 05/18/2022
22-0277-D | WO0007 | Shower Door | 2022-05-18T10:46:00.000 | WO | 0 | 1800 | 8 | 2250 | 1800 |  | 20 |  | 05/18/2022 | 05/18/2022
22-0277-D | WO0008 | HVAC | 2022-05-18T10:47:00.000 | WO | 0 | 5700.0001 | 8 | 6867.47 | 5700 |  | 17 |  | 05/18/2022 | 05/18/2022
22-0277-D | WO0009 | Drywall | 2022-05-18T10:49:00.000 | WO | 0 | 8999.9948 | 8 | 12093.5 | 9000 |  | 25.5799 |  | 05/18/2022 | 05/18/2022
22-0277-D | WO00010 | Cabinetry | 2022-05-18T10:51:00.000 | WO | 0 | 13725.0063 | 8 | 17424.11 | 13725 |  | 21.2298 |  | 05/18/2022 | 05/18/2022
22-0277-D | WO00011 | Countertops | 2022-05-18T10:53:00.000 | WO | 0 | 2699.9998 | 8 | 3255.95 | 2700 |  | 17.0749 |  | 05/18/2022 | 05/18/2022
22-0277-D | WO00012 | Carpentry/Millwork | 2022-05-18T10:55:00.000 | WO | 0 | 2250.0007 | 8 | 3026.79 | 2250 |  | 25.6638 |  | 05/18/2022 | 05/18/2022
22-0277-D | WO00013 | Flooring | 2022-05-18T10:57:00.000 | WO | 0 | 5999.9997 | 8 | 7946.43 | 6000 |  | 24.4944 |  | 05/18/2022 | 05/18/2022
22-0277-D | WO00014 | Painting | 2022-05-18T10:58:00.000 | WO | 0 | 5299.9964 | 8 | 9494.05 | 5300 |  | 44.1756 |  | 05/18/2022 | 05/18/2022
22-0277-D | WO00015 | Doors & Windows | 2022-05-18T11:00:00.000 | WO | 0 | 3640 | 8 | 4550 | 3640 |  | 20 |  | 05/18/2022 | 05/18/2022
22-0277-D | WO00016 | Gutters | 2022-05-18T11:03:00.000 | WO | 0 | 499.9998 | 8 | 892.86 | 500 |  | 44.0002 |  | 05/18/2022 | 05/18/2022
22-0277-D | WO00017 | Final Cleaning | 2022-05-18T11:05:00.000 | WO | 0 | 300 | 8 | 300 | 300 |  | 0 |  | 05/18/2022 | 05/18/2022
22-0277-D | WO00018 | O&P | 2022-05-18T11:06:00.000 | WO | 0 | 0 | 8 | 23775 | 0 |  | 100 |  | 05/18/2022 | 05/18/2022
22-0279-D
22-0284-D
22-0161-D
22-0319-D
22-0113-D
22-0160-D
22-0153-D
22-0158-D
22-0125-D
22-0272-D
22-0285-ER
22-0237-ER
22-0430-ER
22-0442-ER
22-0449-ER
22-0255-ER
22-0193-ER
22-0363-ER
22-0235-ER
22-0350-ER
22-0244-ER
22-0079-ER
22-0238-ER
22-0059-ER
22-0132-ER
22-0151-ER
22-0351-ER
22-0393-ER
22-0218-ER
22-0398-ER
22-0173-ER
22-0190-ER
22-0217-ER
22-0239-ER
22-0242-ER
22-0252-ER
22-0298-ER
22-0367-ER
22-0360-ER
22-0359-ER
22-0339-ER
22-0191-ER
22-0144-ER
22-0185-ER
22-0206-ER
22-0440-ER
22-0399-ER
22-0439-ER
22-0026-ER
22-0220-ER
22-0292-ER
22-0297-ER
22-0289-ER
22-0295-ER
22-0358-ER
22-0044-ER
22-0097-ER
22-0131-ER
22-0041-ER
22-0140-ER
22-0046-ER
22-0127-ER
22-0035-ER
22-0019-ER
22-0128-ER
22-0411-ER
22-0412-ER
22-0414-ER
22-0415-ER
22-0047-ER
22-0145-ER
22-0029-ER
22-0045-ER
22-0024-ER
22-0025-ER
22-0022-ER
22-0027-ER
22-0030-ER
22-0037-ER
22-0040-ER
22-0042-ER
22-0051-ER
22-0052-ER
22-0053-ER
22-0054-ER
22-0055-ER
22-0056-ER
22-0061-ER
22-0065-ER
22-0067-ER
22-0068-ER
22-0080-ER
22-0082-ER
22-0083-ER
22-0084-ER
22-0085-ER
22-0086-ER
22-0087-ER
22-0088-ER
22-0089-ER
22-0090-ER
22-0092-ER
22-0093-ER
22-0094-ER
22-0095-ER
22-0096-ER
22-0143-ER
22-0174-ER
22-0111-ER
22-0050-ER
22-0075-ER
22-0058-ER
22-0064-ER
22-0069-ER
22-0073-ER
22-0023-ER
22-0234-ER
22-0010-ER
22-0241-ER
22-0034-ER
22-0249-ER
22-0178-ER
22-0184-ER
22-0250-ER
22-0033-ER
22-0076-ER
22-0057-ER
22-0071-ER
22-0072-ER
22-0189-ER
22-0141-ER
22-0142-ER
22-0150-ER
22-0204-ER
22-0208-ER
22-0049-ER
22-0233-ER
22-0077-ER
22-0066-ER
22-0074-ER
22-0078-ER
22-0110-ER
22-0216-ER
22-0219-ER
22-0236-ER
22-0288-ER
22-0299-ER
22-0209-ER
22-0212-ER
22-0229-ER
22-0451-ER
22-0428-ER
22-0032-ER
22-0389-ER | WO0001 | DMO | 2022-07-18T10:31:46.763 | WO | 0 | 455 |  | 455 | 100 |  | 0 | [6 empty] | DMO
22-0389-ER | WO0002 | FEE | 2022-07-18T10:31:46.857 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | FEE
22-0389-ER | WO0003 | RFG | 2022-07-18T10:31:47.030 | WO | 0 | 10640.31 | 52.09 | 10640.31 | 100 |  | 0 |  | 07/18/2022 | 07/25/2022 |  |  |  | RFG
22-0389-ER | WO0004 | SDG | 2022-07-18T10:31:47.293 | WO | 0 | 1901.1 | 12.95 | 1901.1 | 100 |  | 0 |  | 07/18/2022 | 07/19/2022 |  |  |  | SDG
22-0389-ER | WO0005 | SFG | 2022-07-18T10:31:47.430 | WO | 0 | 634.69 | 1.62 | 634.69 | 100 |  | 0 |  | 07/18/2022 | 07/18/2022 |  |  |  | SFG
22-0443-ER
22-0397-ER
22-0357-ER
22-0294-ER
22-0253-ER
22-0474-ER
22-0429-ER
22-0406-ER
22-0385-ER
22-0396-ER
22-0390-ER
22-0369-ER
22-0476-ER
22-0457-ER
22-0420-ER
22-0403-ER
22-0405-ER
22-0391-ER
22-0129-ER
22-0192-ER
22-0328-ER
22-0693-ER
22-0243-ER
22-0362-ER
22-0371-ER
22-0324-ER
22-0413-ER
22-0346-ER
22-0434-ER
22-0021-ER
22-0383-RET-ER
22-0427-ER
22-0432-RET-ER
22-0422-ER
22-0441-ER
22-0251-ER
22-0280-ER
22-0036-ER
22-0259-ER
22-0338-ER
22-0348-ER
22-0188-ER
22-0437-ER
22-0138-ER
22-0031-ER | WO0001, Complete | ELE | 2022-05-23T11:31:30.000 | WO | 0 | 117.176 | 1.1 | 146.47 | 80 |  | 20 |  | 05/23/2022 | 05/23/2022 |  | 2022-06-07T16:07:50.633 | Calof, Alex | ELE
22-0031-ER | WO0003, Complete | Roofing Labor | 2022-05-23T11:31:30.000 | WO | 0 | 5000 | 45.64 | 6852.3 | 5000 |  | 27.0318 |  | 05/25/2022 | 06/06/2022 |  | 2022-06-14T10:39:29.583 | Sleem, Michael | RFG
22-0031-ER | WO0004, Complete | Soffit, Fascia Labor | 2022-05-23T11:31:30.000 | WO | 0 | 177.376 | 1.45 | 221.72 | 80 |  | 20 |  | 05/23/2022 | 05/23/2022 |  | 2022-06-14T10:39:29.597 | Sleem, Michael | SFG
22-0031-ER | WO0005, Complete | Roof Mat Measure | 2022-05-24T14:13:00.000 | WO | 0 | 299.9998 | 8 | 548.07 | 300 |  | 45.2625 |  | 05/24/2022 | 05/24/2022 |  | 2022-06-14T10:39:29.613 | Sleem, Michael | RFG
22-0031-ER | WO0006, Complete | Roofing Materials | 2022-05-24T15:36:00.000 | WO | 0 | 6216.0839 | 58.25 | 10993.26 | 6216.08 |  | 43.4555 |  | 05/23/2022 | 06/02/2022 |  | 2022-06-14T10:39:29.630 | Sleem, Michael | RFG
22-0408-ER | WO0001, Complete | DMO | 2022-05-23T12:47:28.000 | WO | 0 | 94.96 | 1.98 | 189.92 | 50 |  | 50 |  | 05/23/2022 | 05/23/2022 |  | 2022-06-07T12:23:16.077 | Sleem, Michael | DMO
22-0408-ER | WO0002, Complete | FEE | 2022-05-23T12:47:28.743 | WO | 0 | 0 |  | 0 | 0 |  | 0 |  |  |  |  | 2022-06-29T09:36:57.523 | Dehnke, Josh | FEE
22-0408-ER | WO0003, Complete | RFG | 2022-05-23T12:47:28.000 | WO | 0 | 5374.41 | 77.57 | 11441.98 | 5374.41 |  | 53.029 |  | 05/23/2022 | 06/02/2022 |  | 2022-06-29T09:36:57.540 | Dehnke, Josh | RFG
22-0408-ER | WO0004, Complete | SDG | 2022-05-23T12:47:29.000 | WO | 0 | 1568.864 | 19.85 | 2852.48 | 55 |  | 45 |  | 05/23/2022 | 05/25/2022 |  | 2022-06-07T12:22:43.580 | Sleem, Michael | SDG
22-0408-ER | WO0005, Complete | SFG | 2022-05-23T12:47:29.000 | WO | 0 | 648.6425 | 4.88 | 1179.35 | 55 |  | 45 |  | 05/23/2022 | 05/23/2022 |  | 2022-06-29T09:36:57.557 | Dehnke, Josh | SFG
22-0408-ER | WO0006, Complete | RFG Materials | 2022-05-27T11:21:00.000 | WO | 0 | 3865.63 | 8 | 3958.08 | 3865.63 |  | 2.3357 |  | 05/27/2022 | 05/27/2022 |  | 2022-06-29T09:36:57.570 | Dehnke, Josh | RFG
22-0416-ER
22-0417-ER
22-0376-ER
22-0475-ER
22-0452-ER
22-0039-ER
22-0240-ER | WO0004, Complete | Roofing Labor | 2022-06-27T09:09:25.000 | WO | 0 | 6805.7595 | 16 | 13431.51 | 6805.76 |  | 49.3299 |  | 06/30/2022 | 06/30/2022 |  | 2022-07-01T08:09:26.350 | Dehnke, Josh | RFG
22-0240-ER | WO0007, Complete | Roofing Materials | 2022-06-27T09:10:00.000 | WO | 0 | 6942.8125 | 16 | 5672.39 | 6942.81 |  | -22.3966 |  | 06/28/2022 | 06/28/2022 |  | 2022-06-28T14:26:26.250 | Dehnke, Josh | RFG
22-0424-ER
22-0334-ER
22-0196-ER
22-0352-ER
22-0484-ER
22-0293-ER
22-0290-RET-ER
22-0450-ER
22-0091-ER
22-0134-ER
22-0384-RET-ER | WO0001 | FEE | 2022-04-28T10:31:22.000 | WO | 0 | 0 |  | 0 | 134 |  | 0 | [6 empty] | FEE
22-0384-RET-ER | WO0002 | RFG | 2022-04-28T10:31:22.000 | WO | 0 | 6219.7965 | 83.5 | 13821.77 | 45 |  | 55 |  | 05/11/2022 | 05/24/2022 |  |  |  | RFG
22-0384-RET-ER | WO0003 | Roofing material | 2022-04-28T10:31:00.000 | WO | 0 | 4335.2199 | 8 | 3493.28 | 4335.22 |  | -24.1017 |  | 04/28/2022 | 04/28/2022
22-0384-RET-ER | WO0004 | OSB | 2022-05-03T16:33:00.000 | WO | 0 | 1947.2209 | 8 | 3093.1 | 1947.22 |  | 37.0463 |  | 05/03/2022 | 05/03/2022 |  |  |  | Materials
22-0382-IR
22-0366-ER
22-0435-ER
22-0473-ER
22-0157-RET-ER
22-0266-ER | WO0001 | DMO | 2022-05-19T11:43:33.333 | WO | 0 | 47.48 | 0.5 | 47.48 | 100 |  | 0 |  | 05/19/2022 | 05/19/2022 |  |  |  | DMO
22-0266-ER | WO0002 | SFG | 2022-05-19T11:43:33.433 | WO | 0 | 2769.96 | 10.22 | 2769.96 | 100 |  | 0 |  | 05/19/2022 | 05/20/2022 |  |  |  | SFG
22-0436-ER
22-0112-ER-IR
22-0195-ER
22-0401-ER
22-0402-ER
22-0418-ER
22-0459-ER
22-0481-ER
22-0017-ER
22-0109-ER | WO0004, Complete | RFG | 2022-05-25T16:44:57.000 | WO | 0 | 5766.752 | 82.07 | 12582.88 | 45.8301 |  | 54.1699 |  | 05/25/2022 | 06/03/2022 |  | 2022-06-14T10:42:10.107 | Sleem, Michael | RFG
22-0109-ER | WO0007 | We are not doing this | 2022-05-25T16:45:19.000 | WO | 0 | 2107.8388 | 0.78 | 2192.24 | 96.15 |  | 3.85 |  | 05/25/2022 | 05/25/2022 |  |  |  | DOR
22-0109-ER | WO00012, Complete |  | 2022-05-31T09:34:00.000 | WO | 0 | 5168.46 | 10.05 | 5330.66 | 5168.46 |  | 3.0428 |  | 05/25/2022 | 05/31/2022 |  | 2022-06-14T10:42:10.087 | Sleem, Michael | Materials
22-0182-RET-ER
22-0456-ER
22-0489-ER
22-0480-ER
22-0455-ER | WO0004, Complete | menards | 2022-09-19T09:31:15.000 | WO | 0 | 4366.49 |  | 4366.49 | 100 |  | 0 |  |  |  |  | 2022-10-06T15:08:47.637 | Olson, Jonathon | RFG
22-0455-ER | WO0005, Complete | labor | 2022-09-19T09:33:00.000 | WO | 0 | 4828.508 | 82.05 | 12071.27 | 40 |  | 60 |  | 09/19/2022 | 09/29/2022 |  | 2022-10-10T07:59:11.647 | Olson, Jonathon | labor
22-0498-RET-ER
22-0028-ER
22-0497-ER | WO0002, Complete | Permit | 2022-08-15T09:52:51.000 | WO | 0 | 200 |  | 500 | 200 |  | 60 |  |  |  |  | 2022-10-28T07:37:19.327 | Olson, Jonathon | FEE
22-0497-ER | WO0004 | Roofing Labor | 2022-08-15T09:52:51.000 | WO | 0 | 3999.9978 | 71.36 | 9578.47 | 4000 |  | 58.2397 |  | 09/19/2022 | 09/23/2022 |  |  |  | RFG
22-0497-ER | WO0005, Complete | Roofing Materials | 2022-08-15T09:54:00.000 | WO | 0 | 4690.83 | 26 | 4752.42 | 98.704 |  | 1.296 |  | 09/19/2022 | 09/21/2022 |  | 2022-09-14T11:49:26.603 | Olson, Jonathon | Roofing Materials
22-0287-ER
22-0923-ER
22-0797-ER
22-0856-RET-ER
22-0517-ER | WO0002, Complete | FEE | 2022-10-03T23:09:09.610 | WO | 0 | 500 |  | 500 | 100 |  | 0 |  |  |  |  | 2022-10-12T12:23:02.097 | Olson, Jonathon | FEE
22-0517-ER | WO0004, Complete | Labor | 2022-10-03T23:09:00.000 | WO | 0 | 4250.19 | 79.88 | 12143.4 | 35 |  | 65 |  | 10/03/2022 | 10/12/2022 |  | 2022-10-12T12:23:02.050 | Olson, Jonathon | Labor
22-0517-ER | WO0005, Complete | Materials | 2022-10-03T23:09:00.000 | WO | 0 | 5013.9 | 8 | 5013.9 | 100 |  | 0 |  | 10/03/2022 | 10/03/2022 |  | 2022-10-07T13:32:14.877 | Olson, Jonathon | Materials
22-0438-ER | WO0002, Complete | Permit | 2022-10-07T08:05:23.000 | WO | 0 | 0 |  | 0 | 0 |  | 0 |  |  |  |  | 2022-10-07T07:12:47.010 | Hicks, Dave | FEE
22-0438-ER | WO0004, Complete | Roofing Labor | 2022-10-07T08:05:23.000 | WO | 0 | 5973.7405 | 77.59 | 11864.43 | 5973.74 |  | 49.65 |  | 10/07/2022 | 10/19/2022 |  | 2022-10-17T09:01:53.517 | Dehnke, Josh | RFG
22-0438-ER | WO0005, Complete | XST | 2022-10-07T08:05:23.723 | WO | 0 | 1957.48 | 10.4 | 1957.48 | 100 |  | 0 |  | 10/07/2022 | 10/10/2022 |  | 2022-10-17T09:01:53.547 | Dehnke, Josh | XST
22-0438-ER | WO0006, Complete | Materials | 2022-10-07T08:08:00.000 | WO | 0 | 5651.15 | 8 | 5651.15 | 100 |  | 0 |  | 10/07/2022 | 10/07/2022 |  | 2022-10-12T10:53:23.413 | Dehnke, Josh
22-0347-ER | WO0003 | Permit | 2022-09-12T13:58:54.000 | WO | 0 | 0 |  | 0 | 549.11 |  | 0 | [6 empty] | FEE
22-0347-ER | WO0004, Complete | Roofing labor | 2022-09-12T13:58:54.000 | WO | 0 | 9342.5019 | 20 | 23835.71 | 9342.5 |  | 60.8046 |  | 09/16/2022 | 09/20/2022 |  | 2022-09-19T07:57:37.840 | Olson, Jonathon | RFG
22-0347-ER | WO0006, Complete | Siding, window, and door Labor | 2022-09-12T13:58:55.000 | WO | 0 | 0 | 39.37 | 1472.36 | 0 |  | 100 |  | 09/19/2022 | 09/23/2022 |  | 2022-09-19T07:57:37.827 | Olson, Jonathon | SFG
22-0347-ER | WO0007, Complete | Materials | 2022-09-12T14:31:00.000 | WO | 0 | 12604.09 | 8 | 12604.09 | 100 |  | 0 |  | 09/12/2022 | 09/12/2022 |  | 2022-09-12T14:18:45.013 | Olson, Jonathon | MAT
22-0664-ER | WO0004, Complete | Roof | 2022-06-13T17:09:26.000 | WO | 0 | 6258.3264 |  | 6519.09 | 96 |  | 4 |  |  |  |  | 2022-07-01T10:57:08.323 | Dehnke, Josh | SFG
22-0664-ER | WO0005, Complete | Window Well | 2022-06-13T17:09:27.000 | WO | 0 | 167.9998 | 0 | 501.23 | 168 |  | 66.4825 |  | 07/01/2022 | 07/01/2022 |  | 2022-07-01T10:57:08.357 | Dehnke, Josh | SPE
22-0664-ER | WO0006, Complete | Roof Labor | 2022-06-13T17:13:00.000 | WO | 0 | 5500 | 38.46 | 10566.24 | 5500 |  | 47.9474 |  | 06/30/2022 | 07/07/2022 |  | 2022-07-11T10:00:48.420 | Trevino, Jeovani | Roof Labor
22-0664-ER | WO0007, Complete | gutters | 2022-07-06T14:51:00.000 | WO | 0 | 1247.2133 | 17.71 | 2788.35 | 44.7294 |  | 55.2706 |  | 07/05/2022 | 07/06/2022 |  | 2022-07-11T10:00:48.457 | Trevino, Jeovani | gutters
22-0478-ER
22-0611-ER | WO0003, Complete | Roofing Labor | 2022-07-07T11:06:46.000 | WO | 0 | 4140 | 29.1 | 10765.33 | 4140 |  | 61.5432 |  | 08/23/2022 | 08/26/2022 |  | 2022-08-24T08:27:53.723 | Deville , Jard | RFG
22-0611-ER | WO0004, Complete | Roofing materials | 2022-07-07T11:07:00.000 | WO | 0 | 4965.6916 | 8 | 4438.73 | 4965.69 |  | -11.8719 |  | 08/20/2022 | 08/20/2022 |  | 2022-08-19T09:42:28.360 | Deville , Jard | RFG
22-0332-ER
22-0345-ER | WO0002, Complete | FEE | 2022-08-26T13:48:02.273 | WO | 0 | 500 |  | 500 | 100 |  | 0 |  |  |  |  | 2022-09-02T13:01:18.333 | Trevino, Jeovani | FEE
22-0345-ER | WO0005, Complete | Labor | 2022-08-31T10:04:00.000 | WO | 0 | 4299.9961 | 113.27 | 15846.97 | 4300 |  | 72.8655 |  | 08/26/2022 | 09/07/2022 |  | 2022-09-06T08:10:36.313 | Trevino, Jeovani | Labor
22-0345-ER | WO0006, Complete | materials | 2022-08-31T10:05:00.000 | WO | 0 | 5305.3368 | 8 | 9630.99 | 5305.34 |  | 44.9139 |  | 08/31/2022 | 08/31/2022 |  | 2022-09-02T13:01:07.720 | Trevino, Jeovani | materials
22-0465-ER
22-0368-ER
22-0556-RET-ER
22-0137-ER
22-0020-ER | WO0001 | DMO | 2022-10-21T08:54:05.793 | WO | 0 | 189.92 | 1.98 | 189.92 | 100 |  | 0 |  | 10/21/2022 | 10/21/2022 |  |  |  | DMO
22-0020-ER | WO0002 | DRY | 2022-10-21T08:54:06.033 | WO | 0 | 924.72 | 7.67 | 924.72 | 100 |  | 0 |  | 10/21/2022 | 10/21/2022 |  |  |  | DRY
22-0020-ER | WO0003 | FEE | 2022-10-21T08:54:06.143 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | FEE
22-0020-ER | WO0004 | RFG | 2022-10-21T08:54:06.213 | WO | 0 | 15962.55 | 43.73 | 15962.55 | 100 |  | 0 |  | 10/21/2022 | 10/27/2022 |  |  |  | RFG
22-0382-ER | WO0001, Complete | Dumpster | 2022-07-21T12:21:59.000 | WO | 0 | 0 | 1.98 | 545.92 | 0 |  | 100 |  | 08/29/2022 | 08/29/2022 |  | 2022-08-29T08:54:11.647 | Deville , Jard | DMO
22-0382-ER | WO0002, Complete | Permit | 2022-07-21T12:21:59.000 | WO | 0 | 151 |  | 151 | 151 |  | 0 |  |  |  |  | 2022-08-29T08:54:08.177 | Deville , Jard | FEE
22-0382-ER | WO0003, Complete | Roofing Labor | 2022-07-21T12:22:00.000 | WO | 0 | 3099.9996 | 25.78 | 7680.11 | 3100 |  | 59.636 |  | 08/29/2022 | 08/31/2022 |  | 2022-08-26T11:05:55.660 | Deville , Jard | RFG
22-0382-ER | WO0004, Complete | Siding | 2022-07-21T12:22:00.000 | WO | 0 | 0 | 0 | 314.59 | 0 |  | 100 |  | 08/31/2022 | 08/31/2022 |  | 2022-09-01T11:46:32.410 | Deville , Jard | SDG
22-0382-ER | WO0005, Complete | Gutter | 2022-07-21T12:22:00.000 | WO | 0 | 242.08 | 31.22 | 594.1 | 242.08 |  | 59.2527 |  | 09/06/2022 | 09/09/2022 |  | 2022-09-13T13:06:10.093 | Sleem, Michael | SFG
22-0382-ER | WO0006, Complete | RFG Materials | 2022-07-21T12:28:00.000 | WO | 0 | 3461.0005 | 8 | 2874.06 | 3461 |  | -20.422 |  | 08/23/2022 | 08/23/2022 |  | 2022-08-15T15:16:33.390 | Deville , Jard | RFG Materails
22-0382-ER | WO0007, Complete | Roof edge venting | 2022-07-27T11:13:00.000 | WO | 0 | 0 | 26 | 0 | 0 |  | 0 |  | 08/29/2022 | 08/31/2022 |  | 2022-08-15T15:16:46.480 | Deville , Jard | Roof edge venting
22-0382-ER | WO0008, Complete | Gutter material | 2022-09-01T12:52:00.000 | WO | 0 | 29.5425 | 8 | 225.33 | 29.5425 |  | 86.8892 |  | 09/01/2022 | 09/01/2022 |  | 2022-09-01T11:52:42.317 | Deville , Jard | Gutter material
22-0521-ER | WO0001 | CON | 2022-08-08T15:56:25.873 | WO | 0 | 137.12 | 2.2 | 137.12 | 100 |  | 0 |  | 08/08/2022 | 08/08/2022 |  |  |  | CON
22-0521-ER | WO0002 | DMO | 2022-08-08T15:56:26.000 | WO | 0 | 427.2 |  | 427.2 | 100 |  | 0 | [6 empty] | DMO
22-0521-ER | WO0003 | DRY | 2022-08-08T15:56:26.177 | WO | 0 | 2276.72 | 12.98 | 2276.72 | 100 |  | 0 |  | 08/08/2022 | 08/09/2022 |  |  |  | DRY
22-0521-ER | WO0004 | ELE | 2022-08-08T15:56:26.310 | WO | 0 | 311.11 | 0.52 | 311.11 | 100 |  | 0 |  | 08/08/2022 | 08/08/2022 |  |  |  | ELE
22-0521-ER | WO0005 | FEE | 2022-08-08T15:56:26.437 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | FEE
22-0521-ER | WO0006 | FNC | 2022-08-08T15:56:26.627 | WO | 0 | 272.94 | 0.67 | 272.94 | 100 |  | 0 |  | 08/08/2022 | 08/08/2022 |  |  |  | FNC
22-0521-ER | WO0007 | FRM | 2022-08-08T15:56:27.007 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | FRM
22-0521-ER | WO0008 | HMR | 2022-08-08T15:56:27.177 | WO | 0 | 331.75 | 0.07 | 331.75 | 100 |  | 0 |  | 08/08/2022 | 08/08/2022 |  |  |  | HMR
22-0521-ER | WO0009 | LIT | 2022-08-08T15:56:27.250 | WO | 0 | 84.72 | 0.53 | 84.72 | 100 |  | 0 |  | 08/08/2022 | 08/08/2022 |  |  |  | LIT
22-0521-ER | WO00010 | PNT | 2022-08-08T15:56:27.347 | WO | 0 | 1499.12 | 10.3 | 1499.12 | 100 |  | 0 |  | 08/08/2022 | 08/09/2022 |  |  |  | PNT
22-0521-ER | WO00011 | RFG | 2022-08-08T15:56:27.460 | WO | 0 | 15833.65 | 63.61 | 15833.65 | 100 |  | 0 |  | 08/08/2022 | 08/17/2022 |  |  |  | RFG
22-0521-ER | WO00012 | SFG | 2022-08-08T15:56:27.750 | WO | 0 | 776.45 | 2.6 | 776.45 | 100 |  | 0 |  | 08/08/2022 | 08/08/2022 |  |  |  | SFG
22-0521-ER | WO00013 | WDT | 2022-08-08T15:56:27.917 | WO | 0 | 223.62 | 1.18 | 223.62 | 100 |  | 0 |  | 08/08/2022 | 08/08/2022 |  |  |  | WDT
22-0521-ER | WO00014 | WPR | 2022-08-08T15:56:28.037 | WO | 0 | 4539.64 | 27.82 | 4539.64 | 100 |  | 0 |  | 08/08/2022 | 08/11/2022 |  |  |  | WPR
22-0521-ER | WO00015 | WTR | 2022-08-08T15:56:28.217 | WO | 0 | 9.19 |  | 9.19 | 100 |  | 0 | [6 empty] | WTR
22-0038-ER | WO0002, Complete | roof Labor | 2022-07-13T13:36:55.000 | WO | 0 | 5700 | 96.43 | 15398.76 | 5700 |  | 62.984 |  | 07/13/2022 | 07/27/2022 |  | 2022-07-28T10:58:35.713 | Trevino, Jeovani | FEE
22-0038-ER | WO0003, Complete | FRM | 2022-07-13T13:36:55.000 | WO | 0 | 0 |  | 0 | 0 |  | 0 |  |  |  |  | 2022-07-28T10:58:35.723 | Trevino, Jeovani | FRM
22-0038-ER | WO0005, Complete | SFG | 2022-07-13T13:36:56.000 | WO | 0 | 1499.9985 | 111.88 | 3104.34 | 1500 |  | 51.6806 |  | 07/13/2022 | 07/29/2022 |  | 2022-07-28T10:58:35.733 | Trevino, Jeovani | SFG
22-0038-ER | WO0006, Complete | MATERIALS | 2022-07-18T10:44:00.000 | WO | 0 | 5872.8583 | 8 | 6657.06 | 88.22 |  | 11.78 |  | 07/15/2022 | 07/15/2022 |  | 2022-07-18T09:48:01.963 | Trevino, Jeovani | MAT
23-0176-ER | WO0002, Complete | Permit Cost | 2022-06-22T12:23:54.000 | WO | 0 | 475 |  | 475 | 100 |  | 0 |  |  |  |  | 2022-07-11T07:38:47.000 | Dehnke, Josh | FEE
23-0176-ER | WO0003, Complete | Roofing Labor | 2022-06-22T12:23:54.000 | WO | 0 | 6508.053 | 11 | 14462.34 | 45 |  | 55 |  | 07/07/2022 | 07/07/2022 |  | 2022-07-11T07:38:47.063 | Dehnke, Josh | RFG
23-0176-ER | WO0004, Complete | Gutter Guard Labor | 2022-06-22T12:23:54.000 | WO | 0 | 483.425 | 3 | 966.85 | 50 |  | 50 |  | 07/08/2022 | 07/08/2022 |  | 2022-07-11T07:38:47.100 | Dehnke, Josh | SFG
23-0176-ER | WO0006, Complete | Window Screen Labor | 2022-06-22T12:23:54.000 | WO | 0 | 134.78 | 2 | 269.56 | 50 |  | 50 |  | 07/07/2022 | 07/07/2022 |  | 2022-07-11T07:38:47.147 | Dehnke, Josh | WDW
23-0176-ER | WO0007, Complete | Roofing Materials | 2022-06-22T12:24:00.000 | WO | 0 | 4731.1725 | 8 | 6308.23 | 75 |  | 25 |  | 06/22/2022 | 06/22/2022 |  | 2022-07-01T08:08:25.027 | Dehnke, Josh | RFG
23-0176-ER | WO0008, Complete | Gutter Screens Material | 2022-06-22T12:27:00.000 | WO | 0 | 269.41 | 8 | 269.41 | 100 |  | 0 |  | 06/22/2022 | 06/22/2022 |  | 2022-07-01T08:08:25.043 | Dehnke, Josh | SFG
23-0176-ER | WO0009, Complete | Window Screens Material | 2022-06-22T12:28:00.000 | WO | 0 | 111.35 | 8 | 111.35 | 100 |  | 0 |  | 06/22/2022 | 06/22/2022 |  | 2022-07-01T08:08:25.043 | Dehnke, Josh | WDW
22-0589-RET-ER
23-0185-ER
23-0149-ER
22-0291-ER
22-1011-May-C | WO0001 | DMO | 2022-06-10T16:47:25.570 | WO | 0 | 455 |  | 455 | 100 |  | 0 | [6 empty] | DMO
22-1011-May-C | WO0002 | ELE | 2022-06-10T16:47:25.707 | WO | 0 | 328.98 | 1.1 | 328.98 | 100 |  | 0 |  | 06/10/2022 | 06/10/2022 |  |  |  | ELE
22-1011-May-C | WO0003 | FEE | 2022-06-10T16:47:25.837 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | FEE
22-1011-May-C | WO0004 | FPL | 2022-06-10T16:47:25.980 | WO | 0 | 172.59 | 0.6 | 172.59 | 100 |  | 0 |  | 06/10/2022 | 06/10/2022 |  |  |  | FPL
22-1011-May-C | WO0005 | FRM | 2022-06-10T16:47:26.117 | WO | 0 | 3337.35 | 14.85 | 3337.35 | 100 |  | 0 |  | 06/10/2022 | 06/13/2022 |  |  |  | FRM
22-1011-May-C | WO0006 | HVC | 2022-06-10T16:47:26.190 | WO | 0 | 348.94 | 0.13 | 348.94 | 100 |  | 0 |  | 06/10/2022 | 06/10/2022 |  |  |  | HVC
22-1011-May-C | WO0007 | RFG | 2022-06-10T16:47:26.287 | WO | 0 | 13870.72 | 65.85 | 13870.72 | 100 |  | 0 |  | 06/10/2022 | 06/21/2022 |  |  |  | RFG
22-1011-May-C | WO0008 | SDG | 2022-06-10T16:47:26.470 | WO | 0 | 26059.1 | 124.08 | 26059.1 | 100 |  | 0 |  | 06/10/2022 | 06/29/2022 |  |  |  | SDG
22-1011-May-C | WO0009 | SFG | 2022-06-10T16:47:26.820 | WO | 0 | 108.96 | 0.55 | 108.96 | 100 |  | 0 |  | 06/10/2022 | 06/10/2022 |  |  |  | SFG
22-1011-June-C-C
23-0162-ER
23-0164-RET-ER
23-0183-ER
22-0938-ER
22-0800-ER
22-0574-ER
22-0130-RET-ER | WO0002, Complete | FEE | 2022-08-29T10:58:26.463 | WO | 0 | 0 |  | 0 | 0 |  | 0 |  |  |  |  | 2022-09-06T07:46:34.960 | Dehnke, Josh | FEE
22-0130-RET-ER | WO0003, Complete | FRM | 2022-08-29T10:58:26.537 | WO | 0 | 0 |  | 0 | 0 |  | 0 |  |  |  |  | 2022-09-06T07:46:34.930 | Dehnke, Josh | FRM
22-0130-RET-ER | WO0004, Complete | Roofing Labor | 2022-08-29T10:58:26.000 | WO | 0 | 5100 | 83.25 | 13293.93 | 5100 |  | 61.6366 |  | 08/29/2022 | 09/09/2022 |  | 2022-09-06T07:46:34.900 | Dehnke, Josh | RFG
22-0130-RET-ER | WO0008, Complete | Window Screen labor | 2022-08-29T10:58:27.000 | WO | 0 | 258.82 | 0 | 258.82 | 100 |  | 0 |  | 08/29/2022 | 08/29/2022 |  | 2022-09-06T07:46:34.867 | Dehnke, Josh | WDW
22-0130-RET-ER | WO0009, Complete | Roofing Materials | 2022-08-29T10:58:00.000 | WO | 0 | 5256.3 | 8 | 5256.3 | 100 |  | 0 |  | 08/29/2022 | 08/29/2022 |  | 2022-08-29T10:06:45.857 | Dehnke, Josh | RFG
22-0130-RET-ER | WO00010, Complete | Soffit fix | 2022-11-29T15:01:00.000 | WO | 0 | 519.18 | 10.14 | 519.18 | 100 |  | 0 |  | 08/29/2022 | 11/29/2022 |  | 2023-01-03T10:17:23.620 | Dehnke, Josh | SFT
22-0222-ER | WO0002, Complete | ELE | 2022-12-02T14:58:47.257 | WO | 0 | 316.66 | 2 | 316.66 | 100 |  | 0 |  | 12/02/2022 | 12/02/2022 |  | 2022-12-02T14:13:32.627 | Trevino, Jeovani | ELE
22-0222-ER | WO0003, Complete | FEE | 2022-12-02T14:58:47.427 | WO | 0 | 500 |  | 500 | 100 |  | 0 |  |  |  |  | 2022-12-02T14:13:32.673 | Trevino, Jeovani | FEE
22-0222-ER | WO0008, Complete | punch | 2022-12-02T14:58:48.000 | WO | 0 | 500 | 27.66 | 3730.73 | 500 |  | 86.5978 |  | 12/02/2022 | 12/12/2022 |  | 2023-01-02T09:11:31.883 | Trevino, Jeovani | SFG
22-0222-ER | WO0009, Complete | materials | 2022-12-02T15:00:00.000 | WO | 0 | 5321.4464 | 8 | 8196.26 | 5321.45 |  | 35.0747 |  | 12/02/2022 | 12/02/2022 |  | 2022-12-02T14:13:24.010 | Trevino, Jeovani | materials
22-0222-ER | WO00010, Complete | siding labor | 2022-12-02T15:02:00.000 | WO | 0 | 7799.9904 | 132.5 | 21352.17 | 7800 |  | 63.4698 |  | 12/02/2022 | 12/22/2022 |  | 2022-12-02T14:13:24.033 | Trevino, Jeovani | siding labor
22-0599-ER | WO0007, Complete | Labor | 2022-07-24T19:14:00.000 | WO | 0 | 7160 | 16.48 | 20216.35 | 7160 |  | 64.5831 |  | 08/08/2022 | 08/09/2022 |  | 2022-08-15T13:53:26.397 | Trevino, Jeovani | Labor
22-0599-ER | WO0008, Complete | material | 2022-07-24T19:17:00.000 | WO | 0 | 9350.04 | 8 | 8191.37 | 9350.04 |  | -14.145 |  | 07/29/2022 | 07/29/2022 |  | 2022-07-27T15:25:45.327 | Trevino, Jeovani | materials
22-0599-ER | WO0009, Complete | RFG | 2022-07-24T19:25:00.000 | WO | 0 | 0 | 8 | 15.01 | 0 |  | 100 |  | 08/08/2022 | 08/08/2022 |  | 2022-08-15T13:53:42.073 | Trevino, Jeovani | RFG
22-0599-ER | WO00010 | window wraps | 2023-02-27T13:46:00.000 | WO | 0 | 684.9997 | 8.53 | 1365.36 | 685 |  | 49.8301 |  | 02/27/2023 | 08/08/2022 |  |  |  | joshua perkins
22-0801-ER | WO0001, Complete | Cleaning | 2022-08-23T11:07:04.000 | WO | 0 | 0 | 22.5 | 1681.55 | 0 |  | 100 |  | 08/23/2022 | 08/25/2022 |  | 2022-11-18T20:11:40.090 | Olson, Jonathon | CLN
22-0801-ER | WO0002, Complete | Permit | 2022-08-23T11:07:05.000 | WO | 0 | 690.0001 |  | 766.31 | 690 |  | 9.9581 |  |  |  |  | 2022-08-29T14:44:46.417 | Deville , Jard | FEE
22-0801-ER | WO0004, Complete | Paint | 2022-08-23T11:07:05.000 | WO | 0 | 0 | 100.4 | 1634.74 | 0 |  | 100 |  | 08/23/2022 | 09/07/2022 |  | 2022-09-20T09:47:22.473 | Olson, Jonathon | PNT
22-0801-ER | WO0005, Complete | Roofing | 2022-08-23T11:07:06.000 | WO | 0 | 7548.6308 | 141.67 | 21224.17 | 7548.64 |  | 64.4338 |  | 08/23/2022 | 09/13/2022 |  | 2022-08-25T08:27:29.210 | Deville , Jard | RFG
22-0801-ER | WO0006, Complete | gutter down spout | 2022-08-23T11:07:06.000 | WO | 0 | 0 | 2.15 | 730.04 | 0 |  | 100 |  | 08/23/2022 | 08/23/2022 |  | 2022-11-18T20:11:40.010 | Olson, Jonathon | SFG
22-0801-ER | WO0007, Complete | door trim | 2022-08-23T11:07:06.000 | WO | 0 | 0 | 0.35 | 83.6 | 0 |  | 100 |  | 08/23/2022 | 08/23/2022 |  | 2022-11-18T20:11:40.060 | Olson, Jonathon | WDR
22-0801-ER | WO0008, Complete | Widow labor | 2022-08-23T11:07:06.000 | WO | 0 | 0 | 0 | 241.65 | 0 |  | 100 |  | 08/23/2022 | 08/23/2022 |  | 2022-11-18T20:11:40.073 | Olson, Jonathon | WDW
22-0801-ER | WO0009, Complete | Roofing Materials | 2022-08-24T14:26:00.000 | WO | 0 | 9499.9972 | 8 | 7578.62 | 9500 |  | -25.3526 |  | 08/24/2022 | 08/24/2022 |  | 2022-08-25T08:27:35.167 | Deville , Jard | Roofing Materials
22-0776-RET-ER | WO0002, Complete | Dumpster | 2022-09-24T15:35:13.000 | WO | 0 | 466.73 |  | 466.73 | 100 |  | 0 |  |  |  |  | 2022-11-29T14:13:42.517 | Dehnke, Josh | DMO
22-0776-RET-ER | WO0006, Complete | House Labor | 2022-09-24T15:35:13.000 | WO | 0 | 12011.1488 | 65.61 | 10370.11 | 12011.15 |  | -15.8247 |  | 09/24/2022 | 10/03/2022 |  | 2022-10-17T12:42:30.253 | Hicks, Dave | RFG
22-0776-RET-ER | WO0007, Complete | Siding Labor | 2022-09-24T15:35:13.000 | WO | 0 | 400 | 0.85 | 471.81 | 400 |  | 15.2201 |  | 09/24/2022 | 09/24/2022 |  | 2022-10-17T08:52:21.800 | Hicks, Dave | SDG
22-0776-RET-ER | WO0008, Complete | Window Materials | 2022-09-24T15:35:13.000 | WO | 0 | 46.62 |  | 46.62 | 100 |  | 0 |  |  |  |  | 2022-10-17T09:15:56.937 | Dehnke, Josh | WDR
22-0776-RET-ER | WO0009 | Window Labor | 2022-09-24T15:35:13.000 | WO | 0 | 0 | 0.13 | 270.8 | 0 |  | 100 |  | 09/24/2022 | 09/24/2022 |  |  |  | WDW
22-0776-RET-ER | WO00010, Complete | House Materials | 2022-09-24T15:40:00.000 | WO | 0 | 3321.69 | 8 | 3321.69 | 100 |  | 0 |  | 09/24/2022 | 09/24/2022 |  | 2022-10-17T08:52:21.817 | Hicks, Dave
22-0776-RET-ER | WO00011, Complete | Siding Materials | 2022-10-17T13:36:00.000 | WO | 0 | 67.23 | 8 | 67.23 | 100 |  | 0 |  | 10/17/2022 | 10/17/2022 |  | 2022-10-17T12:37:37.527 | Hicks, Dave
22-0776-RET-ER | WO00012, Complete | Supplement Roof Sheathing | 2022-12-30T13:03:00.000 | WO | 0 | 6064 | 8 | 6064 | 100 |  | 0 |  | 12/30/2022 | 12/30/2022 |  | 2022-12-30T12:03:59.007 | Dehnke, Josh | SUP
22-0690-ER | WO0001 | RFG | 2022-09-22T22:00:12.783 | WO | 0 | -52.55 |  | -52.55 | 100 |  | 0 | [6 empty] | RFG
22-0690-ER | WO0004, Complete | Roofing Labor | 2022-09-22T22:00:00.000 | WO | 0 | 7036.3418 | 126.65 | 16695.08 | 7036.34 |  | 57.8538 |  | 09/22/2022 | 10/12/2022 |  | 2022-10-17T07:41:54.143 | Olson, Jonathon | Roofing Labor
22-0690-ER | WO0006, Complete | Materials | 2022-09-22T22:01:00.000 | WO | 0 | 5377.41 | 8 | 5377.41 | 100 |  | 0 |  | 09/22/2022 | 09/22/2022 |  | 2022-10-17T07:41:54.097 | Olson, Jonathon | Materials
22-0690-ER | WO0007, Complete | Gutter Labor | 2022-10-21T14:06:00.000 | WO | 0 | 2800.0008 | 41.28 | 3412.18 | 2800 |  | 17.941 |  | 09/22/2022 | 10/21/2022 |  | 2022-11-27T18:59:33.087 | Olson, Jonathon | Gutter Labor
22-0594-ER | WO0001, Complete | Demo | 2022-09-09T14:46:09.000 | WO | 0 | 97.88 | 1 | 97.88 | 100 |  | 0 |  | 09/09/2022 | 09/09/2022 |  | 2022-10-21T11:05:22.173 | Dehnke, Josh | DMO
22-0594-ER | WO0002, Complete | Storm Door | 2022-09-09T14:46:09.000 | WO | 0 | 649.9996 | 1.72 | 1068.4 | 650 |  | 39.1614 |  | 09/09/2022 | 09/09/2022 |  | 2022-10-21T11:05:22.230 | Dehnke, Josh | DOR
22-0594-ER | WO0003 | Permit | 2022-09-09T14:46:10.000 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | FEE
22-0594-ER | WO0004, Complete | Sheething | 2022-09-09T14:46:10.000 | WO | 0 | 214.37 | 2.62 | 214.37 | 100 |  | 0 |  | 09/09/2022 | 09/09/2022 |  | 2022-10-09T21:37:43.213 | Trevino, Jeovani | FRM
22-0594-ER | WO0005, Complete | Roofing Labor | 2022-09-09T14:46:10.000 | WO | 0 | 5719.9986 | 75.45 | 11618.15 | 5720 |  | 50.7667 |  | 09/09/2022 | 09/21/2022 |  | 2022-10-09T21:37:06.243 | Trevino, Jeovani | RFG
22-0594-ER | WO0006, Complete | Gutter guard/Downspouts | 2022-09-09T14:46:11.000 | WO | 0 | 2000 | 19.7 | 3036.5 | 2000 |  | 34.1347 |  | 09/09/2022 | 09/13/2022 |  | 2022-10-02T11:15:47.577 | Trevino, Jeovani | SFG
22-0594-ER | WO0007, Complete | Roofing Materials | 2022-09-09T14:48:00.000 | WO | 0 | 4740.83 | 8 | 4740.83 | 100 |  | 0 |  | 09/09/2022 | 09/09/2022 |  | 2022-09-23T11:56:09.213 | Dehnke, Josh | Roofing materials
22-0594-ER | WO0008, Complete | Materials | 2022-09-23T12:55:00.000 | WO | 0 | 1560.71 | 8 | 1560.71 | 100 |  | 0 |  | 09/23/2022 | 09/23/2022 |  | 2022-09-23T11:56:09.277 | Dehnke, Josh | MAT
22-0594-ER | WO0009, Complete | Gutter Labor | 2023-01-03T14:28:00.000 | WO | 0 | 500 | 11.22 | 532.55 | 500 |  | 6.1121 |  | 01/03/2023 | 09/09/2022 |  | 2023-02-16T10:12:49.027 | Trevino, Jeovani | SFG
22-0580-ER | WO0002, Complete | Permit Fee | 2022-09-24T14:12:22.000 | WO | 0 | 0 |  | 0 | 0 |  | 0 |  |  |  |  | 2022-10-06T15:54:23.780 | Hicks, Dave | FEE
22-0580-ER | WO0003, Complete | OSB 1/2 | 2022-09-24T14:12:22.000 | WO | 0 | 0 |  | 0 | 0 |  | 0 |  |  |  |  | 2022-10-17T09:05:39.977 | Dehnke, Josh | FRM
22-0580-ER | WO0004, Complete | HVC | 2022-09-24T14:12:23.477 | WO | 0 | 262.7 | 1.75 | 262.7 | 100 |  | 0 |  | 09/24/2022 | 09/24/2022 |  | 2022-10-17T09:05:40.023 | Dehnke, Josh | HVC
22-0580-ER | WO0005, Complete | House Materials | 2022-09-24T14:12:23.000 | WO | 0 | 3052.01 |  | 3052.01 | 100 |  | 0 |  |  |  |  | 2022-09-27T13:03:49.227 | Hicks, Dave | RFG
22-0580-ER | WO0007, Complete | Roofing Labor | 2022-09-24T14:24:00.000 | WO | 0 | 5447.3402 | 12.48 | 12293.26 | 5447.34 |  | 55.6884 |  | 09/29/2022 | 09/30/2022 |  | 2022-10-17T09:05:40.057 | Dehnke, Josh
22-0580-ER | WO0009, Complete | Garage Materials | 2022-09-24T14:39:00.000 | WO | 0 | 1503.54 | 8 | 1503.54 | 100 |  | 0 |  | 09/24/2022 | 09/24/2022 |  | 2022-09-27T13:03:49.210 | Hicks, Dave
23-0131-RET-ER | WO0002, Complete | FEE | 2022-11-21T12:56:47.600 | WO | 0 | 0 |  | 0 | 0 |  | 0 |  |  |  |  | 2022-11-21T12:19:20.770 | Olson, Jonathon | FEE
23-0131-RET-ER | WO0007, Complete | Materials | 2022-11-21T12:57:00.000 | WO | 0 | 8501.09 | 8 | 8501.09 | 100 |  | 0 |  | 11/21/2022 | 11/21/2022 |  | 2022-11-21T12:19:20.723 | Olson, Jonathon | Materials
23-0131-RET-ER | WO0008, Complete | Labor | 2022-11-21T12:57:00.000 | WO | 0 | 12969.8692 | 153.03 | 22090.21 | 12969.88 |  | 41.2868 |  | 11/21/2022 | 12/12/2022 |  | 2022-11-21T12:19:20.770 | Olson, Jonathon | Labor
23-0131-RET-ER | WO0009 | Gutter Labor | 2023-01-03T10:51:00.000 | WO | 0 | 2499.9966 | 44 | 6977.89 | 2500 |  | 64.1726 |  | 04/03/2023 | 04/07/2023 |  |  |  | Gutters
22-0479-RET-ER
22-1009-RET-ER | WO0002 | Exhaust vent | 2022-12-11T23:09:43.000 | WO | 0 | 300 | 1.4 | 394.9 | 300 |  | 24.0314 |  | 12/11/2022 | 12/11/2022 |  |  |  | RFG
22-1009-RET-ER | WO0004 | gutter labor and material | 2022-12-11T23:10:00.000 | WO | 0 | 369.9995 | 10.9 | 973.56 | 370 |  | 61.9952 |  | 12/11/2022 | 12/11/2022 |  |  |  | gutter labor and material
22-1004-RET-ER
22-0992-RET-ER
22-0377-ER
22-0885-ER-2 | WO0002, Complete | ELS | 2022-10-20T23:00:10.000 | WO | 0 | 58.224 | 2.77 | 145.56 | 40 |  | 60 |  | 10/20/2022 | 10/20/2022 |  | 2023-01-03T11:43:31.693 | Dehnke, Josh | ELS
22-0885-ER-2 | WO0003, Complete | FEE | 2022-10-20T23:00:10.000 | WO | 0 | 307.035 |  | 682.3 | 45 |  | 55 |  |  |  |  | 2023-01-03T11:43:31.670 | Dehnke, Josh | FEE
22-0885-ER-2 | WO0008, Complete | Materials | 2022-11-10T15:41:00.000 | WO | 0 | 7780.86 | 8 | 7780.86 | 100 |  | 0 |  | 11/10/2022 | 11/10/2022 |  | 2022-12-06T11:58:47.890 | Olson, Jonathon | Materials
22-0885-ER-2 | WO0009, Complete | Roofing Labor | 2022-11-10T15:42:00.000 | WO | 0 | 7000.0056 | 145.37 | 19618.52 | 7000 |  | 64.3194 |  | 10/20/2022 | 11/10/2022 |  | 2022-12-06T11:58:48.037 | Olson, Jonathon | Roofing Labor
22-0885-ER-2 | WO00010, Complete | Gutter Labor | 2022-11-10T15:42:00.000 | WO | 0 | 3300.0023 | 44.55 | 4775.67 | 3300 |  | 30.8997 |  | 10/20/2022 | 11/10/2022 |  | 2023-03-23T09:22:45.810 | Olson, Jonathon | Gutter Labor
22-0562-ER | WO0003, Complete | Roofing, Downspouts, Gutter Screen and Dumpster labor | 2023-05-01T13:00:16.000 | WO | 0 | 3699.9985 | 3.27 | 7259.81 | 3700 |  | 49.0345 |  | 05/01/2023 | 05/01/2023 |  | 2023-05-08T10:56:13.293 | Dehnke, Josh | RFG
22-0562-ER | WO0005, Complete | Roofing Materials | 2023-05-01T13:07:00.000 | WO | 0 | 4927.5519 | 8 | 5158.19 | 4927.55 |  | 4.4713 |  | 05/01/2023 | 05/01/2023 |  | 2023-05-08T10:56:13.310 | Dehnke, Josh | RFG
22-0530-ER | WO0001, Complete | FEE | 2023-04-11T10:23:52.000 | WO | 0 | 0 |  | 0 | 872.25 |  | 0 |  |  |  |  | 2023-05-01T11:09:39.403 | Dehnke, Josh | FEE
22-0530-ER | WO0003, Complete | Roofing Labor | 2023-04-11T10:23:52.000 | WO | 0 | 7000.0019 | 124.92 | 17666.69 | 7000 |  | 60.3774 |  | 04/11/2023 | 05/01/2023 |  | 2023-05-01T11:09:39.427 | Dehnke, Josh | RFG
22-0530-ER | WO0005, Complete | Gutter Covers and Down Spouts Labor | 2023-04-11T10:23:53.000 | WO | 0 | 1499.9983 | 35.77 | 5491.08 | 1500 |  | 72.683 |  | 04/11/2023 | 04/17/2023 |  | 2023-05-01T11:09:39.433 | Dehnke, Josh | SFG
22-0530-ER | WO0007, Complete | WDW Wraps and Screens Labor | 2023-04-11T10:23:53.000 | WO | 0 | 2000.0009 | 21.07 | 3021.3 | 2000 |  | 33.8033 |  | 04/11/2023 | 04/12/2023 |  | 2023-05-01T11:09:39.450 | Dehnke, Josh | WDS
22-0530-ER | WO0009, Complete | Roofing Materials | 2023-04-11T09:24:53.000 | WO | 0 | 9591.5529 |  | 12612.2 | 9591.55 |  | 23.9502 |  |  |  |  | 2023-04-24T09:52:49.047 | Dehnke, Josh | Material Work Order
22-0530-ER | WO00012, Complete | WDW Materials | 2023-04-11T09:28:16.000 | WO | 0 | 0 |  | 1319.24 | 0 |  | 100 |  |  |  |  | 2023-04-24T09:52:49.063 | Dehnke, Josh | Material Work Order
22-0386-ER | WO0002, Complete | FEE | 2022-09-09T14:10:10.503 | WO | 0 | 0 |  | 0 | 0 |  | 0 |  |  |  |  | 2022-09-28T14:41:07.570 | Olson, Jonathon | FEE
22-0386-ER | WO0003, Complete | Roofing Labor | 2022-09-09T14:10:10.000 | WO | 0 | 7578.3622 | 11.23 | 20482.06 | 37 |  | 63 |  | 09/22/2022 | 09/23/2022 |  | 2022-09-28T14:41:07.560 | Olson, Jonathon | RFG
22-0386-ER | WO0004, Complete | Gutter Labor | 2022-09-09T14:10:10.000 | WO | 0 | 1102.7319 | 2.78 | 2808.69 | 39.2614 |  | 60.7386 |  | 09/09/2022 | 09/23/2022 |  | 2022-09-28T14:41:07.540 | Olson, Jonathon | SFG
22-0386-ER | WO0005, Complete | Materials | 2022-09-09T14:10:00.000 | WO | 0 | 9205.84 | 8 | 9205.84 | 100 |  | 0 |  | 09/09/2022 | 09/09/2022 |  | 2022-09-09T14:21:03.170 | Dehnke, Josh | MAT
22-0386-ER | WO0006, Complete | Gutter Punch | 2023-03-15T15:03:00.000 | WO | 0 | 963.63 | 41.43 | 963.63 | 100 |  | 0 |  | 04/03/2023 | 04/07/2023 |  | 2023-06-05T13:16:31.637 | Dehnke, Josh | PUNCH
22-0512-RET-ER | WO0002, Complete | DOR | 2022-07-18T13:50:07.000 | WO | 0 | 2294.592 | 25 | 3824.32 | 60 |  | 40 |  | 08/01/2022 | 08/03/2022 |  | 2022-10-17T09:25:26.713 | Dehnke, Josh | DOR
22-0512-RET-ER | WO0004, Complete | FEE | 2022-07-18T13:50:07.590 | WO | 0 | 0 |  | 0 | 0 |  | 0 |  |  |  |  | 2022-07-22T09:30:36.613 | Dehnke, Josh | FEE
22-0512-RET-ER | WO0008, Complete | Roofing Labor | 2022-07-18T13:50:09.000 | WO | 0 | 8500 | 14.84 | 20486.38 | 8500 |  | 58.509 |  | 07/28/2022 | 07/29/2022 |  | 2022-08-01T11:54:20.833 | Dehnke, Josh | RFG
22-0512-RET-ER | WO0009, Complete | Siding Labor | 2022-07-18T13:50:11.000 | WO | 0 | 2200 | 28.66 | 3000.6 | 2200 |  | 26.6813 |  | 08/16/2022 | 08/19/2022 |  | 2022-12-08T11:31:35.237 | Dehnke, Josh | SDG
22-0512-RET-ER | WO00013, Complete | Materials | 2022-07-19T10:48:00.000 | WO | 0 | 8827.23 | 8 | 11769.64 | 75 |  | 25 |  | 07/20/2022 | 07/20/2022 |  | 2022-07-22T09:09:03.580 | Dehnke, Josh | MAT
22-0512-RET-ER | WO00014, Complete | Siding Punch List | 2022-12-08T12:30:00.000 | WO | 0 | 2000.0013 | 21.03 | 2765.37 | 2000 |  | 27.6769 |  | 03/08/2023 | 03/10/2023 |  | 2023-04-11T09:02:05.087 | Dehnke, Josh | SDG
22-0512-RET-ER | WO00015, Complete | Gutter Down Spout | 2023-03-09T17:57:00.000 | WO | 0 | 400 | 43 | 469.19 | 400 |  | 14.7467 |  | 03/27/2023 | 03/31/2023 |  | 2023-05-15T11:41:46.390 | Dehnke, Josh | Gutter
22-0512-RET-ER | WO00016, Complete | Gutters and Garage Wrap | 2023-05-26T09:39:00.000 | WO | 0 | 926.9 | 30.22 | 926.9 | 100 |  | 0 |  | 05/26/2023 | 07/29/2022 |  | 2023-06-05T13:16:09.360 | Dehnke, Josh | SDG
22-0512-ER
23-0257-ER | WO0003 | FEE | 2023-01-17T08:05:23.553 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | FEE
23-0257-ER | WO0004, Complete | FRM | 2023-01-17T08:05:23.683 | WO | 0 | 0 |  | 0 | 0 |  | 0 |  |  |  |  | 2023-03-12T22:37:04.007 | Olson, Jonathon | FRM
23-0257-ER | WO0005, Complete | PNT | 2023-01-17T08:05:23.777 | WO | 0 | 0 | 3.22 | 0 | 0 |  | 0 |  | 01/17/2023 | 01/17/2023 |  | 2023-03-12T22:37:04.007 | Olson, Jonathon | PNT
23-0257-ER | WO00011, Complete | Roofing Materials | 2023-01-17T08:06:00.000 | WO | 0 | 5671.47 | 8 | 5671.47 | 100 |  | 0 |  | 01/17/2023 | 01/17/2023 |  | 2023-03-14T13:33:40.980 | Olson, Jonathon | Roofing Materials
23-0257-ER | WO00012, Complete | Siding Materials | 2023-01-17T08:06:00.000 | WO | 0 | 3664.1786 | 8 | 6739.81 | 3664.18 |  | 45.6338 |  | 01/17/2023 | 01/17/2023 |  | 2023-01-23T10:32:40.690 | Olson, Jonathon | Siding Materials
23-0257-ER | WO00013, Complete | Siding Labor | 2023-01-17T08:07:00.000 | WO | 0 | 3399.9989 | 53.3 | 5771.71 | 3400 |  | 41.092 |  | 01/17/2023 | 01/23/2023 |  | 2023-03-12T22:37:03.990 | Olson, Jonathon | Siding Labor
23-0257-ER | WO00014, Complete | Roofing Labor | 2023-01-17T08:07:00.000 | WO | 0 | 5600.003 | 24.85 | 15062.72 | 5600 |  | 62.8221 |  | 03/20/2023 | 03/22/2023 |  | 2023-03-27T09:19:20.487 | Olson, Jonathon | Roofing Labor
23-0257-ER | WO00015, Complete | Gutter and window wraps | 2023-01-17T08:12:00.000 | WO | 0 | 1152.0011 | 18.01 | 2737.45 | 1152 |  | 57.917 |  | 01/17/2023 | 01/18/2023 |  | 2023-04-04T10:45:42.863 | Olson, Jonathon | Gutter and window wraps
23-0257-ER | WO00016, Complete | sheathing material | 2023-02-13T22:09:00.000 | WO | 0 | 0 | 8 | 0 | 100 |  | 0 |  | 02/13/2023 | 02/13/2023 |  | 2023-03-12T22:37:03.990 | Olson, Jonathon | sheathing material
23-0257-ER | WO00017, Complete | dumpsters | 2023-03-20T13:29:00.000 | WO | 0 | 1000 | 8 | 1000 | 1000 |  | 0 |  | 03/20/2023 | 03/20/2023 |  | 2023-03-27T09:19:20.520 | Olson, Jonathon | dumpsters
23-0257-ER | WO00018, Complete | DMO | 2023-08-22T16:19:00.177 | WO | 0 | 567.59 | 4.98 | 567.59 | 100 |  | 0 |  | 08/22/2023 | 08/22/2023 |  | 2023-08-22T15:19:37.363 | Sleem, Michael | DMO
23-0257-ER | WO00019, Complete | SDG | 2023-08-22T16:19:00.303 | WO | 0 | 8431.17 | 27.48 | 8431.17 | 100 |  | 0 |  | 08/22/2023 | 08/23/2023 |  | 2023-08-22T15:19:37.393 | Sleem, Michael | SDG
23-0257-ER | WO00020, Complete | SFG | 2023-08-22T16:19:00.413 | WO | 0 | 13648.27 | 70.65 | 13648.27 | 100 |  | 0 |  | 08/22/2023 | 08/25/2023 |  | 2023-08-22T15:19:37.393 | Sleem, Michael | SFG
23-0257-ER | WO00021 | DMO | 2023-08-22T16:20:29.467 | WO | 0 | 567.59 | 4.97 | 567.59 | 100 |  | 0 |  | 08/22/2023 | 08/22/2023 |  |  |  | DMO
23-0257-ER | WO00022 | SDG | 2023-08-22T16:20:29.620 | WO | 0 | 8431.17 | 27.47 | 8431.17 | 100 |  | 0 |  | 08/22/2023 | 08/25/2023 |  |  |  | SDG
23-0257-ER | WO00023 | SFG | 2023-08-22T16:20:29.810 | WO | 0 | 13648.27 | 70.65 | 13648.27 | 100 |  | 0 |  | 08/22/2023 | 08/31/2023 |  |  |  | SFG
23-0248-ER
23-0952-ER
23-0244-IR
22-0565-ER
22-0104-ER | WO0001, Complete | DMO | 2022-10-24T09:48:47.000 | WO | 0 | 0 |  | 466.73 | 0 |  | 100 |  |  |  |  | 2023-05-01T10:44:55.777 | Trevino, Jeovani | DMO
22-0104-ER | WO0002, Complete | FEE | 2022-10-24T09:48:47.370 | WO | 0 | 0 |  | 0 | 0 |  | 0 |  |  |  |  | 2023-05-15T11:38:08.040 | Trevino, Jeovani | FEE
22-0104-ER | WO0003, Complete | PNT | 2022-10-24T09:48:47.000 | WO | 0 | 0 | 0.8 | 297.03 | 0 |  | 100 |  | 10/24/2022 | 10/24/2022 |  | 2023-05-08T10:25:49.037 | Trevino, Jeovani | PNT
22-0104-ER | WO0004, Complete | RFG | 2022-10-24T09:48:47.000 | WO | 0 |  |  |  | 4500 |  | 0 |  |  |  |  | 2022-11-28T01:31:57.447 | Trevino, Jeovani | RFG
22-0104-ER | WO0005, Complete | SFG | 2022-10-24T09:48:47.000 | WO | 0 | 0 | 6.67 | 955.42 | 0 |  | 100 |  | 10/24/2022 | 10/24/2022 |  | 2023-05-15T11:37:54.153 | Trevino, Jeovani | SFG
22-0104-ER | WO0006, Complete | USR | 2022-10-24T09:48:47.780 | WO | 0 | 0 |  | 0 | 0 |  | 0 |  |  |  |  | 2023-05-15T11:38:08.030 | Trevino, Jeovani | USR
22-0104-ER | WO0007, Complete | material | 2022-10-24T09:49:00.000 | WO | 0 | 4664.04 | 8 | 4664.04 | 100 |  | 0 |  | 10/24/2022 | 10/24/2022 |  | 2022-10-24T08:52:46.600 | Trevino, Jeovani | material
22-0104-ER | WO0008, Complete | Jordan roofing | 2023-04-25T14:56:00.000 | WO | 0 | 6542.394 | 75.1 | 10903.99 | 60 |  | 40 |  | 04/25/2023 | 11/02/2022 |  | 2023-05-01T10:44:55.790 | Trevino, Jeovani | jordan roofing
22-0499-ER | WO0002 | FEE | 2022-11-18T16:30:53.033 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | FEE
22-0499-ER | WO0004, Complete | Labor | 2022-11-18T16:31:00.000 | WO | 0 | 3236.9977 | 72.32 | 8988.09 | 3237 |  | 63.9857 |  | 11/18/2022 | 11/29/2022 |  | 2022-12-06T11:55:59.517 | Olson, Jonathon | Labor
22-0499-ER | WO0005, Complete | Materials | 2022-11-18T16:31:00.000 | WO | 0 | 3933.95 | 8 | 3933.95 | 100 |  | 0 |  | 11/18/2022 | 11/18/2022 |  | 2022-12-06T11:55:59.550 | Olson, Jonathon | Materials
22-0892-RET-ER Gutters | WO00011 | FEE | 2023-08-10T12:08:02.263 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | FEE
22-0892-RET-ER Gutters | WO00012 | Roof Replacement | 2023-08-10T12:08:02.000 | WO | 0 | 5569.735 | 71.33 | 11139.47 | 50 |  | 50 |  | 08/10/2023 | 08/22/2023 |  |  |  | RFG
22-0892-RET-ER Gutters | WO00015 | Roof Materials | 2023-08-10T12:08:00.000 | WO | 0 | 4570.129 | 8 | 4051.91 | 4570.13 |  | -12.7895 |  | 08/10/2023 | 08/10/2023
23-0211-IR
22-0561-ER
22-1011-C | WO0002, Complete | DOR | 2022-08-15T15:27:35.000 | WO | 0 | 0 | 1.02 | 341.18 | 0 |  | 100 |  | 08/15/2022 | 08/15/2022 |  | 2022-09-23T11:35:25.300 | Dehnke, Josh | DOR
22-1011-C | WO0003, Complete | FEE | 2022-08-15T15:27:35.417 | WO | 0 | 0 |  | 0 | 0 |  | 0 |  |  |  |  | 2022-09-02T12:57:52.780 | Trevino, Jeovani | FEE
22-1011-C | WO0007, Complete | labor | 2022-08-26T12:18:00.000 | WO | 0 | 3500 | 10.83 | 8765.46 | 3500 |  | 60.0705 |  | 09/01/2022 | 09/02/2022 |  | 2022-09-06T08:04:45.630 | Trevino, Jeovani | labor
22-1011-C | WO0008, Complete | Material | 2022-08-26T12:49:00.000 | WO | 0 | 4539.22 | 8 | 4435.75 | 4539.22 |  | -2.3326 |  | 08/26/2022 | 08/26/2022 |  | 2022-08-30T15:42:31.230 | Trevino, Jeovani | Material
22-1011-C | WO0009, Complete | window wraps labor | 2022-11-16T12:01:00.000 | WO | 0 | 1200 | 11.54 | 2632.52 | 1200 |  | 54.4163 |  | 09/01/2022 | 11/16/2022 |  | 2023-01-03T11:58:00.753 | Trevino, Jeovani | window wraps
22-1011-C | WO00016, Complete | gutter labor | 2023-02-20T11:36:00.000 | WO | 0 | 1552.0007 | 17.02 | 2042.09 | 1552 |  | 23.9994 |  | 02/20/2023 | 02/21/2023 |  | 2023-04-24T09:52:38.437 | Trevino, Jeovani | gutter labor
22-1011-C | WO00017 | wrap repair | 2023-06-21T12:55:00.000 | WO | 0 | 300 | 8 | 300 | 300 |  | 0 |  | 06/21/2023 | 06/21/2023 |  |  |  | wrap repair
22-0709-ER
23-0115-ER
22-0560-ER
22-0711-ER | WO0001 | AWN | 2022-09-14T11:00:41.500 | WO | 0 | 195.12 |  | 195.12 | 100 |  | 0 | [6 empty] | AWN
22-0711-ER | WO0003 | ELE | 2022-09-14T11:00:41.940 | WO | 0 | 822.51 | 6.22 | 822.51 | 100 |  | 0 |  | 09/14/2022 | 09/14/2022 |  |  |  | ELE
22-0711-ER | WO0009, Complete | ORI | 2022-09-14T11:00:43.000 | WO | 0 | 27.252 |  | 45.42 | 60 |  | 40 |  |  |  |  | 2023-02-06T11:08:24.257 | Trevino, Jeovani | ORI
22-0711-ER | WO00010, Complete | PLM | 2022-09-14T11:00:43.000 | WO | 0 | 200.0001 | 1.17 | 511.61 | 200 |  | 60.9077 |  | 09/14/2022 | 09/14/2022 |  | 2023-02-06T11:07:49.420 | Trevino, Jeovani | PLM
22-0711-ER | WO00015, Complete | siding materials | 2022-09-14T11:03:00.000 | WO | 0 | 410.24 | 16 | 410.24 | 100 |  | 0 |  | 09/14/2022 | 12/07/2022 |  | 2022-11-28T01:29:56.963 | Trevino, Jeovani | materials
22-0711-ER | WO00016, Complete | materials | 2022-09-14T11:18:00.000 | WO | 0 | 2949.82 | 8 | 2949.82 | 100 |  | 0 |  | 09/14/2022 | 09/14/2022 |  | 2022-10-14T08:45:13.780 | Trevino, Jeovani | materials
22-0711-ER | WO00017, Complete | roofing labor | 2022-11-03T16:20:00.000 | WO | 0 | 2999.9996 | 54.45 | 7575.68 | 3000 |  | 60.3996 |  | 09/14/2022 | 11/03/2022 |  | 2022-11-08T08:07:11.127 | Trevino, Jeovani | roofing labor
22-0711-ER | WO00018, Complete | siding labor | 2022-12-07T16:06:00.000 | WO | 0 | 6200 | 81.43 | 11491.7 | 6200 |  | 46.048 |  | 09/14/2022 | 09/26/2022 |  | 2023-01-02T09:13:34.770 | Trevino, Jeovani | siding
22-0711-ER | WO00019, Complete | material delivery | 2022-12-20T23:02:00.000 | WO | 0 | 500.0019 | 8 | 7871.69 | 500 |  | 93.6481 |  | 12/20/2022 | 12/20/2022 |  | 2023-01-02T09:13:34.757 | Trevino, Jeovani | material delivery
22-0711-ER | WO00020, Complete | Gutters | 2023-04-10T10:05:00.000 | WO | 0 | 650.0002 | 12.2 | 1024.09 | 650 |  | 36.529 |  | 04/10/2023 | 09/14/2022 |  | 2023-04-24T09:52:09.707 | Trevino, Jeovani | Gutter labor and material
22-0645-ER | WO0003, Complete | Gutter work | 2022-11-07T17:47:53.000 | WO | 0 | 3700.0024 | 19.58 | 5202.8 | 3700 |  | 28.8844 |  | 11/07/2022 | 11/09/2022 |  | 2023-05-09T09:52:47.740 | Olson, Jonathon | SFG
22-0645-ER | WO0004, Complete | Materials | 2023-02-16T12:33:00.000 | WO | 0 | 5879.08 | 8 | 5879.08 | 100 |  | 0 |  | 02/16/2023 | 02/16/2023 |  | 2023-04-15T21:59:52.273 | Olson, Jonathon | Materials
22-0645-ER | WO0005, Complete | Roofing Labor | 2023-02-16T12:34:00.000 | WO | 0 | 5999.9967 | 109.3 | 16133.1 | 6000 |  | 62.8094 |  | 02/16/2023 | 11/22/2022 |  | 2023-04-21T13:58:26.250 | Olson, Jonathon | Roofing Labor
22-0431-IR | WO0001 | DMO | 2023-04-10T10:23:46.960 | WO | 0 |  |  |  | 0 |  | 0 | [6 empty] | DMO
22-0431-IR | WO0002 | FEE | 2023-04-10T10:23:47.177 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | FEE
22-0431-IR | WO0003 | FPL | 2023-04-10T10:23:47.493 | WO | 0 |  |  |  | 0 |  | 0 | [6 empty] | FPL
22-0431-IR | WO0004, Complete | RFG | 2023-04-10T10:23:47.000 | WO | 0 | 4500.0032 | 11.4 | 14897.22 | 4500 |  | 69.793 |  | 05/04/2023 | 05/05/2023 |  | 2023-05-08T10:24:39.453 | Trevino, Jeovani | RFG
22-0431-IR | WO0005, Complete | SDG | 2023-04-10T10:23:48.000 | WO | 0 | 0 | 2.37 | 476.31 | 0 |  | 100 |  | 04/10/2023 | 04/10/2023 |  | 2023-05-15T11:38:55.280 | Trevino, Jeovani | SDG
22-0431-IR | WO0006, Complete | SFG | 2023-04-10T10:23:48.000 | WO | 0 | 0 | 1.25 | 180.66 | 0 |  | 100 |  | 04/10/2023 | 04/10/2023 |  | 2023-05-15T11:38:55.307 | Trevino, Jeovani | SFG
22-0431-IR | WO0007, Complete | material | 2023-04-10T10:24:00.000 | WO | 0 | 6919.6814 | 8 | 6316.35 | 6919.68 |  | -9.5519 |  | 04/10/2023 | 04/10/2023 |  | 2023-04-10T09:26:44.610 | Trevino, Jeovani | roofing material
22-0885-ER | WO0001, Complete | DMO | 2022-07-08T10:17:46.000 | WO | 0 | 0 |  | 75.71 | 0 |  | 100 |  |  |  |  | 2023-01-03T13:10:44.200 | Dehnke, Josh | DMO
22-0885-ER | WO0003 | labor | 2022-07-08T10:17:46.000 | WO | 0 | 1100.0004 | 13.55 | 1897.75 | 1100 |  | 42.0366 |  | 07/08/2022 | 07/08/2022 |  |  |  | HVC
22-0922-ER
23-0167-RET-ER | WO0002 | FEE | 2023-04-26T10:52:29.227 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | FEE
23-0167-RET-ER | WO0003 | FRM | 2023-04-26T10:52:29.277 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | FRM
23-0167-RET-ER | WO0004 | RFG | 2023-04-26T10:52:29.000 | WO | 0 | 3199.999 | 57.6 | 9221.66 | 3200 |  | 65.2991 |  | 04/26/2023 | 05/04/2023 |  |  |  | RFG
23-0167-RET-ER | WO0005 | SFG | 2023-04-26T10:52:29.000 | WO | 0 | 2170.0012 | 11.4 | 2802.75 | 2170 |  | 22.576 |  | 04/26/2023 | 04/27/2023 |  |  |  | SFG
23-0167-RET-ER | WO0006 | Material Work Order | 2023-04-26T10:09:44.280 | WO | 0 | 4037.05 |  | 4037.05 | 100 |  | 0 | [6 empty] | Material Work Order
22-0627-ER | WO0001 | Haul debris away | 2023-06-26T10:33:47.000 | WO | 0 | 150.0001 | 1.98 | 268.66 | 150 |  | 44.1673 |  | 06/26/2023 | 06/26/2023 |  |  |  | DMO
22-0627-ER | WO0002 | decking prep | 2023-06-26T10:33:47.000 | WO | 0 | 88.56 |  | 177.12 | 50 |  | 50 | [6 empty] | FCW
22-0627-ER | WO0003 | baluster- material only | 2023-06-26T10:33:47.000 | WO | 0 | 408.256 |  | 510.32 | 80 |  | 20 | [6 empty] | FNC
22-0627-ER | WO0004 | decking- material only | 2023-06-26T10:33:48.000 | WO | 0 | 391.096 |  | 488.87 | 80 |  | 20 | [6 empty] | FRM
22-0627-ER | WO0005 | paint/stain- material only | 2023-06-26T10:33:48.000 | WO | 0 | 260.448 |  | 325.56 | 80 |  | 20 | [6 empty] | PNT
22-0627-ER | WO0006 | carpentry labor | 2023-06-27T14:46:09.000 | WO | 0 | 1288.308 | 22 | 2629.2 | 49 |  | 51 |  | 06/26/2023 | 06/28/2023 |  |  |  | Labor Work Order
22-0627-ER | WO0007 | painting labor | 2023-06-27T14:49:01.000 | WO | 0 | 803.5902 | 51 | 1639.98 | 49 |  | 51 |  | 06/29/2023 | 07/06/2023 |  |  |  | Labor Work Order
23-0243-IR | WO0002 | Permit | 2022-09-30T10:09:46.000 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | FEE
23-0243-IR | WO0003, Complete | House and Garage Labor | 2022-09-30T10:09:46.000 | WO | 0 | 2500 | 620.46 | 10823.62 | 2500 |  | 76.9024 |  | 04/10/2023 | 05/26/2023 |  | 2023-05-30T12:32:08.903 | Trevino, Jeovani | RFG
23-0243-IR | WO0004, Complete | Siding Labor and Materials | 2022-09-30T10:09:47.000 | WO | 0 | 500 | 308.15 | 632.24 | 500 |  | 20.9161 |  | 04/10/2023 | 05/26/2023 |  | 2023-06-12T10:24:14.003 | Trevino, Jeovani | SDG
23-0243-IR | WO0006, Complete | Materials | 2023-01-03T15:03:00.000 | WO | 0 | 4016.57 | 322 | 4016.57 | 100 |  | 0 |  | 01/03/2023 | 05/26/2023 |  | 2023-05-30T12:32:17.897 | Trevino, Jeovani | MAT
23-0190-ER
22-1021-IR-secondloss
22-0491-ER
22-1015-IR | WO0002, Complete | FEE | 2022-09-21T10:43:57.963 | WO | 0 | -245 |  | -245 | 100 |  | 0 |  |  |  |  | 2022-09-28T14:43:03.847 | Olson, Jonathon | FEE
22-1015-IR | WO0003 | HVC | 2022-09-21T10:43:58.000 | WO | 0 | 100.82 | 0.75 | 100.82 | 100 |  | 0 |  | 09/21/2022 | 09/21/2022 |  |  |  | HVC
22-1015-IR | WO0006, Complete | Roofing and siding material | 2022-09-21T10:46:00.000 | WO | 0 | 2600.48 | 8 | 2600.48 | 100 |  | 0 |  | 09/21/2022 | 09/21/2022 |  | 2022-09-21T12:35:46.193 | Olson, Jonathon | Roofing and siding material
22-1015-IR | WO0007, Complete | Roofing and siding labor | 2022-09-21T10:47:00.000 | WO | 0 | 3427.672 | 26.43 | 8569.18 | 40 |  | 60 |  | 09/26/2022 | 09/28/2022 |  | 2022-09-28T09:11:22.157 | Olson, Jonathon | Roofing and siding labor
22-0048-ER | WO0002 | CLN | 2023-03-06T12:22:25.390 | WO | 0 | 511.24 | 6.47 | 511.24 | 100 |  | 0 |  | 03/06/2023 | 03/06/2023 |  |  |  | CLN
22-0048-ER | WO0003, Complete | Leo Work Order | 2023-03-06T12:22:25.000 | WO | 0 | 7366.08 | 40 | 7366.08 | 100 |  | 0 |  | 02/27/2023 | 03/03/2023 |  | 2023-03-06T11:27:39.277 | Burrell, Bianca | CON
22-0048-ER | WO0006 | Flooring | 2023-03-06T12:22:26.000 | WO | 0 | 4455.41 | 17.85 | 4455.41 | 100 |  | 0 |  | 03/06/2023 | 03/08/2023 |  |  |  | FCC
22-0048-ER | WO0007 | Flooring Material | 2023-03-06T11:26:25.000 | WO | 0 | 4900.99 |  | 4900.99 | 100 |  | 0 | [6 empty] | Material Work Order
22-0331-ER | WO0008 | WDW | 2022-06-07T13:52:09.000 | WO | 0 | 0 | 0 | 245.73 | 0 |  | 100 |  | 06/07/2022 | 06/07/2022 |  |  |  | WDW
22-0331-ER | WO0009 | Roofing Labor | 2022-06-07T15:09:00.000 | WO | 0 | 3604.424 | 69.87 | 9011.06 | 40 |  | 60 |  | 06/07/2022 | 06/14/2022 |  |  |  | Roofing labor
22-0331-ER | WO00010 | Roofing | 2022-06-09T12:56:00.000 | WO | 0 | 3227.8189 | 8 | 3768.25 | 3227.82 |  | 14.3417 |  | 06/09/2022 | 06/09/2022 |  |  |  | Roofing
22-0356-ER | WO0005, Complete | RFG | 2022-08-10T14:05:20.000 | WO | 0 | 0 |  | 62.86 | 0 |  | 100 |  |  |  |  | 2022-08-16T12:31:44.253 | Trevino, Jeovani | RFG
22-0356-ER | WO0008, Complete | materials | 2022-08-10T14:06:00.000 | WO | 0 | 6159.7498 | 8 | 4809.34 | 6159.75 |  | -28.0789 |  | 08/10/2022 | 08/10/2022 |  | 2022-08-16T12:31:44.237 | Trevino, Jeovani | materials
22-0356-ER | WO0009, Complete | labor | 2022-08-10T14:06:00.000 | WO | 0 | 3999.9999 | 66.26 | 9288.63 | 4000 |  | 56.9366 |  | 08/10/2022 | 08/17/2022 |  | 2022-08-16T12:31:49.287 | Trevino, Jeovani | labor
22-0336-ER | WO0003, Complete | FEE | 2022-07-25T10:21:06.640 | WO | 0 | 0 |  | 0 | 0 |  | 0 |  |  |  |  | 2022-08-08T08:42:51.183 | Trevino, Jeovani | FEE
22-0336-ER | WO0004, Complete | FRM | 2022-07-25T10:21:06.890 | WO | 0 | 0 |  | 0 | 0 |  | 0 |  |  |  |  | 2022-08-08T08:42:51.183 | Trevino, Jeovani | FRM
22-0336-ER | WO00010, Complete | Labor | 2022-07-25T10:21:00.000 | WO | 0 | 7000.0047 | 58.61 | 16297.88 | 7000 |  | 57.0496 |  | 08/01/2022 | 08/09/2022 |  | 2022-08-03T14:06:16.613 | Trevino, Jeovani | Roof Labor
22-0336-ER | WO00011, Complete | Material | 2022-07-25T10:26:00.000 | WO | 0 | 6435.1263 | 8 | 10012.94 | 6435.13 |  | 35.7319 |  | 07/25/2022 | 07/25/2022 |  | 2022-07-28T11:02:56.840 | Trevino, Jeovani | Material
22-0336-ER | WO00012, Complete | gutters | 2022-08-05T10:53:00.000 | WO | 0 | 1100.0012 | 25.05 | 3456.33 | 1100 |  | 68.1743 |  | 08/05/2022 | 08/09/2022 |  | 2022-08-08T08:42:51.153 | Trevino, Jeovani | gutters
22-0336-ER | WO00013 | Gutter screen labor | 2022-12-16T12:55:00.000 | WO | 0 | 1000 | 8 | 1000 | 100 |  | 0 |  | 12/16/2022 | 12/16/2022 |  |  |  | gutter screen labor
22-0516-ER | WO00013 | Fence Labor | 2022-08-30T13:50:47.000 | WO | 0 | 0 | 54.34 | 4856.22 | 0 |  | 100 |  | 08/30/2022 | 09/06/2022 |  |  |  | FEN
22-0516-ER | WO00015, Complete | Roofing Labor | 2022-08-30T13:50:48.000 | WO | 0 | 4699.999 | 24.24 | 6078.35 | 4700 |  | 22.6764 |  | 08/31/2022 | 09/06/2022 |  | 2022-09-12T15:17:14.693 | Dehnke, Josh | RFG
22-0516-ER | WO00016 | Shed Repair | 2022-08-30T13:50:48.000 | WO | 0 | 0 | 23.37 | 2456.09 | 0 |  | 100 |  | 08/30/2022 | 09/01/2022 |  |  |  | XST
22-0516-ER | WO00017, Complete | Materials | 2022-09-02T10:20:00.000 | WO | 0 | 5210.4 | 8 | 5210.4 | 100 |  | 0 |  | 09/02/2022 | 09/02/2022 |  | 2022-09-06T07:52:04.063 | Dehnke, Josh | Materials
22-0516-ER | WO00018, Complete | Fence Materials | 2022-09-02T10:23:00.000 | WO | 0 | 0 | 8 | 7825.42 | 0 |  | 100 |  | 09/02/2022 | 09/02/2022 |  | 2022-09-06T07:52:04.097 | Dehnke, Josh | MAT
22-0516-ER | WO00019, Complete | Shed Materials | 2022-09-09T15:41:00.000 | WO | 0 | 0 | 8 | 3587.91 | 0 |  | 100 |  | 09/09/2022 | 09/09/2022 |  | 2022-09-09T14:42:06.783 | Dehnke, Josh | MAT
22-0516-ER | WO00020, Complete | Sheathing Labor | 2022-09-26T10:43:00.000 | WO | 0 | 1749.9992 | 29.38 | 2573.99 | 1750 |  | 32.0122 |  | 08/30/2022 | 09/26/2022 |  | 2022-09-28T08:36:47.170 | Dehnke, Josh | RFG
23-0113-IR | WO0005, Complete | Roofing Labor | 2022-09-30T08:35:00.000 | WO | 0 | 4270 | 91.39 | 13474.12 | 4270 |  | 68.3096 |  | 09/30/2022 | 10/13/2022 |  | 2022-09-30T07:46:39.273 | Olson, Jonathon | Roofing Labor
23-0113-IR | WO0006, Complete | Roofing Material | 2022-09-30T08:36:00.000 | WO | 0 | 6337.19 | 8 | 6337.19 | 6337.19 |  | 0 |  | 09/30/2022 | 09/30/2022 |  | 2022-09-30T07:46:39.253 | Olson, Jonathon | Roofing Material
23-0113-IR | WO0007, Complete | Roofing Labor Extra | 2022-09-30T08:43:00.000 | WO | 0 | 849.9993 | 15.81 | 1593.69 | 850 |  | 46.6647 |  | 09/30/2022 | 10/12/2022 |  | 2022-10-12T10:54:55.287 | Olson, Jonathon | RFG
23-0019-ER
22-0711-RET-ER
23-0097-IR
22-0534-ER
22-1045-IR | WO0004, Complete | materials | 2022-09-12T11:42:21.000 | WO | 0 | 5092.1482 |  | 3866.91 | 5092.15 |  | -31.6852 |  |  |  |  | 2022-09-18T23:09:55.117 | Trevino, Jeovani | RFG
22-1045-IR | WO0006, Complete | labor | 2022-09-12T11:49:00.000 | WO | 0 | 6099.9992 | 71.4 | 10791.34 | 6100 |  | 43.4732 |  | 09/12/2022 | 09/20/2022 |  | 2022-10-31T07:55:15.643 | Trevino, Jeovani | roofing labor
22-1048-RET-ER
22-0953-RET-ER
22-1008-RET-ER
23-0137-ER
23-0142-ER
23-0127-ER
22-0509-ER
22-0935-ER | WO0002, Complete | FEE | 2022-08-18T13:40:07.203 | WO | 0 | 462.42 |  | 462.42 | 100 |  | 0 |  |  |  |  | 2022-08-29T09:23:19.313 | Dehnke, Josh | FEE
22-0935-ER | WO0003, Complete | Roofing Labor | 2022-08-18T13:40:07.000 | WO | 0 | 5050 | 56.96 | 8810.68 | 5050 |  | 42.6832 |  | 08/18/2022 | 09/02/2022 |  | 2022-08-29T09:23:19.297 | Dehnke, Josh | RFG
22-0935-ER | WO0007, Complete | Extra Roof Labor | 2022-10-03T09:12:00.000 | WO | 0 | 3000.0017 | 45.24 | 3922.14 | 3000 |  | 23.5111 |  | 08/18/2022 | 10/03/2022 |  | 2023-01-03T10:16:19.040 | Dehnke, Josh | Roofing
22-0935-ER | WO0008, Complete | Roofing Materials | 2022-10-03T15:05:00.000 | WO | 0 | 6859.2721 | 30.09 | 9648.29 | 71.0931 |  | 28.9069 |  | 08/26/2022 | 10/03/2022 |  | 2023-01-03T10:16:19.070 | Dehnke, Josh | RFG
22-0365-ER
23-0135-ER | WO0002, Complete | FEE | 2022-09-20T09:29:58.193 | WO | 0 | 0 |  | 0 | 0 |  | 0 |  |  |  |  | 2022-09-28T14:42:04.690 | Olson, Jonathon | FEE
23-0135-ER | WO0006, Complete | Roofing and Siding Material | 2022-09-20T09:30:00.000 | WO | 0 | 3761.85 | 16 | 3761.85 | 100 |  | 0 |  | 09/20/2022 | 09/20/2022 |  | 2022-09-23T14:11:41.507 | Dehnke, Josh | Roofing and Siding Material
23-0135-ER | WO0007, Complete | Roofing Labor | 2022-09-20T09:30:00.000 | WO | 0 | 3512.0038 | 67.7 | 9189.83 | 3512 |  | 61.7838 |  | 09/20/2022 | 09/28/2022 |  | 2022-09-28T14:42:04.677 | Olson, Jonathon | Roofing Labor
23-0135-ER | WO0008, Complete | Siding Labor | 2022-09-20T09:31:00.000 | WO | 0 | 1628.585 | 38.38 | 4285.75 | 38 |  | 62 |  | 09/20/2022 | 09/23/2022 |  | 2022-09-28T14:42:29.163 | Olson, Jonathon | Siding Labor
22-0060-ER
23-0022-ER
22-0447-ER
22-0423-RET-ER | WO0002, Complete | FEE | 2022-09-15T13:02:16.520 | WO | 0 | 0 |  | 0 | 0 |  | 0 |  |  |  |  | 2022-10-21T12:38:19.393 | Dehnke, Josh | FEE
22-0423-RET-ER | WO0009, Complete | Roofing and fence Labor | 2022-09-15T13:08:00.000 | WO | 0 | 4700 | 9.14 | 11611.6 | 4700 |  | 59.5232 |  | 09/20/2022 | 09/20/2022 |  | 2022-09-22T09:06:59.783 | Olson, Jonathon | Roofing and fence Labor
22-0423-RET-ER | WO00012, Complete | roofing and fence material | 2022-09-15T13:30:00.000 | WO | 0 | 5746.66 | 16 | 5746.66 | 100 |  | 0 |  | 09/15/2022 | 09/15/2022 |  | 2022-09-20T11:59:27.457 | Olson, Jonathon | roofing and fence material
22-0423-RET-ER | WO00013, Complete | Gutter Labor | 2022-09-30T09:37:00.000 | WO | 0 | 1732.82 | 9.12 | 1732.82 | 100 |  | 0 |  | 09/20/2022 | 09/30/2022 |  | 2022-10-21T12:38:19.377 | Dehnke, Josh | Gutter
22-0423-RET-ER | WO00014, Complete | Punch | 2022-12-13T11:25:00.000 | WO | 0 | 39.1844 | 9.46 | 711.65 | 39.1844 |  | 94.4939 |  | 09/20/2022 | 12/13/2022 |  | 2023-01-14T13:28:09.830 | Olson, Jonathon | Punch
22-0419-ER | WO0004, Complete | Post Labor (Footings and Extra Framing) | 2022-07-15T15:23:14.000 | WO | 0 | 464.784 | 6 | 774.64 | 60 |  | 40 |  | 07/25/2022 | 07/25/2022 |  | 2022-08-08T08:10:33.947 | Dehnke, Josh | FEN
22-0419-ER | WO0005, Complete | Framing Labor (Deck) | 2022-07-15T15:23:14.000 | WO | 0 | 1397.622 | 8.88 | 2329.37 | 60 |  | 40 |  | 07/25/2022 | 07/26/2022 |  | 2022-08-08T08:10:33.977 | Dehnke, Josh | FRM
22-0419-ER | WO0007, Complete | Roof Labor/ Soffit/Fascia | 2022-07-15T15:23:15.000 | WO | 0 | 738.732 | 4.65 | 1231.22 | 60 |  | 40 |  | 07/29/2022 | 07/29/2022 |  | 2022-09-28T08:39:23.110 | Dehnke, Josh | RFG
22-0419-ER | WO0008, Complete | Siding Labor | 2022-07-15T15:23:15.000 | WO | 0 | 1252.72 | 10.95 | 2505.44 | 50 |  | 50 |  | 07/27/2022 | 07/28/2022 |  | 2022-09-19T07:42:27.893 | Dehnke, Josh | SDG
22-0419-ER | WO00011, Complete | Materials | 2022-07-15T15:23:00.000 | WO | 0 | 8499.465 | 8 | 11332.62 | 75 |  | 25 |  | 07/22/2022 | 07/22/2022 |  | 2022-07-22T11:22:20.007 | Dehnke, Josh | MAT
22-0419-ER | WO00012, Complete | Labor WO | 2023-01-03T10:40:00.000 | WO | 0 | 1243 | 8 | 1243 | 100 |  | 0 |  | 01/03/2023 | 01/03/2023 |  | 2023-01-03T09:40:56.387 | Dehnke, Josh | LAB
22-0777-ER | WO0007, Complete | Roofing Labor | 2022-09-19T09:53:00.000 | WO | 0 | 3144.9 | 72.67 | 10483 | 30 |  | 70 |  | 09/19/2022 | 09/28/2022 |  | 2022-10-21T12:37:47.723 | Dehnke, Josh | Roofing Labor
22-0777-ER | WO0008, Complete | Siding Labor | 2022-09-19T09:54:00.000 | WO | 0 | 365 | 8.72 | 462.94 | 365 |  | 21.1561 |  | 09/19/2022 | 09/19/2022 |  | 2022-10-21T12:37:47.677 | Dehnke, Josh | Siding Labor
22-0777-ER | WO0009, Complete | Roofing and Siding Material | 2022-09-19T09:54:00.000 | WO | 0 | 4692.01 | 16 | 4692.01 | 100 |  | 0 |  | 09/19/2022 | 09/19/2022 |  | 2022-10-17T07:53:07.267 | Olson, Jonathon | Siding and Roofing Material
22-0777-ER | WO00010, Complete | gutter labor | 2022-10-21T14:00:00.000 | WO | 0 | 635.87 | 12.4 | 635.87 | 100 |  | 0 |  | 09/19/2022 | 10/21/2022 |  | 2022-11-27T19:00:24.660 | Olson, Jonathon | gutter labor
22-0587-ER | WO0006, Complete | Roofing Labor | 2022-10-03T22:14:00.000 | WO | 0 | 5200 | 102.9 | 13573.46 | 5200 |  | 61.6899 |  | 10/03/2022 | 10/14/2022 |  | 2022-10-10T07:59:38.260 | Olson, Jonathon | Roofing Labor
22-0587-ER | WO0007, Complete | Materials | 2022-10-03T22:15:00.000 | WO | 0 | 6181.81 | 8 | 6181.81 | 100 |  | 0 |  | 10/03/2022 | 10/03/2022 |  | 2022-10-05T07:56:56.777 | Olson, Jonathon | Materials
22-0587-ER | WO0008, Complete | Dumpster | 2022-10-21T09:07:00.000 | WO | 0 | 650.0004 | 14.2 | 991.17 | 650 |  | 34.4209 |  | 10/03/2022 | 10/21/2022 |  | 2022-11-06T21:23:21.153 | Olson, Jonathon | DMO
22-0587-ER | WO0009, Complete | gutter labor | 2022-10-27T11:19:00.000 | WO | 0 | 0 | 8 | 0 | 1600 |  | 0 |  | 10/27/2022 | 10/27/2022 |  | 2022-11-12T22:55:55.987 | Olson, Jonathon | Gutter Labor
22-0491-RET-ER | WO0001, Complete | DMO | 2022-10-05T10:19:26.000 | WO | 0 | 529.9997 |  | 558.52 | 530 |  | 5.1064 |  |  |  |  | 2023-01-02T00:06:33.083 | Trevino, Jeovani | DMO
22-0491-RET-ER | WO0002 | DOR | 2022-10-05T10:19:26.623 | WO | 0 | 2.2737e-13 | 5.32 | 2.2737e-13 | 100 |  | 0 |  | 10/05/2022 | 10/05/2022 |  |  |  | DOR
22-0491-RET-ER | WO0003 | FPL | 2022-10-05T10:19:26.750 | WO | 0 | 576.95 | 2.4 | 576.95 | 100 |  | 0 |  | 10/05/2022 | 10/05/2022 |  |  |  | FPL
22-0491-RET-ER | WO0004, Complete | Roofing material | 2022-10-05T10:19:26.000 | WO | 0 | 6639.4 |  | 6639.4 | 100 |  | 0 |  |  |  |  | 2022-10-09T21:51:55.540 | Trevino, Jeovani | RFG
22-0491-RET-ER | WO0006, Complete | materials | 2022-10-05T10:19:27.000 | WO | 0 | 1219.24 |  | 1219.24 | 100 |  | 0 |  |  |  |  | 2023-01-02T00:06:40.283 | Trevino, Jeovani | SFG
22-0491-RET-ER | WO0007, Complete | roofing labor | 2022-10-05T10:19:00.000 | WO | 0 | 7300 | 137.73 | 20633.84 | 7300 |  | 64.6212 |  | 10/05/2022 | 10/25/2022 |  | 2022-10-09T21:51:55.553 | Trevino, Jeovani | roofing labor
22-0491-RET-ER | WO0008, Complete | gutter labor | 2022-12-06T12:51:00.000 | WO | 0 | 2749.9988 | 58.68 | 6977.16 | 2750 |  | 60.5857 |  | 10/05/2022 | 12/06/2022 |  | 2023-01-02T00:06:20.150 | Trevino, Jeovani | window wrap and gutter labor
22-0491-RET-ER | WO0009, Complete | gutter machine | 2022-12-27T20:18:00.000 | WO | 0 | 249.9995 | 8 | 1024.03 | 250 |  | 75.5867 |  | 12/27/2022 | 12/27/2022 |  | 2023-01-02T00:06:20.167 | Trevino, Jeovani | gutter machine
22-0492-ER | WO0004, Complete | WDS | 2022-09-28T15:46:02.000 | WO | 0 | 0 | 3.15 | 313 | 0 |  | 100 |  | 09/28/2022 | 09/28/2022 |  | 2022-09-28T14:53:49.737 | Olson, Jonathon | WDS
22-0492-ER | WO0005, Complete | Roofing Labor | 2022-09-28T15:49:00.000 | WO | 0 | 0 | 21.42 | 1777.18 | 0 |  | 100 |  | 09/28/2022 | 09/29/2022 |  | 2022-09-28T14:53:49.753 | Olson, Jonathon | Roofing Labor
22-0492-ER | WO0006, Complete | Roofing Materials | 2022-09-28T15:50:00.000 | WO | 0 | 1919.03 | 8 | 1919.03 | 100 |  | 0 |  | 09/28/2022 | 09/28/2022 |  | 2022-09-28T14:53:58.787 | Olson, Jonathon | Roofing Materials
22-0008-IR | WO0001, Complete | DMO | 2022-10-17T00:22:23.717 | WO | 0 | 67.43 |  | 67.43 | 100 |  | 0 |  |  |  |  | 2022-12-09T11:12:32.387 | Trevino, Jeovani | DMO
22-0008-IR | WO0002, Complete | ELS | 2022-10-17T00:22:23.000 | WO | 0 | 0 | 2.77 | 145.56 | 0 |  | 100 |  | 10/16/2022 | 10/16/2022 |  | 2023-02-06T11:03:15.377 | Trevino, Jeovani | ELS
22-0008-IR | WO0003, Complete | FEE | 2022-10-17T00:22:23.903 | WO | 0 | 410.69 |  | 410.69 | 100 |  | 0 |  |  |  |  | 2022-12-09T11:12:32.400 | Trevino, Jeovani | FEE
22-0008-IR | WO0004, Complete | RFG | 2022-10-17T00:22:24.000 | WO | 0 | 5293.01 |  | 5293.01 | 100 |  | 0 |  |  |  |  | 2022-10-16T23:29:38.260 | Trevino, Jeovani | RFG
22-0008-IR | WO0005, Complete | SPE | 2022-10-17T00:22:24.000 | WO | 0 | 0 | 0.82 | 222.29 | 0 |  | 100 |  | 10/16/2022 | 10/16/2022 |  | 2023-02-06T11:03:15.407 | Trevino, Jeovani | SPE
22-0008-IR | WO0006, Complete | labor | 2022-10-17T00:25:00.000 | WO | 0 | 4900.0022 | 93.66 | 12946.05 | 4900 |  | 62.1506 |  | 10/16/2022 | 10/27/2022 |  | 2022-12-09T11:12:32.370 | Trevino, Jeovani | Labor
22-0803-RET-ER | WO0001, Complete | Cleaning | 2022-05-20T10:54:23.000 | WO | 0 | 1287.49 | 41.13 | 2574.98 | 50 |  | 50 |  | 06/06/2022 | 06/13/2022 |  | 2022-06-27T07:48:12.850 | Feltmann, Brandon | CLN
22-0803-RET-ER | WO0002, Complete | Demo | 2022-05-20T10:54:23.000 | WO | 0 | 880.39 | 3.72 | 880.39 | 100 |  | 0 |  | 05/20/2022 | 05/20/2022 |  | 2022-06-14T18:39:35.033 | Sleem, Michael | DMO
22-0803-RET-ER | WO0003, Complete | Drywall | 2022-05-20T10:54:24.000 | WO | 0 | 1548.82 | 12 | 1548.82 | 100 |  | 0 |  | 05/20/2022 | 05/23/2022 |  | 2022-06-27T07:49:03.900 | Feltmann, Brandon | DRY
22-0803-RET-ER | WO0004, Complete | ELE | 2022-05-20T10:54:24.000 | WO | 0 | 4.99 | 0 | 4.99 | 100 |  | 0 |  | 06/06/2022 | 06/06/2022 |  | 2022-06-27T07:48:23.780 | Feltmann, Brandon | ELE
22-0803-RET-ER | WO0005, Complete | Flooring | 2022-05-20T10:54:24.000 | WO | 0 | 10148.89 | 33.6 | 10148.89 | 100 |  | 0 |  | 08/22/2022 | 08/26/2022 |  | 2022-10-17T09:35:30.007 | Dehnke, Josh | FCV
22-0803-RET-ER | WO0008, Complete | Trim | 2022-05-20T10:54:24.000 | WO | 0 | 2272.81 | 15.58 | 2272.81 | 100 |  | 0 |  | 08/10/2022 | 08/12/2022 |  | 2022-10-17T09:35:30.413 | Dehnke, Josh | FNC
22-0803-RET-ER | WO0009, Complete | Hvac | 2022-05-20T10:54:25.000 | WO | 0 | 42135 |  | 42135 | 100 |  | 0 |  |  |  |  | 2022-06-14T10:05:43.253 | Sleem, Michael | HVC
22-0803-RET-ER | WO00010, Complete | Lights | 2022-05-20T10:54:25.000 | WO | 0 | 320.07 | 11.47 | 320.07 | 100 |  | 0 |  | 08/15/2022 | 08/16/2022 |  | 2022-10-17T09:35:30.040 | Dehnke, Josh | LIT
22-0803-RET-ER | WO00011, Complete | drywall | 2022-05-20T10:54:25.000 | WO | 0 | 10234.32 | 88.48 | 10234.32 | 100 |  | 0 |  | 05/20/2022 | 06/02/2022 |  | 2022-06-27T07:49:31.760 | Feltmann, Brandon | PLA
22-0803-RET-ER | WO00012, Complete | Plumbing | 2022-05-20T10:54:25.000 | WO | 0 | 514.07 | 20.1 | 514.07 | 100 |  | 0 |  | 08/08/2022 | 08/10/2022 |  | 2022-08-29T14:35:28.943 | Dehnke, Josh | PLM
22-0803-RET-ER | WO00013, Complete | Painting | 2022-05-20T10:54:25.000 | WO | 0 | 4262.25 | 21.62 | 4262.25 | 100 |  | 0 |  | 08/08/2022 | 08/10/2022 |  | 2022-08-23T13:49:09.507 | Dehnke, Josh | PNT
22-0756-ER
22-0746-ER | WO0001, Complete | Cleaning with Pressure Sprayer | 2022-09-24T16:30:09.000 | WO | 0 | 152.36 | 1.9 | 152.36 | 100 |  | 0 |  | 09/24/2022 | 09/24/2022 |  | 2023-01-03T14:14:39.653 | Dehnke, Josh | CLN
22-0746-ER | WO0002, Complete | Painting Labor and Materials | 2022-09-24T16:30:09.000 | WO | 0 | 411.24 | 1.05 | 411.24 | 100 |  | 0 |  | 09/24/2022 | 09/24/2022 |  | 2023-01-03T14:14:39.623 | Dehnke, Josh | PNT
22-0746-ER | WO0003, Complete | Garage Labor | 2022-09-24T16:30:09.000 | WO | 0 | 700.0004 | 15.28 | 1459.73 | 700 |  | 52.0459 |  | 03/21/2023 | 03/22/2023 |  | 2023-04-03T11:27:36.670 | Trevino, Jeovani | RFG
22-0746-ER | WO0004, Complete | Siding Labor | 2022-09-24T16:30:09.000 | WO | 0 | 224.708 | 1.13 | 561.77 | 40 |  | 60 |  | 09/24/2022 | 09/24/2022 |  | 2022-11-29T14:16:50.503 | Hicks, Dave | SDG
22-0746-ER | WO0005, Complete | Garage Materials | 2022-09-24T16:34:00.000 | WO | 0 | 502.03 | 8 | 149.89 | 502.03 |  | -234.9323 |  | 09/24/2022 | 09/24/2022 |  | 2023-03-06T09:55:29.843 | Trevino, Jeovani
22-0746-ER | WO0006, Complete | Siding Materials | 2022-09-24T16:35:00.000 | WO | 0 | 53.59 | 8 | 53.59 | 100 |  | 0 |  | 09/24/2022 | 09/24/2022 |  | 2022-11-29T14:16:50.520 | Hicks, Dave
22-0508-ER
22-0308-ER | WO0002, Complete | DRY | 2022-10-17T00:36:31.000 | WO | 0 | 350 | 5.43 | 560.81 | 350 |  | 37.5903 |  | 10/16/2022 | 10/16/2022 |  | 2022-12-09T09:42:36.853 | Trevino, Jeovani | DRY
22-0308-ER | WO0009, Complete | WDS | 2022-10-17T00:36:31.560 | WO | 0 | 545.58 |  | 545.58 | 100 |  | 0 |  |  |  |  | 2022-12-02T15:01:14.103 | Trevino, Jeovani | WDS
22-0308-ER | WO00011, Complete | materials | 2022-10-17T00:37:00.000 | WO | 0 | 5389.85 | 8 | 5389.85 | 100 |  | 0 |  | 10/16/2022 | 10/16/2022 |  | 2022-10-16T23:40:09.920 | Trevino, Jeovani | materials
22-0308-ER | WO00012, Complete | Labor | 2022-10-19T13:14:00.000 | WO | 0 | 5600 | 85.89 | 12335.39 | 5600 |  | 54.6022 |  | 10/16/2022 | 10/25/2022 |  | 2022-10-31T09:13:11.267 | Trevino, Jeovani | Labor
22-0308-ER | WO00013, Complete | Gutter labor | 2022-12-15T10:56:00.000 | WO | 0 | 1250.0003 | 28.91 | 3125.79 | 1250 |  | 60.0101 |  | 10/16/2022 | 12/15/2022 |  | 2023-01-02T00:18:28.613 | Trevino, Jeovani | gutter labor
22-0308-ER | WO00014, Complete | Gutter materials | 2022-12-15T10:57:00.000 | WO | 0 | 799.9997 | 8 | 1476.45 | 800 |  | 45.816 |  | 12/15/2022 | 12/15/2022 |  | 2023-01-02T00:18:38.027 | Trevino, Jeovani | Gutter materials
22-0308-ER | WO00015, Complete | rental | 2022-12-28T21:25:00.000 | WO | 0 | 249.9998 | 8 | 439.53 | 250 |  | 43.1211 |  | 12/28/2022 | 12/28/2022 |  | 2023-01-02T00:18:28.630 | Trevino, Jeovani | gutter machine rental
22-0990-ER | WO0002 | DOR | 2022-08-15T13:47:46.000 | WO | 0 | 2809.9995 | 5.32 | 2311.6 | 2810 |  | -21.5608 |  | 08/15/2022 | 08/15/2022 |  |  |  | DOR
22-0990-ER | WO0004 | PNT | 2022-08-15T13:47:47.577 | WO | 0 | 331.95 | 2.67 | 331.95 | 100 |  | 0 |  | 08/15/2022 | 08/15/2022 |  |  |  | PNT
22-0990-ER | WO0007, Complete | materials | 2022-08-15T13:49:00.000 | WO | 0 | 3555.351 | 8 | 2928.22 | 3555.35 |  | -21.4168 |  | 08/15/2022 | 08/15/2022 |  | 2022-08-24T09:03:36.633 | Trevino, Jeovani | materials
22-0990-ER | WO0008, Complete | labor | 2022-08-15T13:50:00.000 | WO | 0 | 4300.0021 | 65.84 | 8142.17 | 4300 |  | 47.1885 |  | 08/15/2022 | 08/22/2022 |  | 2022-08-24T09:03:31.953 | Trevino, Jeovani | labor
22-0960-RET-ER
22-0954-RET-ER
22-0364-RET-ER
22-1050-IR
22-0364-ER
22-1016-ER
22-0809-RET-ER
22-0617-RET-ER
22-0943-ER
22-0470-ER
22-0500-ER | WO0006 | Roofing Labor | 2022-07-14T11:17:58.000 | WO | 0 | 6615.4934 | 15.66 | 16403.69 | 6615.5 |  | 59.6707 |  | 08/11/2022 | 08/12/2022 |  |  |  | RFG
22-0500-ER | WO0008 | Siding Labor | 2022-07-14T11:17:58.000 | WO | 0 | 6949.2465 | 37.32 | 19854.99 | 35 |  | 65 |  | 08/22/2022 | 08/26/2022 |  |  |  | SDG
22-0500-ER | WO00010, Complete | Window Screen Replacement | 2022-07-14T11:17:59.000 | WO | 0 | 295.47 | 1.17 | 590.94 | 50 |  | 50 |  | 08/12/2022 | 08/12/2022 |  | 2022-08-08T11:24:13.300 | Dehnke, Josh | WDW
22-0500-ER | WO00011, Complete | Roofing Materials | 2022-08-08T10:51:00.000 | WO | 0 | 6065.89 | 8 | 6065.89 | 100 |  | 0 |  | 08/08/2022 | 08/08/2022 |  | 2022-08-08T11:24:13.333 | Dehnke, Josh | RFG
22-0500-ER | WO00012 | Siding Materials | 2022-08-08T10:52:00.000 | WO | 0 | 9650.33 | 8 | 9650.33 | 100 |  | 0 |  | 08/08/2022 | 08/08/2022 |  |  |  | SDG
22-0460-ER
22-0460-IR
22-0556-ER
22-1043-ER | WO0001, Complete | DMO | 2022-10-10T15:14:46.353 | WO | 0 | 536.68 | 3.55 | 536.68 | 100 |  | 0 |  | 10/10/2022 | 10/10/2022 |  | 2022-10-17T09:19:32.300 | Dehnke, Josh | DMO
22-1043-ER | WO0004, Complete | Labor | 2022-10-10T15:14:46.000 | WO | 0 | 4017.568 | 59.2 | 9478.28 | 4017.57 |  | 57.6129 |  | 10/10/2022 | 10/18/2022 |  | 2022-10-17T09:19:32.097 | Dehnke, Josh | RFG
22-1043-ER | WO0005, Complete | Materials | 2022-10-10T15:17:00.000 | WO | 0 | 3603.21 | 8 | 3603.21 | 100 |  | 0 |  | 10/10/2022 | 10/10/2022 |  | 2022-10-17T09:19:31.910 | Dehnke, Josh
22-0426-RET-ER
22-0520-ER
22-0327-ER
22-0847-RET-ER | WO0001, Complete | SFG | 2022-08-14T22:33:55.000 | WO | 0 | 2790.001 | 15.87 | 5088.29 | 2790 |  | 45.1682 |  | 08/14/2022 | 08/15/2022 |  | 2022-08-14T21:35:35.807 | Trevino, Jeovani | SFG
22-0810-RET-ER
22-0879-ER
22-0471-RET-ER
22-0599-RET-ER
22-0739-RET-ER
22-0594-RET-ER
22-0557-RET-ER
22-0669-RET-ER
22-0706-RET-ER | WO0001 | DMO | 2022-09-23T12:46:43.043 | WO | 0 | 234.92 | 1.98 | 234.92 | 100 |  | 0 |  | 09/23/2022 | 09/23/2022 |  |  |  | DMO
22-0706-RET-ER | WO0002 | FEE | 2022-09-23T12:46:43.230 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | FEE
22-0706-RET-ER | WO0003 | FRM | 2022-09-23T12:46:43.323 | WO | 0 | 1415.15 | 7.82 | 1415.15 | 100 |  | 0 |  | 09/23/2022 | 09/23/2022 |  |  |  | FRM
22-0706-RET-ER | WO0004 | RFG | 2022-09-23T12:46:43.437 | WO | 0 | 3539.87 | 13.47 | 3539.87 | 100 |  | 0 |  | 09/23/2022 | 09/26/2022 |  |  |  | RFG
22-0534-RET-ER
22-0613-ER | WO0001 | DMO | 2022-10-31T11:36:11.670 | WO | 0 | 80.92 |  | 80.92 | 100 |  | 0 | [6 empty] | DMO
22-0613-ER | WO0002 | FRM | 2022-10-31T11:36:11.783 | WO | 0 | 273.54 |  | 273.54 | 100 |  | 0 | [6 empty] | FRM
22-0613-ER | WO0003 | RFG | 2022-10-31T11:36:11.880 | WO | 0 | 726.66 |  | 726.66 | 100 |  | 0 | [6 empty] | RFG
22-0613-ER | WO0004 | labor | 2022-10-31T11:37:00.000 | WO | 0 | 1400.0005 | 22.92 | 2772.13 | 1400 |  | 49.4973 |  | 10/31/2022 | 11/01/2022 |  |  |  | roofing labor
22-0365-RET-ER
22-1042-IR | WO0001 | DMO | 2022-10-24T13:55:52.947 | WO | 0 |  |  |  | 0 |  | 0 | [6 empty] | DMO
22-1042-IR | WO0002 | DOR | 2022-10-24T13:55:53.260 | WO | 0 | 372.4 |  | 372.4 | 100 |  | 0 | [6 empty] | DOR
22-1042-IR | WO0003 | WDW | 2022-10-24T13:55:53.000 | WO | 0 | 196.9999 |  | 513.01 | 197 |  | 61.5992 | [6 empty] | WDW
22-1042-IR | WO0004 | Labor | 2022-10-24T13:56:00.000 | WO | 0 | 292.528 | 12.82 | 731.32 | 40 |  | 60 |  | 10/24/2022 | 10/24/2022 |  |  |  | Labor
23-0001-IR
22-0969-ER
22-0969-IR
22-0572-IR
22-0100-C
22-0114-C | WO0001, Complete | Deck Hangers Labor | 2022-07-13T12:36:00.000 | WO | 0 | 300 | 8 | 600 | 50 |  | 50 |  | 07/13/2022 | 07/13/2022 |  | 2022-07-15T14:00:43.863 | Dehnke, Josh | FRM
22-0114-C | WO0002, Complete | Deck Materials | 2022-07-13T12:38:00.000 | WO | 0 | 50 | 8 | 100 | 50 |  | 50 |  | 07/14/2022 | 07/14/2022 |  | 2022-07-13T11:40:27.567 | Dehnke, Josh | FRM
22-0221-C | WO0001, Complete | Deck Materials | 2022-06-23T14:18:00.000 | WO | 0 | 700 | 18 | 1000 | 700 |  | 30 |  | 06/22/2022 | 06/23/2022 |  | 2022-06-23T14:36:23.440 | Dehnke, Josh | FRM
22-0221-C | WO0002, Complete | Deck Labor | 2022-06-23T14:19:00.000 | WO | 0 | 2499.999 | 52 | 3000 | 2500 |  | 16.6667 |  | 06/27/2022 | 07/02/2022 |  | 2022-07-15T14:01:02.573 | Dehnke, Josh | FRM
22-0117-D
22-0118-D | WO0001 | Door Materials | 2022-07-01T12:08:00.000 | WO | 0 | 2883 | 8 | 2883 | 100 |  | 0 |  | 07/01/2022 | 07/01/2022 |  |  |  | Door
22-0118-D | WO0002 | French Door Material | 2022-07-01T12:09:00.000 | WO | 0 | 4902 | 8 | 4902 | 100 |  | 0 |  | 07/01/2022 | 07/01/2022 |  |  |  | Door
22-0849-IR
22-0880-IR | WO0001, Complete | Washer/Dryer Labor | 2022-11-15T05:59:54.000 | WO | 0 | 173.62 | 2.27 | 434.05 | 40 |  | 60 |  | 11/15/2022 | 11/15/2022 |  | 2022-12-20T07:21:41.603 | Hicks, Dave | APP
22-0880-IR | WO0002, Complete | CON | 2022-11-15T05:59:54.000 | WO | 0 | 188.472 | 17.8 | 471.18 | 40 |  | 60 |  | 11/14/2022 | 11/16/2022 |  | 2022-11-15T05:02:11.007 | Burrell, Bianca | CON
22-0880-IR | WO0003, Complete | Carpet labor | 2022-11-15T05:59:55.000 | WO | 0 | 1047.2801 | 10.74 | 1592.71 | 1047.28 |  | 34.2454 |  | 11/15/2022 | 11/17/2022 |  | 2022-12-20T07:18:50.477 | Hicks, Dave | FCC
22-0880-IR | WO0004, Complete | Vinyl Tile Labor | 2022-11-15T05:59:55.000 | WO | 0 | 1063.0496 | 10.34 | 1555.69 | 1063.05 |  | 31.667 |  | 11/15/2022 | 11/16/2022 |  | 2022-12-20T07:18:50.477 | Hicks, Dave | FCV
22-0880-IR | WO0005, Complete | Baseboard Reset Labor | 2022-11-15T05:59:55.000 | WO | 0 | 89.424 | 1.72 | 223.56 | 40 |  | 60 |  | 11/15/2022 | 11/15/2022 |  | 2022-12-28T06:34:10.173 | Hicks, Dave | FNC
22-0880-IR | WO0006, Complete | Abatement | 2022-11-29T12:22:00.000 | WO | 0 | 5494.9978 | 8 | 6594 | 5495 |  | 16.6667 |  | 11/29/2022 | 11/29/2022 |  | 2022-12-06T10:48:14.127 | Dehnke, Josh | DMO
22-0880-IR | WO0007, Complete | Vinyl Materials | 2022-11-29T12:24:00.000 | WO | 0 | 639.6506 |  | 1631.2 | 639.65 |  | 60.7865 |  |  |  |  | 2022-12-19T11:24:00.180 | Hicks, Dave | FCV
22-0880-IR | WO0008, Complete | Carpet Materials | 2022-11-29T12:24:00.000 | WO | 0 | 1764.1007 | 16 | 1930.12 | 1764.1 |  | 8.6015 |  | 11/29/2022 | 11/29/2022 |  | 2022-12-19T11:24:00.197 | Hicks, Dave | FCC
22-0524-IR | WO0001, Complete | CDC | 2022-11-15T09:59:35.000 | WO | 0 | 12 |  | 40.76 | 12 |  | 70.5594 |  |  |  |  | 2022-12-05T15:46:28.717 | Burrell, Bianca | CDC
22-0524-IR | WO0002, Complete | Carpet Clean | 2022-11-15T09:59:35.000 | WO | 0 | 154.8399 | 7.12 | 523.12 | 154.84 |  | 70.4007 |  | 12/19/2022 | 12/19/2022 |  | 2023-01-03T11:03:06.777 | Dehnke, Josh | CLN
22-0524-IR | WO0003 | CON | 2022-11-15T09:59:36.000 | WO | 0 | 190.856 | 7.4 | 477.14 | 40 |  | 60 |  | 12/19/2022 | 12/19/2022 |  |  |  | CON
22-0524-IR | WO0004, Complete | CPS | 2022-11-15T09:59:36.000 | WO | 0 | 50.0001 |  | 146.51 | 50 |  | 65.8726 |  |  |  |  | 2022-12-05T15:46:28.733 | Burrell, Bianca | CPS
22-0524-IR | WO0005, Complete | DMO | 2022-11-15T09:59:36.000 | WO | 0 | 94.4 | 28.98 | 236 | 40 |  | 60 |  | 12/01/2022 | 12/06/2022 |  | 2022-12-05T15:48:20.303 | Burrell, Bianca | DMO
22-0524-IR | WO0006, Complete | Drywall & Paint | 2022-11-15T09:59:36.000 | WO | 0 | 2197.44 | 17.97 | 5493.6 | 40 |  | 60 |  | 12/01/2022 | 12/05/2022 |  | 2022-12-05T15:46:41.670 | Burrell, Bianca | DRY
22-0524-IR | WO0007 | FNC | 2022-11-15T09:59:36.270 | WO | 0 | 524.49 | 4.48 | 524.49 | 100 |  | 0 |  | 11/15/2022 | 11/15/2022 |  |  |  | FNC
22-0524-IR | WO0008, Complete | Insulation/ Barrier | 2022-11-15T09:59:36.000 | WO | 0 | 152.982 | 19.15 | 254.97 | 60 |  | 40 |  | 12/01/2022 | 12/05/2022 |  | 2022-12-05T15:46:41.700 | Burrell, Bianca | INS
22-0524-IR | WO0009 | Stain for base | 2022-11-15T09:59:36.000 | WO | 0 | 353.43 | 2.98 | 353.43 | 100 |  | 0 |  | 11/15/2022 | 11/16/2022 |  |  |  | PNT
22-0524-IR | WO00010 | Window Treatments | 2022-11-15T09:59:36.000 | WO | 0 | 107.42 | 1.18 | 107.42 | 100 |  | 0 |  | 11/15/2022 | 11/15/2022 |  |  |  | WDT
22-0524-IR | WO00011 | Final Clean | 2022-12-05T16:40:00.000 | WO | 0 | 100 | 10.52 | 198.24 | 100 |  | 49.5561 |  | 11/15/2022 | 12/05/2022
22-0378-ER | WO0001, Complete | APP | 2022-11-03T10:20:19.000 | WO | 0 | 275.0001 | 39.15 | 577.73 | 275 |  | 52.3999 |  | 11/14/2022 | 11/18/2022 |  | 2022-11-15T04:56:04.637 | Burrell, Bianca | APP
22-0378-ER | WO0003, Complete | CLN | 2022-11-03T10:20:19.000 | WO | 0 | 104.136 | 1.88 | 173.56 | 60 |  | 40 |  | 12/02/2022 | 12/02/2022 |  | 2022-12-05T14:49:38.773 | Burrell, Bianca | CLN
22-0378-ER | WO0004, Complete | Content Manipulation | 2022-11-03T10:20:19.000 | WO | 0 | 554.5555 | 5.5 | 913.45 | 60.71 |  | 39.29 |  | 11/10/2022 | 11/10/2022 |  | 2022-11-07T09:20:22.783 | Burrell, Bianca | CON
22-0378-ER | WO0006, Complete | ELE | 2022-11-03T10:20:19.000 | WO | 0 | 18.18 | 0.18 | 30.3 | 60 |  | 40 |  | 12/02/2022 | 12/02/2022 |  | 2022-12-01T13:08:10.037 | Burrell, Bianca | ELE
22-0378-ER | WO0007, Complete | FCV | 2022-11-03T10:20:20.000 | WO | 0 | 170.616 | 1.6 | 284.36 | 60 |  | 40 |  | 12/02/2022 | 12/02/2022 |  | 2022-12-01T13:08:10.007 | Burrell, Bianca | FCV
22-0378-ER | WO0008, Complete | Hardwood Refinishing | 2022-11-03T10:20:20.000 | WO | 0 | 7598.208 | 41.06 | 12663.68 | 60 |  | 40 |  | 11/14/2022 | 11/18/2022 |  | 2022-11-14T09:10:54.633 | Burrell, Bianca | FCW
22-0378-ER | WO0009, Complete | Base & Shoe Product | 2022-11-03T10:20:20.000 | WO | 0 | 513.6 | 19.95 | 1284 | 40 |  | 60 |  | 11/30/2022 | 12/02/2022 |  | 2022-12-05T14:49:38.820 | Burrell, Bianca | FNC
22-0378-ER | WO00010, Complete | FNH | 2022-11-03T10:20:20.000 | WO | 0 | 9.18 | 0.17 | 15.3 | 60 |  | 40 |  | 12/02/2022 | 12/02/2022 |  | 2022-12-01T13:08:10.100 | Burrell, Bianca | FNH
22-0378-ER | WO00011, Complete | HVC | 2022-11-03T10:20:20.000 | WO | 0 | 122.136 | 1.27 | 203.56 | 60 |  | 40 |  | 11/03/2022 | 11/03/2022 |  | 2022-12-01T13:08:10.070 | Burrell, Bianca | HVC
22-0378-ER | WO00012, Complete | Sink & Toilet | 2022-11-03T10:20:20.000 | WO | 0 | 367.736 | 39.43 | 919.34 | 40 |  | 60 |  | 11/14/2022 | 11/18/2022 |  | 2022-11-15T04:57:09.617 | Burrell, Bianca | PLM
22-0378-ER | WO00013, Complete | Base Clear Coat | 2022-11-03T10:20:20.000 | WO | 0 | 91.472 | 1.7 | 228.68 | 40 |  | 60 |  | 11/30/2022 | 11/30/2022 |  | 2022-12-01T13:07:56.297 | Burrell, Bianca | PNT
22-0378-ER | WO00014, Complete | Hardwood Replacement | 2022-11-03T10:29:00.000 | WO | 0 | 81.714 | 44 | 136.19 | 60 |  | 40 |  | 11/14/2022 | 11/18/2022 |  | 2022-11-14T09:11:25.137 | Burrell, Bianca
22-0378-ER | WO00016, Complete | Paint - BDRM Ceiling | 2022-11-03T12:36:00.000 | WO | 0 | 155.31 | 8 | 258.85 | 60 |  | 40 |  | 12/02/2022 | 12/02/2022 |  | 2022-12-05T14:49:38.837 | Burrell, Bianca
22-0454-ER | WO0001, Complete | Roof Labor | 2022-09-29T09:30:35.000 | WO | 0 | 8652.6542 | 8.64 | 23680.34 | 8652.65 |  | 63.4606 |  | 10/07/2022 | 10/08/2022 |  | 2022-10-05T07:29:45.307 | Hicks, Dave | RFG
22-0454-ER | WO0002, Complete | Roof Materials | 2022-09-29T09:31:00.000 | WO | 0 | 9503.3 | 8 | 9503.3 | 100 |  | 0 |  | 10/03/2022 | 10/03/2022 |  | 2022-09-29T11:22:50.740 | Hicks, Dave
22-0977-IR | WO0001, Complete | Cleaning | 2022-08-05T09:37:37.000 | WO | 0 | 0 | 5.7 | 425.95 | 0 |  | 100 |  | 08/05/2022 | 08/05/2022 |  | 2022-09-02T13:00:14.257 | Deville , Jard | CLN
22-0977-IR | WO0002, Complete | Concrete | 2022-08-05T09:37:37.000 | WO | 0 | 0 | 6 | 701.93 | 0 |  | 100 |  | 08/05/2022 | 08/05/2022 |  | 2022-08-30T08:23:49.657 | Deville , Jard | CNC
22-0977-IR | WO0003, Complete | Contents | 2022-08-05T09:37:37.000 | WO | 0 | 0 | 1.47 | 363.19 | 0 |  | 100 |  | 08/05/2022 | 08/05/2022 |  | 2022-08-29T13:03:09.880 | Deville , Jard | CON
22-0977-IR | WO0004, Complete | DOR | 2022-08-05T09:37:37.000 | WO | 0 | 1600.0008 | 6.78 | 3463.58 | 1600 |  | 53.805 |  | 08/05/2022 | 08/05/2022 |  | 2022-09-02T12:58:25.873 | Deville , Jard | DOR
22-0977-IR | WO0005, Complete | Electrical | 2022-08-05T09:37:37.000 | WO | 0 | 0 | 1.67 | 302.64 | 0 |  | 100 |  | 08/05/2022 | 08/05/2022 |  | 2022-09-02T13:00:14.227 | Deville , Jard | ELE
22-0977-IR | WO0006, Complete | FNC | 2022-08-05T09:37:37.957 | WO | 0 | 286.24 | 1.43 | 286.24 | 100 |  | 0 |  | 08/05/2022 | 08/05/2022 |  | 2022-09-02T13:00:14.210 | Deville , Jard | FNC
22-0977-IR | WO0007, Complete | Framing | 2022-08-05T09:37:38.000 | WO | 0 | 4720.6882 | 37.77 | 3949.59 | 4720.69 |  | -19.5235 |  | 08/05/2022 | 08/11/2022 |  | 2022-08-29T12:27:33.880 | Deville , Jard | FRM
22-0977-IR | WO0008, Complete | Light | 2022-08-05T09:37:38.000 | WO | 0 | 0 | 0.53 | 84.72 | 0 |  | 100 |  | 08/05/2022 | 08/05/2022 |  | 2022-09-02T13:00:14.070 | Deville , Jard | LIT
22-0977-IR | WO0009, Complete | Paint | 2022-08-05T09:37:38.000 | WO | 0 | 2711.04 | 8.87 | 1355.52 | 200 |  | -100 |  | 08/05/2022 | 08/08/2022 |  | 2022-09-02T13:00:14.087 | Deville , Jard | PNT
22-0977-IR | WO00010, Complete | SDG | 2022-08-05T09:37:38.000 | WO | 0 | 849.9995 | 6.32 | 1702.72 | 850 |  | 50.0799 |  | 08/05/2022 | 08/05/2022 |  | 2022-09-02T13:00:14.100 | Deville , Jard | SDG
22-0977-IR | WO00011, Complete | SFG | 2022-08-05T09:37:38.863 | WO | 0 | 262.39 | 0.83 | 262.39 | 100 |  | 0 |  | 08/05/2022 | 08/05/2022 |  | 2022-09-02T13:00:14.150 | Deville , Jard | SFG
22-0977-IR | WO00012, Complete | FRM MAT | 2022-08-10T21:05:00.000 | WO | 0 | 269.9995 | 8 | 1383.01 | 270 |  | 80.4774 |  | 08/10/2022 | 08/10/2022 |  | 2022-09-02T13:00:14.180 | Deville , Jard | FRM MAT
22-0977-IR | WO00013, Complete | Supplement | 2022-12-30T15:33:00.000 | WO | 0 | 2668 | 8 | 2668 | 100 |  | 0 |  | 12/30/2022 | 12/30/2022 |  | 2022-12-30T14:33:31.687 | Dehnke, Josh | SUP
22-0569-EOC | WO0001, Complete | APP | 2022-11-22T16:36:36.000 | WO | 0 | 267.088 | 12.42 | 667.72 | 40 |  | 60 |  | 12/15/2022 | 12/16/2022 |  | 2022-12-19T12:27:52.157 | Burrell, Bianca | APP
22-0569-EOC | WO0002, Complete | CAB | 2022-11-22T16:36:36.000 | WO | 0 | 510.252 | 11.15 | 1275.63 | 40 |  | 60 |  | 01/05/2023 | 01/06/2023 |  | 2023-01-09T21:48:33.800 | Burrell, Bianca | CAB
22-0569-EOC | WO0003, Complete | CON | 2022-11-22T16:36:36.000 | WO | 0 | 79.44 | 12 | 198.6 | 40 |  | 60 |  | 12/15/2022 | 12/16/2022 |  | 2022-12-19T12:27:52.283 | Burrell, Bianca | CON
22-0569-EOC | WO0004, Complete | DOR | 2022-11-22T16:36:37.000 | WO | 0 | 19.104 | 9.42 | 47.76 | 40 |  | 60 |  | 12/15/2022 | 12/16/2022 |  | 2022-12-19T12:27:52.253 | Burrell, Bianca | DOR
22-0569-EOC | WO0005, Complete | DRY/PNT/INS | 2022-11-22T16:36:37.000 | WO | 0 | 361.828 | 4.18 | 904.57 | 40 |  | 60 |  | 01/13/2023 | 01/13/2023 |  | 2023-01-16T20:48:47.670 | Burrell, Bianca | DRY
22-0569-EOC | WO0006, Complete | Carpet Repair | 2022-11-22T16:36:37.000 | WO | 0 | 210.736 | 13.03 | 526.84 | 40 |  | 60 |  | 12/15/2022 | 12/16/2022 |  | 2022-12-19T12:27:52.237 | Burrell, Bianca | FCC
22-0569-EOC | WO0007, Complete | Hard Surface Floor Prep | 2022-11-22T16:36:37.000 | WO | 0 | 131.856 | 14.7 | 219.76 | 60 |  | 40 |  | 12/12/2022 | 12/13/2022 |  | 2022-12-19T12:27:52.220 | Burrell, Bianca | FCV
22-0569-EOC | WO0008, Complete | FNC | 2022-11-22T16:36:37.000 | WO | 0 | 155.022 | 10.83 | 258.37 | 60 |  | 40 |  | 12/15/2022 | 12/16/2022 |  | 2022-12-19T12:27:52.203 | Burrell, Bianca | FNC
22-0569-EOC | WO0009, Complete | Subfloor | 2022-11-22T16:36:38.000 | WO | 0 | 437.135 | 21.95 | 874.27 | 50 |  | 50 |  | 12/08/2022 | 12/12/2022 |  | 2022-12-12T17:15:15.070 | Burrell, Bianca | FRM
22-0569-EOC | WO00011, Complete | PLM | 2022-11-22T16:36:38.000 | WO | 0 | 180.652 | 1.78 | 451.63 | 40 |  | 60 |  | 01/13/2023 | 01/13/2023 |  | 2023-01-09T21:48:33.780 | Burrell, Bianca | PLM
22-0569-EOC | WO00012, Complete | DRT REPAIR/TAPE/PAINT DR | 2022-11-22T16:36:39.000 | WO | 0 | 358.284 | 13.2 | 597.14 | 60 |  | 40 |  | 12/15/2022 | 12/16/2022 |  | 2022-12-19T12:27:52.190 | Burrell, Bianca | PNT
22-0569-EOC | WO00013, Complete | Hard Surface Labor | 2022-11-22T16:41:00.000 | WO | 0 | 276.78 | 17 | 553.56 | 50 |  | 50 |  | 12/15/2022 | 12/16/2022 |  | 2022-12-19T12:27:52.173 | Burrell, Bianca
22-0569-EOC | WO00014, Complete | Hard Surface Material | 2022-11-22T16:42:00.000 | WO | 0 | 410.6298 | 8 | 588.16 | 410.63 |  | 30.184 |  | 12/01/2022 | 12/01/2022 |  | 2022-12-01T20:03:38.203 | Burrell, Bianca
22-0815-EOC
22-0959-EOC
22-1010-EOC
22-1013-EOC
22-0544-EOC
22-0545-C
22-0513-C
22-1003-C-1-302
22-1003-C-1-304
22-1003-C-1-306
22-1003-C-1-310
22-1003-C-2-107
22-1003-C-2-113
22-1003-C-3-115
22-1003-C-3-208
22-1003-C-3-210
22-1003-C-3-211
22-1003-C-3-218
22-1003-C-218
22-1003-C-3-314
22-1003-C-4-317
22-1003-C-5-103
22-1003-C-5-210
22-1003-C-5-301
22-1003-C-5-318
22-1003-C-6-318
22-1003-C-7-106
22-1003-C-7-205
22-1003-C-7-206
22-1003-C-7-210
22-1003-C-7-216
22-1003-C-8-108
22-1003-C-8-122
22-1003-C-8-218
22-0729-EOC
22-0738-C
22-0758-C
22-0946-EOC
22-0997-EOC
22-0996-EOC
22-0975-ER
22-0918-EOC
22-0798-IR
22-0933-C
22-0985-ER
22-0630-ER
22-0584-ER | WO0001, Complete | Dumpster | 2022-10-14T10:37:32.000 | WO | 0 | 340.1 | 1.98 | 340.1 | 100 |  | 0 |  | 10/14/2022 | 10/14/2022 |  | 2022-10-19T07:12:49.773 | Hicks, Dave | DMO
22-0584-ER | WO0002, Complete | Materials | 2022-10-14T10:37:32.000 | WO | 0 | 5015.989 |  | 9119.98 | 55 |  | 45 |  |  |  |  | 2022-10-19T07:12:49.743 | Hicks, Dave | FNC
22-0584-ER | WO0008, Complete | Install Window Labor | 2022-10-14T10:37:35.000 | WO | 0 | 2699.9972 | 64.87 | 7036.41 | 2700 |  | 61.6282 |  | 10/14/2022 | 10/19/2022 |  | 2022-10-19T07:12:49.793 | Hicks, Dave | WDW
22-0940-IR
22-1028-ER
22-1022-EOC
22-1014-EOC
22-0785-EOC
22-0779-EOC
22-0700-EOC
22-0727-EOC
22-0796-EOC
22-0873-EOC
23-0050-IR
22-1034-IR
22-0814-EOC
22-0882-EOC
22-1046-EST
22-1019-C
22-1033-IR | WO0001, Complete | Materials | 2023-03-13T14:03:00.000 | WO | 0 | 160 | 9 | 200 | 80 |  | 20 |  | 03/13/2023 | 03/13/2023 |  | 2023-03-16T07:57:29.283 | Dehnke, Josh | MAT
22-1033-IR | WO0002 | Cabinet Labor | 2023-03-13T14:03:00.000 | WO | 0 | 309.925 | 8 | 885.5 | 35 |  | 65 |  | 03/21/2023 | 03/21/2023 |  |  |  | CAB
22-0721-C | WO0001 | CLN | 2023-03-24T11:20:53.007 | WO | 0 | 51.45 | 0.83 | 51.45 | 100 |  | 0 |  | 03/24/2023 | 03/24/2023 |  |  |  | CLN
22-0721-C | WO0002 | CON | 2023-03-24T11:20:53.190 | WO | 0 | 109.98 | 2 | 109.98 | 100 |  | 0 |  | 03/24/2023 | 03/24/2023 |  |  |  | CON
22-0721-C | WO0003 | CPS | 2023-03-24T11:20:53.357 | WO | 0 | 12.19 |  | 12.19 | 100 |  | 0 | [6 empty] | CPS
22-0721-C | WO0004 | DMO | 2023-03-24T11:20:53.487 | WO | 0 | 201.46 | 1.98 | 201.46 | 100 |  | 0 |  | 03/24/2023 | 03/24/2023 |  |  |  | DMO
22-0721-C | WO0005 | DRY | 2023-03-24T11:20:53.610 | WO | 0 | 543.53 | 0.25 | 543.53 | 100 |  | 0 |  | 03/24/2023 | 03/24/2023 |  |  |  | DRY
22-0721-C | WO0006 | FNC | 2023-03-24T11:20:53.817 | WO | 0 | 251.7 | 2.05 | 251.7 | 100 |  | 0 |  | 03/24/2023 | 03/24/2023 |  |  |  | FNC
22-0721-C | WO0007 | PNT | 2023-03-24T11:20:53.970 | WO | 0 | 1006.59 | 8.82 | 1006.59 | 100 |  | 0 |  | 03/24/2023 | 03/27/2023 |  |  |  | PNT
23-0103-EST | WO0003, Complete | ELE | 2022-09-09T15:33:31.210 | WO | 0 | 434.53 | 3.27 | 434.53 | 100 |  | 0 |  | 09/09/2022 | 09/09/2022 |  | 2022-12-30T08:59:21.037 | Dehnke, Josh | ELE
23-0103-EST | WO0004, Complete | FEE | 2022-09-09T15:33:31.443 | WO | 0 | 500 |  | 500 | 100 |  | 0 |  |  |  |  | 2022-12-30T08:59:21.053 | Dehnke, Josh | FEE
23-0103-EST | WO0006, Complete | LAB | 2022-09-09T15:33:31.803 | WO | 0 | 239.7 | 3 | 239.7 | 100 |  | 0 |  | 09/09/2022 | 09/09/2022 |  | 2022-12-30T08:59:21.067 | Dehnke, Josh | LAB
23-0103-EST | WO0008, Complete | PLM | 2022-09-09T15:33:32.120 | WO | 0 | 200.03 |  | 200.03 | 100 |  | 0 |  |  |  |  | 2022-12-30T08:59:21.067 | Dehnke, Josh | PLM
23-0103-EST | WO00010, Complete | labor | 2022-09-15T10:11:00.000 | WO | 0 | 4500 | 42.33 | 4221.61 | 4500 |  | -6.5944 |  | 09/09/2022 | 09/15/2022 |  | 2022-10-09T21:46:12.093 | Trevino, Jeovani | labor
23-0103-EST | WO00011, Complete | material | 2022-10-02T06:30:00.000 | WO | 0 | 88.497 | 8 | 863.31 | 88.497 |  | 89.7491 |  | 10/02/2022 | 10/02/2022 |  | 2022-10-02T10:29:32.237 | Trevino, Jeovani | material
23-0108-ER
22-0754-ER
22-0903-IR
22-0568-IR
22-0464-IR | WO0002, Complete | roofing labor | 2022-09-14T14:23:00.000 | WO | 0 | 1217.49 | 26.15 | 2434.98 | 50 |  | 50 |  | 09/14/2022 | 09/16/2022 |  | 2022-10-21T12:38:55.507 | Dehnke, Josh | roofing labor
22-0464-IR | WO0003, Complete | roofing material | 2022-09-14T14:24:00.000 | WO | 0 | 234.65 | 8 | 234.65 | 100 |  | 0 |  | 09/14/2022 | 09/14/2022 |  | 2022-10-10T11:23:00.207 | Olson, Jonathon | roofing material
22-0181-C | WO0001, Complete | CAB | 2022-08-01T15:42:27.000 | WO | 0 | 549.9998 | 61.8 | 653.36 | 550 |  | 15.8198 |  | 08/21/2022 | 08/28/2022 |  | 2022-08-12T09:14:11.687 | Deville , Jard | CAB
22-0181-C | WO0002, Complete | CLN | 2022-08-01T15:42:27.000 | WO | 0 | 0 | 45.15 | 11.33 | 0 |  | 100 |  | 08/22/2022 | 08/29/2022 |  | 2022-09-07T10:13:49.233 | Deville , Jard | CLN
22-0181-C | WO0003, Complete | CON | 2022-08-01T15:42:27.000 | WO | 0 | 0 | 62.1 | 68.64 | 0 |  | 100 |  | 08/21/2022 | 08/28/2022 |  | 2022-09-07T10:13:49.217 | Deville , Jard | CON
22-0181-C | WO0004, Complete | DOR | 2022-08-01T15:42:27.000 | WO | 0 | 211.309 | 62.65 | 301.87 | 70 |  | 30 |  | 08/21/2022 | 08/28/2022 |  | 2022-09-07T10:13:49.190 | Deville , Jard | DOR
22-0181-C | WO0005, Complete | DRY | 2022-08-01T15:42:28.000 | WO | 0 | 350.1 | 66 | 700.2 | 50 |  | 50 |  | 08/21/2022 | 08/28/2022 |  | 2022-09-02T13:49:46.303 | Deville , Jard | DRY
22-0181-C | WO0006, Complete | FCV | 2022-08-01T15:42:28.000 | WO | 0 | 202.86 | 62.35 | 405.72 | 50 |  | 50 |  | 08/21/2022 | 08/28/2022 |  | 2022-09-02T13:49:51.033 | Deville , Jard | FCV
22-0181-C | WO0009, Complete | HVC | 2022-08-01T15:42:28.000 | WO | 0 | 0 | 61.15 | 24.12 | 0 |  | 100 |  | 08/21/2022 | 08/28/2022 |  | 2022-09-07T10:13:49.170 | Deville , Jard | HVC
22-0181-C | WO00010, Complete | MPR | 2022-08-01T15:42:29.000 | WO | 0 | 0 | 61.17 | 23.06 | 0 |  | 100 |  | 08/21/2022 | 08/28/2022 |  | 2022-09-07T10:13:49.300 | Deville , Jard | MPR
22-0181-C | WO00011, Complete | PLM | 2022-08-01T15:42:29.000 | WO | 0 | 2200.0012 | 64.37 | 2859.51 | 2200 |  | 23.0637 |  | 08/21/2022 | 08/28/2022 |  | 2022-09-07T10:13:49.253 | Deville , Jard | PLM
22-0181-C | WO00012, Complete | PNL | 2022-08-01T15:42:29.000 | WO | 0 | 0 | 62.62 | 264.88 | 0 |  | 100 | Deville , Jard | 08/28/2022 | 09/04/2022 |  | 2022-09-02T13:50:49.210 | Deville , Jard | PNL
22-0181-C | WO00013, Complete | PNT | 2022-08-01T15:42:29.000 | WO | 0 | 331.45 | 65.2 | 662.9 | 50 |  | 50 |  | 08/21/2022 | 08/28/2022 |  | 2022-09-02T13:50:36.817 | Deville , Jard | PNT
22-0181-C | WO00014, Complete | PLM MAT | 2022-08-10T21:22:00.000 | WO | 0 | 510.2899 | 8 | 1213.11 | 510.29 |  | 57.9354 |  | 08/10/2022 | 08/10/2022 |  | 2022-08-10T20:42:27.127 | Deville , Jard | PLM MAT
22-0181-C | WO00015, Complete | FCV MAT | 2022-08-10T21:42:00.000 | WO | 0 | 95.04 | 8 | 209.85 | 95.04 |  | 54.7105 |  | 08/10/2022 | 08/10/2022 |  | 2022-08-10T20:44:35.653 | Deville , Jard | FCV MAT
22-0181-C | WO00016, Complete | Plumbing | 2022-08-12T10:22:00.000 | WO | 0 | 0 | 8 | 0 | 100 |  | 0 |  | 08/12/2022 | 08/12/2022 |  | 2022-09-23T12:25:00.513 | Dehnke, Josh | Plumbing
22-0548-IR | WO0001, Complete | Gate Labor and Materials | 2022-08-08T09:07:00.000 | WO | 0 | 6210 | 8 | 10350 | 60 |  | 40 |  | 08/08/2022 | 08/08/2022 |  | 2022-08-08T08:08:32.223 | Dehnke, Josh | FNC
22-0548-IR | WO0002, Complete | Door labor and materials | 2022-08-08T09:08:00.000 | WO | 0 | 1638 | 8 | 2730 | 60 |  | 40 |  | 08/08/2022 | 08/08/2022 |  | 2022-08-17T19:10:40.060 | Dehnke, Josh | DOR
22-0748-C
22-0774-IR | WO0003, Complete | FRM | 2022-08-15T09:38:37.117 | WO | 0 | 192 |  | 192 | 100 |  | 0 |  |  |  |  | 2022-09-23T11:57:02.953 | Dehnke, Josh | FRM
22-0774-IR | WO0006, Complete | labor | 2022-08-19T09:53:00.000 | WO | 0 | 2891.43 | 23.37 | 2891.43 | 100 |  | 0 |  | 08/15/2022 | 08/19/2022 |  | 2022-09-23T11:57:03.050 | Dehnke, Josh | labor
22-0774-IR | WO0007, Complete | material | 2022-08-19T09:55:00.000 | WO | 0 | 2285.79 | 8 | 2285.79 | 100 |  | 0 |  | 08/19/2022 | 08/19/2022 |  | 2022-09-23T11:57:03.063 | Dehnke, Josh | material
22-0787-EOC | WO0001, Complete | APP | 2022-09-20T11:47:06.120 | WO | 0 | 932.4 | 4.58 | 932.4 | 100 |  | 0 |  | 09/20/2022 | 09/20/2022 |  | 2022-10-17T08:20:17.633 | Trevino, Jeovani | APP
22-0787-EOC | WO0002, Complete | CAB | 2022-09-20T11:47:06.353 | WO | 0 | 181.49 | 1.65 | 181.49 | 100 |  | 0 |  | 09/20/2022 | 09/20/2022 |  | 2022-10-21T11:18:31.697 | Dehnke, Josh | CAB
22-0787-EOC | WO0003, Complete | CLN | 2022-09-20T11:47:06.513 | WO | 0 | 52.54 | 0.78 | 52.54 | 100 |  | 0 |  | 09/20/2022 | 09/20/2022 |  | 2022-10-21T11:18:31.727 | Dehnke, Josh | CLN
22-0787-EOC | WO0004, Complete | DMO | 2022-09-20T11:47:06.670 | WO | 0 | 234.92 | 1.98 | 234.92 | 100 |  | 0 |  | 09/20/2022 | 09/20/2022 |  | 2022-10-17T08:20:17.823 | Trevino, Jeovani | DMO
22-0787-EOC | WO0005, Complete | DRY | 2022-09-20T11:47:06.797 | WO | 0 | 658.78 | 2.15 | 658.78 | 100 |  | 0 |  | 09/20/2022 | 09/20/2022 |  | 2022-10-17T08:20:17.753 | Trevino, Jeovani | DRY
22-0787-EOC | WO0006, Complete | FCV | 2022-09-20T11:47:06.937 | WO | 0 | 1224.42 | 6.11 | 1224.42 | 100 |  | 0 |  | 09/20/2022 | 09/20/2022 |  | 2022-10-17T08:20:40.203 | Trevino, Jeovani | FCV
22-0787-EOC | WO0007, Complete | FNC | 2022-09-20T11:47:07.107 | WO | 0 | 278.24 | 2.17 | 278.24 | 100 |  | 0 |  | 09/20/2022 | 09/20/2022 |  | 2022-10-17T08:31:09.750 | Trevino, Jeovani | FNC
22-0787-EOC | WO0008, Complete | FNH | 2022-09-20T11:47:07.373 | WO | 0 | 224.82 | 0.17 | 224.82 | 100 |  | 0 |  | 09/20/2022 | 09/20/2022 |  | 2022-10-17T08:31:09.720 | Trevino, Jeovani | FNH
22-0787-EOC | WO0009, Complete | FRM | 2022-09-20T11:47:07.703 | WO | 0 | 157.68 | 0.57 | 157.68 | 100 |  | 0 |  | 09/20/2022 | 09/20/2022 |  | 2022-10-17T08:31:09.703 | Trevino, Jeovani | FRM
22-0787-EOC | WO00010, Complete | HVC | 2022-09-20T11:47:08.063 | WO | 0 | 8.34 | 0.05 | 8.34 | 100 |  | 0 |  | 09/20/2022 | 09/20/2022 |  | 2022-10-17T08:31:09.767 | Trevino, Jeovani | HVC
22-0787-EOC | WO00011, Complete | MSD | 2022-09-20T11:47:08.287 | WO | 0 | 57.74 | 0.63 | 57.74 | 100 |  | 0 |  | 09/20/2022 | 09/20/2022 |  | 2022-11-21T10:31:03.750 | Trevino, Jeovani | MSD
22-0787-EOC | WO00012, Complete | PLM | 2022-09-20T11:47:08.413 | WO | 0 | 518.22 | 1.97 | 518.22 | 100 |  | 0 |  | 09/20/2022 | 09/20/2022 |  | 2022-11-21T10:31:03.727 | Trevino, Jeovani | PLM
22-0787-EOC | WO00013, Complete | PNT | 2022-09-20T11:47:08.663 | WO | 0 | 603.4 | 4.18 | 603.4 | 100 |  | 0 |  | 09/20/2022 | 09/20/2022 |  | 2022-10-17T08:20:18.083 | Trevino, Jeovani | PNT
22-0787-EOC | WO00014, Complete | floor labor | 2022-10-26T12:52:00.000 | WO | 0 | 649.9999 | 9.84 | 202.96 | 650 |  | -220.2601 |  | 09/20/2022 | 10/26/2022 |  | 2022-11-21T10:31:03.687 | Trevino, Jeovani | hallway and bathroom floor labor
22-0772-IR
22-0018-ER
22-0610-C
22-0533-IR | WO0005, Complete | Labor | 2022-07-18T13:38:58.000 | WO | 0 | 1600.0005 | 70 | 1940.34 | 1600 |  | 17.5402 |  | 07/18/2022 | 07/27/2022 |  | 2022-08-02T11:05:35.587 | Trevino, Jeovani | PNT
22-0533-IR | WO0007, Complete | material | 2022-07-18T13:43:00.000 | WO | 0 | 226.16 | 71 | 226.16 | 100 |  | 0 |  | 07/18/2022 | 07/27/2022 |  | 2022-08-02T11:05:04.700 | Trevino, Jeovani | material
22-0583-IR
22-0831-IR
22-0830-IR
22-0754-C
22-0817-EOC
22-0783-C
22-0737-ER
22-0773-IR | WO0001, Complete | Dumpster | 2022-08-18T09:08:13.000 | WO | 0 | 0 | 1.98 | 298.66 | 0 |  | 100 |  | 08/18/2022 | 08/18/2022 |  | 2022-08-18T11:07:10.930 | Deville , Jard | DMO
22-0773-IR | WO0002, Complete | Drywall | 2022-08-18T09:08:13.000 | WO | 0 | 0 |  | 83.05 | 0 |  | 100 |  |  |  |  | 2022-08-18T11:07:10.947 | Deville , Jard | DRY
22-0773-IR | WO0003, Complete | Carpentry | 2022-08-18T09:08:13.000 | WO | 0 | 4600.138 | 1 | 5940 | 4600.14 |  | 22.5566 |  | 08/18/2022 | 08/18/2022 |  | 2022-08-18T11:07:10.963 | Deville , Jard | FNC
22-0773-IR | WO0004, Complete | Framing Material | 2022-08-18T09:08:13.000 | WO | 0 | 777.9399 |  | 350.66 | 777.94 |  | -121.8502 |  |  |  |  | 2022-08-18T11:07:10.977 | Deville , Jard | FRM
22-0773-IR | WO0005, Complete | trailer supplies | 2022-08-18T09:08:13.000 | WO | 0 | 79.0001 |  | 150 | 79 |  | 47.3333 |  |  |  |  | 2022-08-18T11:07:10.993 | Deville , Jard | MTL
22-0773-IR | WO0006, Complete | Roofing | 2022-08-18T09:08:13.000 | WO | 0 | 147.06 |  | 147.06 | 100 |  | 0 |  |  |  |  | 2022-08-18T11:07:10.993 | Deville , Jard | RFG
22-0773-IR | WO0007, Complete | Permit | 2022-08-18T12:22:00.000 | WO | 0 | 207.5 |  | 207.5 | 100 |  | 0 |  |  |  |  | 2022-08-19T09:10:46.417 | Deville , Jard | Permit
22-0904-IR
22-0835-IR
22-0621-IR
22-0962-IR | WO0001 | DRY | 2022-09-13T09:32:24.000 | WO | 0 | 3000 | 45.14 | 7144.73 | 3000 |  | 58.011 |  | 09/13/2022 | 09/15/2022 |  |  |  | DRY
22-0962-IR | WO0002 | FCC | 2022-09-13T09:32:24.743 | WO | 0 | 3600.94 | 9.38 | 3600.94 | 100 |  | 0 |  | 09/13/2022 | 09/14/2022 |  |  |  | FCC
22-0962-IR | WO0003 | FNC | 2022-09-13T09:32:25.263 | WO | 0 |  |  |  | 0 |  | 0 | [6 empty] | FNC
22-0962-IR | WO0004 | INS | 2022-09-13T09:32:25.403 | WO | 0 |  |  |  | 0 |  | 0 | [6 empty] | INS
22-0962-IR | WO0005 | PNL | 2022-09-13T09:32:25.530 | WO | 0 | 4169.64 | 27.14 | 4169.64 | 100 |  | 0 |  | 09/13/2022 | 09/16/2022 |  |  |  | PNL
22-0962-IR | WO0006 | PNT | 2022-09-13T09:32:25.623 | WO | 0 |  |  |  | 0 |  | 0 | [6 empty] | PNT
22-0995-IR
22-0983-ER | WO0004, Complete | DRY | 2022-12-30T09:16:17.000 | WO | 0 | 0 |  | 428.13 | 0 |  | 100 |  |  |  |  | 2023-01-27T12:24:09.320 | Trevino, Jeovani | DRY
22-0983-ER | WO0005, Complete | ELE | 2022-12-30T09:16:17.000 | WO | 0 | 0 | 0 | 349.07 | 0 |  | 100 |  | 12/30/2022 | 12/30/2022 |  | 2023-01-27T12:24:09.310 | Trevino, Jeovani | ELE
22-0983-ER | WO0009, Complete | PLM | 2022-12-30T09:16:18.000 | WO | 0 | 100.0004 | 3.97 | 1064.31 | 100 |  | 90.6042 |  | 12/30/2022 | 12/30/2022 |  | 2023-01-27T12:25:12.060 | Trevino, Jeovani | PLM
22-0983-ER | WO00011, Complete | USR | 2022-12-30T09:16:18.000 | WO | 0 | 0 |  | 5.86 | 0 |  | 100 |  |  |  |  | 2023-01-27T12:24:09.287 | Trevino, Jeovani | USR
22-0983-ER | WO00012, Complete | marlon labor | 2022-12-30T09:19:00.000 | WO | 0 | 1700.0007 | 24.37 | 2712.03 | 1700 |  | 37.3163 |  | 12/30/2022 | 12/30/2022 |  | 2023-01-27T12:23:56.010 | Trevino, Jeovani | marlon labor
22-0988-ER
23-0004-IR
23-0016-IR
22-1051-IR
23-0079-ER
23-0041-IR
23-0031-IR
23-0002-IR
23-0096-IR
23-0090-IR
23-0034-IR
23-0009-IR
23-0074-IR
23-0100-IR
23-0044-IR
23-0069-IR
23-0043-EST
23-0014-EST
23-0066-ER
23-0056-IR
23-0033-IR
23-0156-IR
23-0055-IR
23-0073-IR
23-0140-IR
23-0012-IR
23-0196-ER
23-0123-IR
23-0003-IR
23-0141-IR
23-0037-IR
23-0051-IR | WO0001 | APP | 2023-05-02T11:38:48.150 | WO | 0 | 1434.42 | 3.65 | 1434.42 | 100 |  | 0 |  | 05/02/2023 | 05/02/2023 |  |  |  | APP
23-0051-IR | WO0002 | CAB | 2023-05-02T11:38:48.337 | WO | 0 | 321.59 | 0.75 | 321.59 | 100 |  | 0 |  | 05/02/2023 | 05/02/2023 |  |  |  | CAB
23-0051-IR | WO0003 | CON | 2023-05-02T11:38:48.510 | WO | 0 | 1126.08 | 17 | 1126.08 | 100 |  | 0 |  | 05/02/2023 | 05/03/2023 |  |  |  | CON
23-0051-IR | WO0004 | DMO | 2023-05-02T11:38:48.713 | WO | 0 | 361.93 | 3.08 | 361.93 | 100 |  | 0 |  | 05/02/2023 | 05/02/2023 |  |  |  | DMO
23-0051-IR | WO0005 | DRY | 2023-05-02T11:38:48.887 | WO | 0 | 3041.06 | 18.42 | 3041.06 | 100 |  | 0 |  | 05/02/2023 | 05/04/2023 |  |  |  | DRY
23-0051-IR | WO0006 | FCC | 2023-05-02T11:38:49.103 | WO | 0 | 3528.11 | 11.12 | 3528.11 | 100 |  | 0 |  | 05/02/2023 | 05/03/2023 |  |  |  | FCC
23-0051-IR | WO0007 | FCV | 2023-05-02T11:38:49.417 | WO | 0 | 4681.94 | 25.77 | 4681.94 | 100 |  | 0 |  | 05/02/2023 | 05/04/2023 |  |  |  | FCV
23-0051-IR | WO0008 | FCW | 2023-05-02T11:38:49.653 | WO | 0 | 493.07 | 2.23 | 493.07 | 100 |  | 0 |  | 05/02/2023 | 05/02/2023 |  |  |  | FCW
23-0051-IR | WO0009 | FNC | 2023-05-02T11:38:49.857 | WO | 0 | 764.68 | 3.02 | 764.68 | 100 |  | 0 |  | 05/02/2023 | 05/02/2023 |  |  |  | FNC
23-0051-IR | WO00010 | HVC | 2023-05-02T11:38:50.123 | WO | 0 | 637.25 | 1.52 | 637.25 | 100 |  | 0 |  | 05/02/2023 | 05/02/2023 |  |  |  | HVC
23-0051-IR | WO00011 | INS | 2023-05-02T11:38:50.373 | WO | 0 | 462.51 | 2.37 | 462.51 | 100 |  | 0 |  | 05/02/2023 | 05/02/2023 |  |  |  | INS
23-0051-IR | WO00012 | PLM | 2023-05-02T11:38:50.543 | WO | 0 | 53.28 | 0.08 | 53.28 | 100 |  | 0 |  | 05/02/2023 | 05/02/2023 |  |  |  | PLM
23-0051-IR | WO00013 | PNT | 2023-05-02T11:38:50.733 | WO | 0 | 3649.83 | 25.75 | 3649.83 | 100 |  | 0 |  | 05/02/2023 | 05/04/2023 |  |  |  | PNT
23-0051-IR | WO00014 | Change Order Lines | 2023-05-02T11:39:00.000 | WO | 0 | 1177.215 | 13.05 | 1811.1 | 65 |  | 35 |  | 05/02/2023 | 05/03/2023
23-0285-IR | WO0001 | APP | 2023-06-01T13:38:38.307 | WO | 0 | 886.27 | 6.03 | 886.27 | 100 |  | 0 |  | 06/01/2023 | 06/01/2023 |  |  |  | APP
23-0285-IR | WO0002 | CAB | 2023-06-01T13:38:38.680 | WO | 0 | 4783.54 | 39.58 | 4783.54 | 100 |  | 0 |  | 06/01/2023 | 06/07/2023 |  |  |  | CAB
23-0285-IR | WO0004 | CON | 2023-06-01T13:38:39.163 | WO | 0 | 1257.53 | 18.7 | 1257.53 | 100 |  | 0 |  | 06/01/2023 | 06/05/2023 |  |  |  | CON
23-0285-IR | WO0006 | DOR | 2023-06-01T13:38:39.883 | WO | 0 | 241.84 | 2.07 | 241.84 | 100 |  | 0 |  | 06/01/2023 | 06/01/2023 |  |  |  | DOR
23-0285-IR | WO0007 | DRY | 2023-06-01T13:38:40.163 | WO | 0 | 6653.03 | 51 | 6653.03 | 100 |  | 0 |  | 06/01/2023 | 06/06/2023 |  |  |  | DRY
23-0285-IR | WO0008 | FCC | 2023-06-01T13:38:40.510 | WO | 0 | 8405.49 | 24.23 | 8405.49 | 100 |  | 0 |  | 06/01/2023 | 06/05/2023 |  |  |  | FCC
23-0285-IR | WO0009 | FCW | 2023-06-01T13:38:41.103 | WO | 0 | 13381.64 | 77.2 | 13381.64 | 100 |  | 0 |  | 06/01/2023 | 06/13/2023 |  |  |  | FCW
23-0285-IR | WO00010 | FNC | 2023-06-01T13:38:41.570 | WO | 0 | 204.87 | 0.82 | 204.87 | 100 |  | 0 |  | 06/01/2023 | 06/01/2023 |  |  |  | FNC
23-0285-IR | WO00011 | FNH | 2023-06-01T13:38:41.820 | WO | 0 | 69.86 | 0.62 | 69.86 | 100 |  | 0 |  | 06/01/2023 | 06/01/2023 |  |  |  | FNH
23-0285-IR | WO00012 | HVC | 2023-06-01T13:38:42.057 | WO | 0 | 93.05 | 0.5 | 93.05 | 100 |  | 0 |  | 06/01/2023 | 06/01/2023 |  |  |  | HVC
23-0285-IR | WO00013 | LIT | 2023-06-01T13:38:42.210 | WO | 0 | 1232.33 | 6.68 | 1232.33 | 100 |  | 0 |  | 06/01/2023 | 06/01/2023 |  |  |  | LIT
23-0285-IR | WO00014 | MBL | 2023-06-01T13:38:42.383 | WO | 0 | 196.57 | 1.03 | 196.57 | 100 |  | 0 |  | 06/01/2023 | 06/01/2023 |  |  |  | MBL
23-0285-IR | WO00015 | PLM | 2023-06-01T13:38:42.617 | WO | 0 | 1749.45 | 6.03 | 1749.45 | 100 |  | 0 |  | 06/01/2023 | 06/01/2023 |  |  |  | PLM
23-0285-IR | WO00017 | WDT | 2023-06-01T13:38:43.010 | WO | 0 | 56.1 | 0.6 | 56.1 | 100 |  | 0 |  | 06/01/2023 | 06/01/2023 |  |  |  | WDT
23-0285-IR | WO00018 | CLN | 2023-06-01T13:41:00.000 | WO | 0 | 699.37 | 13.22 | 699.37 | 100 |  | 0 |  | 06/01/2023 | 06/05/2023 |  |  |  | CLN
22-1037-ER
23-0042-ER | WO0002, Complete | CON | 2023-03-15T12:43:29.000 | WO | 0 | 0 | 0 | 574.22 | 0 |  | 100 |  | 03/15/2023 | 03/15/2023 |  | 2023-04-18T13:11:00.780 | Dehnke, Josh | CON
23-0042-ER | WO0004, Complete | Insulation, Drywall, Texture, Paint (Materials and Labor) | 2023-03-15T12:43:29.000 | WO | 0 | 3107.208 | 0 | 4780.32 | 65 |  | 35 |  | 03/15/2023 | 03/25/2023 |  | 2023-04-18T13:11:00.750 | Dehnke, Josh | DRY
23-0042-ER | WO0005, Complete | FNC | 2023-03-15T12:43:29.000 | WO | 0 | 0 | 0 | 649.56 | 0 |  | 100 |  | 03/15/2023 | 03/19/2023 |  | 2023-05-10T11:55:03.710 | Dehnke, Josh | FNC
23-0046-ER | WO0004 | Fascia, Soffit, Gutters and Awning Labor | 2023-05-10T13:26:42.000 | WO | 0 | 1834.0399 | 0 | 2264.82 | 1834.04 |  | 19.0205 |  | 05/10/2023 | 05/12/2023 |  |  |  | RFG
23-0046-ER | WO0005 | Material Work Order | 2023-05-10T12:27:57.000 | WO | 0 | 516.186 | 0 | 860.31 | 60 |  | 40 |  | 05/10/2023 | 05/10/2023 |  |  |  | Material Work Order
23-0046-ER | WO0006 | Gutter Labor/materials | 2023-05-18T13:01:00.000 | WO | 0 | 499.9997 | 8 | 1137.04 | 500 |  | 56.0262 |  | 05/10/2023 | 05/18/2023 |  |  |  | GUtter
23-0255-IR
23-0271-ER
23-0083-IR
23-0029-IR | WO0002, Complete | CLN | 2023-05-02T14:15:27.000 | WO | 0 | 0 | 5.9 | 368.94 | 0 |  | 100 |  | 05/02/2023 | 05/02/2023 |  | 2023-05-22T09:54:05.513 | Trevino, Jeovani | CLN
23-0029-IR | WO0003, Complete | CON | 2023-05-02T14:15:27.783 | WO | 0 | 164.38 | 2.94 | 164.38 | 100 |  | 0 |  | 05/02/2023 | 05/02/2023 |  | 2023-05-08T10:43:04.400 | Trevino, Jeovani | CON
23-0029-IR | WO0005, Complete | DOR | 2023-05-02T14:15:28.103 | WO | 0 | 83.34 | 0.72 | 83.34 | 100 |  | 0 |  | 05/02/2023 | 05/02/2023 |  | 2023-05-08T10:43:19.477 | Trevino, Jeovani | DOR
23-0029-IR | WO0007, Complete | FCC | 2023-05-02T14:15:28.000 | WO | 0 | 0 | 0.77 | 62.98 | 0 |  | 100 |  | 05/02/2023 | 05/02/2023 |  | 2023-05-08T10:43:52.077 | Trevino, Jeovani | FCC
23-0029-IR | WO00010, Complete | HVC | 2023-05-02T14:15:28.763 | WO | 0 | 8.63 | 0.05 | 8.63 | 100 |  | 0 |  | 05/02/2023 | 05/02/2023 |  | 2023-05-08T10:44:06.570 | Trevino, Jeovani | HVC
23-0029-IR | WO00012, Complete | LAB | 2023-05-02T14:15:28.000 | WO | 0 | 0 | 2 | 200.93 | 0 |  | 100 |  | 05/02/2023 | 05/02/2023 |  | 2023-05-08T10:44:47.747 | Trevino, Jeovani | LAB
23-0029-IR | WO00014, Complete | PNL | 2023-05-02T14:15:29.173 | WO | 0 | 43.2 | 0.4 | 43.2 | 100 |  | 0 |  | 05/02/2023 | 05/02/2023 |  | 2023-05-08T10:42:44.230 | Trevino, Jeovani | PNL
23-0029-IR | WO00016, Complete | WDT | 2023-05-02T14:15:29.413 | WO | 0 | 112.2 | 1.2 | 112.2 | 100 |  | 0 |  | 05/02/2023 | 05/02/2023 |  | 2023-05-08T10:45:17.737 | Trevino, Jeovani | WDT
23-0029-IR | WO00017, Complete | marlon | 2023-05-02T15:13:00.000 | WO | 0 | 3100.0016 | 50.7 | 6043.76 | 3100 |  | 48.7074 |  | 05/02/2023 | 05/04/2023 |  | 2023-05-08T10:42:10.280 | Trevino, Jeovani | marlon
22-0986-IR | WO0001, Complete | CLN | 2023-03-15T10:46:36.000 | WO | 0 | 0 | 4.07 | 279.18 | 0 |  | 100 |  | 03/15/2023 | 03/15/2023 |  | 2023-05-22T09:53:29.253 | Trevino, Jeovani | CLN
22-0986-IR | WO0002, Complete | CON | 2023-03-15T10:46:36.000 | WO | 0 | 0 | 8.43 | 567.16 | 0 |  | 100 |  | 03/15/2023 | 03/16/2023 |  | 2023-05-22T09:53:29.270 | Trevino, Jeovani | CON
22-0986-IR | WO0003, Complete | DMO | 2023-03-15T10:46:36.000 | WO | 0 | 0 |  | 111.24 | 0 |  | 100 |  |  |  |  | 2023-05-22T09:53:29.283 | Trevino, Jeovani | DMO
22-0986-IR | WO0004, Complete | DOR | 2023-03-15T10:46:36.000 | WO | 0 | 0 | 0.6 | 69.1 | 0 |  | 100 |  | 03/15/2023 | 03/15/2023 |  | 2023-05-22T09:53:29.317 | Trevino, Jeovani | DOR
22-0986-IR | WO0005, Complete | flooring material | 2023-03-15T10:46:36.000 | WO | 0 | 1962.3527 |  | 5722.78 | 1962.35 |  | 65.7098 |  |  |  |  | 2023-04-03T11:26:47.353 | Trevino, Jeovani | FCC
22-0986-IR | WO0006, Complete | carpet labor | 2023-03-15T11:13:00.000 | WO | 0 | 2372.79 | 28.38 | 2372.79 | 100 |  | 0 |  | 03/15/2023 | 03/17/2023 |  | 2023-05-22T09:52:10.153 | Trevino, Jeovani | carpet labor
22-1040-IR | WO0001, Complete | APP | 2022-12-12T09:31:02.000 | WO | 0 | 649.9998 | 0.8 | 680.73 | 650 |  | 4.5143 |  | 12/12/2022 | 12/12/2022 |  | 2023-03-13T10:51:03.363 | Trevino, Jeovani | APP
22-1040-IR | WO0003, Complete | CON | 2022-12-12T09:31:02.000 | WO | 0 | 131.54 | 4 | 263.08 | 50 |  | 50 |  | 12/12/2022 | 12/12/2022 |  | 2023-02-06T11:41:44.970 | Trevino, Jeovani | CON
22-1040-IR | WO0004 | DOR | 2022-12-12T09:31:02.887 | WO | 0 |  |  |  | 0 |  | 0 | [6 empty] | DOR
22-1040-IR | WO0005, Complete | DRY / paint materials | 2022-12-12T09:31:03.000 | WO | 0 | 1059.74 |  | 1059.74 | 100 |  | 0 |  |  |  |  | 2022-12-29T19:44:52.473 | Trevino, Jeovani | DRY
22-1040-IR | WO0007, Complete | FCC | 2022-12-12T09:31:03.720 | WO | 0 | 512.478 | 2.12 | 623.13 | 82.2425 |  | 17.7575 |  | 12/12/2022 | 12/12/2022 |  | 2023-01-03T13:35:45.610 | Dehnke, Josh | FCC
22-1040-IR | WO0008, Complete | FCW | 2022-12-12T09:31:03.000 | WO | 0 | 7199.9972 | 44.25 | 8163.04 | 7200 |  | 11.7976 |  | 12/12/2022 | 12/19/2022 |  | 2022-12-29T19:45:46.037 | Trevino, Jeovani | FCW
22-1040-IR | WO0009, Complete | FNC | 2022-12-12T09:31:04.210 | WO | 0 | 353.79 | 3.1 | 353.79 | 100 |  | 0 |  | 12/12/2022 | 12/12/2022 |  | 2023-02-20T11:50:50.383 | Trevino, Jeovani | FNC
22-1040-IR | WO00010, Complete | PLM | 2022-12-12T09:31:04.000 | WO | 0 | 559.9996 | 3.85 | 976.79 | 560 |  | 42.6694 |  | 12/12/2022 | 12/12/2022 |  | 2023-01-01T23:46:56.843 | Trevino, Jeovani | PLM
22-1040-IR | WO00012, Complete | Drywall labor | 2022-12-12T09:40:00.000 | WO | 0 | 3200.0019 | 57.92 | 6229.66 | 3200 |  | 48.6328 |  | 12/12/2022 | 12/14/2022 |  | 2022-12-16T09:51:11.427 | Trevino, Jeovani | drywall & paint
22-1040-IR | WO00013, Complete | counter top M | 2022-12-12T20:00:00.000 | WO | 0 | 11985.086 | 66.69 | 13582.69 | 88.2379 |  | 11.7621 |  | 01/05/2023 | 12/12/2022 |  | 2023-02-13T11:32:58.297 | Trevino, Jeovani | material
22-1040-IR | WO00014, Complete | Leo | 2022-12-16T10:50:00.000 | WO | 0 | 1050 | 16.78 | 1244.07 | 1050 |  | 15.5996 |  | 12/12/2022 | 12/20/2022 |  | 2022-12-29T19:44:34.303 | Trevino, Jeovani | additional work for leo
22-1040-IR | WO00015, Complete | becan labor | 2022-12-28T13:55:00.000 | WO | 0 | 1000.0005 | 21.77 | 1570.92 | 1000 |  | 36.343 |  | 12/12/2022 | 12/28/2022 |  | 2022-12-29T19:44:34.287 | Trevino, Jeovani | cabinets for becan
22-1040-IR | WO00016, Complete | carpet labor | 2022-12-29T20:45:00.000 | WO | 0 | 899.9994 | 10.93 | 1401.96 | 900 |  | 35.8042 |  | 12/12/2022 | 12/29/2022 |  | 2023-01-03T13:35:45.627 | Dehnke, Josh | George carpet labor
22-1040-IR | WO00018, Complete | CAB | 2023-01-05T15:48:28.000 | WO | 0 | 1310 | 11.08 | 1248.19 | 1310 |  | -4.952 |  | 01/13/2023 | 01/16/2023 |  | 2023-02-13T11:32:58.313 | Trevino, Jeovani | CAB
22-1040-IR | WO00019, Complete | cabinet liner | 2023-02-14T23:50:00.000 | WO | 0 | 449.9998 | 8 | 785.04 | 450 |  | 42.6781 |  | 02/14/2023 | 02/14/2023 |  | 2023-02-20T10:58:26.647 | Trevino, Jeovani | marlon cabinet
23-0147-RET-ER | WO0001 | APP | 2023-05-22T09:25:29.390 | WO | 0 | 1246.38 | 6.82 | 1246.38 | 100 |  | 0 |  | 05/22/2023 | 05/22/2023 |  |  |  | APP
23-0147-RET-ER | WO0002 | CAB | 2023-05-22T09:25:29.597 | WO | 0 | 18769.11 | 53.53 | 18769.11 | 100 |  | 0 |  | 05/22/2023 | 05/30/2023 |  |  |  | CAB
23-0147-RET-ER | WO0003 | CLN | 2023-05-22T09:25:29.727 | WO | 0 | 869.84 | 13.3 | 869.84 | 100 |  | 0 |  | 05/22/2023 | 05/23/2023 |  |  |  | CLN
23-0147-RET-ER | WO0004 | DMO | 2023-05-22T09:25:30.040 | WO | 0 | 560.08 |  | 560.08 | 100 |  | 0 | [6 empty] | DMO
23-0147-RET-ER | WO0005 | DOR | 2023-05-22T09:25:30.100 | WO | 0 | 168.6 | 1.48 | 168.6 | 100 |  | 0 |  | 05/22/2023 | 05/22/2023 |  |  |  | DOR
23-0147-RET-ER | WO0006 | Carpet Material | 2023-05-22T09:25:30.000 | WO | 0 | 7320.11 |  | 7320.11 | 100 |  | 0 | [6 empty] | FCC
23-0147-RET-ER | WO0007 | FCW | 2023-05-22T09:25:30.260 | WO | 0 | 6152.47 | 32.43 | 6152.47 | 100 |  | 0 |  | 05/22/2023 | 05/25/2023 |  |  |  | FCW
23-0147-RET-ER | WO0008 | FNC | 2023-05-22T09:25:30.337 | WO | 0 | 417.29 | 3.35 | 417.29 | 100 |  | 0 |  | 05/22/2023 | 05/22/2023 |  |  |  | FNC
23-0147-RET-ER | WO0009 | HVC | 2023-05-22T09:25:30.400 | WO | 0 | 76.47 | 0.42 | 76.47 | 100 |  | 0 |  | 05/22/2023 | 05/22/2023 |  |  |  | HVC
23-0147-RET-ER | WO00010 | PLM | 2023-05-22T09:25:30.463 | WO | 0 | 2343.1 | 8.62 | 2343.1 | 100 |  | 0 |  | 05/22/2023 | 05/23/2023 |  |  |  | PLM
23-0147-RET-ER | WO00011 | PNT | 2023-05-22T09:25:30.510 | WO | 0 | 11257.97 | 74.02 | 11257.97 | 100 |  | 0 |  | 05/22/2023 | 06/01/2023 |  |  |  | PNT
23-0147-RET-ER | WO00012 | TIL | 2023-05-22T09:25:30.670 | WO | 0 | 3281.27 | 13.87 | 3281.27 | 100 |  | 0 |  | 05/22/2023 | 05/23/2023 |  |  |  | TIL
23-0147-RET-ER | WO00013 | APP | 2023-05-25T10:26:17.763 | WO | 0 | 1246.38 | 6.82 | 1246.38 | 100 |  | 0 |  | 05/25/2023 | 05/25/2023 |  |  |  | APP
23-0147-RET-ER | WO00014 | CAB | 2023-05-25T10:26:17.833 | WO | 0 | 18769.11 | 53.53 | 18769.11 | 100 |  | 0 |  | 05/25/2023 | 06/02/2023 |  |  |  | CAB
23-0147-RET-ER | WO00015 | CLN | 2023-05-25T10:26:17.943 | WO | 0 | 869.84 | 13.3 | 869.84 | 100 |  | 0 |  | 05/25/2023 | 05/26/2023 |  |  |  | CLN
23-0147-RET-ER | WO00016 | DMO | 2023-05-25T10:26:18.013 | WO | 0 | 560.08 |  | 560.08 | 100 |  | 0 | [6 empty] | DMO
23-0147-RET-ER | WO00017 | DOR | 2023-05-25T10:26:18.063 | WO | 0 | 168.6 | 1.48 | 168.6 | 100 |  | 0 |  | 05/25/2023 | 05/25/2023 |  |  |  | DOR
23-0147-RET-ER | WO00018 | FCC | 2023-05-25T10:26:18.000 | WO | 0 | 3734.983 | 1.64 | 5335.69 | 70 |  | 30 |  | 05/26/2023 | 05/26/2023 |  |  |  | FCC
23-0147-RET-ER | WO00019 | Hard Surface-Material | 2023-05-25T10:26:18.000 | WO | 0 | 1816.059 |  | 2594.37 | 70 |  | 30 | [6 empty] | FCW
23-0147-RET-ER | WO00020 | FNC | 2023-05-25T10:26:18.757 | WO | 0 | 417.29 | 3.35 | 417.29 | 100 |  | 0 |  | 05/25/2023 | 05/25/2023 |  |  |  | FNC
23-0147-RET-ER | WO00021 | HVC | 2023-05-25T10:26:18.817 | WO | 0 | 76.47 | 0.42 | 76.47 | 100 |  | 0 |  | 05/25/2023 | 05/25/2023 |  |  |  | HVC
23-0147-RET-ER | WO00022 | PLM | 2023-05-25T10:26:18.873 | WO | 0 | 2343.1 | 8.62 | 2343.1 | 100 |  | 0 |  | 05/25/2023 | 05/26/2023 |  |  |  | PLM
23-0147-RET-ER | WO00023 | PNT | 2023-05-25T10:26:18.937 | WO | 0 | 11257.97 | 74.02 | 11257.97 | 100 |  | 0 |  | 05/25/2023 | 06/06/2023 |  |  |  | PNT
23-0147-RET-ER | WO00024 | TIL | 2023-05-25T10:26:19.110 | WO | 0 | 3281.27 | 13.87 | 3281.27 | 100 |  | 0 |  | 05/25/2023 | 05/26/2023 |  |  |  | TIL
23-0147-RET-ER | WO00025 | Flooring labor | 2023-05-25T13:38:00.000 | WO | 0 | 3558.1 | 40.43 | 3558.1 | 100 |  | 0 |  | 05/25/2023 | 05/30/2023
23-0147-RET-ER | WO00026 | Carpet Labor | 2023-05-26T09:39:00.000 | WO | 0 | 5385.5 | 43.04 | 5385.5 | 100 |  | 0 |  | 05/22/2023 | 05/29/2023
23-0147-RET-ER | WO00027 | Office & Family Room Carpet Material | 2023-05-26T09:43:00.000 | WO | 0 | 2272.55 | 13.65 | 3246.5 | 70 |  | 30 |  | 05/25/2023 | 05/26/2023
23-0024-IR | WO0001 | DMO | 2023-06-21T11:45:10.747 | WO | 0 | 84.14 |  | 84.14 | 100 |  | 0 | [6 empty] | DMO
23-0024-IR | WO0002 | PNT | 2023-06-21T11:45:11.030 | WO | 0 | 15.17 |  | 15.17 | 100 |  | 0 | [6 empty] | PNT
23-0024-IR | WO0003 | SFG | 2023-06-21T11:45:11.280 | WO | 0 | 196.33 |  | 196.33 | 100 |  | 0 | [6 empty] | SFG
23-0024-IR | WO0004 | Labor | 2023-06-21T11:45:00.000 | WO | 0 | 349.9996 | 12.75 | 878.48 | 350 |  | 60.1585 |  | 06/21/2023 | 06/21/2023 |  |  |  | Labor
22-0898-ER | WO0001 | CLN | 2023-03-24T13:37:03.167 | WO | 0 |  |  |  | 0 |  | 0 | [6 empty] | CLN
22-0898-ER | WO0002, Complete | material / Equipment | 2023-03-24T13:37:03.000 | WO | 0 | 351.66 | 28 | 703.32 | 50 |  | 50 |  | 04/11/2023 | 04/14/2023 |  | 2023-04-17T09:44:19.373 | Trevino, Jeovani | DMO
22-0898-ER | WO0003, Complete | DRY | 2023-03-24T13:37:03.000 | WO | 0 | 1550 | 33.83 | 2635.79 | 1550 |  | 41.1941 |  | 04/12/2023 | 04/17/2023 |  | 2023-04-17T09:44:19.420 | Trevino, Jeovani | DRY
22-0898-ER | WO0004 | ELE | 2023-03-24T13:37:03.403 | WO | 0 |  |  |  | 0 |  | 0 | [6 empty] | ELE
22-0898-ER | WO0005 | FNC | 2023-03-24T13:37:03.510 | WO | 0 |  |  |  | 0 |  | 0 | [6 empty] | FNC
22-0898-ER | WO0006 | HVC | 2023-03-24T13:37:03.663 | WO | 0 |  |  |  | 0 |  | 0 | [6 empty] | HVC
22-0898-ER | WO0007 | INS | 2023-03-24T13:37:03.780 | WO | 0 |  |  |  | 0 |  | 0 | [6 empty] | INS
22-0898-ER | WO0008 | LIT | 2023-03-24T13:37:03.860 | WO | 0 |  |  |  | 0 |  | 0 | [6 empty] | LIT
22-0898-ER | WO0009 | PLA | 2023-03-24T13:37:03.997 | WO | 0 |  |  |  | 0 |  | 0 | [6 empty] | PLA
22-0898-ER | WO00010 | PNT | 2023-03-24T13:37:04.110 | WO | 0 |  |  |  | 0 |  | 0 | [6 empty] | PNT
23-0179-IR | WO0003 | Gutter Labor | 2023-01-11T14:56:00.000 | WO | 0 | 650.4603 | 8 | 946.27 | 650 |  | 31.2606 |  | 01/11/2023 | 01/11/2023 |  |  |  | Gutter Labor
23-0179-IR | WO0004, Complete | Roofing Labor | 2023-01-11T15:02:00.000 | WO | 0 | 1000 | 11.45 | 1213.15 | 1000 |  | 17.57 |  | 01/11/2023 | 01/11/2023 |  | 2023-01-11T14:05:28.803 | Olson, Jonathon | Roofing Labor
23-0218-IR
23-0223-IR
23-0235-IR
23-0220-IR
23-0161-C
23-0256-IR
23-0071-IR
23-0201-IR | WO0003, Complete | Insulation, Drywall, Paint (materials and labor) | 2023-05-18T12:08:11.000 | WO | 0 | 1521.87 | 16.43 | 2536.45 | 60 |  | 40 |  | 05/18/2023 | 05/19/2023 |  | 2023-05-26T13:21:54.067 | Dehnke, Josh | DRY
23-0201-IR | WO0004 | FPL | 2023-05-18T12:08:12.000 | WO | 0 | 156.836 | 3.72 | 392.09 | 40 |  | 60 |  | 05/18/2023 | 05/18/2023 |  |  |  | FPL
23-0084-IR
23-0125-D | WO0001, Complete | CON | 2023-05-18T11:44:51.000 | WO | 0 | 0 | 2 | 112 | 0 |  | 100 |  | 05/18/2023 | 05/18/2023 |  | 2023-05-26T13:22:40.530 | Dehnke, Josh | CON
23-0125-D | WO0002 | Roof Inspection | 2023-05-18T11:44:52.000 | WO | 0 | 204.91 | 1.98 | 204.91 | 100 |  | 0 |  | 05/18/2023 | 05/18/2023 |  |  |  | DMO
23-0125-D | WO0003, Complete | Insulation, Drywall (Materials and Labor) | 2023-05-18T11:44:52.000 | WO | 0 | 1236.96 | 9.9 | 2061.6 | 60 |  | 40 |  | 05/18/2023 | 05/19/2023 |  | 2023-05-26T13:22:40.500 | Dehnke, Josh | DRY
23-0125-D | WO0004, Complete | ELE | 2023-05-18T11:44:52.000 | WO | 0 | 136.452 | 0.02 | 341.13 | 40 |  | 60 |  | 05/18/2023 | 05/18/2023 |  | 2023-05-26T13:22:40.513 | Dehnke, Josh | ELE
23-0136-RET-ER
23-0047-IR-Kitchen
23-0172-D | WO0001, Complete | CAB | 2023-03-27T12:46:53.000 | WO | 0 | 2349.9993 | 35.95 | 3978.7 | 2350 |  | 40.9355 |  | 04/03/2023 | 04/07/2023 |  | 2023-04-10T11:25:48.650 | Trevino, Jeovani | CAB
23-0172-D | WO0002 | CLN | 2023-03-27T12:46:53.667 | WO | 0 |  |  |  | 0 |  | 0 | [6 empty] | CLN
23-0172-D | WO0003, Complete | CON | 2023-03-27T12:46:53.000 | WO | 0 | 0 | 37.5 | 100.8 | 0 |  | 100 |  | 04/03/2023 | 04/07/2023 |  | 2023-04-10T11:25:48.697 | Trevino, Jeovani | CON
23-0172-D | WO0004, Complete | DMO | 2023-03-27T12:46:53.000 | WO | 0 | 0 | 38 | 245.89 | 0 |  | 100 |  | 04/03/2023 | 04/07/2023 |  | 2023-04-10T11:25:48.730 | Trevino, Jeovani | DMO
23-0172-D | WO0005 | DRY | 2023-03-27T12:46:53.917 | WO | 0 |  |  |  | 0 |  | 0 | [6 empty] | DRY
23-0172-D | WO0006 | FEE | 2023-03-27T12:46:54.090 | WO | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | FEE
23-0172-D | WO0007 | FNC | 2023-03-27T12:46:54.167 | WO | 0 |  |  |  | 0 |  | 0 | [6 empty] | FNC
23-0172-D | WO0008 | INS | 2023-03-27T12:46:54.277 | WO | 0 |  |  |  | 0 |  | 0 | [6 empty] | INS
23-0172-D | WO0009 | LIT | 2023-03-27T12:46:54.403 | WO | 0 |  |  |  | 0 |  | 0 | [6 empty] | LIT
23-0172-D | WO00010 | PNT | 2023-03-27T12:46:54.560 | WO | 0 |  |  |  | 0 |  | 0 | [6 empty] | PNT
23-0175-D
23-0121-C
23-0210-IR
22-1031-EOC
23-0215-IR
23-0187-D
23-0171-IR
23-0064-IR
23-0173-D
23-0191-D
23-0118-D
23-0158-IR
23-0116-IR
23-0128-IR
23-0091-D
23-0063-IR
23-0154-IR
22-1047-RET-ER
23-0124-IR
23-0082-D
23-0120-IR
23-0047-IR-Garage
23-0105-IR
23-0129-IR
23-0053-D
23-0077-D
23-0061-ER
23-0089-IR
23-0060-ER
23-0032-IR
23-0087-IR
23-0030-ER
23-0104-IR
23-0020-ER